## Projects
Project_ID | Project_Name | Project_Type | City | State | Start_Date | End_Date | Original_Budget | Contract_Value | Actual_Cost_To_Date | Progress_Pct | Status | Contingency_Budget
PRJ-001 | Green Valley Residential Complex | Residential | Lucknow | Uttar Pradesh | 2025-01-01 | 2026-12-31 | 168000000 | 185000000 | 142800000 | 82 | In Progress | 950000
PRJ-002 | Riverside Commercial Tower | Commercial | Noida | Uttar Pradesh | 2025-04-01 | 2027-03-31 | 245000000 | 270000000 | 121500000 | 51 | In Progress | 1350000
PRJ-003 | Sunrise Industrial Park | Industrial | Kanpur | Uttar Pradesh | 2024-07-01 | 2026-06-30 | 132000000 | 145000000 | 118600000 | 89 | In Progress | 780000
PRJ-004 | CityCare Hospital Expansion | Healthcare | Delhi | Delhi | 2025-02-15 | 2026-08-31 | 98000000 | 108000000 | 92300000 | 91 | In Progress | 620000
PRJ-005 | Smart City Road Package A | Infrastructure | Agra | Uttar Pradesh | 2024-10-01 | 2026-03-31 | 76000000 | 84000000 | 74800000 | 96 | Near Completion | 480000
PRJ-006 | Grand Horizon Hotel & Convention Centre | Hospitality | Jaipur | Rajasthan | 2025-06-01 | 2027-02-28 | 142000000 | 158000000 | 84200000 | 59 | In Progress | 7100000

## Activities
Activity_ID | Project_ID | Activity_Code | Activity_Name | Work_Category | Budget_Weight | Planned_Progress_Pct | Actual_Progress_Pct | Schedule_Variance_Pct | Status
PRJ-001-ACT-01 | PRJ-001 | ACT-01 | Site Preparation | Site Preparation | 0.05 | 87.5 | 88.1 | 0.6 | On Track
PRJ-001-ACT-02 | PRJ-001 | ACT-02 | Foundation | Foundation | 0.12 | 88.2 | 82.1 | -6.1 | Delayed
PRJ-001-ACT-03 | PRJ-001 | ACT-03 | Structural Work | Structure | 0.28 | 83.8 | 84.7 | 0.9 | On Track
PRJ-001-ACT-04 | PRJ-001 | ACT-04 | Brick & Block Work | Masonry | 0.12 | 92.9 | 89.8 | -3.1 | On Track
PRJ-001-ACT-05 | PRJ-001 | ACT-05 | Electrical & Plumbing | MEP | 0.13 | 82.7 | 80.5 | -2.2 | On Track
PRJ-001-ACT-06 | PRJ-001 | ACT-06 | Flooring & Tiling | Finishing | 0.09 | 82.7 | 84.6 | 1.9 | On Track
PRJ-001-ACT-07 | PRJ-001 | ACT-07 | Painting | Finishing | 0.07 | 86.2 | 93.9 | 7.7 | Ahead
PRJ-001-ACT-08 | PRJ-001 | ACT-08 | Doors & Windows | Finishing | 0.05 | 76.4 | 78.6 | 2.2 | On Track
PRJ-001-ACT-09 | PRJ-001 | ACT-09 | External Development | External | 0.05 | 79.9 | 78.6 | -1.3 | On Track
PRJ-001-ACT-10 | PRJ-001 | ACT-10 | Testing & Handover | Handover | 0.04 | 80.5 | 86.1 | 5.6 | Ahead
PRJ-002-ACT-01 | PRJ-002 | ACT-01 | Site Preparation | Site Preparation | 0.05 | 61.3 | 62.2 | 0.9 | On Track
PRJ-002-ACT-02 | PRJ-002 | ACT-02 | Foundation | Foundation | 0.12 | 54.3 | 60 | 5.7 | Ahead
PRJ-002-ACT-03 | PRJ-002 | ACT-03 | Structural Work | Structure | 0.28 | 51.3 | 50.9 | -0.4 | On Track
PRJ-002-ACT-04 | PRJ-002 | ACT-04 | Brick & Block Work | Masonry | 0.12 | 48.2 | 46.7 | -1.5 | On Track
PRJ-002-ACT-05 | PRJ-002 | ACT-05 | Electrical & Plumbing | MEP | 0.13 | 51 | 52.2 | 1.2 | On Track
PRJ-002-ACT-06 | PRJ-002 | ACT-06 | Flooring & Tiling | Finishing | 0.09 | 51 | 43.6 | -7.4 | Delayed
PRJ-002-ACT-07 | PRJ-002 | ACT-07 | Painting | Finishing | 0.07 | 53.9 | 58.1 | 4.2 | Ahead
PRJ-002-ACT-08 | PRJ-002 | ACT-08 | Doors & Windows | Finishing | 0.05 | 58.1 | 63 | 4.9 | Ahead
PRJ-002-ACT-09 | PRJ-002 | ACT-09 | External Development | External | 0.05 | 55 | 62.8 | 7.8 | Ahead
PRJ-002-ACT-10 | PRJ-002 | ACT-10 | Testing & Handover | Handover | 0.04 | 47.4 | 46.6 | -0.8 | On Track
PRJ-003-ACT-01 | PRJ-003 | ACT-01 | Site Preparation | Site Preparation | 0.05 | 95.7 | 95 | -0.7 | On Track
PRJ-003-ACT-02 | PRJ-003 | ACT-02 | Foundation | Foundation | 0.12 | 91.4 | 92.6 | 1.2 | On Track
PRJ-003-ACT-03 | PRJ-003 | ACT-03 | Structural Work | Structure | 0.28 | 84.6 | 87.5 | 2.9 | On Track
PRJ-003-ACT-04 | PRJ-003 | ACT-04 | Brick & Block Work | Masonry | 0.12 | 89.7 | 85.5 | -4.2 | On Track
PRJ-003-ACT-05 | PRJ-003 | ACT-05 | Electrical & Plumbing | MEP | 0.13 | 93.7 | 100 | 6.3 | Ahead
PRJ-003-ACT-06 | PRJ-003 | ACT-06 | Flooring & Tiling | Finishing | 0.09 | 93.6 | 95.1 | 1.5 | On Track
PRJ-003-ACT-07 | PRJ-003 | ACT-07 | Painting | Finishing | 0.07 | 88.6 | 86.2 | -2.4 | On Track
PRJ-003-ACT-08 | PRJ-003 | ACT-08 | Doors & Windows | Finishing | 0.05 | 97.2 | 93.5 | -3.7 | On Track
PRJ-003-ACT-09 | PRJ-003 | ACT-09 | External Development | External | 0.05 | 87.8 | 89 | 1.2 | On Track
PRJ-003-ACT-10 | PRJ-003 | ACT-10 | Testing & Handover | Handover | 0.04 | 93.7 | 89.8 | -3.9 | On Track
PRJ-004-ACT-01 | PRJ-004 | ACT-01 | Site Preparation | Site Preparation | 0.05 | 91.6 | 92.3 | 0.7 | On Track
PRJ-004-ACT-02 | PRJ-004 | ACT-02 | Foundation | Foundation | 0.12 | 88.5 | 93.3 | 4.8 | Ahead
PRJ-004-ACT-03 | PRJ-004 | ACT-03 | Structural Work | Structure | 0.28 | 98.1 | 92.7 | -5.4 | Delayed
PRJ-004-ACT-04 | PRJ-004 | ACT-04 | Brick & Block Work | Masonry | 0.12 | 93.6 | 89.6 | -4 | On Track
PRJ-004-ACT-05 | PRJ-004 | ACT-05 | Electrical & Plumbing | MEP | 0.13 | 95.8 | 98.4 | 2.6 | On Track
PRJ-004-ACT-06 | PRJ-004 | ACT-06 | Flooring & Tiling | Finishing | 0.09 | 95.8 | 89.6 | -6.2 | Delayed
PRJ-004-ACT-07 | PRJ-004 | ACT-07 | Painting | Finishing | 0.07 | 93.8 | 87.5 | -6.3 | Delayed
PRJ-004-ACT-08 | PRJ-004 | ACT-08 | Doors & Windows | Finishing | 0.05 | 80.9 | 77.6 | -3.3 | On Track
PRJ-004-ACT-09 | PRJ-004 | ACT-09 | External Development | External | 0.05 | 94.4 | 95.6 | 1.2 | On Track
PRJ-004-ACT-10 | PRJ-004 | ACT-10 | Testing & Handover | Handover | 0.04 | 94.5 | 100 | 5.5 | Ahead
PRJ-005-ACT-01 | PRJ-005 | ACT-01 | Site Preparation | Site Preparation | 0.05 | 97.9 | 96.5 | -1.4 | On Track
PRJ-005-ACT-02 | PRJ-005 | ACT-02 | Foundation | Foundation | 0.12 | 100 | 100 | 0 | On Track
PRJ-005-ACT-03 | PRJ-005 | ACT-03 | Structural Work | Structure | 0.28 | 95 | 97 | 2 | On Track
PRJ-005-ACT-04 | PRJ-005 | ACT-04 | Brick & Block Work | Masonry | 0.12 | 100 | 98.7 | -1.3 | On Track
PRJ-005-ACT-05 | PRJ-005 | ACT-05 | Electrical & Plumbing | MEP | 0.13 | 96.4 | 94.3 | -2.1 | On Track
PRJ-005-ACT-06 | PRJ-005 | ACT-06 | Flooring & Tiling | Finishing | 0.09 | 99.5 | 95.6 | -3.9 | On Track
PRJ-005-ACT-07 | PRJ-005 | ACT-07 | Painting | Finishing | 0.07 | 95.5 | 96.8 | 1.3 | On Track
PRJ-005-ACT-08 | PRJ-005 | ACT-08 | Doors & Windows | Finishing | 0.05 | 97 | 100 | 3 | On Track
PRJ-005-ACT-09 | PRJ-005 | ACT-09 | External Development | External | 0.05 | 100 | 99 | -1 | On Track
PRJ-005-ACT-10 | PRJ-005 | ACT-10 | Testing & Handover | Handover | 0.04 | 99 | 99.9 | 0.9 | On Track
PRJ-006-ACT-01 | PRJ-006 | ACT-01 | Site Preparation | Site Preparation | 0.05 | 58.7 | 54.2 | -4.5 | On Track
PRJ-006-ACT-02 | PRJ-006 | ACT-02 | Foundation | Foundation | 0.12 | 64.1 | 67.1 | 3 | On Track
PRJ-006-ACT-03 | PRJ-006 | ACT-03 | Structural Work | Structure | 0.28 | 60.7 | 54.2 | -6.5 | Delayed
PRJ-006-ACT-04 | PRJ-006 | ACT-04 | Brick & Block Work | Masonry | 0.12 | 53.3 | 53.1 | -0.2 | On Track
PRJ-006-ACT-05 | PRJ-006 | ACT-05 | Electrical & Plumbing | MEP | 0.13 | 68.1 | 69.2 | 1.1 | On Track
PRJ-006-ACT-06 | PRJ-006 | ACT-06 | Flooring & Tiling | Finishing | 0.09 | 60.3 | 59.1 | -1.2 | On Track
PRJ-006-ACT-07 | PRJ-006 | ACT-07 | Painting | Finishing | 0.07 | 69 | 69.4 | 0.4 | On Track
PRJ-006-ACT-08 | PRJ-006 | ACT-08 | Doors & Windows | Finishing | 0.05 | 61.2 | 61 | -0.2 | On Track
PRJ-006-ACT-09 | PRJ-006 | ACT-09 | External Development | External | 0.05 | 71.8 | 63.7 | -8.1 | Delayed
PRJ-006-ACT-10 | PRJ-006 | ACT-10 | Testing & Handover | Handover | 0.04 | 67 | 64.3 | -2.7 | On Track

## Expenses
Expense_ID | Project_ID | Activity_ID | Expense_Date | Cost_Category | Item_Code | Item_Name | Vendor_ID | Quantity | Unit | Planned_Cost | Actual_Cost_Excl_Tax | Tax_18pct | Total_Cost | Payment_Status | Cost_Risk
EXP-00001 | PRJ-001 | PRJ-001-ACT-03 | 2025-01-01 | Labour | LAB-002 | Helper | VEN-001 | 15 | Worker | 13220.2 | 13961.17 | 2513.01 | 16474.18 | Paid | Medium
EXP-00002 | PRJ-001 | PRJ-001-ACT-01 | 2025-01-01 | Material | MAT-010 | Glass | VEN-002 | 2.14 | Sq Ft | 296.57 | 320.3 | 57.65 | 377.95 | Paid | Low
EXP-00003 | PRJ-001 | PRJ-001-ACT-01 | 2025-01-01 | Material | MAT-001 | Cement | VEN-001 | 8.85 | Bag | 4001.4 | 4242.44 | 763.64 | 5006.08 | Paid | High
EXP-00004 | PRJ-001 | PRJ-001-ACT-07 | 2025-01-01 | Material | MAT-008 | Tiles | VEN-010 | 16.33 | Sq Ft | 1201.07 | 1176.17 | 211.71 | 1387.88 | Paid | Low
EXP-00005 | PRJ-001 | PRJ-001-ACT-09 | 2025-01-01 | Material | MAT-006 | Electrical Cable | VEN-001 | 4.56 | Meter | 433.9 | 410.37 | 73.87 | 484.24 | Paid | Low
EXP-00006 | PRJ-001 | PRJ-001-ACT-03 | 2025-01-01 | Equipment | EQ-004 | Scaffolding | VEN-006 | 7 | Day | 16860.09 | 16360.28 | 2944.85 | 19305.13 | Paid | High
EXP-00007 | PRJ-001 | PRJ-001-ACT-09 | 2025-01-06 | Equipment | EQ-002 | Excavator | VEN-001 | 7 | Day | 101907.73 | 98812.38 | 17786.23 | 116598.61 | Paid | Low
EXP-00008 | PRJ-001 | PRJ-001-ACT-01 | 2025-01-06 | Other | OTH-001 | Transport | VEN-010 | 1 | Lot | 85655.47 | 79719.03 | 14349.43 | 94068.46 | Paid | Medium
EXP-00009 | PRJ-001 | PRJ-001-ACT-03 | 2025-01-06 | Material | MAT-003 | Sand | VEN-001 | 13.35 | Ton | 28021.53 | 26820.51 | 4827.69 | 31648.2 | Paid | Low
EXP-00010 | PRJ-001 | PRJ-001-ACT-08 | 2025-01-06 | Material | MAT-004 | Aggregate | VEN-002 | 11.28 | Ton | 16975.44 | 17329.57 | 3119.32 | 20448.89 | Pending | High
EXP-00011 | PRJ-001 | PRJ-001-ACT-02 | 2025-01-06 | Material | MAT-002 | Steel | VEN-002 | 19.83 | Ton | 1166046 | 1127760.04 | 202996.81 | 1330756.85 | Paid | Low
EXP-00012 | PRJ-001 | PRJ-001-ACT-08 | 2025-01-06 | Contractor | CON-003 | Plumbing Contract | VEN-010 | 1 | Contract | 334746.6 | 345352.47 | 62163.44 | 407515.91 | Paid | Low
EXP-00013 | PRJ-001 | PRJ-001-ACT-02 | 2025-01-11 | Labour | LAB-005 | Plumber | VEN-010 | 33 | Worker | 47173.1 | 45931.67 | 8267.7 | 54199.37 | Partially Paid | Low
EXP-00014 | PRJ-001 | PRJ-001-ACT-03 | 2025-01-11 | Labour | LAB-001 | Mason | VEN-010 | 20 | Worker | 35702.14 | 35874.66 | 6457.44 | 42332.1 | Paid | Medium
EXP-00015 | PRJ-001 | PRJ-001-ACT-08 | 2025-01-11 | Contractor | CON-001 | Civil Structure Contract | VEN-001 | 1 | Contract | 253157.77 | 235569.06 | 42402.43 | 277971.49 | Pending | Medium
EXP-00016 | PRJ-001 | PRJ-001-ACT-07 | 2025-01-11 | Material | MAT-001 | Cement | VEN-001 | 24.38 | Bag | 11347.71 | 11981.3 | 2156.63 | 14137.93 | Paid | High
EXP-00017 | PRJ-001 | PRJ-001-ACT-08 | 2025-01-11 | Equipment | EQ-002 | Excavator | VEN-010 | 7 | Day | 101408.46 | 107605.06 | 19368.91 | 126973.97 | Paid | Medium
EXP-00018 | PRJ-001 | PRJ-001-ACT-09 | 2025-01-11 | Contractor | CON-003 | Plumbing Contract | VEN-001 | 1 | Contract | 343722.14 | 340841.62 | 61351.49 | 402193.11 | Paid | Low
EXP-00019 | PRJ-001 | PRJ-001-ACT-10 | 2025-01-11 | Material | MAT-007 | PVC Pipe | VEN-010 | 26.52 | Meter | 3433.03 | 3325.57 | 598.6 | 3924.17 | Paid | Medium
EXP-00020 | PRJ-001 | PRJ-001-ACT-02 | 2025-01-11 | Material | MAT-002 | Steel | VEN-010 | 9.07 | Ton | 567152.72 | 551960.46 | 99352.88 | 651313.34 | Paid | Low
EXP-00021 | PRJ-001 | PRJ-001-ACT-10 | 2025-01-11 | Other | OTH-001 | Transport | VEN-002 | 1 | Lot | 6748.07 | 7287.52 | 1311.75 | 8599.27 | Partially Paid | Low
EXP-00022 | PRJ-001 | PRJ-001-ACT-08 | 2025-01-11 | Material | MAT-005 | Bricks | VEN-001 | 22.37 | Piece | 180.28 | 182.87 | 32.92 | 215.79 | Paid | Low
EXP-00023 | PRJ-001 | PRJ-001-ACT-03 | 2025-01-16 | Other | OTH-001 | Permit | VEN-002 | 1 | Lot | 34540.23 | 34911.57 | 6284.08 | 41195.65 | Paid | Low
EXP-00024 | PRJ-001 | PRJ-001-ACT-07 | 2025-01-16 | Material | MAT-009 | Paint | VEN-002 | 8.06 | Litre | 1661.91 | 1788.32 | 321.9 | 2110.22 | Partially Paid | Low
EXP-00025 | PRJ-001 | PRJ-001-ACT-09 | 2025-01-16 | Material | MAT-008 | Tiles | VEN-002 | 10.36 | Sq Ft | 800.52 | 780.89 | 140.56 | 921.45 | Paid | Medium
EXP-00026 | PRJ-001 | PRJ-001-ACT-03 | 2025-01-16 | Material | MAT-005 | Bricks | VEN-002 | 13.92 | Piece | 108.19 | 111 | 19.98 | 130.98 | Paid | Low
EXP-00027 | PRJ-001 | PRJ-001-ACT-04 | 2025-01-16 | Material | MAT-005 | Bricks | VEN-002 | 4.5 | Piece | 40.23 | 40.4 | 7.27 | 47.67 | Paid | Low
EXP-00028 | PRJ-001 | PRJ-001-ACT-06 | 2025-01-16 | Material | MAT-005 | Bricks | VEN-002 | 8.63 | Piece | 83.36 | 86.68 | 15.6 | 102.28 | Paid | High
EXP-00029 | PRJ-001 | PRJ-001-ACT-05 | 2025-01-16 | Labour | LAB-005 | Plumber | VEN-010 | 7 | Worker | 10182.86 | 9507.6 | 1711.37 | 11218.97 | Pending | Medium
EXP-00030 | PRJ-001 | PRJ-001-ACT-08 | 2025-01-16 | Labour | LAB-004 | Electrician | VEN-010 | 21 | Worker | 25862.4 | 27496.81 | 4949.43 | 32446.24 | Partially Paid | Medium
EXP-00031 | PRJ-001 | PRJ-001-ACT-01 | 2025-01-16 | Labour | LAB-002 | Helper | VEN-001 | 14 | Worker | 11408.03 | 12252.24 | 2205.4 | 14457.64 | Paid | Low
EXP-00032 | PRJ-001 | PRJ-001-ACT-07 | 2025-01-16 | Material | MAT-001 | Cement | VEN-006 | 3.79 | Bag | 2025.19 | 2078.18 | 374.07 | 2452.25 | Paid | Low
EXP-00033 | PRJ-001 | PRJ-001-ACT-08 | 2025-01-21 | Equipment | EQ-004 | Scaffolding | VEN-001 | 1 | Day | 2559.26 | 2651.74 | 477.31 | 3129.05 | Paid | Medium
EXP-00034 | PRJ-001 | PRJ-001-ACT-03 | 2025-01-21 | Contractor | CON-004 | Finishing Contract | VEN-001 | 1 | Contract | 117968.63 | 122883.65 | 22119.06 | 145002.71 | Paid | Medium
EXP-00035 | PRJ-001 | PRJ-001-ACT-01 | 2025-01-21 | Labour | LAB-005 | Plumber | VEN-010 | 26 | Worker | 36955.06 | 39460.83 | 7102.95 | 46563.78 | Partially Paid | Low
EXP-00036 | PRJ-001 | PRJ-001-ACT-03 | 2025-01-21 | Contractor | CON-001 | Civil Structure Contract | VEN-002 | 1 | Contract | 102031 | 95056.99 | 17110.26 | 112167.25 | Partially Paid | Low
EXP-00037 | PRJ-001 | PRJ-001-ACT-04 | 2025-01-21 | Other | OTH-001 | Safety | VEN-006 | 1 | Lot | 39178.13 | 41976.92 | 7555.85 | 49532.77 | Paid | Medium
EXP-00038 | PRJ-001 | PRJ-001-ACT-04 | 2025-01-21 | Labour | LAB-005 | Plumber | VEN-001 | 26 | Worker | 37770.8 | 40260.75 | 7246.93 | 47507.68 | Pending | High
EXP-00039 | PRJ-001 | PRJ-001-ACT-05 | 2025-01-21 | Other | OTH-001 | Safety | VEN-002 | 1 | Lot | 69870.42 | 71577.81 | 12884.01 | 84461.82 | Paid | Low
EXP-00040 | PRJ-001 | PRJ-001-ACT-06 | 2025-01-26 | Contractor | CON-003 | Plumbing Contract | VEN-001 | 1 | Contract | 224362.75 | 234784.3 | 42261.17 | 277045.47 | Paid | Medium
EXP-00041 | PRJ-001 | PRJ-001-ACT-05 | 2025-01-26 | Material | MAT-006 | Electrical Cable | VEN-001 | 29.3 | Meter | 2796.68 | 2854.09 | 513.74 | 3367.83 | Paid | Medium
EXP-00042 | PRJ-001 | PRJ-001-ACT-04 | 2025-01-26 | Contractor | CON-004 | Finishing Contract | VEN-001 | 1 | Contract | 201696.64 | 216097.34 | 38897.52 | 254994.86 | Paid | Medium
EXP-00043 | PRJ-001 | PRJ-001-ACT-03 | 2025-01-26 | Labour | LAB-006 | Painter | VEN-002 | 6 | Worker | 5564.71 | 5650.41 | 1017.07 | 6667.48 | Paid | Medium
EXP-00044 | PRJ-001 | PRJ-001-ACT-09 | 2025-01-26 | Contractor | CON-003 | Plumbing Contract | VEN-006 | 1 | Contract | 359499.07 | 354766.83 | 63858.03 | 418624.86 | Pending | Low
EXP-00045 | PRJ-001 | PRJ-001-ACT-01 | 2025-01-26 | Material | MAT-006 | Electrical Cable | VEN-010 | 25.01 | Meter | 2452.41 | 2430.63 | 437.51 | 2868.14 | Paid | Low
EXP-00046 | PRJ-001 | PRJ-001-ACT-05 | 2025-01-26 | Contractor | CON-004 | Finishing Contract | VEN-010 | 1 | Contract | 303922.5 | 282695.36 | 50885.16 | 333580.52 | Paid | Medium
EXP-00047 | PRJ-001 | PRJ-001-ACT-03 | 2025-01-31 | Labour | LAB-001 | Mason | VEN-002 | 14 | Worker | 14605.3 | 13623.51 | 2452.23 | 16075.74 | Partially Paid | Low
EXP-00048 | PRJ-001 | PRJ-001-ACT-10 | 2025-01-31 | Labour | LAB-004 | Electrician | VEN-010 | 7 | Worker | 8088.43 | 8282.77 | 1490.9 | 9773.67 | Paid | Low
EXP-00049 | PRJ-001 | PRJ-001-ACT-06 | 2025-01-31 | Other | OTH-001 | Permit | VEN-010 | 1 | Lot | 25613.13 | 25982.26 | 4676.81 | 30659.07 | Paid | Low
EXP-00050 | PRJ-001 | PRJ-001-ACT-06 | 2025-01-31 | Material | MAT-002 | Steel | VEN-006 | 7.28 | Ton | 445787.05 | 440072.26 | 79213.01 | 519285.27 | Partially Paid | Low
EXP-00051 | PRJ-001 | PRJ-001-ACT-05 | 2025-01-31 | Contractor | CON-003 | Plumbing Contract | VEN-006 | 1 | Contract | 239401.82 | 229220.67 | 41259.72 | 270480.39 | Paid | High
EXP-00052 | PRJ-001 | PRJ-001-ACT-09 | 2025-01-31 | Material | MAT-006 | Electrical Cable | VEN-002 | 10.96 | Meter | 749.61 | 809.61 | 145.73 | 955.34 | Paid | Low
EXP-00053 | PRJ-001 | PRJ-001-ACT-05 | 2025-02-05 | Contractor | CON-002 | Electrical Contract | VEN-006 | 1 | Contract | 423124.29 | 417437.16 | 75138.69 | 492575.85 | Paid | Medium
EXP-00054 | PRJ-001 | PRJ-001-ACT-09 | 2025-02-05 | Material | MAT-001 | Cement | VEN-001 | 22.75 | Bag | 13669.77 | 13441.43 | 2419.46 | 15860.89 | Paid | Medium
EXP-00055 | PRJ-001 | PRJ-001-ACT-08 | 2025-02-05 | Labour | LAB-002 | Helper | VEN-010 | 29 | Worker | 37779.63 | 36202.26 | 6516.41 | 42718.67 | Paid | Medium
EXP-00056 | PRJ-001 | PRJ-001-ACT-09 | 2025-02-05 | Labour | LAB-001 | Mason | VEN-001 | 19 | Worker | 22548.62 | 22839 | 4111.02 | 26950.02 | Paid | Medium
EXP-00057 | PRJ-001 | PRJ-001-ACT-06 | 2025-02-05 | Contractor | CON-004 | Finishing Contract | VEN-006 | 1 | Contract | 78530.91 | 80454.25 | 14481.76 | 94936.01 | Paid | Low
EXP-00058 | PRJ-001 | PRJ-001-ACT-02 | 2025-02-05 | Labour | LAB-004 | Electrician | VEN-006 | 28 | Worker | 36327.59 | 34750.46 | 6255.08 | 41005.54 | Paid | Medium
EXP-00059 | PRJ-001 | PRJ-001-ACT-04 | 2025-02-05 | Contractor | CON-002 | Electrical Contract | VEN-001 | 1 | Contract | 421937.46 | 422470.36 | 76044.66 | 498515.02 | Paid | Low
EXP-00060 | PRJ-001 | PRJ-001-ACT-02 | 2025-02-05 | Other | OTH-001 | Miscellaneous | VEN-001 | 1 | Lot | 20948.42 | 20684.81 | 3723.27 | 24408.08 | Paid | Low
EXP-00061 | PRJ-001 | PRJ-001-ACT-06 | 2025-02-05 | Labour | LAB-004 | Electrician | VEN-010 | 11 | Worker | 15735.15 | 15960.74 | 2872.93 | 18833.67 | Partially Paid | Low
EXP-00062 | PRJ-001 | PRJ-001-ACT-03 | 2025-02-10 | Labour | LAB-005 | Plumber | VEN-006 | 8 | Worker | 8170.58 | 8374.76 | 1507.46 | 9882.22 | Paid | Low
EXP-00063 | PRJ-001 | PRJ-001-ACT-10 | 2025-02-10 | Labour | LAB-006 | Painter | VEN-010 | 5 | Worker | 3881.83 | 3990.3 | 718.25 | 4708.55 | Paid | Low
EXP-00064 | PRJ-001 | PRJ-001-ACT-08 | 2025-02-10 | Labour | LAB-006 | Painter | VEN-002 | 14 | Worker | 22245.78 | 23926.05 | 4306.69 | 28232.74 | Paid | Medium
EXP-00065 | PRJ-001 | PRJ-001-ACT-04 | 2025-02-10 | Contractor | CON-003 | Plumbing Contract | VEN-001 | 1 | Contract | 294962.2 | 276221.49 | 49719.87 | 325941.36 | Paid | Medium
EXP-00066 | PRJ-001 | PRJ-001-ACT-10 | 2025-02-10 | Labour | LAB-006 | Painter | VEN-002 | 30 | Worker | 29172.01 | 28209.07 | 5077.63 | 33286.7 | Partially Paid | Low
EXP-00067 | PRJ-001 | PRJ-001-ACT-02 | 2025-02-10 | Labour | LAB-002 | Helper | VEN-001 | 9 | Worker | 10894.4 | 11362.59 | 2045.27 | 13407.86 | Paid | Low
EXP-00068 | PRJ-001 | PRJ-001-ACT-01 | 2025-02-10 | Material | MAT-007 | PVC Pipe | VEN-001 | 9.55 | Meter | 1027.78 | 1054.28 | 189.77 | 1244.05 | Paid | Low
EXP-00069 | PRJ-001 | PRJ-001-ACT-04 | 2025-02-15 | Labour | LAB-006 | Painter | VEN-006 | 5 | Worker | 6546.42 | 6457.02 | 1162.26 | 7619.28 | Paid | Low
EXP-00070 | PRJ-001 | PRJ-001-ACT-10 | 2025-02-15 | Material | MAT-002 | Steel | VEN-010 | 4.68 | Ton | 267831.34 | 267906.45 | 48223.16 | 316129.61 | Paid | High
EXP-00071 | PRJ-001 | PRJ-001-ACT-06 | 2025-02-15 | Material | MAT-006 | Electrical Cable | VEN-001 | 5.54 | Meter | 411.95 | 426.62 | 76.79 | 503.41 | Paid | Medium
EXP-00072 | PRJ-001 | PRJ-001-ACT-08 | 2025-02-15 | Material | MAT-005 | Bricks | VEN-006 | 6.26 | Piece | 60.49 | 64.49 | 11.61 | 76.1 | Paid | High
EXP-00073 | PRJ-001 | PRJ-001-ACT-06 | 2025-02-15 | Contractor | CON-001 | Civil Structure Contract | VEN-002 | 1 | Contract | 268268.7 | 259030.79 | 46625.54 | 305656.33 | Partially Paid | Medium
EXP-00074 | PRJ-001 | PRJ-001-ACT-03 | 2025-02-15 | Labour | LAB-005 | Plumber | VEN-002 | 15 | Worker | 14282.55 | 13287.59 | 2391.77 | 15679.36 | Paid | Low
EXP-00075 | PRJ-001 | PRJ-001-ACT-01 | 2025-02-20 | Material | MAT-010 | Glass | VEN-006 | 7.69 | Sq Ft | 1317.85 | 1232.65 | 221.88 | 1454.53 | Paid | Medium
EXP-00076 | PRJ-001 | PRJ-001-ACT-10 | 2025-02-20 | Material | MAT-005 | Bricks | VEN-010 | 10.01 | Piece | 84.43 | 78.29 | 14.09 | 92.38 | Paid | Medium
EXP-00077 | PRJ-001 | PRJ-001-ACT-09 | 2025-02-20 | Material | MAT-001 | Cement | VEN-001 | 8.55 | Bag | 4803.53 | 4587.52 | 825.75 | 5413.27 | Paid | Medium
EXP-00078 | PRJ-001 | PRJ-001-ACT-05 | 2025-02-20 | Contractor | CON-004 | Finishing Contract | VEN-002 | 1 | Contract | 425519.23 | 446598.55 | 80387.74 | 526986.29 | Paid | High
EXP-00079 | PRJ-001 | PRJ-001-ACT-08 | 2025-02-20 | Equipment | EQ-003 | Concrete Mixer | VEN-010 | 1 | Day | 4951.92 | 4725.45 | 850.58 | 5576.03 | Partially Paid | Low
EXP-00080 | PRJ-001 | PRJ-001-ACT-10 | 2025-02-20 | Material | MAT-004 | Aggregate | VEN-002 | 4.19 | Ton | 6022.34 | 5938.44 | 1068.92 | 7007.36 | Paid | Low
EXP-00081 | PRJ-001 | PRJ-001-ACT-03 | 2025-02-20 | Equipment | EQ-001 | Crane | VEN-010 | 6 | Day | 107792.36 | 108859.27 | 19594.67 | 128453.94 | Paid | Low
EXP-00082 | PRJ-001 | PRJ-001-ACT-05 | 2025-02-20 | Material | MAT-008 | Tiles | VEN-002 | 10.82 | Sq Ft | 773.57 | 794.83 | 143.07 | 937.9 | Paid | Medium
EXP-00083 | PRJ-001 | PRJ-001-ACT-01 | 2025-02-20 | Material | MAT-004 | Aggregate | VEN-006 | 2.86 | Ton | 4654.61 | 4600.76 | 828.14 | 5428.9 | Pending | Medium
EXP-00084 | PRJ-001 | PRJ-001-ACT-01 | 2025-02-25 | Material | MAT-004 | Aggregate | VEN-006 | 28 | Ton | 45566.09 | 46747.25 | 8414.5 | 55161.75 | Partially Paid | Low
EXP-00085 | PRJ-001 | PRJ-001-ACT-04 | 2025-02-25 | Contractor | CON-004 | Finishing Contract | VEN-010 | 1 | Contract | 265037.75 | 263358.13 | 47404.46 | 310762.59 | Paid | Low
EXP-00086 | PRJ-001 | PRJ-001-ACT-03 | 2025-02-25 | Contractor | CON-003 | Plumbing Contract | VEN-006 | 1 | Contract | 296994.84 | 287065.63 | 51671.81 | 338737.44 | Paid | Medium
EXP-00087 | PRJ-001 | PRJ-001-ACT-06 | 2025-02-25 | Other | OTH-001 | Transport | VEN-010 | 1 | Lot | 71828.44 | 76046.25 | 13688.32 | 89734.57 | Paid | Low
EXP-00088 | PRJ-001 | PRJ-001-ACT-08 | 2025-02-25 | Labour | LAB-004 | Electrician | VEN-006 | 14 | Worker | 24358.33 | 24107.1 | 4339.28 | 28446.38 | Paid | High
EXP-00089 | PRJ-001 | PRJ-001-ACT-01 | 2025-02-25 | Equipment | EQ-004 | Scaffolding | VEN-002 | 7 | Day | 17656.53 | 17873.5 | 3217.23 | 21090.73 | Paid | High
EXP-00090 | PRJ-001 | PRJ-001-ACT-01 | 2025-02-25 | Contractor | CON-002 | Electrical Contract | VEN-006 | 1 | Contract | 154716.66 | 163464.76 | 29423.66 | 192888.42 | Paid | Medium
EXP-00091 | PRJ-001 | PRJ-001-ACT-07 | 2025-02-25 | Material | MAT-003 | Sand | VEN-002 | 12.2 | Ton | 22196.74 | 22561.32 | 4061.04 | 26622.36 | Paid | Low
EXP-00092 | PRJ-001 | PRJ-001-ACT-10 | 2025-02-25 | Contractor | CON-001 | Civil Structure Contract | VEN-001 | 1 | Contract | 116238.14 | 117850.24 | 21213.04 | 139063.28 | Partially Paid | High
EXP-00093 | PRJ-001 | PRJ-001-ACT-02 | 2025-02-25 | Labour | LAB-003 | Carpenter | VEN-006 | 20 | Worker | 24521.65 | 26502.57 | 4770.46 | 31273.03 | Partially Paid | Low
EXP-00094 | PRJ-001 | PRJ-001-ACT-05 | 2025-03-02 | Labour | LAB-001 | Mason | VEN-002 | 20 | Worker | 29849.96 | 30951.4 | 5571.25 | 36522.65 | Paid | Low
EXP-00095 | PRJ-001 | PRJ-001-ACT-04 | 2025-03-02 | Labour | LAB-001 | Mason | VEN-001 | 20 | Worker | 27307.75 | 25818.02 | 4647.24 | 30465.26 | Paid | Low
EXP-00096 | PRJ-001 | PRJ-001-ACT-07 | 2025-03-02 | Material | MAT-003 | Sand | VEN-010 | 10.47 | Ton | 16328.74 | 17178.92 | 3092.21 | 20271.13 | Paid | Low
EXP-00097 | PRJ-001 | PRJ-001-ACT-01 | 2025-03-02 | Labour | LAB-006 | Painter | VEN-002 | 22 | Worker | 25868.77 | 25768.21 | 4638.28 | 30406.49 | Paid | Low
EXP-00098 | PRJ-001 | PRJ-001-ACT-04 | 2025-03-02 | Labour | LAB-001 | Mason | VEN-006 | 11 | Worker | 19340.08 | 18051.59 | 3249.29 | 21300.88 | Paid | Low
EXP-00099 | PRJ-001 | PRJ-001-ACT-01 | 2025-03-02 | Equipment | EQ-003 | Concrete Mixer | VEN-010 | 7 | Day | 30347.4 | 29333.76 | 5280.08 | 34613.84 | Paid | Low
EXP-00100 | PRJ-001 | PRJ-001-ACT-08 | 2025-03-07 | Material | MAT-006 | Electrical Cable | VEN-006 | 8.1 | Meter | 662.58 | 655.3 | 117.95 | 773.25 | Partially Paid | Medium
EXP-00101 | PRJ-001 | PRJ-001-ACT-08 | 2025-03-07 | Equipment | EQ-002 | Excavator | VEN-006 | 6 | Day | 88074.57 | 89547.69 | 16118.58 | 105666.27 | Paid | Low
EXP-00102 | PRJ-001 | PRJ-001-ACT-02 | 2025-03-07 | Material | MAT-007 | PVC Pipe | VEN-010 | 25.09 | Meter | 3124.54 | 3325.24 | 598.54 | 3923.78 | Partially Paid | Medium
EXP-00103 | PRJ-001 | PRJ-001-ACT-05 | 2025-03-07 | Equipment | EQ-004 | Scaffolding | VEN-001 | 3 | Day | 7001.72 | 7139.14 | 1285.05 | 8424.19 | Paid | Low
EXP-00104 | PRJ-001 | PRJ-001-ACT-09 | 2025-03-07 | Labour | LAB-002 | Helper | VEN-002 | 24 | Worker | 25429.74 | 23727.25 | 4270.9 | 27998.15 | Paid | Low
EXP-00105 | PRJ-001 | PRJ-001-ACT-07 | 2025-03-07 | Contractor | CON-004 | Finishing Contract | VEN-010 | 1 | Contract | 142941.2 | 143290.18 | 25792.23 | 169082.41 | Paid | Medium
EXP-00106 | PRJ-001 | PRJ-001-ACT-07 | 2025-03-07 | Equipment | EQ-001 | Crane | VEN-001 | 6 | Day | 109740.96 | 111133.17 | 20003.97 | 131137.14 | Paid | High
EXP-00107 | PRJ-001 | PRJ-001-ACT-06 | 2025-03-07 | Equipment | EQ-002 | Excavator | VEN-001 | 5 | Day | 74388.03 | 74410.76 | 13393.94 | 87804.7 | Paid | Low
EXP-00108 | PRJ-001 | PRJ-001-ACT-10 | 2025-03-12 | Equipment | EQ-002 | Excavator | VEN-001 | 5 | Day | 64199.96 | 66691.57 | 12004.48 | 78696.05 | Paid | Low
EXP-00109 | PRJ-001 | PRJ-001-ACT-07 | 2025-03-12 | Labour | LAB-002 | Helper | VEN-001 | 16 | Worker | 25426.13 | 25821.17 | 4647.81 | 30468.98 | Paid | Low
EXP-00110 | PRJ-001 | PRJ-001-ACT-01 | 2025-03-12 | Material | MAT-003 | Sand | VEN-002 | 16.08 | Ton | 26487.52 | 25386.81 | 4569.63 | 29956.44 | Paid | Medium
EXP-00111 | PRJ-001 | PRJ-001-ACT-01 | 2025-03-12 | Labour | LAB-003 | Carpenter | VEN-010 | 10 | Worker | 14491.57 | 13519.65 | 2433.54 | 15953.19 | Paid | High
EXP-00112 | PRJ-001 | PRJ-001-ACT-01 | 2025-03-12 | Material | MAT-010 | Glass | VEN-010 | 5.86 | Sq Ft | 951.09 | 936.58 | 168.58 | 1105.16 | Paid | Medium
EXP-00113 | PRJ-001 | PRJ-001-ACT-08 | 2025-03-12 | Material | MAT-001 | Cement | VEN-001 | 9.89 | Bag | 5172.46 | 5008.25 | 901.49 | 5909.74 | Paid | Low
EXP-00114 | PRJ-001 | PRJ-001-ACT-05 | 2025-03-12 | Material | MAT-003 | Sand | VEN-002 | 14.39 | Ton | 23199.66 | 24821.68 | 4467.9 | 29289.58 | Partially Paid | Low
EXP-00115 | PRJ-001 | PRJ-001-ACT-08 | 2025-03-17 | Equipment | EQ-003 | Concrete Mixer | VEN-001 | 7 | Day | 34280.67 | 33431.34 | 6017.64 | 39448.98 | Paid | Medium
EXP-00116 | PRJ-001 | PRJ-001-ACT-10 | 2025-03-17 | Material | MAT-009 | Paint | VEN-001 | 2.78 | Litre | 612.82 | 661.57 | 119.08 | 780.65 | Paid | High
EXP-00117 | PRJ-001 | PRJ-001-ACT-06 | 2025-03-17 | Material | MAT-010 | Glass | VEN-001 | 5.21 | Sq Ft | 847.53 | 891.37 | 160.45 | 1051.82 | Paid | Low
EXP-00118 | PRJ-001 | PRJ-001-ACT-04 | 2025-03-17 | Contractor | CON-003 | Plumbing Contract | VEN-006 | 1 | Contract | 246560.75 | 245678.88 | 44222.2 | 289901.08 | Paid | Medium
EXP-00119 | PRJ-001 | PRJ-001-ACT-02 | 2025-03-17 | Material | MAT-003 | Sand | VEN-010 | 6.88 | Ton | 12777.29 | 13113.25 | 2360.38 | 15473.63 | Paid | Low
EXP-00120 | PRJ-001 | PRJ-001-ACT-04 | 2025-03-17 | Material | MAT-006 | Electrical Cable | VEN-001 | 19.57 | Meter | 1890.48 | 1856.07 | 334.09 | 2190.16 | Paid | Low
EXP-00121 | PRJ-001 | PRJ-001-ACT-07 | 2025-03-17 | Contractor | CON-001 | Civil Structure Contract | VEN-002 | 1 | Contract | 292554.6 | 273351.43 | 49203.26 | 322554.69 | Paid | High
EXP-00122 | PRJ-001 | PRJ-001-ACT-05 | 2025-03-22 | Material | MAT-009 | Paint | VEN-001 | 2.96 | Litre | 613.4 | 636.66 | 114.6 | 751.26 | Paid | Low
EXP-00123 | PRJ-001 | PRJ-001-ACT-05 | 2025-03-22 | Material | MAT-001 | Cement | VEN-010 | 6.59 | Bag | 3165.78 | 3277.35 | 589.92 | 3867.27 | Paid | Low
EXP-00124 | PRJ-001 | PRJ-001-ACT-05 | 2025-03-22 | Material | MAT-009 | Paint | VEN-001 | 7.31 | Litre | 1331.75 | 1355.25 | 243.94 | 1599.19 | Paid | High
EXP-00125 | PRJ-001 | PRJ-001-ACT-06 | 2025-03-22 | Contractor | CON-003 | Plumbing Contract | VEN-001 | 1 | Contract | 433464.48 | 404669.37 | 72840.49 | 477509.86 | Paid | Medium
EXP-00126 | PRJ-001 | PRJ-001-ACT-04 | 2025-03-22 | Material | MAT-008 | Tiles | VEN-010 | 10.23 | Sq Ft | 793.66 | 792.05 | 142.57 | 934.62 | Paid | Low
EXP-00127 | PRJ-001 | PRJ-001-ACT-10 | 2025-03-22 | Material | MAT-003 | Sand | VEN-001 | 13.06 | Ton | 27050.52 | 25808.53 | 4645.54 | 30454.07 | Paid | Low
EXP-00128 | PRJ-001 | PRJ-001-ACT-10 | 2025-03-22 | Labour | LAB-001 | Mason | VEN-010 | 32 | Worker | 30450.7 | 30376.59 | 5467.79 | 35844.38 | Paid | High
EXP-00129 | PRJ-001 | PRJ-001-ACT-06 | 2025-03-22 | Contractor | CON-001 | Civil Structure Contract | VEN-006 | 1 | Contract | 159871.83 | 158931.61 | 28607.69 | 187539.3 | Paid | Medium
EXP-00130 | PRJ-001 | PRJ-001-ACT-08 | 2025-03-22 | Material | MAT-003 | Sand | VEN-001 | 7.88 | Ton | 12935.26 | 12245.23 | 2204.14 | 14449.37 | Paid | Low
EXP-00131 | PRJ-001 | PRJ-001-ACT-02 | 2025-03-27 | Labour | LAB-004 | Electrician | VEN-006 | 18 | Worker | 12174.87 | 11805.2 | 2124.94 | 13930.14 | Paid | Low
EXP-00132 | PRJ-001 | PRJ-001-ACT-05 | 2025-03-27 | Other | OTH-001 | Miscellaneous | VEN-010 | 1 | Lot | 68787.06 | 68840.52 | 12391.29 | 81231.81 | Paid | Medium
EXP-00133 | PRJ-001 | PRJ-001-ACT-08 | 2025-03-27 | Contractor | CON-002 | Electrical Contract | VEN-010 | 1 | Contract | 295183.22 | 278917.09 | 50205.08 | 329122.17 | Paid | Low
EXP-00134 | PRJ-001 | PRJ-001-ACT-01 | 2025-03-27 | Contractor | CON-003 | Plumbing Contract | VEN-010 | 1 | Contract | 413578.41 | 400235.33 | 72042.36 | 472277.69 | Partially Paid | Medium
EXP-00135 | PRJ-001 | PRJ-001-ACT-06 | 2025-03-27 | Equipment | EQ-004 | Scaffolding | VEN-006 | 7 | Day | 20226 | 18835.73 | 3390.43 | 22226.16 | Paid | Medium
EXP-00136 | PRJ-001 | PRJ-001-ACT-05 | 2025-03-27 | Material | MAT-007 | PVC Pipe | VEN-010 | 2.41 | Meter | 272.99 | 259.77 | 46.76 | 306.53 | Partially Paid | Low
EXP-00137 | PRJ-001 | PRJ-001-ACT-01 | 2025-04-01 | Material | MAT-009 | Paint | VEN-002 | 3.25 | Litre | 714.48 | 709.94 | 127.79 | 837.73 | Paid | Low
EXP-00138 | PRJ-001 | PRJ-001-ACT-09 | 2025-04-01 | Contractor | CON-004 | Finishing Contract | VEN-002 | 1 | Contract | 383315.01 | 390045.56 | 70208.2 | 460253.76 | Paid | Medium
EXP-00139 | PRJ-001 | PRJ-001-ACT-04 | 2025-04-01 | Contractor | CON-002 | Electrical Contract | VEN-010 | 1 | Contract | 407270.85 | 430236.71 | 77442.61 | 507679.32 | Paid | Medium
EXP-00140 | PRJ-001 | PRJ-001-ACT-10 | 2025-04-01 | Labour | LAB-003 | Carpenter | VEN-002 | 21 | Worker | 37326.24 | 34697.61 | 6245.57 | 40943.18 | Pending | Medium
EXP-00141 | PRJ-001 | PRJ-001-ACT-07 | 2025-04-01 | Material | MAT-001 | Cement | VEN-001 | 15.79 | Bag | 7762.18 | 7776.31 | 1399.74 | 9176.05 | Paid | Medium
EXP-00142 | PRJ-001 | PRJ-001-ACT-02 | 2025-04-01 | Labour | LAB-005 | Plumber | VEN-002 | 7 | Worker | 7918.69 | 7980.76 | 1436.54 | 9417.3 | Paid | Medium
EXP-00143 | PRJ-001 | PRJ-001-ACT-02 | 2025-04-01 | Equipment | EQ-003 | Concrete Mixer | VEN-010 | 6 | Day | 24035.64 | 25542.29 | 4597.61 | 30139.9 | Partially Paid | High
EXP-00144 | PRJ-001 | PRJ-001-ACT-05 | 2025-04-06 | Equipment | EQ-003 | Concrete Mixer | VEN-006 | 4 | Day | 16994.4 | 17631.34 | 3173.64 | 20804.98 | Pending | Low
EXP-00145 | PRJ-001 | PRJ-001-ACT-02 | 2025-04-06 | Contractor | CON-001 | Civil Structure Contract | VEN-006 | 1 | Contract | 158977.56 | 150134.68 | 27024.24 | 177158.92 | Paid | Medium
EXP-00146 | PRJ-001 | PRJ-001-ACT-08 | 2025-04-06 | Labour | LAB-004 | Electrician | VEN-006 | 17 | Worker | 14049.04 | 15032.36 | 2705.82 | 17738.18 | Paid | Low
EXP-00147 | PRJ-001 | PRJ-001-ACT-03 | 2025-04-06 | Labour | LAB-005 | Plumber | VEN-006 | 15 | Worker | 11005.38 | 10311.08 | 1855.99 | 12167.07 | Paid | Medium
EXP-00148 | PRJ-001 | PRJ-001-ACT-07 | 2025-04-06 | Labour | LAB-001 | Mason | VEN-002 | 33 | Worker | 46937.89 | 47467.2 | 8544.1 | 56011.3 | Paid | Low
EXP-00149 | PRJ-001 | PRJ-001-ACT-05 | 2025-04-06 | Material | MAT-005 | Bricks | VEN-002 | 3.03 | Piece | 29.48 | 31.23 | 5.62 | 36.85 | Paid | Medium
EXP-00150 | PRJ-001 | PRJ-001-ACT-06 | 2025-04-06 | Material | MAT-009 | Paint | VEN-006 | 39.41 | Litre | 9580.83 | 9170.22 | 1650.64 | 10820.86 | Paid | Low
EXP-00151 | PRJ-001 | PRJ-001-ACT-09 | 2025-04-06 | Material | MAT-006 | Electrical Cable | VEN-001 | 27.87 | Meter | 2222.2 | 2411.34 | 434.04 | 2845.38 | Paid | Low
EXP-00152 | PRJ-001 | PRJ-001-ACT-01 | 2025-04-06 | Material | MAT-004 | Aggregate | VEN-001 | 17.43 | Ton | 24317.19 | 25029.66 | 4505.34 | 29535 | Pending | Low
EXP-00153 | PRJ-001 | PRJ-001-ACT-10 | 2025-04-11 | Contractor | CON-003 | Plumbing Contract | VEN-002 | 1 | Contract | 349975.9 | 326394.55 | 58751.02 | 385145.57 | Paid | Medium
EXP-00154 | PRJ-001 | PRJ-001-ACT-07 | 2025-04-11 | Labour | LAB-001 | Mason | VEN-001 | 21 | Worker | 38828.69 | 36235.12 | 6522.32 | 42757.44 | Paid | Medium
EXP-00155 | PRJ-001 | PRJ-001-ACT-07 | 2025-04-11 | Labour | LAB-003 | Carpenter | VEN-006 | 23 | Worker | 30038.18 | 29576.89 | 5323.84 | 34900.73 | Paid | Low
EXP-00156 | PRJ-001 | PRJ-001-ACT-10 | 2025-04-11 | Material | MAT-002 | Steel | VEN-010 | 4.16 | Ton | 287454.34 | 280335.71 | 50460.43 | 330796.14 | Paid | Medium
EXP-00157 | PRJ-001 | PRJ-001-ACT-05 | 2025-04-11 | Equipment | EQ-004 | Scaffolding | VEN-002 | 1 | Day | 2329.48 | 2496.64 | 449.4 | 2946.04 | Paid | Low
EXP-00158 | PRJ-001 | PRJ-001-ACT-01 | 2025-04-11 | Material | MAT-007 | PVC Pipe | VEN-006 | 6.07 | Meter | 762.67 | 720.23 | 129.64 | 849.87 | Paid | Medium
EXP-00159 | PRJ-001 | PRJ-001-ACT-04 | 2025-04-11 | Labour | LAB-004 | Electrician | VEN-010 | 27 | Worker | 34496.56 | 34419.48 | 6195.51 | 40614.99 | Paid | Low
EXP-00160 | PRJ-001 | PRJ-001-ACT-02 | 2025-04-16 | Labour | LAB-004 | Electrician | VEN-002 | 9 | Worker | 13623.8 | 12629.35 | 2273.28 | 14902.63 | Paid | Low
EXP-00161 | PRJ-001 | PRJ-001-ACT-08 | 2025-04-16 | Material | MAT-005 | Bricks | VEN-002 | 5.65 | Piece | 57.68 | 54.14 | 9.75 | 63.89 | Paid | Low
EXP-00162 | PRJ-001 | PRJ-001-ACT-05 | 2025-04-16 | Other | OTH-001 | Miscellaneous | VEN-006 | 1 | Lot | 10082.57 | 10184.96 | 1833.29 | 12018.25 | Paid | Low
EXP-00163 | PRJ-001 | PRJ-001-ACT-09 | 2025-04-16 | Labour | LAB-004 | Electrician | VEN-006 | 5 | Worker | 3890.19 | 3797.75 | 683.6 | 4481.35 | Paid | Low
EXP-00164 | PRJ-001 | PRJ-001-ACT-01 | 2025-04-16 | Contractor | CON-004 | Finishing Contract | VEN-001 | 1 | Contract | 294565.38 | 299517.74 | 53913.19 | 353430.93 | Paid | Low
EXP-00165 | PRJ-001 | PRJ-001-ACT-10 | 2025-04-16 | Contractor | CON-001 | Civil Structure Contract | VEN-002 | 1 | Contract | 211972.87 | 201376.19 | 36247.71 | 237623.9 | Paid | Low
EXP-00166 | PRJ-001 | PRJ-001-ACT-09 | 2025-04-16 | Labour | LAB-006 | Painter | VEN-001 | 23 | Worker | 25405.91 | 24984.03 | 4497.13 | 29481.16 | Paid | Low
EXP-00167 | PRJ-001 | PRJ-001-ACT-08 | 2025-04-21 | Contractor | CON-004 | Finishing Contract | VEN-010 | 1 | Contract | 402793.5 | 399081.07 | 71834.59 | 470915.66 | Paid | Low
EXP-00168 | PRJ-001 | PRJ-001-ACT-05 | 2025-04-21 | Other | OTH-001 | Site Office | VEN-001 | 1 | Lot | 9076.11 | 8877.26 | 1597.91 | 10475.17 | Paid | Low
EXP-00169 | PRJ-001 | PRJ-001-ACT-01 | 2025-04-21 | Material | MAT-003 | Sand | VEN-001 | 12.14 | Ton | 17786.33 | 18846.74 | 3392.41 | 22239.15 | Pending | High
EXP-00170 | PRJ-001 | PRJ-001-ACT-09 | 2025-04-21 | Material | MAT-002 | Steel | VEN-002 | 9.5 | Ton | 547468.33 | 545571.48 | 98202.87 | 643774.35 | Paid | Low
EXP-00171 | PRJ-001 | PRJ-001-ACT-04 | 2025-04-21 | Material | MAT-002 | Steel | VEN-002 | 12.18 | Ton | 706696.27 | 687615.5 | 123770.79 | 811386.29 | Pending | Low
EXP-00172 | PRJ-001 | PRJ-001-ACT-06 | 2025-04-21 | Equipment | EQ-001 | Crane | VEN-010 | 7 | Day | 121496.76 | 117864.17 | 21215.55 | 139079.72 | Partially Paid | High
EXP-00173 | PRJ-001 | PRJ-001-ACT-01 | 2025-04-26 | Material | MAT-010 | Glass | VEN-002 | 10.49 | Sq Ft | 1541.36 | 1441.94 | 259.55 | 1701.49 | Paid | Medium
EXP-00174 | PRJ-001 | PRJ-001-ACT-05 | 2025-04-26 | Material | MAT-005 | Bricks | VEN-010 | 19.85 | Piece | 178.36 | 182.79 | 32.9 | 215.69 | Paid | Medium
EXP-00175 | PRJ-001 | PRJ-001-ACT-09 | 2025-04-26 | Material | MAT-009 | Paint | VEN-001 | 11.48 | Litre | 2553.1 | 2459.27 | 442.67 | 2901.94 | Partially Paid | Low
EXP-00176 | PRJ-001 | PRJ-001-ACT-03 | 2025-04-26 | Material | MAT-006 | Electrical Cable | VEN-002 | 12.38 | Meter | 1250.3 | 1179.01 | 212.22 | 1391.23 | Paid | Medium
EXP-00177 | PRJ-001 | PRJ-001-ACT-06 | 2025-04-26 | Material | MAT-007 | PVC Pipe | VEN-002 | 3.46 | Meter | 431.71 | 439.55 | 79.12 | 518.67 | Paid | Low
EXP-00178 | PRJ-001 | PRJ-001-ACT-06 | 2025-04-26 | Material | MAT-010 | Glass | VEN-010 | 2.63 | Sq Ft | 408.88 | 431.79 | 77.72 | 509.51 | Paid | Medium
EXP-00179 | PRJ-001 | PRJ-001-ACT-10 | 2025-04-26 | Labour | LAB-002 | Helper | VEN-001 | 9 | Worker | 16081.07 | 15312.35 | 2756.22 | 18068.57 | Paid | Low
EXP-00180 | PRJ-001 | PRJ-001-ACT-07 | 2025-05-01 | Material | MAT-006 | Electrical Cable | VEN-010 | 17.14 | Meter | 1541.81 | 1466.18 | 263.91 | 1730.09 | Paid | Medium
EXP-00181 | PRJ-001 | PRJ-001-ACT-09 | 2025-05-01 | Material | MAT-004 | Aggregate | VEN-006 | 18.81 | Ton | 29590.19 | 31829.63 | 5729.33 | 37558.96 | Pending | Low
EXP-00182 | PRJ-001 | PRJ-001-ACT-04 | 2025-05-01 | Material | MAT-005 | Bricks | VEN-001 | 4.3 | Piece | 42.48 | 42.22 | 7.6 | 49.82 | Paid | Medium
EXP-00183 | PRJ-001 | PRJ-001-ACT-04 | 2025-05-01 | Equipment | EQ-002 | Excavator | VEN-001 | 1 | Day | 13215.17 | 14062.95 | 2531.33 | 16594.28 | Partially Paid | Medium
EXP-00184 | PRJ-001 | PRJ-001-ACT-08 | 2025-05-01 | Material | MAT-001 | Cement | VEN-006 | 3.94 | Bag | 2008.76 | 2090.17 | 376.23 | 2466.4 | Pending | Low
EXP-00185 | PRJ-001 | PRJ-001-ACT-08 | 2025-05-01 | Contractor | CON-001 | Civil Structure Contract | VEN-001 | 1 | Contract | 334997.01 | 312431.77 | 56237.72 | 368669.49 | Paid | Medium
EXP-00186 | PRJ-001 | PRJ-001-ACT-10 | 2025-05-01 | Contractor | CON-001 | Civil Structure Contract | VEN-001 | 1 | Contract | 300956.9 | 317477.22 | 57145.9 | 374623.12 | Paid | High
EXP-00187 | PRJ-001 | PRJ-001-ACT-10 | 2025-05-01 | Contractor | CON-003 | Plumbing Contract | VEN-001 | 1 | Contract | 354448.56 | 367697.07 | 66185.47 | 433882.54 | Partially Paid | Low
EXP-00188 | PRJ-001 | PRJ-001-ACT-03 | 2025-05-01 | Equipment | EQ-004 | Scaffolding | VEN-002 | 2 | Day | 5020.39 | 4951.77 | 891.32 | 5843.09 | Paid | Medium
EXP-00189 | PRJ-001 | PRJ-001-ACT-05 | 2025-05-01 | Contractor | CON-001 | Civil Structure Contract | VEN-006 | 1 | Contract | 137654.54 | 141917.24 | 25545.1 | 167462.34 | Paid | Low
EXP-00190 | PRJ-001 | PRJ-001-ACT-09 | 2025-05-06 | Material | MAT-009 | Paint | VEN-002 | 4.94 | Litre | 1050.39 | 1015.05 | 182.71 | 1197.76 | Paid | High
EXP-00191 | PRJ-001 | PRJ-001-ACT-04 | 2025-05-06 | Material | MAT-010 | Glass | VEN-006 | 30.86 | Sq Ft | 5001.22 | 4696.49 | 845.37 | 5541.86 | Paid | Low
EXP-00192 | PRJ-001 | PRJ-001-ACT-03 | 2025-05-06 | Equipment | EQ-001 | Crane | VEN-010 | 1 | Day | 16621.18 | 17015.96 | 3062.87 | 20078.83 | Paid | Low
EXP-00193 | PRJ-001 | PRJ-001-ACT-05 | 2025-05-06 | Material | MAT-008 | Tiles | VEN-001 | 11.57 | Sq Ft | 851.7 | 876.33 | 157.74 | 1034.07 | Paid | Medium
EXP-00194 | PRJ-001 | PRJ-001-ACT-06 | 2025-05-06 | Other | OTH-001 | Permit | VEN-002 | 1 | Lot | 78977.26 | 79661.04 | 14338.99 | 94000.03 | Paid | Medium
EXP-00195 | PRJ-001 | PRJ-001-ACT-09 | 2025-05-06 | Material | MAT-007 | PVC Pipe | VEN-001 | 16.86 | Meter | 1912.99 | 2044.95 | 368.09 | 2413.04 | Paid | Medium
EXP-00196 | PRJ-001 | PRJ-001-ACT-08 | 2025-05-06 | Material | MAT-004 | Aggregate | VEN-010 | 1.57 | Ton | 2244.7 | 2086.41 | 375.55 | 2461.96 | Paid | Medium
EXP-00197 | PRJ-001 | PRJ-001-ACT-09 | 2025-05-06 | Contractor | CON-002 | Electrical Contract | VEN-001 | 1 | Contract | 275705.25 | 270359.24 | 48664.66 | 319023.9 | Paid | Medium
EXP-00198 | PRJ-001 | PRJ-001-ACT-06 | 2025-05-11 | Labour | LAB-004 | Electrician | VEN-010 | 5 | Worker | 3391.86 | 3612.88 | 650.32 | 4263.2 | Paid | Low
EXP-00199 | PRJ-001 | PRJ-001-ACT-09 | 2025-05-11 | Material | MAT-009 | Paint | VEN-002 | 6.21 | Litre | 1375.97 | 1307.9 | 235.42 | 1543.32 | Paid | High
EXP-00200 | PRJ-001 | PRJ-001-ACT-03 | 2025-05-11 | Contractor | CON-002 | Electrical Contract | VEN-002 | 1 | Contract | 281942.28 | 261361.31 | 47045.04 | 308406.35 | Partially Paid | Low
EXP-00201 | PRJ-001 | PRJ-001-ACT-06 | 2025-05-11 | Contractor | CON-002 | Electrical Contract | VEN-002 | 1 | Contract | 319140.16 | 310481.27 | 55886.63 | 366367.9 | Paid | Medium
EXP-00202 | PRJ-001 | PRJ-001-ACT-04 | 2025-05-11 | Material | MAT-009 | Paint | VEN-006 | 6.52 | Litre | 1575.25 | 1557.05 | 280.27 | 1837.32 | Pending | Medium
EXP-00203 | PRJ-001 | PRJ-001-ACT-04 | 2025-05-11 | Labour | LAB-006 | Painter | VEN-001 | 4 | Worker | 5617.08 | 5388.76 | 969.98 | 6358.74 | Paid | Low
EXP-00204 | PRJ-001 | PRJ-001-ACT-05 | 2025-05-16 | Contractor | CON-002 | Electrical Contract | VEN-001 | 1 | Contract | 92934.77 | 100564.62 | 18101.63 | 118666.25 | Paid | High
EXP-00205 | PRJ-001 | PRJ-001-ACT-04 | 2025-05-16 | Labour | LAB-002 | Helper | VEN-010 | 32 | Worker | 25244.75 | 24688.46 | 4443.92 | 29132.38 | Paid | Medium
EXP-00206 | PRJ-001 | PRJ-001-ACT-03 | 2025-05-16 | Equipment | EQ-001 | Crane | VEN-006 | 3 | Day | 48334.34 | 50671.25 | 9120.82 | 59792.07 | Paid | Medium
EXP-00207 | PRJ-001 | PRJ-001-ACT-09 | 2025-05-16 | Labour | LAB-003 | Carpenter | VEN-006 | 12 | Worker | 9171.61 | 9763.04 | 1757.35 | 11520.39 | Paid | Low
EXP-00208 | PRJ-001 | PRJ-001-ACT-01 | 2025-05-16 | Equipment | EQ-004 | Scaffolding | VEN-010 | 4 | Day | 11545.65 | 10993.39 | 1978.81 | 12972.2 | Paid | Low
EXP-00209 | PRJ-001 | PRJ-001-ACT-06 | 2025-05-16 | Labour | LAB-002 | Helper | VEN-010 | 34 | Worker | 52262.47 | 53070.86 | 9552.75 | 62623.61 | Paid | Low
EXP-00210 | PRJ-001 | PRJ-001-ACT-07 | 2025-05-21 | Material | MAT-005 | Bricks | VEN-002 | 6 | Piece | 56.04 | 52.17 | 9.39 | 61.56 | Paid | Low
EXP-00211 | PRJ-001 | PRJ-001-ACT-05 | 2025-05-21 | Material | MAT-010 | Glass | VEN-002 | 4.28 | Sq Ft | 689.21 | 709.24 | 127.66 | 836.9 | Partially Paid | Medium
EXP-00212 | PRJ-001 | PRJ-001-ACT-04 | 2025-05-21 | Material | MAT-001 | Cement | VEN-001 | 13.94 | Bag | 6449.23 | 6400.12 | 1152.02 | 7552.14 | Paid | Medium
EXP-00213 | PRJ-001 | PRJ-001-ACT-04 | 2025-05-21 | Material | MAT-002 | Steel | VEN-002 | 21.68 | Ton | 1307989.24 | 1334489.36 | 240208.08 | 1574697.44 | Paid | Low
EXP-00214 | PRJ-001 | PRJ-001-ACT-01 | 2025-05-21 | Contractor | CON-001 | Civil Structure Contract | VEN-001 | 1 | Contract | 116183 | 113306.07 | 20395.09 | 133701.16 | Pending | Medium
EXP-00215 | PRJ-001 | PRJ-001-ACT-10 | 2025-05-21 | Material | MAT-002 | Steel | VEN-001 | 4.72 | Ton | 268324.13 | 252117.53 | 45381.16 | 297498.69 | Paid | Medium
EXP-00216 | PRJ-001 | PRJ-001-ACT-06 | 2025-05-21 | Equipment | EQ-004 | Scaffolding | VEN-006 | 1 | Day | 2379.68 | 2556.97 | 460.25 | 3017.22 | Paid | Low
EXP-00217 | PRJ-001 | PRJ-001-ACT-07 | 2025-05-21 | Equipment | EQ-001 | Crane | VEN-001 | 5 | Day | 84902.2 | 81684.39 | 14703.19 | 96387.58 | Paid | Medium
EXP-00218 | PRJ-001 | PRJ-001-ACT-04 | 2025-05-26 | Material | MAT-005 | Bricks | VEN-001 | 5.07 | Piece | 56.3 | 52.36 | 9.42 | 61.78 | Pending | Medium
EXP-00219 | PRJ-001 | PRJ-001-ACT-05 | 2025-05-26 | Material | MAT-005 | Bricks | VEN-002 | 1.64 | Piece | 16.12 | 15.47 | 2.78 | 18.25 | Paid | Low
EXP-00220 | PRJ-001 | PRJ-001-ACT-01 | 2025-05-26 | Material | MAT-008 | Tiles | VEN-010 | 14.23 | Sq Ft | 980.97 | 1029.45 | 185.3 | 1214.75 | Paid | Medium
EXP-00221 | PRJ-001 | PRJ-001-ACT-09 | 2025-05-26 | Contractor | CON-002 | Electrical Contract | VEN-001 | 1 | Contract | 270453.54 | 254345.74 | 45782.23 | 300127.97 | Paid | Low
EXP-00222 | PRJ-001 | PRJ-001-ACT-06 | 2025-05-26 | Labour | LAB-005 | Plumber | VEN-002 | 24 | Worker | 41136.44 | 41000.2 | 7380.04 | 48380.24 | Paid | Low
EXP-00223 | PRJ-001 | PRJ-001-ACT-08 | 2025-05-26 | Material | MAT-002 | Steel | VEN-001 | 24.13 | Ton | 1344391.17 | 1372462.53 | 247043.26 | 1619505.79 | Paid | Low
EXP-00224 | PRJ-001 | PRJ-001-ACT-04 | 2025-05-26 | Labour | LAB-006 | Painter | VEN-002 | 23 | Worker | 17284.5 | 18163.71 | 3269.47 | 21433.18 | Partially Paid | Medium
EXP-00225 | PRJ-001 | PRJ-001-ACT-07 | 2025-05-26 | Material | MAT-007 | PVC Pipe | VEN-010 | 16.91 | Meter | 2114.9 | 2005.18 | 360.93 | 2366.11 | Paid | Medium
EXP-00226 | PRJ-001 | PRJ-001-ACT-06 | 2025-05-31 | Material | MAT-006 | Electrical Cable | VEN-010 | 4.9 | Meter | 510.45 | 477.06 | 85.87 | 562.93 | Paid | Low
EXP-00227 | PRJ-001 | PRJ-001-ACT-04 | 2025-05-31 | Material | MAT-002 | Steel | VEN-006 | 9.23 | Ton | 654245.59 | 630751.21 | 113535.22 | 744286.43 | Paid | Medium
EXP-00228 | PRJ-001 | PRJ-001-ACT-06 | 2025-05-31 | Labour | LAB-003 | Carpenter | VEN-006 | 26 | Worker | 39737.47 | 37497.67 | 6749.58 | 44247.25 | Paid | Medium
EXP-00229 | PRJ-001 | PRJ-001-ACT-10 | 2025-05-31 | Material | MAT-008 | Tiles | VEN-002 | 2.95 | Sq Ft | 211.85 | 204.44 | 36.8 | 241.24 | Pending | Low
EXP-00230 | PRJ-001 | PRJ-001-ACT-02 | 2025-05-31 | Material | MAT-009 | Paint | VEN-002 | 31.58 | Litre | 6520.01 | 6862.56 | 1235.26 | 8097.82 | Paid | Medium
EXP-00231 | PRJ-001 | PRJ-001-ACT-10 | 2025-05-31 | Labour | LAB-002 | Helper | VEN-002 | 29 | Worker | 20815.06 | 20027.63 | 3604.97 | 23632.6 | Paid | High
EXP-00232 | PRJ-001 | PRJ-001-ACT-03 | 2025-05-31 | Material | MAT-007 | PVC Pipe | VEN-006 | 12.13 | Meter | 1443.11 | 1442.64 | 259.68 | 1702.32 | Paid | Low
EXP-00233 | PRJ-001 | PRJ-001-ACT-08 | 2025-05-31 | Equipment | EQ-002 | Excavator | VEN-002 | 3 | Day | 39973.99 | 38957.71 | 7012.39 | 45970.1 | Paid | Low
EXP-00234 | PRJ-001 | PRJ-001-ACT-04 | 2025-05-31 | Material | MAT-009 | Paint | VEN-002 | 3.05 | Litre | 713.56 | 712.41 | 128.23 | 840.64 | Paid | Low
EXP-00235 | PRJ-001 | PRJ-001-ACT-08 | 2025-06-05 | Labour | LAB-006 | Painter | VEN-010 | 27 | Worker | 40435.71 | 38554.33 | 6939.78 | 45494.11 | Paid | Medium
EXP-00236 | PRJ-001 | PRJ-001-ACT-03 | 2025-06-05 | Labour | LAB-006 | Painter | VEN-002 | 27 | Worker | 29201.16 | 27928.1 | 5027.06 | 32955.16 | Paid | Medium
EXP-00237 | PRJ-001 | PRJ-001-ACT-04 | 2025-06-05 | Labour | LAB-006 | Painter | VEN-010 | 26 | Worker | 37247.95 | 38891.62 | 7000.49 | 45892.11 | Paid | Low
EXP-00238 | PRJ-001 | PRJ-001-ACT-09 | 2025-06-05 | Contractor | CON-004 | Finishing Contract | VEN-006 | 1 | Contract | 177506.62 | 187291.32 | 33712.44 | 221003.76 | Paid | Low
EXP-00239 | PRJ-001 | PRJ-001-ACT-06 | 2025-06-05 | Material | MAT-007 | PVC Pipe | VEN-006 | 2.6 | Meter | 323.21 | 318.73 | 57.37 | 376.1 | Paid | Low
EXP-00240 | PRJ-001 | PRJ-001-ACT-01 | 2025-06-05 | Material | MAT-006 | Electrical Cable | VEN-001 | 10.03 | Meter | 857.55 | 801.07 | 144.19 | 945.26 | Paid | Low
EXP-00241 | PRJ-001 | PRJ-001-ACT-05 | 2025-06-05 | Contractor | CON-004 | Finishing Contract | VEN-001 | 1 | Contract | 373475.82 | 375991.24 | 67678.42 | 443669.66 | Paid | Low
EXP-00242 | PRJ-001 | PRJ-001-ACT-02 | 2025-06-10 | Material | MAT-003 | Sand | VEN-006 | 2.4 | Ton | 4393.79 | 4238.16 | 762.87 | 5001.03 | Paid | Low
EXP-00243 | PRJ-001 | PRJ-001-ACT-09 | 2025-06-10 | Labour | LAB-004 | Electrician | VEN-010 | 27 | Worker | 29699.95 | 32207.48 | 5797.35 | 38004.83 | Paid | Low
EXP-00244 | PRJ-001 | PRJ-001-ACT-03 | 2025-06-10 | Material | MAT-007 | PVC Pipe | VEN-006 | 7.62 | Meter | 887.19 | 851.84 | 153.33 | 1005.17 | Paid | Medium
EXP-00245 | PRJ-001 | PRJ-001-ACT-04 | 2025-06-10 | Material | MAT-008 | Tiles | VEN-001 | 11.89 | Sq Ft | 785.19 | 770.43 | 138.68 | 909.11 | Paid | Low
EXP-00246 | PRJ-001 | PRJ-001-ACT-07 | 2025-06-10 | Material | MAT-006 | Electrical Cable | VEN-006 | 10.86 | Meter | 1005.44 | 939.76 | 169.16 | 1108.92 | Paid | Low
EXP-00247 | PRJ-001 | PRJ-001-ACT-05 | 2025-06-10 | Material | MAT-010 | Glass | VEN-001 | 9.64 | Sq Ft | 1664.08 | 1764.3 | 317.57 | 2081.87 | Paid | Low
EXP-00248 | PRJ-001 | PRJ-001-ACT-09 | 2025-06-10 | Material | MAT-005 | Bricks | VEN-006 | 2.69 | Piece | 20.22 | 21.41 | 3.85 | 25.26 | Paid | Low
EXP-00249 | PRJ-001 | PRJ-001-ACT-01 | 2025-06-10 | Contractor | CON-001 | Civil Structure Contract | VEN-006 | 1 | Contract | 423385.95 | 442693.81 | 79684.89 | 522378.7 | Paid | Low
EXP-00250 | PRJ-001 | PRJ-001-ACT-01 | 2025-06-10 | Contractor | CON-002 | Electrical Contract | VEN-001 | 1 | Contract | 104942.13 | 105647 | 19016.46 | 124663.46 | Paid | Low
EXP-00251 | PRJ-001 | PRJ-001-ACT-02 | 2025-06-15 | Equipment | EQ-002 | Excavator | VEN-001 | 2 | Day | 29835.74 | 30027.13 | 5404.88 | 35432.01 | Paid | Low
EXP-00252 | PRJ-001 | PRJ-001-ACT-10 | 2025-06-15 | Contractor | CON-003 | Plumbing Contract | VEN-002 | 1 | Contract | 98811.5 | 94483.72 | 17007.07 | 111490.79 | Paid | Low
EXP-00253 | PRJ-001 | PRJ-001-ACT-04 | 2025-06-15 | Material | MAT-004 | Aggregate | VEN-006 | 21.62 | Ton | 31078.39 | 32618.61 | 5871.35 | 38489.96 | Partially Paid | Medium
EXP-00254 | PRJ-001 | PRJ-001-ACT-09 | 2025-06-15 | Contractor | CON-004 | Finishing Contract | VEN-006 | 1 | Contract | 463711.04 | 444371.12 | 79986.8 | 524357.92 | Paid | Low
EXP-00255 | PRJ-001 | PRJ-001-ACT-01 | 2025-06-15 | Labour | LAB-002 | Helper | VEN-010 | 23 | Worker | 35327.18 | 36066.2 | 6491.92 | 42558.12 | Paid | Low
EXP-00256 | PRJ-001 | PRJ-001-ACT-03 | 2025-06-15 | Material | MAT-008 | Tiles | VEN-001 | 23.41 | Sq Ft | 1588.82 | 1638 | 294.84 | 1932.84 | Paid | Low
EXP-00257 | PRJ-001 | PRJ-001-ACT-10 | 2025-06-15 | Contractor | CON-004 | Finishing Contract | VEN-002 | 1 | Contract | 351726.13 | 335962.17 | 60473.19 | 396435.36 | Paid | Medium
EXP-00258 | PRJ-001 | PRJ-001-ACT-08 | 2025-06-20 | Contractor | CON-002 | Electrical Contract | VEN-006 | 1 | Contract | 121675.22 | 127766.82 | 22998.03 | 150764.85 | Paid | Medium
EXP-00259 | PRJ-001 | PRJ-001-ACT-05 | 2025-06-20 | Equipment | EQ-004 | Scaffolding | VEN-006 | 6 | Day | 14323.15 | 15345.89 | 2762.26 | 18108.15 | Partially Paid | Medium
EXP-00260 | PRJ-001 | PRJ-001-ACT-01 | 2025-06-20 | Labour | LAB-005 | Plumber | VEN-010 | 26 | Worker | 21301.57 | 20560.77 | 3700.94 | 24261.71 | Paid | High
EXP-00261 | PRJ-001 | PRJ-001-ACT-07 | 2025-06-20 | Other | OTH-001 | Safety | VEN-006 | 1 | Lot | 52834.62 | 56514.57 | 10172.62 | 66687.19 | Paid | Medium
EXP-00262 | PRJ-001 | PRJ-001-ACT-05 | 2025-06-20 | Material | MAT-003 | Sand | VEN-002 | 5.31 | Ton | 9158.08 | 8661.69 | 1559.1 | 10220.79 | Partially Paid | Low
EXP-00263 | PRJ-001 | PRJ-001-ACT-09 | 2025-06-20 | Equipment | EQ-003 | Concrete Mixer | VEN-010 | 2 | Day | 9516.52 | 9578.95 | 1724.21 | 11303.16 | Paid | Low
EXP-00264 | PRJ-001 | PRJ-001-ACT-10 | 2025-06-20 | Contractor | CON-004 | Finishing Contract | VEN-010 | 1 | Contract | 359843.06 | 342005.26 | 61560.95 | 403566.21 | Paid | Low
EXP-00265 | PRJ-001 | PRJ-001-ACT-03 | 2025-06-20 | Material | MAT-002 | Steel | VEN-001 | 16 | Ton | 1003707.25 | 1027988.34 | 185037.9 | 1213026.24 | Partially Paid | Low
EXP-00266 | PRJ-001 | PRJ-001-ACT-02 | 2025-06-25 | Labour | LAB-002 | Helper | VEN-010 | 6 | Worker | 8041.03 | 8635.66 | 1554.42 | 10190.08 | Paid | Medium
EXP-00267 | PRJ-001 | PRJ-001-ACT-07 | 2025-06-25 | Material | MAT-007 | PVC Pipe | VEN-010 | 23.17 | Meter | 2365.63 | 2427.63 | 436.97 | 2864.6 | Partially Paid | Low
EXP-00268 | PRJ-001 | PRJ-001-ACT-03 | 2025-06-25 | Material | MAT-009 | Paint | VEN-001 | 19.52 | Litre | 4913.69 | 4638.21 | 834.88 | 5473.09 | Paid | Medium
EXP-00269 | PRJ-001 | PRJ-001-ACT-03 | 2025-06-25 | Equipment | EQ-001 | Crane | VEN-002 | 6 | Day | 112767.9 | 111687.82 | 20103.81 | 131791.63 | Paid | Low
EXP-00270 | PRJ-001 | PRJ-001-ACT-05 | 2025-06-25 | Labour | LAB-006 | Painter | VEN-010 | 6 | Worker | 7074.5 | 6748.05 | 1214.65 | 7962.7 | Paid | Low
EXP-00271 | PRJ-001 | PRJ-001-ACT-10 | 2025-06-25 | Labour | LAB-006 | Painter | VEN-002 | 26 | Worker | 21399.09 | 20710.87 | 3727.96 | 24438.83 | Pending | Medium
EXP-00272 | PRJ-001 | PRJ-001-ACT-04 | 2025-06-25 | Equipment | EQ-001 | Crane | VEN-010 | 7 | Day | 130280 | 129057.88 | 23230.42 | 152288.3 | Paid | Low
EXP-00273 | PRJ-001 | PRJ-001-ACT-08 | 2025-06-25 | Labour | LAB-006 | Painter | VEN-010 | 24 | Worker | 28552.87 | 30523.28 | 5494.19 | 36017.47 | Paid | Low
EXP-00274 | PRJ-001 | PRJ-001-ACT-05 | 2025-06-30 | Material | MAT-003 | Sand | VEN-006 | 3.36 | Ton | 5756 | 5551.49 | 999.27 | 6550.76 | Paid | Low
EXP-00275 | PRJ-001 | PRJ-001-ACT-09 | 2025-06-30 | Contractor | CON-001 | Civil Structure Contract | VEN-002 | 1 | Contract | 316129.06 | 297458.09 | 53542.46 | 351000.55 | Paid | Low
EXP-00276 | PRJ-001 | PRJ-001-ACT-03 | 2025-06-30 | Material | MAT-002 | Steel | VEN-001 | 36.43 | Ton | 1997230.35 | 2090823.89 | 376348.3 | 2467172.19 | Paid | Medium
EXP-00277 | PRJ-001 | PRJ-001-ACT-04 | 2025-06-30 | Labour | LAB-003 | Carpenter | VEN-001 | 20 | Worker | 15544.42 | 14487.8 | 2607.8 | 17095.6 | Paid | Medium
EXP-00278 | PRJ-001 | PRJ-001-ACT-09 | 2025-06-30 | Material | MAT-003 | Sand | VEN-002 | 17.19 | Ton | 34272.32 | 34585.64 | 6225.42 | 40811.06 | Paid | Medium
EXP-00279 | PRJ-001 | PRJ-001-ACT-03 | 2025-06-30 | Labour | LAB-004 | Electrician | VEN-001 | 26 | Worker | 30179.4 | 32219.68 | 5799.54 | 38019.22 | Paid | Low
EXP-00280 | PRJ-001 | PRJ-001-ACT-08 | 2025-06-30 | Equipment | EQ-002 | Excavator | VEN-002 | 3 | Day | 44090.35 | 44046.19 | 7928.31 | 51974.5 | Paid | Low
EXP-00281 | PRJ-001 | PRJ-001-ACT-06 | 2025-06-30 | Material | MAT-010 | Glass | VEN-001 | 7.8 | Sq Ft | 1226.83 | 1236.63 | 222.59 | 1459.22 | Paid | Medium
EXP-00282 | PRJ-001 | PRJ-001-ACT-04 | 2025-06-30 | Labour | LAB-001 | Mason | VEN-010 | 16 | Worker | 21430.09 | 20280.94 | 3650.57 | 23931.51 | Paid | Medium
EXP-00283 | PRJ-001 | PRJ-001-ACT-07 | 2025-07-05 | Material | MAT-005 | Bricks | VEN-002 | 11.34 | Piece | 95.67 | 100.18 | 18.03 | 118.21 | Paid | Low
EXP-00284 | PRJ-001 | PRJ-001-ACT-05 | 2025-07-05 | Material | MAT-001 | Cement | VEN-010 | 4.64 | Bag | 2303.5 | 2300.77 | 414.14 | 2714.91 | Partially Paid | Low
EXP-00285 | PRJ-001 | PRJ-001-ACT-01 | 2025-07-05 | Equipment | EQ-004 | Scaffolding | VEN-006 | 4 | Day | 11099.45 | 10459.72 | 1882.75 | 12342.47 | Paid | Low
EXP-00286 | PRJ-001 | PRJ-001-ACT-10 | 2025-07-05 | Equipment | EQ-003 | Concrete Mixer | VEN-001 | 4 | Day | 17628.6 | 19156.31 | 3448.14 | 22604.45 | Paid | Low
EXP-00287 | PRJ-001 | PRJ-001-ACT-01 | 2025-07-05 | Material | MAT-004 | Aggregate | VEN-006 | 11.04 | Ton | 16408.35 | 17486.98 | 3147.66 | 20634.64 | Paid | Low
EXP-00288 | PRJ-001 | PRJ-001-ACT-08 | 2025-07-05 | Material | MAT-004 | Aggregate | VEN-006 | 7.74 | Ton | 11426.04 | 10986.83 | 1977.63 | 12964.46 | Paid | Medium
EXP-00289 | PRJ-001 | PRJ-001-ACT-10 | 2025-07-05 | Equipment | EQ-002 | Excavator | VEN-006 | 2 | Day | 24380.52 | 25977.68 | 4675.98 | 30653.66 | Paid | Low
EXP-00290 | PRJ-001 | PRJ-001-ACT-02 | 2025-07-05 | Labour | LAB-005 | Plumber | VEN-001 | 9 | Worker | 15564.58 | 14430.33 | 2597.46 | 17027.79 | Partially Paid | Medium
EXP-00291 | PRJ-001 | PRJ-001-ACT-01 | 2025-07-05 | Labour | LAB-005 | Plumber | VEN-006 | 18 | Worker | 11845.05 | 12605.4 | 2268.97 | 14874.37 | Paid | Low
EXP-00292 | PRJ-001 | PRJ-001-ACT-06 | 2025-07-10 | Material | MAT-002 | Steel | VEN-001 | 17.17 | Ton | 963979.43 | 1033848.63 | 186092.75 | 1219941.38 | Paid | Medium
EXP-00293 | PRJ-001 | PRJ-001-ACT-02 | 2025-07-10 | Labour | LAB-003 | Carpenter | VEN-010 | 6 | Worker | 10471.61 | 9817.18 | 1767.09 | 11584.27 | Paid | Low
EXP-00294 | PRJ-001 | PRJ-001-ACT-09 | 2025-07-10 | Labour | LAB-006 | Painter | VEN-002 | 7 | Worker | 7745.3 | 7713.44 | 1388.42 | 9101.86 | Paid | Low
EXP-00295 | PRJ-001 | PRJ-001-ACT-08 | 2025-07-10 | Equipment | EQ-001 | Crane | VEN-001 | 1 | Day | 19105.23 | 19607.92 | 3529.43 | 23137.35 | Paid | Low
EXP-00296 | PRJ-001 | PRJ-001-ACT-01 | 2025-07-10 | Material | MAT-001 | Cement | VEN-006 | 18.61 | Bag | 8865.03 | 9284.09 | 1671.14 | 10955.23 | Pending | Low
EXP-00297 | PRJ-001 | PRJ-001-ACT-02 | 2025-07-10 | Equipment | EQ-001 | Crane | VEN-001 | 6 | Day | 97880.15 | 97794.79 | 17603.06 | 115397.85 | Pending | Low
EXP-00298 | PRJ-001 | PRJ-001-ACT-10 | 2025-07-15 | Material | MAT-003 | Sand | VEN-006 | 30.32 | Ton | 48689.32 | 46771.94 | 8418.95 | 55190.89 | Paid | Low
EXP-00299 | PRJ-001 | PRJ-001-ACT-05 | 2025-07-15 | Contractor | CON-002 | Electrical Contract | VEN-001 | 1 | Contract | 214654.87 | 215551.34 | 38799.24 | 254350.58 | Paid | High
EXP-00300 | PRJ-001 | PRJ-001-ACT-04 | 2025-07-15 | Labour | LAB-001 | Mason | VEN-001 | 16 | Worker | 29498.57 | 28261.66 | 5087.1 | 33348.76 | Pending | Low
EXP-00301 | PRJ-001 | PRJ-001-ACT-06 | 2025-07-15 | Labour | LAB-005 | Plumber | VEN-001 | 30 | Worker | 47315.56 | 48429.95 | 8717.39 | 57147.34 | Partially Paid | Medium
EXP-00302 | PRJ-001 | PRJ-001-ACT-05 | 2025-07-15 | Material | MAT-007 | PVC Pipe | VEN-001 | 3.56 | Meter | 472.85 | 437.84 | 78.81 | 516.65 | Paid | Medium
EXP-00303 | PRJ-001 | PRJ-001-ACT-01 | 2025-07-15 | Material | MAT-003 | Sand | VEN-001 | 10.22 | Ton | 20899.55 | 20494.88 | 3689.08 | 24183.96 | Paid | Medium
EXP-00304 | PRJ-001 | PRJ-001-ACT-08 | 2025-07-15 | Material | MAT-005 | Bricks | VEN-001 | 65.58 | Piece | 582.25 | 542.01 | 97.56 | 639.57 | Partially Paid | Medium
EXP-00305 | PRJ-001 | PRJ-001-ACT-06 | 2025-07-15 | Labour | LAB-005 | Plumber | VEN-010 | 25 | Worker | 36637.41 | 38977.16 | 7015.89 | 45993.05 | Paid | Low
EXP-00306 | PRJ-001 | PRJ-001-ACT-03 | 2025-07-20 | Contractor | CON-003 | Plumbing Contract | VEN-001 | 1 | Contract | 249958.09 | 267338.41 | 48120.91 | 315459.32 | Paid | Low
EXP-00307 | PRJ-001 | PRJ-001-ACT-06 | 2025-07-20 | Material | MAT-001 | Cement | VEN-010 | 2.92 | Bag | 1532.42 | 1546.97 | 278.45 | 1825.42 | Paid | High
EXP-00308 | PRJ-001 | PRJ-001-ACT-03 | 2025-07-20 | Material | MAT-005 | Bricks | VEN-001 | 8.66 | Piece | 89.22 | 85.6 | 15.41 | 101.01 | Paid | High
EXP-00309 | PRJ-001 | PRJ-001-ACT-08 | 2025-07-20 | Material | MAT-004 | Aggregate | VEN-001 | 11.18 | Ton | 14590.55 | 14270.44 | 2568.68 | 16839.12 | Paid | Low
EXP-00310 | PRJ-001 | PRJ-001-ACT-05 | 2025-07-20 | Material | MAT-007 | PVC Pipe | VEN-006 | 8.9 | Meter | 1168.35 | 1128.15 | 203.07 | 1331.22 | Paid | Low
EXP-00311 | PRJ-001 | PRJ-001-ACT-02 | 2025-07-20 | Material | MAT-009 | Paint | VEN-010 | 6.74 | Litre | 1260.29 | 1321.46 | 237.86 | 1559.32 | Pending | Low
EXP-00312 | PRJ-001 | PRJ-001-ACT-10 | 2025-07-20 | Other | OTH-001 | Permit | VEN-010 | 1 | Lot | 10801.39 | 11735.91 | 2112.46 | 13848.37 | Paid | Low
EXP-00313 | PRJ-001 | PRJ-001-ACT-08 | 2025-07-25 | Contractor | CON-004 | Finishing Contract | VEN-001 | 1 | Contract | 372562.85 | 363346.04 | 65402.29 | 428748.33 | Paid | Medium
EXP-00314 | PRJ-001 | PRJ-001-ACT-07 | 2025-07-25 | Labour | LAB-001 | Mason | VEN-010 | 5 | Worker | 3641.8 | 3696.48 | 665.37 | 4361.85 | Paid | Low
EXP-00315 | PRJ-001 | PRJ-001-ACT-02 | 2025-07-25 | Material | MAT-003 | Sand | VEN-006 | 2.18 | Ton | 3426.22 | 3425.88 | 616.66 | 4042.54 | Paid | Medium
EXP-00316 | PRJ-001 | PRJ-001-ACT-10 | 2025-07-25 | Material | MAT-008 | Tiles | VEN-002 | 10.59 | Sq Ft | 713.55 | 745.47 | 134.18 | 879.65 | Paid | Medium
EXP-00317 | PRJ-001 | PRJ-001-ACT-07 | 2025-07-25 | Contractor | CON-003 | Plumbing Contract | VEN-002 | 1 | Contract | 84369.22 | 83260.1 | 14986.82 | 98246.92 | Partially Paid | Low
EXP-00318 | PRJ-001 | PRJ-001-ACT-05 | 2025-07-25 | Material | MAT-003 | Sand | VEN-001 | 25.04 | Ton | 42459.04 | 39973.28 | 7195.19 | 47168.47 | Paid | Low
EXP-00319 | PRJ-001 | PRJ-001-ACT-06 | 2025-07-25 | Labour | LAB-004 | Electrician | VEN-010 | 23 | Worker | 31642.41 | 33005.23 | 5940.94 | 38946.17 | Paid | Medium
EXP-00320 | PRJ-001 | PRJ-001-ACT-04 | 2025-07-25 | Contractor | CON-001 | Civil Structure Contract | VEN-002 | 1 | Contract | 433582.43 | 418796.88 | 75383.44 | 494180.32 | Paid | Low
EXP-00321 | PRJ-001 | PRJ-001-ACT-02 | 2025-07-25 | Contractor | CON-003 | Plumbing Contract | VEN-010 | 1 | Contract | 99168.82 | 95374.51 | 17167.41 | 112541.92 | Paid | Low
EXP-00322 | PRJ-001 | PRJ-001-ACT-02 | 2025-07-25 | Labour | LAB-006 | Painter | VEN-002 | 9 | Worker | 15322.22 | 15120.77 | 2721.74 | 17842.51 | Paid | Low
EXP-00323 | PRJ-001 | PRJ-001-ACT-09 | 2025-07-30 | Contractor | CON-001 | Civil Structure Contract | VEN-001 | 1 | Contract | 125010.14 | 123723.72 | 22270.27 | 145993.99 | Partially Paid | Medium
EXP-00324 | PRJ-001 | PRJ-001-ACT-03 | 2025-07-30 | Contractor | CON-001 | Civil Structure Contract | VEN-006 | 1 | Contract | 231606.27 | 216492.62 | 38968.67 | 255461.29 | Paid | Low
EXP-00325 | PRJ-001 | PRJ-001-ACT-01 | 2025-07-30 | Material | MAT-009 | Paint | VEN-001 | 3.38 | Litre | 693.48 | 753.21 | 135.58 | 888.79 | Paid | Medium
EXP-00326 | PRJ-001 | PRJ-001-ACT-08 | 2025-07-30 | Equipment | EQ-004 | Scaffolding | VEN-001 | 3 | Day | 8441.12 | 8176.16 | 1471.71 | 9647.87 | Paid | Low
EXP-00327 | PRJ-001 | PRJ-001-ACT-05 | 2025-07-30 | Contractor | CON-002 | Electrical Contract | VEN-010 | 1 | Contract | 114276.88 | 114303.02 | 20574.54 | 134877.56 | Paid | Medium
EXP-00328 | PRJ-001 | PRJ-001-ACT-02 | 2025-07-30 | Labour | LAB-006 | Painter | VEN-010 | 6 | Worker | 5989.62 | 6451.71 | 1161.31 | 7613.02 | Paid | Low
EXP-00329 | PRJ-001 | PRJ-001-ACT-02 | 2025-07-30 | Contractor | CON-004 | Finishing Contract | VEN-006 | 1 | Contract | 226857.28 | 214185.61 | 38553.41 | 252739.02 | Paid | Medium
EXP-00330 | PRJ-001 | PRJ-001-ACT-02 | 2025-07-30 | Contractor | CON-001 | Civil Structure Contract | VEN-006 | 1 | Contract | 129287.86 | 126225.34 | 22720.56 | 148945.9 | Paid | Low
EXP-00331 | PRJ-001 | PRJ-001-ACT-08 | 2025-07-30 | Equipment | EQ-002 | Excavator | VEN-001 | 6 | Day | 79668.88 | 85330.14 | 15359.43 | 100689.57 | Paid | Medium
EXP-00332 | PRJ-001 | PRJ-001-ACT-05 | 2025-08-04 | Material | MAT-005 | Bricks | VEN-002 | 4.01 | Piece | 42.73 | 40.54 | 7.3 | 47.84 | Paid | High
EXP-00333 | PRJ-001 | PRJ-001-ACT-06 | 2025-08-04 | Material | MAT-001 | Cement | VEN-006 | 16.3 | Bag | 9153.57 | 9508.54 | 1711.54 | 11220.08 | Paid | Medium
EXP-00334 | PRJ-001 | PRJ-001-ACT-06 | 2025-08-04 | Material | MAT-001 | Cement | VEN-002 | 19.89 | Bag | 11227.76 | 11189.63 | 2014.13 | 13203.76 | Pending | Low
EXP-00335 | PRJ-001 | PRJ-001-ACT-09 | 2025-08-04 | Material | MAT-002 | Steel | VEN-006 | 5.25 | Ton | 291383.76 | 294421.83 | 52995.93 | 347417.76 | Paid | Low
EXP-00336 | PRJ-001 | PRJ-001-ACT-04 | 2025-08-04 | Equipment | EQ-001 | Crane | VEN-006 | 6 | Day | 110719.29 | 109526.03 | 19714.69 | 129240.72 | Paid | Low
EXP-00337 | PRJ-001 | PRJ-001-ACT-09 | 2025-08-04 | Contractor | CON-004 | Finishing Contract | VEN-006 | 1 | Contract | 430626.87 | 411960.23 | 74152.84 | 486113.07 | Paid | Low
EXP-00338 | PRJ-001 | PRJ-001-ACT-09 | 2025-08-09 | Material | MAT-002 | Steel | VEN-006 | 5.67 | Ton | 313485.9 | 305106.82 | 54919.23 | 360026.05 | Paid | High
EXP-00339 | PRJ-001 | PRJ-001-ACT-04 | 2025-08-09 | Material | MAT-002 | Steel | VEN-010 | 54.9 | Ton | 3586276.76 | 3551447.83 | 639260.61 | 4190708.44 | Paid | Low
EXP-00340 | PRJ-001 | PRJ-001-ACT-10 | 2025-08-09 | Equipment | EQ-001 | Crane | VEN-006 | 2 | Day | 37361.11 | 38499.8 | 6929.96 | 45429.76 | Paid | High
EXP-00341 | PRJ-001 | PRJ-001-ACT-01 | 2025-08-09 | Labour | LAB-001 | Mason | VEN-010 | 18 | Worker | 29663.19 | 30691.96 | 5524.55 | 36216.51 | Paid | Medium
EXP-00342 | PRJ-001 | PRJ-001-ACT-10 | 2025-08-09 | Equipment | EQ-001 | Crane | VEN-002 | 2 | Day | 33136.34 | 32456.46 | 5842.16 | 38298.62 | Paid | Low
EXP-00343 | PRJ-001 | PRJ-001-ACT-02 | 2025-08-09 | Other | OTH-001 | Miscellaneous | VEN-006 | 1 | Lot | 81815.37 | 76180.34 | 13712.46 | 89892.8 | Paid | High
EXP-00344 | PRJ-001 | PRJ-001-ACT-10 | 2025-08-09 | Contractor | CON-002 | Electrical Contract | VEN-002 | 1 | Contract | 219988.36 | 237306 | 42715.08 | 280021.08 | Paid | Low
EXP-00345 | PRJ-001 | PRJ-001-ACT-01 | 2025-08-09 | Material | MAT-001 | Cement | VEN-006 | 6.54 | Bag | 3683.05 | 3870.75 | 696.74 | 4567.49 | Pending | High
EXP-00346 | PRJ-001 | PRJ-001-ACT-05 | 2025-08-14 | Other | OTH-001 | Permit | VEN-001 | 1 | Lot | 70121.41 | 73954.06 | 13311.73 | 87265.79 | Paid | Low
EXP-00347 | PRJ-001 | PRJ-001-ACT-03 | 2025-08-14 | Material | MAT-002 | Steel | VEN-010 | 14.03 | Ton | 906158.18 | 921610.88 | 165889.96 | 1087500.84 | Pending | High
EXP-00348 | PRJ-001 | PRJ-001-ACT-08 | 2025-08-14 | Material | MAT-004 | Aggregate | VEN-002 | 15.48 | Ton | 23064.77 | 24380.54 | 4388.5 | 28769.04 | Paid | Medium
EXP-00349 | PRJ-001 | PRJ-001-ACT-05 | 2025-08-14 | Labour | LAB-002 | Helper | VEN-001 | 7 | Worker | 7930.35 | 7424.09 | 1336.34 | 8760.43 | Paid | Medium
EXP-00350 | PRJ-001 | PRJ-001-ACT-08 | 2025-08-14 | Material | MAT-002 | Steel | VEN-010 | 3.42 | Ton | 223478.8 | 212974.05 | 38335.33 | 251309.38 | Paid | Low
EXP-00351 | PRJ-001 | PRJ-001-ACT-10 | 2025-08-14 | Material | MAT-004 | Aggregate | VEN-010 | 5.11 | Ton | 9310.77 | 8629.71 | 1553.35 | 10183.06 | Paid | Medium
EXP-00352 | PRJ-001 | PRJ-001-ACT-04 | 2025-08-14 | Material | MAT-005 | Bricks | VEN-010 | 2.79 | Piece | 20.06 | 21.59 | 3.89 | 25.48 | Paid | Low
EXP-00353 | PRJ-001 | PRJ-001-ACT-04 | 2025-08-14 | Labour | LAB-005 | Plumber | VEN-001 | 23 | Worker | 29721.27 | 30128.1 | 5423.06 | 35551.16 | Partially Paid | High
EXP-00354 | PRJ-001 | PRJ-001-ACT-07 | 2025-08-19 | Contractor | CON-002 | Electrical Contract | VEN-010 | 1 | Contract | 405638.87 | 389931.06 | 70187.59 | 460118.65 | Paid | High
EXP-00355 | PRJ-001 | PRJ-001-ACT-09 | 2025-08-19 | Material | MAT-004 | Aggregate | VEN-010 | 2.84 | Ton | 4374.01 | 4362.35 | 785.22 | 5147.57 | Paid | Low
EXP-00356 | PRJ-001 | PRJ-001-ACT-07 | 2025-08-19 | Material | MAT-007 | PVC Pipe | VEN-006 | 39.95 | Meter | 5207.53 | 5291.4 | 952.45 | 6243.85 | Paid | Medium
EXP-00357 | PRJ-001 | PRJ-001-ACT-04 | 2025-08-19 | Contractor | CON-001 | Civil Structure Contract | VEN-002 | 1 | Contract | 281775.42 | 296673.86 | 53401.29 | 350075.15 | Paid | Medium
EXP-00358 | PRJ-001 | PRJ-001-ACT-04 | 2025-08-19 | Material | MAT-010 | Glass | VEN-001 | 9.1 | Sq Ft | 1486.88 | 1416.43 | 254.96 | 1671.39 | Partially Paid | Low
EXP-00359 | PRJ-001 | PRJ-001-ACT-08 | 2025-08-19 | Equipment | EQ-002 | Excavator | VEN-010 | 4 | Day | 55231.09 | 52097.86 | 9377.61 | 61475.47 | Paid | Low
EXP-00360 | PRJ-001 | PRJ-001-ACT-05 | 2025-08-19 | Labour | LAB-006 | Painter | VEN-001 | 12 | Worker | 7696.03 | 7800.16 | 1404.03 | 9204.19 | Paid | Low
EXP-00361 | PRJ-001 | PRJ-001-ACT-06 | 2025-08-24 | Material | MAT-005 | Bricks | VEN-006 | 15.37 | Piece | 124.57 | 130.19 | 23.43 | 153.62 | Paid | Medium
EXP-00362 | PRJ-001 | PRJ-001-ACT-03 | 2025-08-24 | Other | OTH-001 | Site Office | VEN-002 | 1 | Lot | 64022.91 | 60642.22 | 10915.6 | 71557.82 | Paid | Low
EXP-00363 | PRJ-001 | PRJ-001-ACT-03 | 2025-08-24 | Material | MAT-009 | Paint | VEN-001 | 16.24 | Litre | 4013.09 | 3724.18 | 670.35 | 4394.53 | Paid | Low
EXP-00364 | PRJ-001 | PRJ-001-ACT-07 | 2025-08-24 | Labour | LAB-002 | Helper | VEN-001 | 13 | Worker | 8435.33 | 8759.04 | 1576.63 | 10335.67 | Paid | Low
EXP-00365 | PRJ-001 | PRJ-001-ACT-09 | 2025-08-24 | Labour | LAB-001 | Mason | VEN-002 | 7 | Worker | 12448.92 | 12191.13 | 2194.4 | 14385.53 | Paid | Medium
EXP-00366 | PRJ-001 | PRJ-001-ACT-09 | 2025-08-24 | Contractor | CON-003 | Plumbing Contract | VEN-006 | 1 | Contract | 228267.64 | 213480.29 | 38426.45 | 251906.74 | Partially Paid | Medium
EXP-00367 | PRJ-001 | PRJ-001-ACT-06 | 2025-08-24 | Equipment | EQ-001 | Crane | VEN-006 | 7 | Day | 135699.72 | 130903.8 | 23562.68 | 154466.48 | Partially Paid | Low
EXP-00368 | PRJ-001 | PRJ-001-ACT-06 | 2025-08-29 | Material | MAT-006 | Electrical Cable | VEN-001 | 7.47 | Meter | 629.87 | 666.41 | 119.95 | 786.36 | Paid | Medium
EXP-00369 | PRJ-001 | PRJ-001-ACT-07 | 2025-08-29 | Equipment | EQ-004 | Scaffolding | VEN-001 | 1 | Day | 2399.25 | 2405.99 | 433.08 | 2839.07 | Paid | Low
EXP-00370 | PRJ-001 | PRJ-001-ACT-03 | 2025-08-29 | Contractor | CON-003 | Plumbing Contract | VEN-001 | 1 | Contract | 359165.88 | 389624 | 70132.32 | 459756.32 | Paid | High
EXP-00371 | PRJ-001 | PRJ-001-ACT-08 | 2025-08-29 | Labour | LAB-003 | Carpenter | VEN-010 | 32 | Worker | 51248.23 | 50870.32 | 9156.66 | 60026.98 | Pending | Low
EXP-00372 | PRJ-001 | PRJ-001-ACT-06 | 2025-08-29 | Labour | LAB-005 | Plumber | VEN-006 | 19 | Worker | 30081.64 | 29830.08 | 5369.41 | 35199.49 | Paid | Low
EXP-00373 | PRJ-001 | PRJ-001-ACT-04 | 2025-08-29 | Contractor | CON-004 | Finishing Contract | VEN-010 | 1 | Contract | 194687.66 | 183767.07 | 33078.07 | 216845.14 | Paid | Medium
EXP-00374 | PRJ-001 | PRJ-001-ACT-07 | 2025-08-29 | Material | MAT-003 | Sand | VEN-010 | 3.29 | Ton | 5056.31 | 5322.96 | 958.13 | 6281.09 | Paid | Low
EXP-00375 | PRJ-001 | PRJ-001-ACT-01 | 2025-08-29 | Material | MAT-006 | Electrical Cable | VEN-010 | 15.05 | Meter | 1260.82 | 1215.56 | 218.8 | 1434.36 | Paid | Low
EXP-00376 | PRJ-001 | PRJ-001-ACT-09 | 2025-09-03 | Material | MAT-003 | Sand | VEN-002 | 6.15 | Ton | 9900.21 | 10091.64 | 1816.5 | 11908.14 | Pending | Medium
EXP-00377 | PRJ-001 | PRJ-001-ACT-07 | 2025-09-03 | Equipment | EQ-003 | Concrete Mixer | VEN-006 | 6 | Day | 29707.15 | 27545.95 | 4958.27 | 32504.22 | Paid | High
EXP-00378 | PRJ-001 | PRJ-001-ACT-10 | 2025-09-03 | Contractor | CON-002 | Electrical Contract | VEN-010 | 1 | Contract | 255686.41 | 269512.87 | 48512.32 | 318025.19 | Pending | Low
EXP-00379 | PRJ-001 | PRJ-001-ACT-02 | 2025-09-03 | Material | MAT-010 | Glass | VEN-001 | 10.58 | Sq Ft | 1652.51 | 1734.54 | 312.22 | 2046.76 | Paid | Low
EXP-00380 | PRJ-001 | PRJ-001-ACT-09 | 2025-09-03 | Labour | LAB-003 | Carpenter | VEN-002 | 19 | Worker | 26338.21 | 26130.81 | 4703.55 | 30834.36 | Paid | Low
EXP-00381 | PRJ-001 | PRJ-001-ACT-06 | 2025-09-03 | Labour | LAB-004 | Electrician | VEN-006 | 30 | Worker | 35423.97 | 34347.93 | 6182.63 | 40530.56 | Paid | Low
EXP-00382 | PRJ-001 | PRJ-001-ACT-02 | 2025-09-03 | Labour | LAB-006 | Painter | VEN-001 | 6 | Worker | 6541.45 | 6475.49 | 1165.59 | 7641.08 | Paid | Medium
EXP-00383 | PRJ-001 | PRJ-001-ACT-04 | 2025-09-03 | Labour | LAB-003 | Carpenter | VEN-006 | 31 | Worker | 19167.45 | 20221.96 | 3639.95 | 23861.91 | Paid | Low
EXP-00384 | PRJ-001 | PRJ-001-ACT-03 | 2025-09-08 | Contractor | CON-004 | Finishing Contract | VEN-002 | 1 | Contract | 80882.59 | 77505.8 | 13951.04 | 91456.84 | Paid | Low
EXP-00385 | PRJ-001 | PRJ-001-ACT-01 | 2025-09-08 | Material | MAT-004 | Aggregate | VEN-001 | 9.51 | Ton | 15424.38 | 16146.49 | 2906.37 | 19052.86 | Paid | Medium
EXP-00386 | PRJ-001 | PRJ-001-ACT-06 | 2025-09-08 | Equipment | EQ-001 | Crane | VEN-002 | 2 | Day | 32114.96 | 32459.9 | 5842.78 | 38302.68 | Paid | Medium
EXP-00387 | PRJ-001 | PRJ-001-ACT-04 | 2025-09-08 | Contractor | CON-001 | Civil Structure Contract | VEN-010 | 1 | Contract | 264637.52 | 267272.4 | 48109.03 | 315381.43 | Pending | Low
EXP-00388 | PRJ-001 | PRJ-001-ACT-10 | 2025-09-08 | Labour | LAB-002 | Helper | VEN-001 | 23 | Worker | 20847.77 | 20346.45 | 3662.36 | 24008.81 | Partially Paid | Low
EXP-00389 | PRJ-001 | PRJ-001-ACT-01 | 2025-09-08 | Contractor | CON-001 | Civil Structure Contract | VEN-010 | 1 | Contract | 75454.49 | 80929.95 | 14567.39 | 95497.34 | Partially Paid | Low
EXP-00390 | PRJ-001 | PRJ-001-ACT-10 | 2025-09-08 | Labour | LAB-001 | Mason | VEN-002 | 14 | Worker | 18294.44 | 18676.33 | 3361.74 | 22038.07 | Paid | Medium
EXP-00391 | PRJ-001 | PRJ-001-ACT-08 | 2025-09-08 | Material | MAT-003 | Sand | VEN-010 | 15.52 | Ton | 30038.4 | 28914.74 | 5204.65 | 34119.39 | Paid | Low
EXP-00392 | PRJ-001 | PRJ-001-ACT-01 | 2025-09-08 | Material | MAT-009 | Paint | VEN-002 | 14.13 | Litre | 2983.91 | 2819.18 | 507.45 | 3326.63 | Partially Paid | Medium
EXP-00393 | PRJ-001 | PRJ-001-ACT-05 | 2025-09-08 | Material | MAT-002 | Steel | VEN-006 | 5.82 | Ton | 359844.97 | 374939.52 | 67489.11 | 442428.63 | Paid | Low
EXP-00394 | PRJ-001 | PRJ-001-ACT-05 | 2025-09-13 | Labour | LAB-004 | Electrician | VEN-006 | 21 | Worker | 32452.48 | 33567.55 | 6042.16 | 39609.71 | Paid | Low
EXP-00395 | PRJ-001 | PRJ-001-ACT-07 | 2025-09-13 | Material | MAT-006 | Electrical Cable | VEN-010 | 18.81 | Meter | 1344.61 | 1364.53 | 245.62 | 1610.15 | Partially Paid | Low
EXP-00396 | PRJ-001 | PRJ-001-ACT-10 | 2025-09-13 | Labour | LAB-004 | Electrician | VEN-001 | 24 | Worker | 37488.95 | 36211.04 | 6517.99 | 42729.03 | Partially Paid | Low
EXP-00397 | PRJ-001 | PRJ-001-ACT-04 | 2025-09-13 | Contractor | CON-004 | Finishing Contract | VEN-001 | 1 | Contract | 169138.96 | 168733.85 | 30372.09 | 199105.94 | Paid | Low
EXP-00398 | PRJ-001 | PRJ-001-ACT-08 | 2025-09-13 | Material | MAT-009 | Paint | VEN-010 | 4.24 | Litre | 933.62 | 978.05 | 176.05 | 1154.1 | Paid | Medium
EXP-00399 | PRJ-001 | PRJ-001-ACT-10 | 2025-09-13 | Labour | LAB-002 | Helper | VEN-001 | 10 | Worker | 8899.5 | 9165.51 | 1649.79 | 10815.3 | Partially Paid | Low
EXP-00400 | PRJ-001 | PRJ-001-ACT-06 | 2025-09-13 | Contractor | CON-001 | Civil Structure Contract | VEN-006 | 1 | Contract | 408297.16 | 397056.29 | 71470.13 | 468526.42 | Partially Paid | Medium
EXP-00401 | PRJ-001 | PRJ-001-ACT-06 | 2025-09-13 | Contractor | CON-001 | Civil Structure Contract | VEN-001 | 1 | Contract | 138891.58 | 135137.03 | 24324.67 | 159461.7 | Paid | Medium
EXP-00402 | PRJ-001 | PRJ-001-ACT-01 | 2025-09-13 | Material | MAT-007 | PVC Pipe | VEN-006 | 9.82 | Meter | 988.14 | 1058.68 | 190.56 | 1249.24 | Paid | Low
EXP-00403 | PRJ-001 | PRJ-001-ACT-10 | 2025-09-18 | Contractor | CON-003 | Plumbing Contract | VEN-002 | 1 | Contract | 109418.02 | 114504.56 | 20610.82 | 135115.38 | Paid | Medium
EXP-00404 | PRJ-001 | PRJ-001-ACT-06 | 2025-09-18 | Material | MAT-003 | Sand | VEN-006 | 33.4 | Ton | 59436.88 | 57156.21 | 10288.12 | 67444.33 | Paid | High
EXP-00405 | PRJ-001 | PRJ-001-ACT-01 | 2025-09-18 | Material | MAT-003 | Sand | VEN-001 | 4.78 | Ton | 8819.6 | 9258.58 | 1666.54 | 10925.12 | Paid | Low
EXP-00406 | PRJ-001 | PRJ-001-ACT-01 | 2025-09-18 | Labour | LAB-005 | Plumber | VEN-001 | 32 | Worker | 31311.45 | 33209.2 | 5977.66 | 39186.86 | Paid | Low
EXP-00407 | PRJ-001 | PRJ-001-ACT-03 | 2025-09-18 | Material | MAT-007 | PVC Pipe | VEN-001 | 32.78 | Meter | 4563.15 | 4255.75 | 766.03 | 5021.78 | Paid | Medium
EXP-00408 | PRJ-001 | PRJ-001-ACT-03 | 2025-09-18 | Contractor | CON-003 | Plumbing Contract | VEN-006 | 1 | Contract | 388992.79 | 407107.41 | 73279.33 | 480386.74 | Paid | Medium
EXP-00409 | PRJ-001 | PRJ-001-ACT-08 | 2025-09-18 | Equipment | EQ-004 | Scaffolding | VEN-001 | 1 | Day | 2631.15 | 2482.53 | 446.86 | 2929.39 | Paid | Low
EXP-00410 | PRJ-001 | PRJ-001-ACT-03 | 2025-09-23 | Labour | LAB-003 | Carpenter | VEN-001 | 5 | Worker | 5562.3 | 5576.27 | 1003.73 | 6580 | Paid | Low
EXP-00411 | PRJ-001 | PRJ-001-ACT-03 | 2025-09-23 | Equipment | EQ-004 | Scaffolding | VEN-002 | 2 | Day | 4842.71 | 4566.97 | 822.05 | 5389.02 | Paid | Low
EXP-00412 | PRJ-001 | PRJ-001-ACT-04 | 2025-09-23 | Other | OTH-001 | Permit | VEN-010 | 1 | Lot | 78005.05 | 78628.05 | 14153.05 | 92781.1 | Paid | High
EXP-00413 | PRJ-001 | PRJ-001-ACT-10 | 2025-09-23 | Material | MAT-003 | Sand | VEN-001 | 5.6 | Ton | 9025.56 | 9694.54 | 1745.02 | 11439.56 | Paid | Low
EXP-00414 | PRJ-001 | PRJ-001-ACT-02 | 2025-09-23 | Equipment | EQ-002 | Excavator | VEN-002 | 1 | Day | 13933.24 | 13645.08 | 2456.11 | 16101.19 | Paid | Low
EXP-00415 | PRJ-001 | PRJ-001-ACT-08 | 2025-09-23 | Material | MAT-009 | Paint | VEN-010 | 3.7 | Litre | 832.44 | 796.51 | 143.37 | 939.88 | Paid | Medium
EXP-00416 | PRJ-001 | PRJ-001-ACT-05 | 2025-09-28 | Contractor | CON-003 | Plumbing Contract | VEN-006 | 1 | Contract | 319603.41 | 307677.67 | 55381.98 | 363059.65 | Paid | Low
EXP-00417 | PRJ-001 | PRJ-001-ACT-10 | 2025-09-28 | Contractor | CON-001 | Civil Structure Contract | VEN-001 | 1 | Contract | 174734.81 | 171836.63 | 30930.59 | 202767.22 | Paid | Medium
EXP-00418 | PRJ-001 | PRJ-001-ACT-06 | 2025-09-28 | Contractor | CON-002 | Electrical Contract | VEN-001 | 1 | Contract | 133120.98 | 133678.77 | 24062.18 | 157740.95 | Paid | Low
EXP-00419 | PRJ-001 | PRJ-001-ACT-09 | 2025-09-28 | Material | MAT-008 | Tiles | VEN-006 | 19.6 | Sq Ft | 1691.17 | 1632.57 | 293.86 | 1926.43 | Paid | Medium
EXP-00420 | PRJ-001 | PRJ-001-ACT-03 | 2025-09-28 | Labour | LAB-002 | Helper | VEN-002 | 26 | Worker | 38355.08 | 36619.37 | 6591.49 | 43210.86 | Paid | Medium
EXP-00421 | PRJ-001 | PRJ-001-ACT-03 | 2025-09-28 | Material | MAT-001 | Cement | VEN-002 | 11.18 | Bag | 6169.47 | 5863.7 | 1055.47 | 6919.17 | Paid | Low
EXP-00422 | PRJ-001 | PRJ-001-ACT-06 | 2025-09-28 | Equipment | EQ-002 | Excavator | VEN-006 | 7 | Day | 108747.72 | 103425.09 | 18616.52 | 122041.61 | Paid | High
EXP-00423 | PRJ-001 | PRJ-001-ACT-01 | 2025-10-03 | Contractor | CON-004 | Finishing Contract | VEN-010 | 1 | Contract | 155560.11 | 156461.58 | 28163.08 | 184624.66 | Paid | Low
EXP-00424 | PRJ-001 | PRJ-001-ACT-05 | 2025-10-03 | Contractor | CON-004 | Finishing Contract | VEN-006 | 1 | Contract | 92009.63 | 89617.25 | 16131.1 | 105748.35 | Paid | Medium
EXP-00425 | PRJ-001 | PRJ-001-ACT-07 | 2025-10-03 | Contractor | CON-004 | Finishing Contract | VEN-010 | 1 | Contract | 303941.93 | 325039.47 | 58507.1 | 383546.57 | Paid | Medium
EXP-00426 | PRJ-001 | PRJ-001-ACT-04 | 2025-10-03 | Equipment | EQ-004 | Scaffolding | VEN-002 | 3 | Day | 8543.34 | 8150.36 | 1467.06 | 9617.42 | Paid | Low
EXP-00427 | PRJ-001 | PRJ-001-ACT-01 | 2025-10-03 | Labour | LAB-003 | Carpenter | VEN-006 | 23 | Worker | 40688.69 | 38535.75 | 6936.43 | 45472.18 | Paid | Low
EXP-00428 | PRJ-001 | PRJ-001-ACT-03 | 2025-10-03 | Material | MAT-006 | Electrical Cable | VEN-001 | 24.56 | Meter | 1895.88 | 1798.85 | 323.79 | 2122.64 | Paid | Medium
EXP-00429 | PRJ-001 | PRJ-001-ACT-10 | 2025-10-03 | Labour | LAB-003 | Carpenter | VEN-001 | 28 | Worker | 20884.57 | 20432.37 | 3677.83 | 24110.2 | Paid | Medium
EXP-00430 | PRJ-001 | PRJ-001-ACT-04 | 2025-10-03 | Material | MAT-003 | Sand | VEN-001 | 14.47 | Ton | 28365.3 | 28924.69 | 5206.44 | 34131.13 | Paid | Medium
EXP-00431 | PRJ-001 | PRJ-001-ACT-03 | 2025-10-03 | Labour | LAB-005 | Plumber | VEN-001 | 15 | Worker | 19329.69 | 18274.05 | 3289.33 | 21563.38 | Paid | High
EXP-00432 | PRJ-001 | PRJ-001-ACT-02 | 2025-10-08 | Contractor | CON-003 | Plumbing Contract | VEN-001 | 1 | Contract | 322394.03 | 329074.36 | 59233.38 | 388307.74 | Pending | Low
EXP-00433 | PRJ-001 | PRJ-001-ACT-09 | 2025-10-08 | Labour | LAB-001 | Mason | VEN-001 | 25 | Worker | 22835.32 | 24164.54 | 4349.62 | 28514.16 | Paid | Medium
EXP-00434 | PRJ-001 | PRJ-001-ACT-06 | 2025-10-08 | Material | MAT-006 | Electrical Cable | VEN-010 | 3.35 | Meter | 300.37 | 323.08 | 58.15 | 381.23 | Paid | Low
EXP-00435 | PRJ-001 | PRJ-001-ACT-08 | 2025-10-08 | Material | MAT-006 | Electrical Cable | VEN-006 | 48.29 | Meter | 4617.73 | 4333.32 | 780 | 5113.32 | Paid | High
EXP-00436 | PRJ-001 | PRJ-001-ACT-05 | 2025-10-08 | Contractor | CON-001 | Civil Structure Contract | VEN-002 | 1 | Contract | 190937.84 | 178879.7 | 32198.35 | 211078.05 | Paid | Medium
EXP-00437 | PRJ-001 | PRJ-001-ACT-04 | 2025-10-08 | Material | MAT-008 | Tiles | VEN-002 | 10.54 | Sq Ft | 752.61 | 730.33 | 131.46 | 861.79 | Paid | Low
EXP-00438 | PRJ-001 | PRJ-001-ACT-05 | 2025-10-08 | Other | OTH-001 | Permit | VEN-010 | 1 | Lot | 73792.75 | 79792.84 | 14362.71 | 94155.55 | Partially Paid | Medium
EXP-00439 | PRJ-001 | PRJ-001-ACT-05 | 2025-10-08 | Other | OTH-001 | Site Office | VEN-010 | 1 | Lot | 30741.93 | 31063.03 | 5591.35 | 36654.38 | Paid | Medium
EXP-00440 | PRJ-001 | PRJ-001-ACT-02 | 2025-10-13 | Contractor | CON-002 | Electrical Contract | VEN-006 | 1 | Contract | 218811.07 | 231081.77 | 41594.72 | 272676.49 | Paid | Low
EXP-00441 | PRJ-001 | PRJ-001-ACT-04 | 2025-10-13 | Contractor | CON-003 | Plumbing Contract | VEN-010 | 1 | Contract | 140085.62 | 130228.34 | 23441.1 | 153669.44 | Paid | High
EXP-00442 | PRJ-001 | PRJ-001-ACT-07 | 2025-10-13 | Labour | LAB-003 | Carpenter | VEN-010 | 17 | Worker | 22329.44 | 23377.86 | 4208.01 | 27585.87 | Paid | Medium
EXP-00443 | PRJ-001 | PRJ-001-ACT-04 | 2025-10-13 | Material | MAT-005 | Bricks | VEN-010 | 15.7 | Piece | 135.43 | 127.32 | 22.92 | 150.24 | Paid | Low
EXP-00444 | PRJ-001 | PRJ-001-ACT-07 | 2025-10-13 | Other | OTH-001 | Transport | VEN-010 | 1 | Lot | 69420.7 | 67198.57 | 12095.74 | 79294.31 | Paid | Low
EXP-00445 | PRJ-001 | PRJ-001-ACT-08 | 2025-10-13 | Labour | LAB-006 | Painter | VEN-002 | 27 | Worker | 35587.81 | 36925.15 | 6646.53 | 43571.68 | Paid | Low
EXP-00446 | PRJ-001 | PRJ-001-ACT-10 | 2025-10-13 | Labour | LAB-001 | Mason | VEN-006 | 26 | Worker | 18361.39 | 18603.66 | 3348.66 | 21952.32 | Paid | Medium
EXP-00447 | PRJ-001 | PRJ-001-ACT-01 | 2025-10-18 | Equipment | EQ-003 | Concrete Mixer | VEN-010 | 2 | Day | 8717.69 | 8664.98 | 1559.7 | 10224.68 | Partially Paid | High
EXP-00448 | PRJ-001 | PRJ-001-ACT-10 | 2025-10-18 | Contractor | CON-003 | Plumbing Contract | VEN-010 | 1 | Contract | 269771.7 | 271035.05 | 48786.31 | 319821.36 | Paid | Medium
EXP-00449 | PRJ-001 | PRJ-001-ACT-07 | 2025-10-18 | Equipment | EQ-001 | Crane | VEN-010 | 3 | Day | 53786.55 | 57236.95 | 10302.65 | 67539.6 | Paid | Low
EXP-00450 | PRJ-001 | PRJ-001-ACT-01 | 2025-10-18 | Labour | LAB-001 | Mason | VEN-010 | 8 | Worker | 10267.32 | 9893.37 | 1780.81 | 11674.18 | Paid | Medium
EXP-00451 | PRJ-001 | PRJ-001-ACT-07 | 2025-10-18 | Material | MAT-008 | Tiles | VEN-010 | 27.32 | Sq Ft | 1849.2 | 1828.46 | 329.12 | 2157.58 | Paid | Low
EXP-00452 | PRJ-001 | PRJ-001-ACT-06 | 2025-10-18 | Material | MAT-002 | Steel | VEN-001 | 3.76 | Ton | 265659.64 | 261317.55 | 47037.16 | 308354.71 | Paid | Medium
EXP-00453 | PRJ-001 | PRJ-001-ACT-03 | 2025-10-18 | Material | MAT-010 | Glass | VEN-002 | 5.27 | Sq Ft | 904.91 | 857.56 | 154.36 | 1011.92 | Paid | Low
EXP-00454 | PRJ-001 | PRJ-001-ACT-05 | 2025-10-23 | Material | MAT-010 | Glass | VEN-006 | 7.59 | Sq Ft | 1239.79 | 1222.4 | 220.03 | 1442.43 | Paid | Medium
EXP-00455 | PRJ-001 | PRJ-001-ACT-04 | 2025-10-23 | Labour | LAB-004 | Electrician | VEN-001 | 16 | Worker | 14119.11 | 14669.83 | 2640.57 | 17310.4 | Paid | Low
EXP-00456 | PRJ-001 | PRJ-001-ACT-02 | 2025-10-23 | Material | MAT-007 | PVC Pipe | VEN-010 | 4.47 | Meter | 526.56 | 494.26 | 88.97 | 583.23 | Paid | Low
EXP-00457 | PRJ-001 | PRJ-001-ACT-07 | 2025-10-23 | Contractor | CON-002 | Electrical Contract | VEN-010 | 1 | Contract | 360903.77 | 360159.12 | 64828.64 | 424987.76 | Paid | High
EXP-00458 | PRJ-001 | PRJ-001-ACT-02 | 2025-10-23 | Material | MAT-005 | Bricks | VEN-002 | 5.47 | Piece | 49.25 | 53.11 | 9.56 | 62.67 | Paid | Low
EXP-00459 | PRJ-001 | PRJ-001-ACT-10 | 2025-10-23 | Equipment | EQ-004 | Scaffolding | VEN-010 | 7 | Day | 16508.96 | 16181.9 | 2912.74 | 19094.64 | Paid | Medium
EXP-00460 | PRJ-001 | PRJ-001-ACT-03 | 2025-10-28 | Contractor | CON-003 | Plumbing Contract | VEN-001 | 1 | Contract | 233166.34 | 243389.54 | 43810.12 | 287199.66 | Paid | Medium
EXP-00461 | PRJ-001 | PRJ-001-ACT-08 | 2025-10-28 | Material | MAT-008 | Tiles | VEN-001 | 10.68 | Sq Ft | 787.87 | 827.62 | 148.97 | 976.59 | Paid | Medium
EXP-00462 | PRJ-001 | PRJ-001-ACT-10 | 2025-10-28 | Equipment | EQ-001 | Crane | VEN-001 | 5 | Day | 97445.06 | 91184.07 | 16413.13 | 107597.2 | Paid | Low
EXP-00463 | PRJ-001 | PRJ-001-ACT-03 | 2025-10-28 | Material | MAT-006 | Electrical Cable | VEN-010 | 12.99 | Meter | 933.91 | 967.53 | 174.16 | 1141.69 | Paid | Low
EXP-00464 | PRJ-001 | PRJ-001-ACT-08 | 2025-10-28 | Material | MAT-003 | Sand | VEN-002 | 22.34 | Ton | 39991.61 | 42062.36 | 7571.22 | 49633.58 | Paid | Medium
EXP-00465 | PRJ-001 | PRJ-001-ACT-04 | 2025-10-28 | Labour | LAB-006 | Painter | VEN-010 | 29 | Worker | 48032.45 | 49296.25 | 8873.32 | 58169.57 | Paid | Medium
EXP-00466 | PRJ-001 | PRJ-001-ACT-03 | 2025-11-02 | Equipment | EQ-002 | Excavator | VEN-006 | 4 | Day | 50555.73 | 54207.68 | 9757.38 | 63965.06 | Paid | Low
EXP-00467 | PRJ-001 | PRJ-001-ACT-01 | 2025-11-02 | Material | MAT-008 | Tiles | VEN-010 | 32.37 | Sq Ft | 2726.74 | 2747.48 | 494.55 | 3242.03 | Paid | Low
EXP-00468 | PRJ-001 | PRJ-001-ACT-08 | 2025-11-02 | Material | MAT-007 | PVC Pipe | VEN-010 | 8.66 | Meter | 997.53 | 1039.67 | 187.14 | 1226.81 | Paid | Medium
EXP-00469 | PRJ-001 | PRJ-001-ACT-08 | 2025-11-02 | Contractor | CON-002 | Electrical Contract | VEN-010 | 1 | Contract | 136791.13 | 141447.19 | 25460.49 | 166907.68 | Paid | High
EXP-00470 | PRJ-001 | PRJ-001-ACT-09 | 2025-11-02 | Contractor | CON-001 | Civil Structure Contract | VEN-006 | 1 | Contract | 174402.03 | 168546.83 | 30338.43 | 198885.26 | Partially Paid | Low
EXP-00471 | PRJ-001 | PRJ-001-ACT-07 | 2025-11-02 | Contractor | CON-004 | Finishing Contract | VEN-010 | 1 | Contract | 321936.68 | 334145.93 | 60146.27 | 394292.2 | Paid | Low
EXP-00472 | PRJ-001 | PRJ-001-ACT-01 | 2025-11-07 | Labour | LAB-004 | Electrician | VEN-010 | 25 | Worker | 21185.43 | 21233.61 | 3822.05 | 25055.66 | Paid | Medium
EXP-00473 | PRJ-001 | PRJ-001-ACT-04 | 2025-11-07 | Contractor | CON-003 | Plumbing Contract | VEN-002 | 1 | Contract | 224928.6 | 237691.47 | 42784.46 | 280475.93 | Paid | Low
EXP-00474 | PRJ-001 | PRJ-001-ACT-07 | 2025-11-07 | Contractor | CON-004 | Finishing Contract | VEN-010 | 1 | Contract | 274551.83 | 293031.41 | 52745.65 | 345777.06 | Partially Paid | Low
EXP-00475 | PRJ-001 | PRJ-001-ACT-02 | 2025-11-07 | Equipment | EQ-002 | Excavator | VEN-010 | 1 | Day | 14222.03 | 15239.45 | 2743.1 | 17982.55 | Paid | Medium
EXP-00476 | PRJ-001 | PRJ-001-ACT-07 | 2025-11-07 | Material | MAT-005 | Bricks | VEN-001 | 12.98 | Piece | 111.42 | 103.46 | 18.62 | 122.08 | Paid | Low
EXP-00477 | PRJ-001 | PRJ-001-ACT-08 | 2025-11-07 | Labour | LAB-004 | Electrician | VEN-001 | 22 | Worker | 31125.55 | 30965.56 | 5573.8 | 36539.36 | Paid | Low
EXP-00478 | PRJ-001 | PRJ-001-ACT-06 | 2025-11-07 | Labour | LAB-004 | Electrician | VEN-006 | 29 | Worker | 41920.74 | 45315.58 | 8156.8 | 53472.38 | Paid | Low
EXP-00479 | PRJ-001 | PRJ-001-ACT-09 | 2025-11-12 | Material | MAT-001 | Cement | VEN-010 | 2.89 | Bag | 1492.72 | 1554.18 | 279.75 | 1833.93 | Paid | Low
EXP-00480 | PRJ-001 | PRJ-001-ACT-06 | 2025-11-12 | Contractor | CON-002 | Electrical Contract | VEN-001 | 1 | Contract | 430283.32 | 410956.57 | 73972.18 | 484928.75 | Paid | Low
EXP-00481 | PRJ-001 | PRJ-001-ACT-01 | 2025-11-12 | Labour | LAB-006 | Painter | VEN-001 | 20 | Worker | 22644.99 | 21241.7 | 3823.51 | 25065.21 | Paid | Low
EXP-00482 | PRJ-001 | PRJ-001-ACT-06 | 2025-11-12 | Material | MAT-001 | Cement | VEN-006 | 7.57 | Bag | 3497.85 | 3671.59 | 660.89 | 4332.48 | Paid | Medium
EXP-00483 | PRJ-001 | PRJ-001-ACT-09 | 2025-11-12 | Material | MAT-002 | Steel | VEN-006 | 8.85 | Ton | 504595.28 | 533514.42 | 96032.6 | 629547.02 | Paid | High
EXP-00484 | PRJ-001 | PRJ-001-ACT-07 | 2025-11-12 | Labour | LAB-004 | Electrician | VEN-002 | 26 | Worker | 33628 | 32217.78 | 5799.2 | 38016.98 | Paid | Medium
EXP-00485 | PRJ-001 | PRJ-001-ACT-04 | 2025-11-12 | Equipment | EQ-003 | Concrete Mixer | VEN-010 | 2 | Day | 10083.92 | 9600.56 | 1728.1 | 11328.66 | Paid | Low
EXP-00486 | PRJ-001 | PRJ-001-ACT-04 | 2025-11-17 | Other | OTH-001 | Miscellaneous | VEN-006 | 1 | Lot | 45145.86 | 44874.58 | 8077.42 | 52952 | Paid | Low
EXP-00487 | PRJ-001 | PRJ-001-ACT-04 | 2025-11-17 | Material | MAT-010 | Glass | VEN-010 | 6.14 | Sq Ft | 938.3 | 884.61 | 159.23 | 1043.84 | Paid | Low
EXP-00488 | PRJ-001 | PRJ-001-ACT-09 | 2025-11-17 | Labour | LAB-005 | Plumber | VEN-006 | 5 | Worker | 8925.47 | 8345.55 | 1502.2 | 9847.75 | Partially Paid | Medium
EXP-00489 | PRJ-001 | PRJ-001-ACT-10 | 2025-11-17 | Labour | LAB-006 | Painter | VEN-006 | 21 | Worker | 15350.08 | 14689.72 | 2644.15 | 17333.87 | Paid | Low
EXP-00490 | PRJ-001 | PRJ-001-ACT-05 | 2025-11-17 | Contractor | CON-002 | Electrical Contract | VEN-006 | 1 | Contract | 292920.5 | 277611.2 | 49970.02 | 327581.22 | Paid | Low
EXP-00491 | PRJ-001 | PRJ-001-ACT-10 | 2025-11-17 | Contractor | CON-002 | Electrical Contract | VEN-010 | 1 | Contract | 169843.96 | 168563.65 | 30341.46 | 198905.11 | Paid | High
EXP-00492 | PRJ-001 | PRJ-001-ACT-03 | 2025-11-17 | Material | MAT-010 | Glass | VEN-010 | 8.41 | Sq Ft | 1402.32 | 1437.79 | 258.8 | 1696.59 | Paid | Medium
EXP-00493 | PRJ-001 | PRJ-001-ACT-06 | 2025-11-17 | Contractor | CON-004 | Finishing Contract | VEN-010 | 1 | Contract | 305012.23 | 307253.8 | 55305.68 | 362559.48 | Paid | High
EXP-00494 | PRJ-001 | PRJ-001-ACT-02 | 2025-11-22 | Equipment | EQ-001 | Crane | VEN-001 | 3 | Day | 55739.95 | 58736.12 | 10572.5 | 69308.62 | Paid | Low
EXP-00495 | PRJ-001 | PRJ-001-ACT-07 | 2025-11-22 | Material | MAT-009 | Paint | VEN-010 | 12.36 | Litre | 2208.29 | 2331.02 | 419.58 | 2750.6 | Paid | Medium
EXP-00496 | PRJ-001 | PRJ-001-ACT-10 | 2025-11-22 | Contractor | CON-002 | Electrical Contract | VEN-001 | 1 | Contract | 103883.63 | 112592.09 | 20266.58 | 132858.67 | Paid | Medium
EXP-00497 | PRJ-001 | PRJ-001-ACT-05 | 2025-11-22 | Material | MAT-005 | Bricks | VEN-006 | 8.25 | Piece | 66.57 | 69 | 12.42 | 81.42 | Paid | Low
EXP-00498 | PRJ-001 | PRJ-001-ACT-01 | 2025-11-22 | Contractor | CON-003 | Plumbing Contract | VEN-006 | 1 | Contract | 205568.09 | 222335.67 | 40020.42 | 262356.09 | Paid | Low
EXP-00499 | PRJ-001 | PRJ-001-ACT-10 | 2025-11-22 | Contractor | CON-004 | Finishing Contract | VEN-006 | 1 | Contract | 213783.45 | 211542.29 | 38077.61 | 249619.9 | Paid | Low
EXP-00500 | PRJ-001 | PRJ-001-ACT-08 | 2025-11-22 | Labour | LAB-006 | Painter | VEN-006 | 34 | Worker | 23792.8 | 24077.41 | 4333.93 | 28411.34 | Partially Paid | Medium
EXP-00501 | PRJ-001 | PRJ-001-ACT-04 | 2025-11-22 | Material | MAT-005 | Bricks | VEN-010 | 11.08 | Piece | 81.65 | 87.38 | 15.73 | 103.11 | Paid | Low
EXP-00502 | PRJ-001 | PRJ-001-ACT-07 | 2025-11-22 | Labour | LAB-006 | Painter | VEN-001 | 13 | Worker | 19447.5 | 18358.8 | 3304.58 | 21663.38 | Paid | Medium
EXP-00503 | PRJ-001 | PRJ-001-ACT-03 | 2025-11-27 | Equipment | EQ-001 | Crane | VEN-010 | 2 | Day | 32797.41 | 33901.84 | 6102.33 | 40004.17 | Partially Paid | Low
EXP-00504 | PRJ-001 | PRJ-001-ACT-04 | 2025-11-27 | Equipment | EQ-002 | Excavator | VEN-006 | 6 | Day | 73622.54 | 77709.5 | 13987.71 | 91697.21 | Partially Paid | Medium
EXP-00505 | PRJ-001 | PRJ-001-ACT-06 | 2025-11-27 | Material | MAT-004 | Aggregate | VEN-002 | 4.26 | Ton | 5961.75 | 6219.97 | 1119.59 | 7339.56 | Paid | Medium
EXP-00506 | PRJ-001 | PRJ-001-ACT-02 | 2025-11-27 | Equipment | EQ-002 | Excavator | VEN-010 | 5 | Day | 67670.3 | 65188.44 | 11733.92 | 76922.36 | Paid | Medium
EXP-00507 | PRJ-001 | PRJ-001-ACT-10 | 2025-11-27 | Material | MAT-009 | Paint | VEN-002 | 5.13 | Litre | 1041.7 | 966.19 | 173.91 | 1140.1 | Pending | Medium
EXP-00508 | PRJ-001 | PRJ-001-ACT-05 | 2025-11-27 | Equipment | EQ-001 | Crane | VEN-001 | 7 | Day | 120069.77 | 120693.88 | 21724.9 | 142418.78 | Paid | Low
EXP-00509 | PRJ-001 | PRJ-001-ACT-08 | 2025-11-27 | Labour | LAB-001 | Mason | VEN-010 | 19 | Worker | 24424.56 | 26440.22 | 4759.24 | 31199.46 | Paid | Low
EXP-00510 | PRJ-001 | PRJ-001-ACT-04 | 2025-11-27 | Material | MAT-007 | PVC Pipe | VEN-001 | 14.84 | Meter | 1745.3 | 1648.86 | 296.79 | 1945.65 | Paid | Low
EXP-00511 | PRJ-001 | PRJ-001-ACT-03 | 2025-11-27 | Other | OTH-001 | Site Office | VEN-006 | 1 | Lot | 17404.36 | 16383.16 | 2948.97 | 19332.13 | Pending | Medium
EXP-00512 | PRJ-001 | PRJ-001-ACT-04 | 2025-12-02 | Labour | LAB-006 | Painter | VEN-002 | 31 | Worker | 45467.4 | 47549.92 | 8558.99 | 56108.91 | Paid | Low
EXP-00513 | PRJ-001 | PRJ-001-ACT-06 | 2025-12-02 | Labour | LAB-002 | Helper | VEN-001 | 18 | Worker | 12176.75 | 12940.83 | 2329.35 | 15270.18 | Paid | Medium
EXP-00514 | PRJ-001 | PRJ-001-ACT-02 | 2025-12-02 | Material | MAT-010 | Glass | VEN-001 | 5.24 | Sq Ft | 849.86 | 862.08 | 155.17 | 1017.25 | Paid | Low
EXP-00515 | PRJ-001 | PRJ-001-ACT-02 | 2025-12-02 | Labour | LAB-004 | Electrician | VEN-001 | 10 | Worker | 13598.77 | 13760.82 | 2476.95 | 16237.77 | Paid | Low
EXP-00516 | PRJ-001 | PRJ-001-ACT-09 | 2025-12-02 | Material | MAT-002 | Steel | VEN-006 | 30.47 | Ton | 1759131.01 | 1889297.86 | 340073.61 | 2229371.47 | Paid | Medium
EXP-00517 | PRJ-001 | PRJ-001-ACT-10 | 2025-12-02 | Material | MAT-006 | Electrical Cable | VEN-010 | 38.99 | Meter | 3061.15 | 2959.48 | 532.71 | 3492.19 | Paid | Low
EXP-00518 | PRJ-001 | PRJ-001-ACT-08 | 2025-12-02 | Equipment | EQ-001 | Crane | VEN-010 | 1 | Day | 19567.09 | 19215.11 | 3458.72 | 22673.83 | Paid | Low
EXP-00519 | PRJ-001 | PRJ-001-ACT-05 | 2025-12-07 | Material | MAT-004 | Aggregate | VEN-006 | 4.94 | Ton | 6748.81 | 7281.88 | 1310.74 | 8592.62 | Paid | High
EXP-00520 | PRJ-001 | PRJ-001-ACT-07 | 2025-12-07 | Contractor | CON-002 | Electrical Contract | VEN-001 | 1 | Contract | 117324.23 | 125466.1 | 22583.9 | 148050 | Partially Paid | High
EXP-00521 | PRJ-001 | PRJ-001-ACT-04 | 2025-12-07 | Equipment | EQ-003 | Concrete Mixer | VEN-001 | 3 | Day | 13767.7 | 12956.71 | 2332.21 | 15288.92 | Paid | Low
EXP-00522 | PRJ-001 | PRJ-001-ACT-06 | 2025-12-07 | Labour | LAB-006 | Painter | VEN-002 | 26 | Worker | 43881.52 | 41276.76 | 7429.82 | 48706.58 | Partially Paid | Medium
EXP-00523 | PRJ-001 | PRJ-001-ACT-09 | 2025-12-07 | Labour | LAB-006 | Painter | VEN-006 | 5 | Worker | 6621.01 | 6741.03 | 1213.39 | 7954.42 | Paid | Low
EXP-00524 | PRJ-001 | PRJ-001-ACT-07 | 2025-12-07 | Material | MAT-006 | Electrical Cable | VEN-006 | 6.81 | Meter | 572.04 | 569.14 | 102.45 | 671.59 | Partially Paid | High
EXP-00525 | PRJ-001 | PRJ-001-ACT-10 | 2025-12-07 | Labour | LAB-005 | Plumber | VEN-001 | 18 | Worker | 18256.81 | 18288.89 | 3292 | 21580.89 | Partially Paid | Medium
EXP-00526 | PRJ-001 | PRJ-001-ACT-03 | 2025-12-07 | Equipment | EQ-004 | Scaffolding | VEN-001 | 3 | Day | 7278.19 | 7749.93 | 1394.99 | 9144.92 | Paid | Low
EXP-00527 | PRJ-001 | PRJ-001-ACT-06 | 2025-12-07 | Contractor | CON-003 | Plumbing Contract | VEN-006 | 1 | Contract | 355495.07 | 348843.45 | 62791.82 | 411635.27 | Paid | Low
EXP-00528 | PRJ-001 | PRJ-001-ACT-05 | 2025-12-07 | Material | MAT-006 | Electrical Cable | VEN-010 | 5.18 | Meter | 448.73 | 447.04 | 80.47 | 527.51 | Paid | Low
EXP-00529 | PRJ-001 | PRJ-001-ACT-08 | 2025-12-12 | Labour | LAB-003 | Carpenter | VEN-010 | 19 | Worker | 14855.49 | 14654.81 | 2637.87 | 17292.68 | Paid | Low
EXP-00530 | PRJ-001 | PRJ-001-ACT-06 | 2025-12-12 | Labour | LAB-002 | Helper | VEN-006 | 14 | Worker | 13258.35 | 13475.76 | 2425.64 | 15901.4 | Paid | Medium
EXP-00531 | PRJ-001 | PRJ-001-ACT-08 | 2025-12-12 | Material | MAT-008 | Tiles | VEN-006 | 5.25 | Sq Ft | 418.44 | 403.57 | 72.64 | 476.21 | Paid | Medium
EXP-00532 | PRJ-001 | PRJ-001-ACT-10 | 2025-12-12 | Labour | LAB-006 | Painter | VEN-001 | 17 | Worker | 18890.88 | 17644.27 | 3175.97 | 20820.24 | Paid | Medium
EXP-00533 | PRJ-001 | PRJ-001-ACT-09 | 2025-12-12 | Contractor | CON-001 | Civil Structure Contract | VEN-001 | 1 | Contract | 329161.99 | 338290.3 | 60892.25 | 399182.55 | Paid | Low
EXP-00534 | PRJ-001 | PRJ-001-ACT-10 | 2025-12-12 | Contractor | CON-003 | Plumbing Contract | VEN-002 | 1 | Contract | 215485.41 | 213759.2 | 38476.66 | 252235.86 | Paid | Low
EXP-00535 | PRJ-001 | PRJ-001-ACT-10 | 2025-12-12 | Labour | LAB-001 | Mason | VEN-001 | 25 | Worker | 27659.15 | 29668.43 | 5340.32 | 35008.75 | Paid | Low
EXP-00536 | PRJ-001 | PRJ-001-ACT-04 | 2025-12-12 | Labour | LAB-005 | Plumber | VEN-006 | 16 | Worker | 13286.38 | 12518.69 | 2253.36 | 14772.05 | Paid | Low
EXP-00537 | PRJ-001 | PRJ-001-ACT-06 | 2025-12-12 | Equipment | EQ-004 | Scaffolding | VEN-010 | 2 | Day | 4790.42 | 4561.45 | 821.06 | 5382.51 | Pending | Medium
EXP-00538 | PRJ-001 | PRJ-001-ACT-10 | 2025-12-12 | Other | OTH-001 | Transport | VEN-001 | 1 | Lot | 24785.05 | 24685.29 | 4443.35 | 29128.64 | Paid | Medium
EXP-00539 | PRJ-001 | PRJ-001-ACT-02 | 2025-12-17 | Material | MAT-004 | Aggregate | VEN-001 | 4.81 | Ton | 6311.96 | 6259.51 | 1126.71 | 7386.22 | Paid | Medium
EXP-00540 | PRJ-001 | PRJ-001-ACT-08 | 2025-12-17 | Labour | LAB-003 | Carpenter | VEN-001 | 7 | Worker | 8300.2 | 8899.25 | 1601.87 | 10501.12 | Paid | High
EXP-00541 | PRJ-001 | PRJ-001-ACT-03 | 2025-12-17 | Material | MAT-004 | Aggregate | VEN-010 | 14.99 | Ton | 23344.74 | 23256.69 | 4186.2 | 27442.89 | Paid | Low
EXP-00542 | PRJ-001 | PRJ-001-ACT-06 | 2025-12-17 | Labour | LAB-003 | Carpenter | VEN-002 | 5 | Worker | 7234.46 | 6873.04 | 1237.15 | 8110.19 | Paid | Low
EXP-00543 | PRJ-001 | PRJ-001-ACT-10 | 2025-12-17 | Contractor | CON-002 | Electrical Contract | VEN-001 | 1 | Contract | 416420.55 | 439102.59 | 79038.47 | 518141.06 | Paid | Low
EXP-00544 | PRJ-001 | PRJ-001-ACT-02 | 2025-12-17 | Material | MAT-005 | Bricks | VEN-001 | 12.17 | Piece | 110.54 | 113.41 | 20.41 | 133.82 | Partially Paid | Low
EXP-00545 | PRJ-001 | PRJ-001-ACT-05 | 2025-12-22 | Material | MAT-002 | Steel | VEN-002 | 6.25 | Ton | 396535.2 | 404234.95 | 72762.29 | 476997.24 | Paid | Medium
EXP-00546 | PRJ-001 | PRJ-001-ACT-06 | 2025-12-22 | Contractor | CON-001 | Civil Structure Contract | VEN-010 | 1 | Contract | 436823.1 | 414577.06 | 74623.87 | 489200.93 | Paid | Low
EXP-00547 | PRJ-001 | PRJ-001-ACT-01 | 2025-12-22 | Material | MAT-002 | Steel | VEN-010 | 10.91 | Ton | 758178.71 | 742560.14 | 133660.83 | 876220.97 | Paid | Medium
EXP-00548 | PRJ-001 | PRJ-001-ACT-07 | 2025-12-22 | Material | MAT-003 | Sand | VEN-010 | 25.49 | Ton | 48157.03 | 47611.53 | 8570.08 | 56181.61 | Paid | Low
EXP-00549 | PRJ-001 | PRJ-001-ACT-05 | 2025-12-22 | Labour | LAB-003 | Carpenter | VEN-002 | 13 | Worker | 16233.3 | 16567.82 | 2982.21 | 19550.03 | Paid | Low
EXP-00550 | PRJ-001 | PRJ-001-ACT-03 | 2025-12-22 | Material | MAT-006 | Electrical Cable | VEN-002 | 19.54 | Meter | 2002.08 | 1886.32 | 339.54 | 2225.86 | Paid | Low
EXP-00551 | PRJ-001 | PRJ-001-ACT-05 | 2025-12-22 | Labour | LAB-003 | Carpenter | VEN-006 | 16 | Worker | 20647.89 | 20580.55 | 3704.5 | 24285.05 | Pending | Low
EXP-00552 | PRJ-001 | PRJ-001-ACT-09 | 2025-12-22 | Material | MAT-007 | PVC Pipe | VEN-001 | 7.03 | Meter | 687.74 | 741.86 | 133.53 | 875.39 | Paid | Low
EXP-00553 | PRJ-001 | PRJ-001-ACT-10 | 2025-12-22 | Equipment | EQ-003 | Concrete Mixer | VEN-001 | 6 | Day | 26545.78 | 26753.1 | 4815.56 | 31568.66 | Pending | High
EXP-00554 | PRJ-001 | PRJ-001-ACT-09 | 2025-12-22 | Contractor | CON-004 | Finishing Contract | VEN-002 | 1 | Contract | 225695.13 | 209302.39 | 37674.43 | 246976.82 | Paid | High
EXP-00555 | PRJ-001 | PRJ-001-ACT-02 | 2025-12-27 | Contractor | CON-003 | Plumbing Contract | VEN-006 | 1 | Contract | 78658.32 | 76570.29 | 13782.65 | 90352.94 | Paid | Low
EXP-00556 | PRJ-001 | PRJ-001-ACT-04 | 2025-12-27 | Labour | LAB-004 | Electrician | VEN-010 | 4 | Worker | 2913.43 | 2702.21 | 486.4 | 3188.61 | Paid | High
EXP-00557 | PRJ-001 | PRJ-001-ACT-07 | 2025-12-27 | Labour | LAB-006 | Painter | VEN-010 | 16 | Worker | 13807.63 | 14759.4 | 2656.69 | 17416.09 | Paid | Medium
EXP-00558 | PRJ-001 | PRJ-001-ACT-02 | 2025-12-27 | Equipment | EQ-003 | Concrete Mixer | VEN-006 | 7 | Day | 32939.16 | 33274.29 | 5989.37 | 39263.66 | Paid | Medium
EXP-00559 | PRJ-001 | PRJ-001-ACT-05 | 2025-12-27 | Contractor | CON-002 | Electrical Contract | VEN-006 | 1 | Contract | 424176.68 | 402865.25 | 72515.74 | 475380.99 | Paid | Low
EXP-00560 | PRJ-001 | PRJ-001-ACT-06 | 2025-12-27 | Material | MAT-007 | PVC Pipe | VEN-006 | 5.73 | Meter | 720.32 | 735.37 | 132.37 | 867.74 | Paid | Low
EXP-00561 | PRJ-001 | PRJ-001-ACT-10 | 2025-12-27 | Material | MAT-003 | Sand | VEN-001 | 16.77 | Ton | 26563.14 | 26925.8 | 4846.64 | 31772.44 | Paid | Low
EXP-00562 | PRJ-001 | PRJ-001-ACT-03 | 2026-01-01 | Other | OTH-001 | Site Office | VEN-010 | 1 | Lot | 73332.65 | 79556.12 | 14320.1 | 93876.22 | Paid | Medium
EXP-00563 | PRJ-001 | PRJ-001-ACT-09 | 2026-01-01 | Labour | LAB-001 | Mason | VEN-001 | 4 | Worker | 4096.69 | 4230.14 | 761.43 | 4991.57 | Paid | Medium
EXP-00564 | PRJ-001 | PRJ-001-ACT-02 | 2026-01-01 | Labour | LAB-001 | Mason | VEN-001 | 24 | Worker | 28864.88 | 28620.02 | 5151.6 | 33771.62 | Paid | Low
EXP-00565 | PRJ-001 | PRJ-001-ACT-03 | 2026-01-01 | Contractor | CON-002 | Electrical Contract | VEN-010 | 1 | Contract | 233943.63 | 252385.31 | 45429.36 | 297814.67 | Paid | Low
EXP-00566 | PRJ-001 | PRJ-001-ACT-05 | 2026-01-01 | Contractor | CON-002 | Electrical Contract | VEN-001 | 1 | Contract | 251629.76 | 267440.66 | 48139.32 | 315579.98 | Paid | Low
EXP-00567 | PRJ-001 | PRJ-001-ACT-01 | 2026-01-01 | Contractor | CON-004 | Finishing Contract | VEN-010 | 1 | Contract | 258569.99 | 267640.45 | 48175.28 | 315815.73 | Paid | Low
EXP-00568 | PRJ-001 | PRJ-001-ACT-06 | 2026-01-01 | Material | MAT-002 | Steel | VEN-002 | 4.63 | Ton | 300291.88 | 297883.47 | 53619.02 | 351502.49 | Paid | Low
EXP-00569 | PRJ-001 | PRJ-001-ACT-09 | 2026-01-01 | Contractor | CON-001 | Civil Structure Contract | VEN-010 | 1 | Contract | 244680.98 | 260445.42 | 46880.18 | 307325.6 | Paid | Low
EXP-00570 | PRJ-001 | PRJ-001-ACT-03 | 2026-01-01 | Labour | LAB-001 | Mason | VEN-006 | 19 | Worker | 18076.88 | 18812.08 | 3386.17 | 22198.25 | Paid | Low
EXP-00571 | PRJ-001 | PRJ-001-ACT-02 | 2026-01-06 | Contractor | CON-001 | Civil Structure Contract | VEN-002 | 1 | Contract | 287161.9 | 283175.17 | 50971.53 | 334146.7 | Paid | Medium
EXP-00572 | PRJ-001 | PRJ-001-ACT-10 | 2026-01-06 | Material | MAT-010 | Glass | VEN-006 | 8.62 | Sq Ft | 1323.22 | 1386.68 | 249.6 | 1636.28 | Paid | Low
EXP-00573 | PRJ-001 | PRJ-001-ACT-04 | 2026-01-06 | Contractor | CON-003 | Plumbing Contract | VEN-006 | 1 | Contract | 386604.86 | 398804.96 | 71784.89 | 470589.85 | Paid | Low
EXP-00574 | PRJ-001 | PRJ-001-ACT-04 | 2026-01-06 | Material | MAT-005 | Bricks | VEN-001 | 50.79 | Piece | 493.21 | 479.47 | 86.3 | 565.77 | Pending | High
EXP-00575 | PRJ-001 | PRJ-001-ACT-09 | 2026-01-06 | Equipment | EQ-004 | Scaffolding | VEN-006 | 3 | Day | 6530.22 | 6823.83 | 1228.29 | 8052.12 | Partially Paid | Low
EXP-00576 | PRJ-001 | PRJ-001-ACT-10 | 2026-01-06 | Material | MAT-004 | Aggregate | VEN-001 | 2.98 | Ton | 4595.17 | 4470.08 | 804.61 | 5274.69 | Paid | Medium
EXP-00577 | PRJ-001 | PRJ-001-ACT-06 | 2026-01-06 | Contractor | CON-004 | Finishing Contract | VEN-002 | 1 | Contract | 432560.17 | 424386.74 | 76389.61 | 500776.35 | Paid | Low
EXP-00578 | PRJ-001 | PRJ-001-ACT-03 | 2026-01-06 | Material | MAT-005 | Bricks | VEN-002 | 15.96 | Piece | 160.92 | 163.71 | 29.47 | 193.18 | Paid | Medium
EXP-00579 | PRJ-001 | PRJ-001-ACT-10 | 2026-01-06 | Equipment | EQ-003 | Concrete Mixer | VEN-006 | 6 | Day | 24798.16 | 26281.59 | 4730.69 | 31012.28 | Paid | Low
EXP-00580 | PRJ-001 | PRJ-001-ACT-03 | 2026-01-11 | Material | MAT-008 | Tiles | VEN-006 | 19.9 | Sq Ft | 1715.44 | 1638.11 | 294.86 | 1932.97 | Paid | Medium
EXP-00581 | PRJ-001 | PRJ-001-ACT-06 | 2026-01-11 | Material | MAT-004 | Aggregate | VEN-006 | 2.91 | Ton | 3783.61 | 3792 | 682.56 | 4474.56 | Paid | Low
EXP-00582 | PRJ-001 | PRJ-001-ACT-03 | 2026-01-11 | Material | MAT-010 | Glass | VEN-010 | 3.79 | Sq Ft | 656.67 | 614.75 | 110.66 | 725.41 | Partially Paid | Medium
EXP-00583 | PRJ-001 | PRJ-001-ACT-08 | 2026-01-11 | Material | MAT-002 | Steel | VEN-002 | 10.09 | Ton | 594033.92 | 593978.86 | 106916.19 | 700895.05 | Paid | Low
EXP-00584 | PRJ-001 | PRJ-001-ACT-03 | 2026-01-11 | Material | MAT-006 | Electrical Cable | VEN-002 | 11.86 | Meter | 850.94 | 858.44 | 154.52 | 1012.96 | Paid | Medium
EXP-00585 | PRJ-001 | PRJ-001-ACT-08 | 2026-01-11 | Material | MAT-003 | Sand | VEN-006 | 8.11 | Ton | 15215.26 | 16168.04 | 2910.25 | 19078.29 | Paid | Medium
EXP-00586 | PRJ-001 | PRJ-001-ACT-03 | 2026-01-11 | Equipment | EQ-003 | Concrete Mixer | VEN-010 | 3 | Day | 11705.62 | 12605.92 | 2269.07 | 14874.99 | Paid | Low
EXP-00587 | PRJ-001 | PRJ-001-ACT-07 | 2026-01-11 | Contractor | CON-001 | Civil Structure Contract | VEN-010 | 1 | Contract | 393523.55 | 382707.05 | 68887.27 | 451594.32 | Paid | Low
EXP-00588 | PRJ-001 | PRJ-001-ACT-01 | 2026-01-11 | Labour | LAB-003 | Carpenter | VEN-006 | 19 | Worker | 32063.3 | 30457.29 | 5482.31 | 35939.6 | Paid | Low
EXP-00589 | PRJ-001 | PRJ-001-ACT-01 | 2026-01-11 | Contractor | CON-004 | Finishing Contract | VEN-006 | 1 | Contract | 325504.48 | 347014.35 | 62462.58 | 409476.93 | Paid | Medium
EXP-00590 | PRJ-001 | PRJ-001-ACT-07 | 2026-01-16 | Equipment | EQ-004 | Scaffolding | VEN-010 | 7 | Day | 17796.35 | 16620.77 | 2991.74 | 19612.51 | Paid | Medium
EXP-00591 | PRJ-001 | PRJ-001-ACT-04 | 2026-01-16 | Material | MAT-001 | Cement | VEN-010 | 11.63 | Bag | 5148.77 | 5542.35 | 997.62 | 6539.97 | Paid | Low
EXP-00592 | PRJ-001 | PRJ-001-ACT-06 | 2026-01-16 | Material | MAT-007 | PVC Pipe | VEN-002 | 9.13 | Meter | 1034.61 | 1098.15 | 197.67 | 1295.82 | Pending | Low
EXP-00593 | PRJ-001 | PRJ-001-ACT-09 | 2026-01-16 | Material | MAT-008 | Tiles | VEN-002 | 19.8 | Sq Ft | 1490.71 | 1498.39 | 269.71 | 1768.1 | Paid | Medium
EXP-00594 | PRJ-001 | PRJ-001-ACT-10 | 2026-01-16 | Contractor | CON-004 | Finishing Contract | VEN-002 | 1 | Contract | 230554.93 | 232113.67 | 41780.46 | 273894.13 | Paid | Medium
EXP-00595 | PRJ-001 | PRJ-001-ACT-06 | 2026-01-16 | Labour | LAB-001 | Mason | VEN-002 | 10 | Worker | 15600.95 | 16225.02 | 2920.5 | 19145.52 | Paid | Low
EXP-00596 | PRJ-001 | PRJ-001-ACT-05 | 2026-01-16 | Labour | LAB-002 | Helper | VEN-001 | 28 | Worker | 21780.01 | 21594.05 | 3886.93 | 25480.98 | Paid | Low
EXP-00597 | PRJ-001 | PRJ-001-ACT-06 | 2026-01-16 | Contractor | CON-003 | Plumbing Contract | VEN-001 | 1 | Contract | 103948.86 | 100351.78 | 18063.32 | 118415.1 | Partially Paid | Low
EXP-00598 | PRJ-001 | PRJ-001-ACT-01 | 2026-01-21 | Labour | LAB-004 | Electrician | VEN-002 | 13 | Worker | 9352.77 | 10103.52 | 1818.63 | 11922.15 | Pending | Low
EXP-00599 | PRJ-001 | PRJ-001-ACT-08 | 2026-01-21 | Material | MAT-008 | Tiles | VEN-002 | 5.32 | Sq Ft | 408.32 | 393.28 | 70.79 | 464.07 | Paid | Medium
EXP-00600 | PRJ-001 | PRJ-001-ACT-07 | 2026-01-21 | Contractor | CON-002 | Electrical Contract | VEN-002 | 1 | Contract | 82218.4 | 78716.51 | 14168.97 | 92885.48 | Paid | High
EXP-00601 | PRJ-001 | PRJ-001-ACT-07 | 2026-01-21 | Labour | LAB-006 | Painter | VEN-002 | 25 | Worker | 41143 | 38746.88 | 6974.44 | 45721.32 | Paid | Medium
EXP-00602 | PRJ-001 | PRJ-001-ACT-09 | 2026-01-21 | Material | MAT-010 | Glass | VEN-002 | 10.56 | Sq Ft | 1634.49 | 1555.15 | 279.93 | 1835.08 | Paid | Medium
EXP-00603 | PRJ-001 | PRJ-001-ACT-06 | 2026-01-21 | Material | MAT-001 | Cement | VEN-001 | 9.84 | Bag | 4579.88 | 4633.14 | 833.97 | 5467.11 | Paid | Low
EXP-00604 | PRJ-001 | PRJ-001-ACT-06 | 2026-01-21 | Material | MAT-004 | Aggregate | VEN-001 | 3.91 | Ton | 6650.05 | 6406.69 | 1153.2 | 7559.89 | Paid | Medium
EXP-00605 | PRJ-001 | PRJ-001-ACT-07 | 2026-01-21 | Material | MAT-010 | Glass | VEN-002 | 4.13 | Sq Ft | 621.17 | 594.25 | 106.96 | 701.21 | Paid | Medium
EXP-00606 | PRJ-001 | PRJ-001-ACT-02 | 2026-01-21 | Material | MAT-003 | Sand | VEN-010 | 3.75 | Ton | 6745.8 | 7278.29 | 1310.09 | 8588.38 | Partially Paid | Low
EXP-00607 | PRJ-001 | PRJ-001-ACT-05 | 2026-01-26 | Other | OTH-001 | Miscellaneous | VEN-006 | 1 | Lot | 15277.26 | 15425.17 | 2776.53 | 18201.7 | Paid | Low
EXP-00608 | PRJ-001 | PRJ-001-ACT-10 | 2026-01-26 | Material | MAT-001 | Cement | VEN-010 | 5.59 | Bag | 2669.21 | 2722.77 | 490.1 | 3212.87 | Paid | Low
EXP-00609 | PRJ-001 | PRJ-001-ACT-02 | 2026-01-26 | Material | MAT-010 | Glass | VEN-006 | 4.63 | Sq Ft | 667.18 | 672.86 | 121.11 | 793.97 | Partially Paid | Medium
EXP-00610 | PRJ-001 | PRJ-001-ACT-06 | 2026-01-26 | Material | MAT-005 | Bricks | VEN-001 | 24.18 | Piece | 189.35 | 199.37 | 35.89 | 235.26 | Pending | Low
EXP-00611 | PRJ-001 | PRJ-001-ACT-10 | 2026-01-26 | Material | MAT-001 | Cement | VEN-006 | 6.48 | Bag | 2758.43 | 2907.73 | 523.39 | 3431.12 | Paid | High
EXP-00612 | PRJ-001 | PRJ-001-ACT-10 | 2026-01-26 | Material | MAT-001 | Cement | VEN-006 | 53.79 | Bag | 27686.94 | 27784.03 | 5001.13 | 32785.16 | Paid | Medium
EXP-00613 | PRJ-001 | PRJ-001-ACT-09 | 2026-01-31 | Material | MAT-007 | PVC Pipe | VEN-001 | 10.18 | Meter | 1380.05 | 1311.65 | 236.1 | 1547.75 | Paid | High
EXP-00614 | PRJ-001 | PRJ-001-ACT-04 | 2026-01-31 | Contractor | CON-004 | Finishing Contract | VEN-001 | 1 | Contract | 430418.8 | 422365.6 | 76025.81 | 498391.41 | Partially Paid | Medium
EXP-00615 | PRJ-001 | PRJ-001-ACT-01 | 2026-01-31 | Labour | LAB-001 | Mason | VEN-010 | 13 | Worker | 23496.26 | 22917.76 | 4125.2 | 27042.96 | Paid | High
EXP-00616 | PRJ-001 | PRJ-001-ACT-01 | 2026-01-31 | Labour | LAB-006 | Painter | VEN-010 | 30 | Worker | 44720.41 | 47132.39 | 8483.83 | 55616.22 | Paid | Medium
EXP-00617 | PRJ-001 | PRJ-001-ACT-06 | 2026-01-31 | Material | MAT-010 | Glass | VEN-006 | 6.86 | Sq Ft | 1086.74 | 1133.76 | 204.08 | 1337.84 | Paid | Low
EXP-00618 | PRJ-001 | PRJ-001-ACT-01 | 2026-01-31 | Material | MAT-001 | Cement | VEN-010 | 8.06 | Bag | 4068.86 | 3853.72 | 693.67 | 4547.39 | Paid | Low
EXP-00619 | PRJ-001 | PRJ-001-ACT-01 | 2026-01-31 | Contractor | CON-001 | Civil Structure Contract | VEN-010 | 1 | Contract | 145744.8 | 135635.46 | 24414.38 | 160049.84 | Paid | Medium
EXP-00620 | PRJ-001 | PRJ-001-ACT-08 | 2026-01-31 | Labour | LAB-002 | Helper | VEN-006 | 16 | Worker | 27501.19 | 26529.69 | 4775.34 | 31305.03 | Paid | Medium
EXP-00621 | PRJ-001 | PRJ-001-ACT-01 | 2026-01-31 | Material | MAT-004 | Aggregate | VEN-002 | 18.4 | Ton | 22942.89 | 23870.74 | 4296.73 | 28167.47 | Paid | Low
EXP-00622 | PRJ-001 | PRJ-001-ACT-10 | 2026-01-31 | Contractor | CON-001 | Civil Structure Contract | VEN-010 | 1 | Contract | 321538.29 | 334281.02 | 60170.58 | 394451.6 | Paid | Medium
EXP-00623 | PRJ-001 | PRJ-001-ACT-03 | 2026-02-05 | Material | MAT-001 | Cement | VEN-002 | 10.83 | Bag | 5233.86 | 5292.41 | 952.63 | 6245.04 | Paid | Medium
EXP-00624 | PRJ-001 | PRJ-001-ACT-03 | 2026-02-05 | Contractor | CON-004 | Finishing Contract | VEN-002 | 1 | Contract | 399024.75 | 372725.68 | 67090.62 | 439816.3 | Paid | Medium
EXP-00625 | PRJ-001 | PRJ-001-ACT-06 | 2026-02-05 | Contractor | CON-002 | Electrical Contract | VEN-001 | 1 | Contract | 223630.71 | 242233.33 | 43602 | 285835.33 | Paid | Low
EXP-00626 | PRJ-001 | PRJ-001-ACT-06 | 2026-02-05 | Labour | LAB-004 | Electrician | VEN-006 | 19 | Worker | 25603.47 | 26808.23 | 4825.48 | 31633.71 | Paid | Medium
EXP-00627 | PRJ-001 | PRJ-001-ACT-04 | 2026-02-05 | Labour | LAB-003 | Carpenter | VEN-001 | 23 | Worker | 28520.73 | 29004.39 | 5220.79 | 34225.18 | Paid | Medium
EXP-00628 | PRJ-001 | PRJ-001-ACT-01 | 2026-02-05 | Material | MAT-008 | Tiles | VEN-002 | 21.27 | Sq Ft | 1582.26 | 1600.5 | 288.09 | 1888.59 | Paid | Low
EXP-00629 | PRJ-001 | PRJ-001-ACT-07 | 2026-02-05 | Material | MAT-001 | Cement | VEN-001 | 22.85 | Bag | 13196.86 | 13090.75 | 2356.34 | 15447.09 | Paid | Medium
EXP-00630 | PRJ-001 | PRJ-001-ACT-08 | 2026-02-05 | Labour | LAB-002 | Helper | VEN-010 | 7 | Worker | 7675.81 | 7917.24 | 1425.1 | 9342.34 | Pending | Low
EXP-00631 | PRJ-001 | PRJ-001-ACT-02 | 2026-02-10 | Contractor | CON-004 | Finishing Contract | VEN-002 | 1 | Contract | 397926.41 | 390790.07 | 70342.21 | 461132.28 | Paid | Low
EXP-00632 | PRJ-001 | PRJ-001-ACT-06 | 2026-02-10 | Labour | LAB-004 | Electrician | VEN-006 | 30 | Worker | 45622.55 | 48873.5 | 8797.23 | 57670.73 | Paid | Medium
EXP-00633 | PRJ-001 | PRJ-001-ACT-10 | 2026-02-10 | Material | MAT-005 | Bricks | VEN-006 | 11.43 | Piece | 101.85 | 107.05 | 19.27 | 126.32 | Paid | Low
EXP-00634 | PRJ-001 | PRJ-001-ACT-06 | 2026-02-10 | Material | MAT-008 | Tiles | VEN-006 | 35.82 | Sq Ft | 3147.75 | 3031.93 | 545.75 | 3577.68 | Paid | Low
EXP-00635 | PRJ-001 | PRJ-001-ACT-07 | 2026-02-10 | Equipment | EQ-002 | Excavator | VEN-002 | 2 | Day | 26418.11 | 25495.83 | 4589.25 | 30085.08 | Paid | Low
EXP-00636 | PRJ-001 | PRJ-001-ACT-07 | 2026-02-10 | Labour | LAB-004 | Electrician | VEN-010 | 13 | Worker | 10725.1 | 10935.52 | 1968.39 | 12903.91 | Paid | High
EXP-00637 | PRJ-001 | PRJ-001-ACT-01 | 2026-02-10 | Equipment | EQ-002 | Excavator | VEN-002 | 2 | Day | 25508.98 | 26229.19 | 4721.25 | 30950.44 | Paid | Low
EXP-00638 | PRJ-001 | PRJ-001-ACT-08 | 2026-02-10 | Material | MAT-010 | Glass | VEN-002 | 10.83 | Sq Ft | 1652.51 | 1575.58 | 283.6 | 1859.18 | Paid | Low
EXP-00639 | PRJ-001 | PRJ-001-ACT-06 | 2026-02-10 | Labour | LAB-002 | Helper | VEN-002 | 24 | Worker | 35623.64 | 37821.23 | 6807.82 | 44629.05 | Paid | Medium
EXP-00640 | PRJ-001 | PRJ-001-ACT-01 | 2026-02-10 | Material | MAT-010 | Glass | VEN-001 | 1.89 | Sq Ft | 299.9 | 323.91 | 58.3 | 382.21 | Paid | Low
EXP-00641 | PRJ-001 | PRJ-001-ACT-02 | 2026-02-15 | Material | MAT-006 | Electrical Cable | VEN-006 | 4.72 | Meter | 459.39 | 458.07 | 82.45 | 540.52 | Paid | Low
EXP-00642 | PRJ-001 | PRJ-001-ACT-02 | 2026-02-15 | Labour | LAB-004 | Electrician | VEN-006 | 28 | Worker | 34729.65 | 32909.53 | 5923.72 | 38833.25 | Paid | Low
EXP-00643 | PRJ-001 | PRJ-001-ACT-10 | 2026-02-15 | Contractor | CON-002 | Electrical Contract | VEN-002 | 1 | Contract | 261515.16 | 249844.98 | 44972.1 | 294817.08 | Paid | Low
EXP-00644 | PRJ-001 | PRJ-001-ACT-07 | 2026-02-15 | Material | MAT-008 | Tiles | VEN-006 | 8.82 | Sq Ft | 719.69 | 749.57 | 134.92 | 884.49 | Paid | Low
EXP-00645 | PRJ-001 | PRJ-001-ACT-02 | 2026-02-15 | Labour | LAB-005 | Plumber | VEN-006 | 25 | Worker | 34206.37 | 35046.37 | 6308.35 | 41354.72 | Paid | Medium
EXP-00646 | PRJ-001 | PRJ-001-ACT-04 | 2026-02-15 | Material | MAT-001 | Cement | VEN-006 | 11.14 | Bag | 5930.79 | 6141.87 | 1105.54 | 7247.41 | Paid | Low
EXP-00647 | PRJ-001 | PRJ-001-ACT-06 | 2026-02-15 | Labour | LAB-001 | Mason | VEN-006 | 15 | Worker | 23875.26 | 25700.07 | 4626.01 | 30326.08 | Paid | High
EXP-00648 | PRJ-001 | PRJ-001-ACT-03 | 2026-02-20 | Material | MAT-003 | Sand | VEN-002 | 19.34 | Ton | 38853.33 | 38488.65 | 6927.96 | 45416.61 | Paid | Low
EXP-00649 | PRJ-001 | PRJ-001-ACT-02 | 2026-02-20 | Material | MAT-005 | Bricks | VEN-010 | 5.19 | Piece | 52.69 | 49.28 | 8.87 | 58.15 | Paid | Low
EXP-00650 | PRJ-001 | PRJ-001-ACT-09 | 2026-02-20 | Labour | LAB-005 | Plumber | VEN-010 | 16 | Worker | 23762.58 | 22335.77 | 4020.44 | 26356.21 | Paid | Low
EXP-00651 | PRJ-001 | PRJ-001-ACT-08 | 2026-02-20 | Material | MAT-007 | PVC Pipe | VEN-002 | 10.34 | Meter | 1375.49 | 1337.73 | 240.79 | 1578.52 | Paid | Low
EXP-00652 | PRJ-001 | PRJ-001-ACT-04 | 2026-02-20 | Contractor | CON-003 | Plumbing Contract | VEN-001 | 1 | Contract | 359798.31 | 335923.11 | 60466.16 | 396389.27 | Pending | Low
EXP-00653 | PRJ-001 | PRJ-001-ACT-07 | 2026-02-20 | Material | MAT-008 | Tiles | VEN-001 | 12.17 | Sq Ft | 795.07 | 862.89 | 155.32 | 1018.21 | Paid | Low
EXP-00654 | PRJ-001 | PRJ-001-ACT-05 | 2026-02-20 | Material | MAT-006 | Electrical Cable | VEN-001 | 12.53 | Meter | 1129.52 | 1108.04 | 199.45 | 1307.49 | Paid | High
EXP-00655 | PRJ-001 | PRJ-001-ACT-10 | 2026-02-20 | Material | MAT-010 | Glass | VEN-006 | 13.72 | Sq Ft | 1992.42 | 2047.4 | 368.53 | 2415.93 | Paid | Medium
EXP-00656 | PRJ-001 | PRJ-001-ACT-09 | 2026-02-20 | Contractor | CON-003 | Plumbing Contract | VEN-002 | 1 | Contract | 327390.84 | 351954.77 | 63351.86 | 415306.63 | Paid | Low
EXP-00657 | PRJ-001 | PRJ-001-ACT-02 | 2026-02-20 | Material | MAT-008 | Tiles | VEN-010 | 7.92 | Sq Ft | 556.7 | 565.28 | 101.75 | 667.03 | Paid | Medium
EXP-00658 | PRJ-001 | PRJ-001-ACT-03 | 2026-02-25 | Contractor | CON-002 | Electrical Contract | VEN-002 | 1 | Contract | 152672.95 | 157039.39 | 28267.09 | 185306.48 | Paid | Low
EXP-00659 | PRJ-001 | PRJ-001-ACT-02 | 2026-02-25 | Labour | LAB-004 | Electrician | VEN-001 | 13 | Worker | 21307.81 | 22268.43 | 4008.32 | 26276.75 | Paid | Low
EXP-00660 | PRJ-001 | PRJ-001-ACT-08 | 2026-02-25 | Equipment | EQ-003 | Concrete Mixer | VEN-001 | 6 | Day | 27455.33 | 29075.45 | 5233.58 | 34309.03 | Paid | Medium
EXP-00661 | PRJ-001 | PRJ-001-ACT-09 | 2026-02-25 | Material | MAT-004 | Aggregate | VEN-001 | 7.52 | Ton | 12236.72 | 11928.78 | 2147.18 | 14075.96 | Paid | Low
EXP-00662 | PRJ-001 | PRJ-001-ACT-02 | 2026-02-25 | Other | OTH-001 | Permit | VEN-006 | 1 | Lot | 59566.69 | 58794.64 | 10583.04 | 69377.68 | Paid | Medium
EXP-00663 | PRJ-001 | PRJ-001-ACT-04 | 2026-02-25 | Labour | LAB-003 | Carpenter | VEN-010 | 25 | Worker | 38160.42 | 36062.23 | 6491.2 | 42553.43 | Pending | Low
EXP-00664 | PRJ-001 | PRJ-001-ACT-04 | 2026-03-02 | Labour | LAB-004 | Electrician | VEN-010 | 34 | Worker | 29050.52 | 30729.86 | 5531.37 | 36261.23 | Paid | Medium
EXP-00665 | PRJ-001 | PRJ-001-ACT-01 | 2026-03-02 | Material | MAT-002 | Steel | VEN-001 | 9.04 | Ton | 632460.72 | 617557.02 | 111160.26 | 728717.28 | Paid | Low
EXP-00666 | PRJ-001 | PRJ-001-ACT-04 | 2026-03-02 | Labour | LAB-003 | Carpenter | VEN-010 | 16 | Worker | 12998.95 | 14105.88 | 2539.06 | 16644.94 | Paid | Low
EXP-00667 | PRJ-001 | PRJ-001-ACT-10 | 2026-03-02 | Contractor | CON-004 | Finishing Contract | VEN-006 | 1 | Contract | 243770.62 | 256961.42 | 46253.06 | 303214.48 | Partially Paid | Low
EXP-00668 | PRJ-001 | PRJ-001-ACT-03 | 2026-03-02 | Equipment | EQ-001 | Crane | VEN-010 | 1 | Day | 18137.59 | 18793.64 | 3382.86 | 22176.5 | Paid | Low
EXP-00669 | PRJ-001 | PRJ-001-ACT-10 | 2026-03-02 | Material | MAT-009 | Paint | VEN-001 | 6.94 | Litre | 1636.63 | 1647.95 | 296.63 | 1944.58 | Paid | Medium
EXP-00670 | PRJ-001 | PRJ-001-ACT-01 | 2026-03-02 | Material | MAT-001 | Cement | VEN-010 | 3.47 | Bag | 1985.42 | 2067.85 | 372.21 | 2440.06 | Paid | High
EXP-00671 | PRJ-001 | PRJ-001-ACT-05 | 2026-03-02 | Contractor | CON-004 | Finishing Contract | VEN-006 | 1 | Contract | 453832.17 | 422590.34 | 76066.26 | 498656.6 | Paid | Low
EXP-00672 | PRJ-001 | PRJ-001-ACT-05 | 2026-03-02 | Material | MAT-008 | Tiles | VEN-010 | 2 | Sq Ft | 179.17 | 170.35 | 30.66 | 201.01 | Paid | Medium
EXP-00673 | PRJ-001 | PRJ-001-ACT-08 | 2026-03-07 | Labour | LAB-003 | Carpenter | VEN-001 | 28 | Worker | 32408.08 | 32353.93 | 5823.71 | 38177.64 | Paid | Low
EXP-00674 | PRJ-001 | PRJ-001-ACT-08 | 2026-03-07 | Material | MAT-007 | PVC Pipe | VEN-001 | 7.11 | Meter | 892.14 | 907.69 | 163.38 | 1071.07 | Paid | Low
EXP-00675 | PRJ-001 | PRJ-001-ACT-02 | 2026-03-07 | Contractor | CON-003 | Plumbing Contract | VEN-001 | 1 | Contract | 402480.04 | 430638.58 | 77514.94 | 508153.52 | Paid | High
EXP-00676 | PRJ-001 | PRJ-001-ACT-02 | 2026-03-07 | Labour | LAB-006 | Painter | VEN-001 | 7 | Worker | 10091.56 | 10577.02 | 1903.86 | 12480.88 | Partially Paid | High
EXP-00677 | PRJ-001 | PRJ-001-ACT-04 | 2026-03-07 | Material | MAT-008 | Tiles | VEN-006 | 8.99 | Sq Ft | 664.8 | 695.13 | 125.12 | 820.25 | Paid | Medium
EXP-00678 | PRJ-001 | PRJ-001-ACT-03 | 2026-03-07 | Labour | LAB-004 | Electrician | VEN-001 | 21 | Worker | 23593.51 | 22609.02 | 4069.62 | 26678.64 | Paid | Low
EXP-00679 | PRJ-001 | PRJ-001-ACT-09 | 2026-03-07 | Material | MAT-008 | Tiles | VEN-010 | 21.84 | Sq Ft | 1560.79 | 1557.33 | 280.32 | 1837.65 | Paid | Low
EXP-00680 | PRJ-001 | PRJ-001-ACT-01 | 2026-03-12 | Material | MAT-010 | Glass | VEN-001 | 10.21 | Sq Ft | 1726.96 | 1606.9 | 289.24 | 1896.14 | Paid | Medium
EXP-00681 | PRJ-001 | PRJ-001-ACT-02 | 2026-03-12 | Material | MAT-008 | Tiles | VEN-001 | 46.86 | Sq Ft | 3727.77 | 3602.12 | 648.38 | 4250.5 | Paid | Low
EXP-00682 | PRJ-001 | PRJ-001-ACT-09 | 2026-03-12 | Labour | LAB-003 | Carpenter | VEN-006 | 12 | Worker | 12001.07 | 11167.14 | 2010.09 | 13177.23 | Pending | Low
EXP-00683 | PRJ-001 | PRJ-001-ACT-07 | 2026-03-12 | Material | MAT-004 | Aggregate | VEN-010 | 15.5 | Ton | 19790.41 | 20882.92 | 3758.93 | 24641.85 | Paid | Low
EXP-00684 | PRJ-001 | PRJ-001-ACT-04 | 2026-03-12 | Material | MAT-008 | Tiles | VEN-006 | 7.06 | Sq Ft | 490.83 | 472.15 | 84.99 | 557.14 | Paid | High
EXP-00685 | PRJ-001 | PRJ-001-ACT-06 | 2026-03-12 | Equipment | EQ-004 | Scaffolding | VEN-002 | 4 | Day | 10476.4 | 10028.16 | 1805.07 | 11833.23 | Paid | Medium
EXP-00686 | PRJ-001 | PRJ-001-ACT-09 | 2026-03-12 | Contractor | CON-003 | Plumbing Contract | VEN-006 | 1 | Contract | 386226.42 | 393729.94 | 70871.39 | 464601.33 | Paid | Low
EXP-00687 | PRJ-001 | PRJ-001-ACT-10 | 2026-03-12 | Labour | LAB-003 | Carpenter | VEN-001 | 33 | Worker | 37548 | 36456.12 | 6562.1 | 43018.22 | Partially Paid | Low
EXP-00688 | PRJ-001 | PRJ-001-ACT-06 | 2026-03-12 | Material | MAT-006 | Electrical Cable | VEN-006 | 5.9 | Meter | 523.31 | 519.59 | 93.53 | 613.12 | Paid | Low
EXP-00689 | PRJ-001 | PRJ-001-ACT-05 | 2026-03-17 | Material | MAT-010 | Glass | VEN-006 | 3.9 | Sq Ft | 532.56 | 531.78 | 95.72 | 627.5 | Paid | Medium
EXP-00690 | PRJ-001 | PRJ-001-ACT-03 | 2026-03-17 | Contractor | CON-004 | Finishing Contract | VEN-006 | 1 | Contract | 154175.29 | 165622.1 | 29811.98 | 195434.08 | Paid | Low
EXP-00691 | PRJ-001 | PRJ-001-ACT-04 | 2026-03-17 | Labour | LAB-006 | Painter | VEN-010 | 17 | Worker | 11557.4 | 11296.26 | 2033.33 | 13329.59 | Paid | Low
EXP-00692 | PRJ-001 | PRJ-001-ACT-09 | 2026-03-17 | Labour | LAB-005 | Plumber | VEN-002 | 23 | Worker | 19838.87 | 20923.46 | 3766.22 | 24689.68 | Partially Paid | Low
EXP-00693 | PRJ-001 | PRJ-001-ACT-03 | 2026-03-17 | Material | MAT-010 | Glass | VEN-006 | 10.18 | Sq Ft | 1633.12 | 1644.18 | 295.95 | 1940.13 | Paid | Low
EXP-00694 | PRJ-001 | PRJ-001-ACT-03 | 2026-03-17 | Labour | LAB-005 | Plumber | VEN-006 | 29 | Worker | 40545.81 | 38170.1 | 6870.62 | 45040.72 | Paid | Medium
EXP-00695 | PRJ-001 | PRJ-001-ACT-07 | 2026-03-22 | Labour | LAB-005 | Plumber | VEN-006 | 5 | Worker | 8079.23 | 8595.49 | 1547.19 | 10142.68 | Paid | Low
EXP-00696 | PRJ-001 | PRJ-001-ACT-07 | 2026-03-22 | Labour | LAB-001 | Mason | VEN-010 | 16 | Worker | 27241.57 | 26365.72 | 4745.83 | 31111.55 | Paid | Medium
EXP-00697 | PRJ-001 | PRJ-001-ACT-04 | 2026-03-22 | Contractor | CON-001 | Civil Structure Contract | VEN-002 | 1 | Contract | 221819.03 | 239493.38 | 43108.81 | 282602.19 | Paid | Medium
EXP-00698 | PRJ-001 | PRJ-001-ACT-05 | 2026-03-22 | Material | MAT-007 | PVC Pipe | VEN-002 | 4.52 | Meter | 555.59 | 595.08 | 107.11 | 702.19 | Partially Paid | Low
EXP-00699 | PRJ-001 | PRJ-001-ACT-10 | 2026-03-22 | Material | MAT-002 | Steel | VEN-006 | 7.31 | Ton | 463929.85 | 464781.89 | 83660.74 | 548442.63 | Paid | Medium
EXP-00700 | PRJ-001 | PRJ-001-ACT-07 | 2026-03-22 | Material | MAT-005 | Bricks | VEN-001 | 7.78 | Piece | 64.64 | 62.23 | 11.2 | 73.43 | Paid | Low
EXP-00701 | PRJ-001 | PRJ-001-ACT-07 | 2026-03-22 | Labour | LAB-002 | Helper | VEN-002 | 18 | Worker | 16768.82 | 17082.99 | 3074.94 | 20157.93 | Pending | Medium
EXP-00702 | PRJ-001 | PRJ-001-ACT-09 | 2026-03-27 | Labour | LAB-005 | Plumber | VEN-006 | 25 | Worker | 33743.3 | 34624.35 | 6232.38 | 40856.73 | Pending | Low
EXP-00703 | PRJ-001 | PRJ-001-ACT-01 | 2026-03-27 | Material | MAT-006 | Electrical Cable | VEN-010 | 20.29 | Meter | 2042.82 | 1898.69 | 341.76 | 2240.45 | Pending | Low
EXP-00704 | PRJ-001 | PRJ-001-ACT-01 | 2026-03-27 | Contractor | CON-003 | Plumbing Contract | VEN-002 | 1 | Contract | 126090.06 | 123131.22 | 22163.62 | 145294.84 | Pending | High
EXP-00705 | PRJ-001 | PRJ-001-ACT-03 | 2026-03-27 | Labour | LAB-002 | Helper | VEN-006 | 21 | Worker | 15426.82 | 15201.36 | 2736.24 | 17937.6 | Partially Paid | Medium
EXP-00706 | PRJ-001 | PRJ-001-ACT-10 | 2026-03-27 | Labour | LAB-002 | Helper | VEN-002 | 15 | Worker | 17761.85 | 16614.82 | 2990.67 | 19605.49 | Paid | High
EXP-00707 | PRJ-001 | PRJ-001-ACT-10 | 2026-03-27 | Other | OTH-001 | Miscellaneous | VEN-001 | 1 | Lot | 63170.27 | 61215.92 | 11018.87 | 72234.79 | Paid | Low
EXP-00708 | PRJ-001 | PRJ-001-ACT-01 | 2026-03-27 | Material | MAT-005 | Bricks | VEN-006 | 18.3 | Piece | 151.97 | 146.9 | 26.44 | 173.34 | Pending | High
EXP-00709 | PRJ-001 | PRJ-001-ACT-06 | 2026-04-01 | Material | MAT-010 | Glass | VEN-002 | 6.36 | Sq Ft | 1188.68 | 1121.04 | 201.79 | 1322.83 | Paid | Medium
EXP-00710 | PRJ-001 | PRJ-001-ACT-08 | 2026-04-01 | Material | MAT-003 | Sand | VEN-001 | 2.9 | Ton | 5012.89 | 5425.22 | 976.54 | 6401.76 | Paid | Low
EXP-00711 | PRJ-001 | PRJ-001-ACT-09 | 2026-04-01 | Labour | LAB-005 | Plumber | VEN-002 | 19 | Worker | 25815.82 | 25078.36 | 4514.1 | 29592.46 | Paid | Medium
EXP-00712 | PRJ-001 | PRJ-001-ACT-06 | 2026-04-01 | Contractor | CON-001 | Civil Structure Contract | VEN-001 | 1 | Contract | 97729.76 | 96375.9 | 17347.66 | 113723.56 | Partially Paid | Low
EXP-00713 | PRJ-001 | PRJ-001-ACT-05 | 2026-04-01 | Material | MAT-001 | Cement | VEN-002 | 2.37 | Bag | 1520.98 | 1415.33 | 254.76 | 1670.09 | Paid | Low
EXP-00714 | PRJ-001 | PRJ-001-ACT-07 | 2026-04-01 | Contractor | CON-001 | Civil Structure Contract | VEN-010 | 1 | Contract | 312766.29 | 328211.56 | 59078.08 | 387289.64 | Paid | Low
EXP-00715 | PRJ-001 | PRJ-001-ACT-09 | 2026-04-01 | Material | MAT-005 | Bricks | VEN-001 | 11.66 | Piece | 101.36 | 108.71 | 19.57 | 128.28 | Paid | Low
EXP-00716 | PRJ-001 | PRJ-001-ACT-10 | 2026-04-01 | Material | MAT-006 | Electrical Cable | VEN-002 | 20.1 | Meter | 1796.28 | 1797.08 | 323.47 | 2120.55 | Pending | Low
EXP-00717 | PRJ-001 | PRJ-001-ACT-05 | 2026-04-06 | Material | MAT-004 | Aggregate | VEN-001 | 13.67 | Ton | 22216.09 | 23297.39 | 4193.53 | 27490.92 | Paid | Medium
EXP-00718 | PRJ-001 | PRJ-001-ACT-10 | 2026-04-06 | Material | MAT-001 | Cement | VEN-010 | 14.86 | Bag | 7607.8 | 7155.49 | 1287.99 | 8443.48 | Paid | Low
EXP-00719 | PRJ-001 | PRJ-001-ACT-03 | 2026-04-06 | Contractor | CON-004 | Finishing Contract | VEN-002 | 1 | Contract | 239314.27 | 242989.37 | 43738.09 | 286727.46 | Pending | Low
EXP-00720 | PRJ-001 | PRJ-001-ACT-02 | 2026-04-06 | Material | MAT-007 | PVC Pipe | VEN-002 | 5.08 | Meter | 665.98 | 670.51 | 120.69 | 791.2 | Paid | Medium
EXP-00721 | PRJ-001 | PRJ-001-ACT-02 | 2026-04-06 | Material | MAT-009 | Paint | VEN-010 | 3.34 | Litre | 731.94 | 711.01 | 127.98 | 838.99 | Paid | Low
EXP-00722 | PRJ-001 | PRJ-001-ACT-06 | 2026-04-06 | Labour | LAB-004 | Electrician | VEN-006 | 28 | Worker | 36788.37 | 36701.55 | 6606.28 | 43307.83 | Paid | Low
EXP-00723 | PRJ-001 | PRJ-001-ACT-04 | 2026-04-11 | Material | MAT-005 | Bricks | VEN-006 | 13.57 | Piece | 101.67 | 107.39 | 19.33 | 126.72 | Partially Paid | Medium
EXP-00724 | PRJ-001 | PRJ-001-ACT-02 | 2026-04-11 | Material | MAT-006 | Electrical Cable | VEN-001 | 5.27 | Meter | 358.16 | 388.11 | 69.86 | 457.97 | Paid | Low
EXP-00725 | PRJ-001 | PRJ-001-ACT-03 | 2026-04-11 | Labour | LAB-001 | Mason | VEN-010 | 34 | Worker | 57596.27 | 60872.51 | 10957.05 | 71829.56 | Paid | Medium
EXP-00726 | PRJ-001 | PRJ-001-ACT-10 | 2026-04-11 | Other | OTH-001 | Transport | VEN-006 | 1 | Lot | 24382.75 | 23271.11 | 4188.8 | 27459.91 | Paid | Medium
EXP-00727 | PRJ-001 | PRJ-001-ACT-04 | 2026-04-11 | Contractor | CON-004 | Finishing Contract | VEN-010 | 1 | Contract | 246792.26 | 258464.57 | 46523.62 | 304988.19 | Paid | Medium
EXP-00728 | PRJ-001 | PRJ-001-ACT-10 | 2026-04-11 | Material | MAT-001 | Cement | VEN-010 | 5.39 | Bag | 3050.78 | 3183.56 | 573.04 | 3756.6 | Paid | Low
EXP-00729 | PRJ-001 | PRJ-001-ACT-09 | 2026-04-11 | Contractor | CON-001 | Civil Structure Contract | VEN-002 | 1 | Contract | 323492.68 | 312442 | 56239.56 | 368681.56 | Paid | Medium
EXP-00730 | PRJ-001 | PRJ-001-ACT-04 | 2026-04-11 | Material | MAT-002 | Steel | VEN-001 | 4.58 | Ton | 340023.17 | 317877.3 | 57217.91 | 375095.21 | Pending | Medium
EXP-00731 | PRJ-001 | PRJ-001-ACT-10 | 2026-04-16 | Material | MAT-002 | Steel | VEN-001 | 8.41 | Ton | 555712.57 | 585962.15 | 105473.19 | 691435.34 | Paid | Medium
EXP-00732 | PRJ-001 | PRJ-001-ACT-01 | 2026-04-16 | Material | MAT-004 | Aggregate | VEN-006 | 9.07 | Ton | 13946.38 | 14809.49 | 2665.71 | 17475.2 | Pending | High
EXP-00733 | PRJ-001 | PRJ-001-ACT-03 | 2026-04-16 | Material | MAT-002 | Steel | VEN-002 | 17.18 | Ton | 1042372.08 | 992212.82 | 178598.31 | 1170811.13 | Paid | Low
EXP-00734 | PRJ-001 | PRJ-001-ACT-03 | 2026-04-16 | Material | MAT-004 | Aggregate | VEN-002 | 3.71 | Ton | 6704.02 | 6376.67 | 1147.8 | 7524.47 | Paid | Low
EXP-00735 | PRJ-001 | PRJ-001-ACT-02 | 2026-04-16 | Material | MAT-002 | Steel | VEN-010 | 7.22 | Ton | 420435.63 | 421573.23 | 75883.18 | 497456.41 | Paid | Medium
EXP-00736 | PRJ-001 | PRJ-001-ACT-09 | 2026-04-16 | Other | OTH-001 | Transport | VEN-006 | 1 | Lot | 49171.07 | 52797.66 | 9503.58 | 62301.24 | Paid | Low
EXP-00737 | PRJ-001 | PRJ-001-ACT-09 | 2026-04-16 | Other | OTH-001 | Miscellaneous | VEN-002 | 1 | Lot | 30316.09 | 30857.73 | 5554.39 | 36412.12 | Partially Paid | Medium
EXP-00738 | PRJ-001 | PRJ-001-ACT-02 | 2026-04-21 | Labour | LAB-002 | Helper | VEN-006 | 21 | Worker | 16020.83 | 17135.14 | 3084.33 | 20219.47 | Paid | Medium
EXP-00739 | PRJ-001 | PRJ-001-ACT-08 | 2026-04-21 | Material | MAT-002 | Steel | VEN-002 | 26.61 | Ton | 1357705.39 | 1473557.93 | 265240.43 | 1738798.36 | Paid | Medium
EXP-00740 | PRJ-001 | PRJ-001-ACT-02 | 2026-04-21 | Labour | LAB-002 | Helper | VEN-010 | 32 | Worker | 37623.32 | 36354.87 | 6543.88 | 42898.75 | Paid | Medium
EXP-00741 | PRJ-001 | PRJ-001-ACT-07 | 2026-04-21 | Material | MAT-010 | Glass | VEN-006 | 6.15 | Sq Ft | 867.82 | 888.91 | 160 | 1048.91 | Paid | Low
EXP-00742 | PRJ-001 | PRJ-001-ACT-06 | 2026-04-21 | Labour | LAB-005 | Plumber | VEN-001 | 31 | Worker | 43643.85 | 44009.41 | 7921.69 | 51931.1 | Paid | Low
EXP-00743 | PRJ-001 | PRJ-001-ACT-07 | 2026-04-21 | Labour | LAB-001 | Mason | VEN-010 | 29 | Worker | 31590.18 | 33574.16 | 6043.35 | 39617.51 | Paid | Medium
EXP-00744 | PRJ-001 | PRJ-001-ACT-08 | 2026-04-21 | Contractor | CON-002 | Electrical Contract | VEN-002 | 1 | Contract | 294478.23 | 294838.31 | 53070.9 | 347909.21 | Paid | Low
EXP-00745 | PRJ-001 | PRJ-001-ACT-06 | 2026-04-21 | Material | MAT-006 | Electrical Cable | VEN-002 | 9.34 | Meter | 830.9 | 825.23 | 148.54 | 973.77 | Paid | Low
EXP-00746 | PRJ-001 | PRJ-001-ACT-05 | 2026-04-21 | Material | MAT-009 | Paint | VEN-001 | 14.4 | Litre | 2648.7 | 2735.18 | 492.33 | 3227.51 | Paid | Low
EXP-00747 | PRJ-001 | PRJ-001-ACT-10 | 2026-04-26 | Contractor | CON-002 | Electrical Contract | VEN-006 | 1 | Contract | 119659.68 | 121961.26 | 21953.03 | 143914.29 | Paid | Medium
EXP-00748 | PRJ-001 | PRJ-001-ACT-01 | 2026-04-26 | Material | MAT-003 | Sand | VEN-010 | 12.94 | Ton | 22262.22 | 21513.34 | 3872.4 | 25385.74 | Paid | Medium
EXP-00749 | PRJ-001 | PRJ-001-ACT-09 | 2026-04-26 | Labour | LAB-002 | Helper | VEN-002 | 8 | Worker | 8068.63 | 7484.24 | 1347.16 | 8831.4 | Paid | Medium
EXP-00750 | PRJ-001 | PRJ-001-ACT-03 | 2026-04-26 | Equipment | EQ-004 | Scaffolding | VEN-002 | 6 | Day | 12985.51 | 13624.68 | 2452.44 | 16077.12 | Partially Paid | Low
EXP-00751 | PRJ-001 | PRJ-001-ACT-03 | 2026-04-26 | Material | MAT-002 | Steel | VEN-010 | 4.09 | Ton | 254799.33 | 235996.02 | 42479.28 | 278475.3 | Partially Paid | Low
EXP-00752 | PRJ-001 | PRJ-001-ACT-09 | 2026-04-26 | Other | OTH-001 | Permit | VEN-002 | 1 | Lot | 14421.06 | 14120.39 | 2541.67 | 16662.06 | Partially Paid | Medium
EXP-00753 | PRJ-001 | PRJ-001-ACT-10 | 2026-05-01 | Contractor | CON-003 | Plumbing Contract | VEN-001 | 1 | Contract | 237315.03 | 227423.52 | 40936.23 | 268359.75 | Paid | Medium
EXP-00754 | PRJ-001 | PRJ-001-ACT-10 | 2026-05-01 | Contractor | CON-004 | Finishing Contract | VEN-010 | 1 | Contract | 163676.52 | 155853.66 | 28053.66 | 183907.32 | Paid | Low
EXP-00755 | PRJ-001 | PRJ-001-ACT-09 | 2026-05-01 | Other | OTH-001 | Miscellaneous | VEN-001 | 1 | Lot | 70915.6 | 76419.51 | 13755.51 | 90175.02 | Paid | Low
EXP-00756 | PRJ-001 | PRJ-001-ACT-05 | 2026-05-01 | Labour | LAB-003 | Carpenter | VEN-002 | 31 | Worker | 39291.7 | 39275.17 | 7069.53 | 46344.7 | Paid | Medium
EXP-00757 | PRJ-001 | PRJ-001-ACT-07 | 2026-05-01 | Material | MAT-005 | Bricks | VEN-002 | 1.96 | Piece | 16.42 | 17.63 | 3.17 | 20.8 | Paid | Low
EXP-00758 | PRJ-001 | PRJ-001-ACT-09 | 2026-05-01 | Contractor | CON-001 | Civil Structure Contract | VEN-002 | 1 | Contract | 384446.52 | 382212.83 | 68798.31 | 451011.14 | Partially Paid | Low
EXP-00759 | PRJ-001 | PRJ-001-ACT-03 | 2026-05-01 | Labour | LAB-003 | Carpenter | VEN-001 | 15 | Worker | 23214.95 | 22903.71 | 4122.67 | 27026.38 | Paid | Low
EXP-00760 | PRJ-001 | PRJ-001-ACT-05 | 2026-05-01 | Material | MAT-004 | Aggregate | VEN-010 | 44 | Ton | 65561.1 | 66037.02 | 11886.66 | 77923.68 | Paid | Low
EXP-00761 | PRJ-001 | PRJ-001-ACT-02 | 2026-05-01 | Labour | LAB-004 | Electrician | VEN-010 | 15 | Worker | 13683.23 | 14871.45 | 2676.86 | 17548.31 | Pending | High
EXP-00762 | PRJ-001 | PRJ-001-ACT-09 | 2026-05-01 | Contractor | CON-004 | Finishing Contract | VEN-010 | 1 | Contract | 322983.22 | 344998.8 | 62099.78 | 407098.58 | Paid | Low
EXP-00763 | PRJ-001 | PRJ-001-ACT-05 | 2026-05-06 | Equipment | EQ-002 | Excavator | VEN-001 | 1 | Day | 15449.49 | 14736.82 | 2652.63 | 17389.45 | Paid | Low
EXP-00764 | PRJ-001 | PRJ-001-ACT-03 | 2026-05-06 | Material | MAT-010 | Glass | VEN-006 | 19.53 | Sq Ft | 2757.97 | 2755.26 | 495.95 | 3251.21 | Partially Paid | High
EXP-00765 | PRJ-001 | PRJ-001-ACT-10 | 2026-05-06 | Labour | LAB-006 | Painter | VEN-001 | 32 | Worker | 37273.21 | 35306.21 | 6355.12 | 41661.33 | Paid | Low
EXP-00766 | PRJ-001 | PRJ-001-ACT-01 | 2026-05-06 | Labour | LAB-002 | Helper | VEN-002 | 12 | Worker | 12383.53 | 12399.54 | 2231.92 | 14631.46 | Paid | Low
EXP-00767 | PRJ-001 | PRJ-001-ACT-02 | 2026-05-06 | Contractor | CON-004 | Finishing Contract | VEN-001 | 1 | Contract | 305778.8 | 284040.36 | 51127.26 | 335167.62 | Paid | Low
EXP-00768 | PRJ-001 | PRJ-001-ACT-01 | 2026-05-06 | Contractor | CON-004 | Finishing Contract | VEN-001 | 1 | Contract | 353732.55 | 333593.65 | 60046.86 | 393640.51 | Paid | Low
EXP-00769 | PRJ-001 | PRJ-001-ACT-02 | 2026-05-06 | Material | MAT-004 | Aggregate | VEN-001 | 16.4 | Ton | 21803.09 | 22962.47 | 4133.24 | 27095.71 | Paid | Low
EXP-00770 | PRJ-001 | PRJ-001-ACT-05 | 2026-05-11 | Material | MAT-006 | Electrical Cable | VEN-010 | 26.32 | Meter | 2150.67 | 2128.96 | 383.21 | 2512.17 | Paid | Medium
EXP-00771 | PRJ-001 | PRJ-001-ACT-09 | 2026-05-11 | Material | MAT-010 | Glass | VEN-002 | 6.59 | Sq Ft | 1145.16 | 1172.83 | 211.11 | 1383.94 | Paid | Low
EXP-00772 | PRJ-001 | PRJ-001-ACT-01 | 2026-05-11 | Contractor | CON-002 | Electrical Contract | VEN-002 | 1 | Contract | 242502.54 | 259886.3 | 46779.53 | 306665.83 | Paid | High
EXP-00773 | PRJ-001 | PRJ-001-ACT-04 | 2026-05-11 | Other | OTH-001 | Transport | VEN-001 | 1 | Lot | 15506.74 | 14541.87 | 2617.54 | 17159.41 | Paid | Low
EXP-00774 | PRJ-001 | PRJ-001-ACT-10 | 2026-05-11 | Material | MAT-006 | Electrical Cable | VEN-002 | 14.03 | Meter | 1157.77 | 1196.03 | 215.29 | 1411.32 | Paid | Low
EXP-00775 | PRJ-001 | PRJ-001-ACT-02 | 2026-05-11 | Material | MAT-010 | Glass | VEN-006 | 14.37 | Sq Ft | 2212.41 | 2170.54 | 390.7 | 2561.24 | Paid | Medium
EXP-00776 | PRJ-001 | PRJ-001-ACT-08 | 2026-05-16 | Contractor | CON-002 | Electrical Contract | VEN-006 | 1 | Contract | 122606.41 | 115650.14 | 20817.03 | 136467.17 | Paid | Low
EXP-00777 | PRJ-001 | PRJ-001-ACT-10 | 2026-05-16 | Labour | LAB-003 | Carpenter | VEN-002 | 12 | Worker | 21123.59 | 20857.38 | 3754.33 | 24611.71 | Paid | Low
EXP-00778 | PRJ-001 | PRJ-001-ACT-07 | 2026-05-16 | Material | MAT-009 | Paint | VEN-010 | 17.34 | Litre | 3418.25 | 3243.82 | 583.89 | 3827.71 | Paid | Low
EXP-00779 | PRJ-001 | PRJ-001-ACT-05 | 2026-05-16 | Material | MAT-004 | Aggregate | VEN-001 | 18.39 | Ton | 23766.22 | 23957.64 | 4312.38 | 28270.02 | Paid | Medium
EXP-00780 | PRJ-001 | PRJ-001-ACT-01 | 2026-05-16 | Equipment | EQ-004 | Scaffolding | VEN-002 | 3 | Day | 7019.2 | 7169.01 | 1290.42 | 8459.43 | Paid | Medium
EXP-00781 | PRJ-001 | PRJ-001-ACT-04 | 2026-05-16 | Material | MAT-002 | Steel | VEN-010 | 17.31 | Ton | 919735.48 | 979887.78 | 176379.8 | 1156267.58 | Pending | Low
EXP-00782 | PRJ-001 | PRJ-001-ACT-06 | 2026-05-16 | Contractor | CON-003 | Plumbing Contract | VEN-002 | 1 | Contract | 104454.74 | 108683.3 | 19562.99 | 128246.29 | Paid | Low
EXP-00783 | PRJ-001 | PRJ-001-ACT-06 | 2026-05-16 | Material | MAT-006 | Electrical Cable | VEN-010 | 2.55 | Meter | 206.44 | 193.42 | 34.82 | 228.24 | Paid | High
EXP-00784 | PRJ-001 | PRJ-001-ACT-02 | 2026-05-21 | Material | MAT-006 | Electrical Cable | VEN-001 | 17.28 | Meter | 1652.49 | 1656.81 | 298.23 | 1955.04 | Paid | Medium
EXP-00785 | PRJ-001 | PRJ-001-ACT-05 | 2026-05-21 | Equipment | EQ-004 | Scaffolding | VEN-002 | 4 | Day | 10124.93 | 9701.42 | 1746.26 | 11447.68 | Paid | Low
EXP-00786 | PRJ-001 | PRJ-001-ACT-10 | 2026-05-21 | Material | MAT-009 | Paint | VEN-006 | 5.07 | Litre | 1128.76 | 1154.32 | 207.78 | 1362.1 | Paid | Medium
EXP-00787 | PRJ-001 | PRJ-001-ACT-05 | 2026-05-21 | Material | MAT-002 | Steel | VEN-006 | 9.36 | Ton | 533185.15 | 579150.22 | 104247.04 | 683397.26 | Paid | Low
EXP-00788 | PRJ-001 | PRJ-001-ACT-08 | 2026-05-21 | Other | OTH-001 | Safety | VEN-006 | 1 | Lot | 35212.15 | 34302.02 | 6174.36 | 40476.38 | Paid | Low
EXP-00789 | PRJ-001 | PRJ-001-ACT-03 | 2026-05-21 | Equipment | EQ-002 | Excavator | VEN-001 | 1 | Day | 13688.82 | 13067 | 2352.06 | 15419.06 | Paid | Low
EXP-00790 | PRJ-001 | PRJ-001-ACT-08 | 2026-05-21 | Labour | LAB-002 | Helper | VEN-006 | 34 | Worker | 34533.94 | 37295.47 | 6713.18 | 44008.65 | Partially Paid | Medium
EXP-00791 | PRJ-001 | PRJ-001-ACT-10 | 2026-05-21 | Other | OTH-001 | Safety | VEN-010 | 1 | Lot | 65081.7 | 68865.29 | 12395.75 | 81261.04 | Pending | Medium
EXP-00792 | PRJ-001 | PRJ-001-ACT-06 | 2026-05-21 | Labour | LAB-003 | Carpenter | VEN-002 | 30 | Worker | 30618.27 | 29955.77 | 5392.04 | 35347.81 | Paid | High
EXP-00793 | PRJ-001 | PRJ-001-ACT-02 | 2026-05-26 | Labour | LAB-004 | Electrician | VEN-002 | 26 | Worker | 40856.81 | 40074.95 | 7213.49 | 47288.44 | Paid | Medium
EXP-00794 | PRJ-001 | PRJ-001-ACT-03 | 2026-05-26 | Labour | LAB-003 | Carpenter | VEN-001 | 4 | Worker | 5607.3 | 5882.59 | 1058.87 | 6941.46 | Paid | Medium
EXP-00795 | PRJ-001 | PRJ-001-ACT-10 | 2026-05-26 | Labour | LAB-002 | Helper | VEN-001 | 12 | Worker | 9597.6 | 9770.44 | 1758.68 | 11529.12 | Pending | Low
EXP-00796 | PRJ-001 | PRJ-001-ACT-03 | 2026-05-26 | Contractor | CON-004 | Finishing Contract | VEN-001 | 1 | Contract | 337597.18 | 327019.7 | 58863.55 | 385883.25 | Paid | Low
EXP-00797 | PRJ-001 | PRJ-001-ACT-03 | 2026-05-26 | Equipment | EQ-001 | Crane | VEN-006 | 6 | Day | 104499.41 | 105459.05 | 18982.63 | 124441.68 | Paid | Low
EXP-00798 | PRJ-001 | PRJ-001-ACT-01 | 2026-05-26 | Labour | LAB-001 | Mason | VEN-010 | 18 | Worker | 22509.35 | 21715.69 | 3908.82 | 25624.51 | Paid | Low
EXP-00799 | PRJ-001 | PRJ-001-ACT-05 | 2026-05-26 | Material | MAT-010 | Glass | VEN-001 | 1.7 | Sq Ft | 262.66 | 284.05 | 51.13 | 335.18 | Paid | Low
EXP-00800 | PRJ-001 | PRJ-001-ACT-08 | 2026-05-31 | Material | MAT-010 | Glass | VEN-006 | 3.59 | Sq Ft | 641.88 | 605.87 | 109.06 | 714.93 | Paid | High
EXP-00801 | PRJ-001 | PRJ-001-ACT-07 | 2026-05-31 | Material | MAT-005 | Bricks | VEN-010 | 20.95 | Piece | 180.83 | 174.02 | 31.32 | 205.34 | Paid | Low
EXP-00802 | PRJ-001 | PRJ-001-ACT-08 | 2026-05-31 | Labour | LAB-003 | Carpenter | VEN-002 | 16 | Worker | 23258.45 | 22765.16 | 4097.73 | 26862.89 | Paid | Medium
EXP-00803 | PRJ-001 | PRJ-001-ACT-08 | 2026-05-31 | Contractor | CON-001 | Civil Structure Contract | VEN-001 | 1 | Contract | 189622.74 | 175593.88 | 31606.9 | 207200.78 | Paid | Low
EXP-00804 | PRJ-001 | PRJ-001-ACT-10 | 2026-05-31 | Material | MAT-010 | Glass | VEN-006 | 1.86 | Sq Ft | 346.7 | 337.33 | 60.72 | 398.05 | Paid | Low
EXP-00805 | PRJ-001 | PRJ-001-ACT-02 | 2026-05-31 | Material | MAT-008 | Tiles | VEN-001 | 41.75 | Sq Ft | 3300.36 | 3134.74 | 564.25 | 3698.99 | Paid | Low
EXP-00806 | PRJ-001 | PRJ-001-ACT-05 | 2026-06-05 | Labour | LAB-005 | Plumber | VEN-006 | 34 | Worker | 54933.42 | 59157.79 | 10648.4 | 69806.19 | Paid | Low
EXP-00807 | PRJ-001 | PRJ-001-ACT-03 | 2026-06-05 | Equipment | EQ-003 | Concrete Mixer | VEN-006 | 7 | Day | 33011.2 | 32967.13 | 5934.08 | 38901.21 | Pending | Low
EXP-00808 | PRJ-001 | PRJ-001-ACT-08 | 2026-06-05 | Contractor | CON-001 | Civil Structure Contract | VEN-002 | 1 | Contract | 355167.24 | 347725.68 | 62590.62 | 410316.3 | Paid | Low
EXP-00809 | PRJ-001 | PRJ-001-ACT-08 | 2026-06-05 | Labour | LAB-004 | Electrician | VEN-006 | 13 | Worker | 15150.92 | 15033.59 | 2706.05 | 17739.64 | Paid | Medium
EXP-00810 | PRJ-001 | PRJ-001-ACT-03 | 2026-06-05 | Other | OTH-001 | Miscellaneous | VEN-010 | 1 | Lot | 28533.06 | 27443.63 | 4939.85 | 32383.48 | Paid | Low
EXP-00811 | PRJ-001 | PRJ-001-ACT-09 | 2026-06-05 | Material | MAT-007 | PVC Pipe | VEN-006 | 2.17 | Meter | 305.12 | 292.85 | 52.71 | 345.56 | Paid | High
EXP-00812 | PRJ-001 | PRJ-001-ACT-02 | 2026-06-05 | Labour | LAB-006 | Painter | VEN-006 | 27 | Worker | 29383.29 | 31089.99 | 5596.2 | 36686.19 | Pending | Medium
EXP-00813 | PRJ-001 | PRJ-001-ACT-04 | 2026-06-05 | Material | MAT-006 | Electrical Cable | VEN-002 | 3.53 | Meter | 308.44 | 321.18 | 57.81 | 378.99 | Paid | Low
EXP-00814 | PRJ-001 | PRJ-001-ACT-09 | 2026-06-10 | Equipment | EQ-002 | Excavator | VEN-006 | 3 | Day | 46644.95 | 45143.02 | 8125.74 | 53268.76 | Paid | Low
EXP-00815 | PRJ-001 | PRJ-001-ACT-07 | 2026-06-10 | Equipment | EQ-001 | Crane | VEN-002 | 2 | Day | 40371.47 | 39596.17 | 7127.31 | 46723.48 | Paid | Low
EXP-00816 | PRJ-001 | PRJ-001-ACT-07 | 2026-06-10 | Labour | LAB-002 | Helper | VEN-002 | 20 | Worker | 13753.87 | 13755.7 | 2476.03 | 16231.73 | Paid | Low
EXP-00817 | PRJ-001 | PRJ-001-ACT-06 | 2026-06-10 | Equipment | EQ-004 | Scaffolding | VEN-006 | 2 | Day | 5649.52 | 5481.9 | 986.74 | 6468.64 | Partially Paid | High
EXP-00818 | PRJ-001 | PRJ-001-ACT-02 | 2026-06-10 | Labour | LAB-005 | Plumber | VEN-010 | 15 | Worker | 15294.44 | 15901.5 | 2862.27 | 18763.77 | Pending | Medium
EXP-00819 | PRJ-001 | PRJ-001-ACT-06 | 2026-06-10 | Material | MAT-006 | Electrical Cable | VEN-006 | 9.25 | Meter | 699.07 | 695.93 | 125.27 | 821.2 | Paid | Medium
EXP-00820 | PRJ-001 | PRJ-001-ACT-03 | 2026-06-10 | Labour | LAB-006 | Painter | VEN-006 | 19 | Worker | 24749.59 | 23085.57 | 4155.4 | 27240.97 | Paid | Low
EXP-00821 | PRJ-001 | PRJ-001-ACT-10 | 2026-06-10 | Equipment | EQ-003 | Concrete Mixer | VEN-010 | 6 | Day | 25130.59 | 25586.33 | 4605.54 | 30191.87 | Paid | Medium
EXP-00822 | PRJ-001 | PRJ-001-ACT-01 | 2026-06-15 | Material | MAT-007 | PVC Pipe | VEN-002 | 16.51 | Meter | 1724.53 | 1731.61 | 311.69 | 2043.3 | Paid | Low
EXP-00823 | PRJ-001 | PRJ-001-ACT-09 | 2026-06-15 | Contractor | CON-001 | Civil Structure Contract | VEN-010 | 1 | Contract | 407032.98 | 395443.29 | 71179.79 | 466623.08 | Paid | Medium
EXP-00824 | PRJ-001 | PRJ-001-ACT-02 | 2026-06-15 | Contractor | CON-003 | Plumbing Contract | VEN-006 | 1 | Contract | 418392.75 | 442785.44 | 79701.38 | 522486.82 | Paid | Low
EXP-00825 | PRJ-001 | PRJ-001-ACT-07 | 2026-06-15 | Contractor | CON-001 | Civil Structure Contract | VEN-010 | 1 | Contract | 430678.26 | 415406.55 | 74773.18 | 490179.73 | Paid | Low
EXP-00826 | PRJ-001 | PRJ-001-ACT-02 | 2026-06-15 | Material | MAT-009 | Paint | VEN-001 | 16.42 | Litre | 3825.18 | 3849.85 | 692.97 | 4542.82 | Paid | Low
EXP-00827 | PRJ-001 | PRJ-001-ACT-07 | 2026-06-15 | Contractor | CON-001 | Civil Structure Contract | VEN-001 | 1 | Contract | 108308.74 | 107293.54 | 19312.84 | 126606.38 | Paid | Low
EXP-00828 | PRJ-001 | PRJ-001-ACT-05 | 2026-06-20 | Contractor | CON-004 | Finishing Contract | VEN-001 | 1 | Contract | 178315.53 | 185476.25 | 33385.72 | 218861.97 | Paid | Low
EXP-00829 | PRJ-001 | PRJ-001-ACT-04 | 2026-06-20 | Labour | LAB-005 | Plumber | VEN-002 | 29 | Worker | 26100.67 | 26859.06 | 4834.63 | 31693.69 | Paid | Medium
EXP-00830 | PRJ-001 | PRJ-001-ACT-06 | 2026-06-20 | Material | MAT-004 | Aggregate | VEN-010 | 3.73 | Ton | 5075.2 | 4951.61 | 891.29 | 5842.9 | Paid | Medium
EXP-00831 | PRJ-001 | PRJ-001-ACT-08 | 2026-06-20 | Labour | LAB-004 | Electrician | VEN-001 | 20 | Worker | 15280.64 | 14791.22 | 2662.42 | 17453.64 | Partially Paid | Low
EXP-00832 | PRJ-001 | PRJ-001-ACT-03 | 2026-06-20 | Material | MAT-009 | Paint | VEN-010 | 14.65 | Litre | 3422.49 | 3421.49 | 615.87 | 4037.36 | Paid | Low
EXP-00833 | PRJ-001 | PRJ-001-ACT-10 | 2026-06-20 | Equipment | EQ-001 | Crane | VEN-001 | 3 | Day | 49738.82 | 52447.5 | 9440.55 | 61888.05 | Paid | Medium
EXP-00834 | PRJ-001 | PRJ-001-ACT-01 | 2026-06-20 | Labour | LAB-001 | Mason | VEN-006 | 24 | Worker | 31373.23 | 32060.46 | 5770.88 | 37831.34 | Paid | Low
EXP-00835 | PRJ-001 | PRJ-001-ACT-06 | 2026-06-20 | Material | MAT-004 | Aggregate | VEN-006 | 10.92 | Ton | 17957.26 | 18525.31 | 3334.56 | 21859.87 | Partially Paid | Medium
EXP-00836 | PRJ-001 | PRJ-001-ACT-01 | 2026-06-20 | Material | MAT-006 | Electrical Cable | VEN-002 | 42.52 | Meter | 3666.06 | 3711.97 | 668.15 | 4380.12 | Paid | Low
EXP-00837 | PRJ-001 | PRJ-001-ACT-10 | 2026-06-25 | Equipment | EQ-001 | Crane | VEN-006 | 4 | Day | 76106.38 | 78806.72 | 14185.21 | 92991.93 | Paid | Low
EXP-00838 | PRJ-001 | PRJ-001-ACT-04 | 2026-06-25 | Contractor | CON-004 | Finishing Contract | VEN-006 | 1 | Contract | 300320.65 | 280997.39 | 50579.53 | 331576.92 | Pending | Low
EXP-00839 | PRJ-001 | PRJ-001-ACT-07 | 2026-06-25 | Labour | LAB-005 | Plumber | VEN-006 | 12 | Worker | 13799.11 | 13417.66 | 2415.18 | 15832.84 | Paid | Medium
EXP-00840 | PRJ-001 | PRJ-001-ACT-04 | 2026-06-25 | Equipment | EQ-004 | Scaffolding | VEN-010 | 2 | Day | 4983.87 | 4689.56 | 844.12 | 5533.68 | Paid | Low
EXP-00841 | PRJ-001 | PRJ-001-ACT-08 | 2026-06-25 | Labour | LAB-002 | Helper | VEN-001 | 11 | Worker | 14606.67 | 14557.35 | 2620.32 | 17177.67 | Paid | Low
EXP-00842 | PRJ-001 | PRJ-001-ACT-02 | 2026-06-25 | Equipment | EQ-004 | Scaffolding | VEN-001 | 1 | Day | 2606.64 | 2654.18 | 477.75 | 3131.93 | Paid | Low
EXP-00843 | PRJ-001 | PRJ-001-ACT-06 | 2026-06-25 | Material | MAT-004 | Aggregate | VEN-010 | 12.06 | Ton | 15243.01 | 16201.3 | 2916.23 | 19117.53 | Paid | Medium
EXP-00844 | PRJ-001 | PRJ-001-ACT-07 | 2026-06-25 | Material | MAT-008 | Tiles | VEN-010 | 20.13 | Sq Ft | 1253.14 | 1302.96 | 234.53 | 1537.49 | Partially Paid | Medium
EXP-00845 | PRJ-001 | PRJ-001-ACT-05 | 2026-06-25 | Material | MAT-001 | Cement | VEN-001 | 9.48 | Bag | 4128.15 | 4214.01 | 758.52 | 4972.53 | Paid | Low
EXP-00846 | PRJ-001 | PRJ-001-ACT-10 | 2026-06-25 | Material | MAT-010 | Glass | VEN-006 | 11.11 | Sq Ft | 1955.42 | 1906.06 | 343.09 | 2249.15 | Paid | Medium
EXP-00847 | PRJ-001 | PRJ-001-ACT-07 | 2026-06-30 | Material | MAT-007 | PVC Pipe | VEN-010 | 24.98 | Meter | 2797.59 | 2888.75 | 519.98 | 3408.73 | Paid | Medium
EXP-00848 | PRJ-001 | PRJ-001-ACT-03 | 2026-06-30 | Contractor | CON-004 | Finishing Contract | VEN-001 | 1 | Contract | 156123.93 | 160245.78 | 28844.24 | 189090.02 | Paid | Low
EXP-00849 | PRJ-001 | PRJ-001-ACT-07 | 2026-06-30 | Material | MAT-009 | Paint | VEN-002 | 12.89 | Litre | 2486.17 | 2498.72 | 449.77 | 2948.49 | Paid | Medium
EXP-00850 | PRJ-001 | PRJ-001-ACT-05 | 2026-06-30 | Contractor | CON-001 | Civil Structure Contract | VEN-002 | 1 | Contract | 278924.19 | 298523.97 | 53734.31 | 352258.28 | Paid | Low
EXP-00851 | PRJ-001 | PRJ-001-ACT-04 | 2026-06-30 | Other | OTH-001 | Site Office | VEN-002 | 1 | Lot | 23280.01 | 21770.19 | 3918.63 | 25688.82 | Paid | Low
EXP-00852 | PRJ-001 | PRJ-001-ACT-02 | 2026-06-30 | Labour | LAB-005 | Plumber | VEN-001 | 30 | Worker | 32760.28 | 34745.82 | 6254.25 | 41000.07 | Paid | Medium
EXP-00853 | PRJ-001 | PRJ-001-ACT-10 | 2026-06-30 | Labour | LAB-001 | Mason | VEN-006 | 13 | Worker | 17335.82 | 18603.62 | 3348.65 | 21952.27 | Pending | Low
EXP-00854 | PRJ-001 | PRJ-001-ACT-09 | 2026-07-05 | Material | MAT-007 | PVC Pipe | VEN-010 | 4.95 | Meter | 478.8 | 520.31 | 93.66 | 613.97 | Paid | Medium
EXP-00855 | PRJ-001 | PRJ-001-ACT-09 | 2026-07-05 | Labour | LAB-004 | Electrician | VEN-006 | 32 | Worker | 29426.53 | 31120.75 | 5601.73 | 36722.48 | Paid | Low
EXP-00856 | PRJ-001 | PRJ-001-ACT-10 | 2026-07-05 | Contractor | CON-002 | Electrical Contract | VEN-001 | 1 | Contract | 274827.66 | 270043.28 | 48607.79 | 318651.07 | Paid | Low
EXP-00857 | PRJ-001 | PRJ-001-ACT-06 | 2026-07-05 | Labour | LAB-004 | Electrician | VEN-010 | 19 | Worker | 28332.51 | 29978.1 | 5396.06 | 35374.16 | Paid | Low
EXP-00858 | PRJ-001 | PRJ-001-ACT-02 | 2026-07-05 | Labour | LAB-001 | Mason | VEN-006 | 10 | Worker | 13055.03 | 12851.7 | 2313.31 | 15165.01 | Paid | Low
EXP-00859 | PRJ-001 | PRJ-001-ACT-01 | 2026-07-05 | Contractor | CON-002 | Electrical Contract | VEN-002 | 1 | Contract | 222743.08 | 228859.8 | 41194.76 | 270054.56 | Paid | Low
EXP-00860 | PRJ-001 | PRJ-001-ACT-07 | 2026-07-10 | Labour | LAB-005 | Plumber | VEN-001 | 14 | Worker | 10746.38 | 11483.76 | 2067.08 | 13550.84 | Paid | Medium
EXP-00861 | PRJ-001 | PRJ-001-ACT-01 | 2026-07-10 | Material | MAT-009 | Paint | VEN-001 | 2.27 | Litre | 470.2 | 450.45 | 81.08 | 531.53 | Paid | Low
EXP-00862 | PRJ-001 | PRJ-001-ACT-02 | 2026-07-10 | Contractor | CON-001 | Civil Structure Contract | VEN-001 | 1 | Contract | 96059.91 | 95517.82 | 17193.21 | 112711.03 | Pending | Medium
EXP-00863 | PRJ-001 | PRJ-001-ACT-10 | 2026-07-10 | Contractor | CON-002 | Electrical Contract | VEN-010 | 1 | Contract | 473560.35 | 440716.7 | 79329.01 | 520045.71 | Paid | Medium
EXP-00864 | PRJ-001 | PRJ-001-ACT-01 | 2026-07-10 | Material | MAT-005 | Bricks | VEN-002 | 4.9 | Piece | 43.65 | 41.32 | 7.44 | 48.76 | Paid | Low
EXP-00865 | PRJ-001 | PRJ-001-ACT-02 | 2026-07-10 | Contractor | CON-003 | Plumbing Contract | VEN-001 | 1 | Contract | 216539.06 | 212489.14 | 38248.05 | 250737.19 | Paid | High
EXP-00866 | PRJ-001 | PRJ-001-ACT-02 | 2026-07-10 | Contractor | CON-002 | Electrical Contract | VEN-001 | 1 | Contract | 355285.22 | 354465.56 | 63803.8 | 418269.36 | Paid | Medium
EXP-00867 | PRJ-001 | PRJ-001-ACT-06 | 2026-07-10 | Material | MAT-004 | Aggregate | VEN-001 | 9.75 | Ton | 12169.93 | 12516.37 | 2252.95 | 14769.32 | Paid | Low
EXP-00868 | PRJ-001 | PRJ-001-ACT-07 | 2026-07-10 | Contractor | CON-002 | Electrical Contract | VEN-010 | 1 | Contract | 169339.78 | 159806.85 | 28765.23 | 188572.08 | Partially Paid | Low
EXP-00869 | PRJ-001 | PRJ-001-ACT-09 | 2026-07-10 | Material | MAT-002 | Steel | VEN-006 | 10.09 | Ton | 556464.23 | 589246.09 | 106064.3 | 695310.39 | Paid | Low
EXP-00870 | PRJ-001 | PRJ-001-ACT-08 | 2026-07-15 | Material | MAT-009 | Paint | VEN-002 | 3.32 | Litre | 716.87 | 694.19 | 124.95 | 819.14 | Paid | Low
EXP-00871 | PRJ-001 | PRJ-001-ACT-03 | 2026-07-15 | Material | MAT-010 | Glass | VEN-010 | 8.43 | Sq Ft | 1228.7 | 1148.46 | 206.72 | 1355.18 | Paid | Medium
EXP-00872 | PRJ-001 | PRJ-001-ACT-09 | 2026-07-15 | Labour | LAB-003 | Carpenter | VEN-006 | 32 | Worker | 53999.14 | 55024.2 | 9904.36 | 64928.56 | Paid | Medium
EXP-00873 | PRJ-001 | PRJ-001-ACT-10 | 2026-07-15 | Contractor | CON-004 | Finishing Contract | VEN-002 | 1 | Contract | 272715.76 | 273521.48 | 49233.87 | 322755.35 | Paid | Medium
EXP-00874 | PRJ-001 | PRJ-001-ACT-03 | 2026-07-15 | Labour | LAB-004 | Electrician | VEN-006 | 34 | Worker | 34727.46 | 36029.82 | 6485.37 | 42515.19 | Paid | Low
EXP-00875 | PRJ-001 | PRJ-001-ACT-05 | 2026-07-15 | Contractor | CON-004 | Finishing Contract | VEN-010 | 1 | Contract | 143370.73 | 150211.75 | 27038.11 | 177249.86 | Paid | Low
EXP-00876 | PRJ-001 | PRJ-001-ACT-08 | 2026-07-15 | Material | MAT-006 | Electrical Cable | VEN-006 | 15.03 | Meter | 1053.29 | 1104.49 | 198.81 | 1303.3 | Paid | Medium
EXP-00877 | PRJ-001 | PRJ-001-ACT-04 | 2026-07-15 | Material | MAT-009 | Paint | VEN-001 | 8.14 | Litre | 1851 | 1810.97 | 325.97 | 2136.94 | Paid | Low
EXP-00878 | PRJ-001 | PRJ-001-ACT-08 | 2026-07-15 | Labour | LAB-003 | Carpenter | VEN-006 | 20 | Worker | 23229.28 | 23928.93 | 4307.21 | 28236.14 | Paid | Low
EXP-00879 | PRJ-001 | PRJ-001-ACT-09 | 2026-07-15 | Material | MAT-001 | Cement | VEN-002 | 7.99 | Bag | 3500.33 | 3621.81 | 651.93 | 4273.74 | Partially Paid | Low
EXP-00880 | PRJ-001 | PRJ-001-ACT-02 | 2026-07-20 | Other | OTH-001 | Permit | VEN-010 | 1 | Lot | 40187.8 | 40533 | 7295.94 | 47828.94 | Paid | Medium
EXP-00881 | PRJ-001 | PRJ-001-ACT-05 | 2026-07-20 | Material | MAT-001 | Cement | VEN-010 | 9.11 | Bag | 5391.79 | 5025.17 | 904.53 | 5929.7 | Paid | Low
EXP-00882 | PRJ-001 | PRJ-001-ACT-02 | 2026-07-20 | Other | OTH-001 | Site Office | VEN-006 | 1 | Lot | 15278.71 | 14484.82 | 2607.27 | 17092.09 | Paid | Medium
EXP-00883 | PRJ-001 | PRJ-001-ACT-10 | 2026-07-20 | Labour | LAB-006 | Painter | VEN-010 | 9 | Worker | 13200.95 | 12501.2 | 2250.22 | 14751.42 | Paid | Low
EXP-00884 | PRJ-001 | PRJ-001-ACT-06 | 2026-07-20 | Material | MAT-008 | Tiles | VEN-010 | 15.67 | Sq Ft | 1364.23 | 1293.35 | 232.8 | 1526.15 | Paid | Low
EXP-00885 | PRJ-001 | PRJ-001-ACT-06 | 2026-07-20 | Labour | LAB-005 | Plumber | VEN-010 | 23 | Worker | 35293.06 | 36168.27 | 6510.29 | 42678.56 | Paid | Low
EXP-00886 | PRJ-001 | PRJ-001-ACT-09 | 2026-07-20 | Contractor | CON-002 | Electrical Contract | VEN-006 | 1 | Contract | 406545.03 | 416841.33 | 75031.44 | 491872.77 | Paid | Low
EXP-00887 | PRJ-001 | PRJ-001-ACT-05 | 2026-07-20 | Material | MAT-007 | PVC Pipe | VEN-001 | 9.45 | Meter | 1177.01 | 1198.65 | 215.76 | 1414.41 | Paid | Medium
EXP-00888 | PRJ-001 | PRJ-001-ACT-03 | 2026-07-25 | Equipment | EQ-001 | Crane | VEN-001 | 2 | Day | 34174.12 | 33600.7 | 6048.13 | 39648.83 | Paid | Low
EXP-00889 | PRJ-001 | PRJ-001-ACT-03 | 2026-07-25 | Material | MAT-004 | Aggregate | VEN-001 | 15.84 | Ton | 23689.76 | 22403.78 | 4032.68 | 26436.46 | Paid | Low
EXP-00890 | PRJ-001 | PRJ-001-ACT-04 | 2026-07-25 | Material | MAT-001 | Cement | VEN-010 | 4.77 | Bag | 1944.85 | 2110.51 | 379.89 | 2490.4 | Paid | Low
EXP-00891 | PRJ-001 | PRJ-001-ACT-02 | 2026-07-25 | Labour | LAB-006 | Painter | VEN-001 | 15 | Worker | 13121.23 | 12401.05 | 2232.19 | 14633.24 | Paid | Medium
EXP-00892 | PRJ-001 | PRJ-001-ACT-02 | 2026-07-25 | Labour | LAB-006 | Painter | VEN-001 | 34 | Worker | 38439.22 | 37077.6 | 6673.97 | 43751.57 | Paid | Low
EXP-00893 | PRJ-001 | PRJ-001-ACT-05 | 2026-07-25 | Labour | LAB-005 | Plumber | VEN-010 | 12 | Worker | 20578.72 | 20632.21 | 3713.8 | 24346.01 | Paid | Low
EXP-00894 | PRJ-001 | PRJ-001-ACT-01 | 2026-07-25 | Contractor | CON-002 | Electrical Contract | VEN-002 | 1 | Contract | 446105.46 | 416559.08 | 74980.63 | 491539.71 | Paid | Medium
EXP-00895 | PRJ-001 | PRJ-001-ACT-07 | 2026-07-25 | Contractor | CON-003 | Plumbing Contract | VEN-010 | 1 | Contract | 87827.49 | 87861.71 | 15815.11 | 103676.82 | Paid | Low
EXP-00896 | PRJ-001 | PRJ-001-ACT-07 | 2026-07-25 | Material | MAT-004 | Aggregate | VEN-010 | 7.92 | Ton | 10852.6 | 11016.84 | 1983.03 | 12999.87 | Paid | Low
EXP-00897 | PRJ-001 | PRJ-001-ACT-06 | 2026-07-30 | Material | MAT-010 | Glass | VEN-010 | 9.2 | Sq Ft | 1204.72 | 1289.09 | 232.04 | 1521.13 | Partially Paid | Medium
EXP-00898 | PRJ-001 | PRJ-001-ACT-10 | 2026-07-30 | Material | MAT-005 | Bricks | VEN-010 | 12.27 | Piece | 89.67 | 94.17 | 16.95 | 111.12 | Pending | Medium
EXP-00899 | PRJ-001 | PRJ-001-ACT-07 | 2026-07-30 | Material | MAT-010 | Glass | VEN-006 | 7.33 | Sq Ft | 1236.06 | 1230.54 | 221.5 | 1452.04 | Pending | Medium
EXP-00900 | PRJ-001 | PRJ-001-ACT-02 | 2026-07-30 | Material | MAT-005 | Bricks | VEN-006 | 17.71 | Piece | 161.86 | 173.94 | 31.31 | 205.25 | Paid | Medium
EXP-00901 | PRJ-001 | PRJ-001-ACT-08 | 2026-07-30 | Contractor | CON-004 | Finishing Contract | VEN-001 | 1 | Contract | 374061.36 | 369104.93 | 66438.89 | 435543.82 | Paid | Medium
EXP-00902 | PRJ-001 | PRJ-001-ACT-02 | 2026-07-30 | Material | MAT-002 | Steel | VEN-001 | 9.28 | Ton | 534479.19 | 537846.65 | 96812.4 | 634659.05 | Paid | Low
EXP-00903 | PRJ-001 | PRJ-001-ACT-09 | 2026-07-30 | Labour | LAB-005 | Plumber | VEN-002 | 12 | Worker | 22189.05 | 21380.84 | 3848.55 | 25229.39 | Paid | Medium
EXP-00904 | PRJ-001 | PRJ-001-ACT-04 | 2026-07-30 | Labour | LAB-002 | Helper | VEN-006 | 28 | Worker | 43063.26 | 41382.7 | 7448.89 | 48831.59 | Paid | Low
EXP-00905 | PRJ-001 | PRJ-001-ACT-01 | 2026-08-04 | Material | MAT-005 | Bricks | VEN-006 | 7.1 | Piece | 70.3 | 70.09 | 12.62 | 82.71 | Paid | Low
EXP-00906 | PRJ-001 | PRJ-001-ACT-06 | 2026-08-04 | Labour | LAB-002 | Helper | VEN-002 | 21 | Worker | 29765.53 | 28845.64 | 5192.22 | 34037.86 | Paid | Low
EXP-00907 | PRJ-001 | PRJ-001-ACT-10 | 2026-08-04 | Contractor | CON-004 | Finishing Contract | VEN-002 | 1 | Contract | 435433.48 | 414360.71 | 74584.93 | 488945.64 | Paid | Medium
EXP-00908 | PRJ-001 | PRJ-001-ACT-10 | 2026-08-04 | Material | MAT-008 | Tiles | VEN-010 | 13.56 | Sq Ft | 987.19 | 1003.61 | 180.65 | 1184.26 | Paid | High
EXP-00909 | PRJ-001 | PRJ-001-ACT-04 | 2026-08-04 | Material | MAT-010 | Glass | VEN-006 | 1.31 | Sq Ft | 178.46 | 189.21 | 34.06 | 223.27 | Paid | High
EXP-00910 | PRJ-001 | PRJ-001-ACT-06 | 2026-08-04 | Material | MAT-001 | Cement | VEN-002 | 2.05 | Bag | 1010.68 | 962.52 | 173.25 | 1135.77 | Paid | Low
EXP-00911 | PRJ-001 | PRJ-001-ACT-02 | 2026-08-09 | Labour | LAB-003 | Carpenter | VEN-002 | 27 | Worker | 39533.6 | 37295.92 | 6713.27 | 44009.19 | Paid | High
EXP-00912 | PRJ-001 | PRJ-001-ACT-07 | 2026-08-09 | Material | MAT-007 | PVC Pipe | VEN-001 | 6.41 | Meter | 927.68 | 871.55 | 156.88 | 1028.43 | Partially Paid | Low
EXP-00913 | PRJ-001 | PRJ-001-ACT-04 | 2026-08-09 | Contractor | CON-003 | Plumbing Contract | VEN-001 | 1 | Contract | 297019.7 | 287155.24 | 51687.94 | 338843.18 | Pending | High
EXP-00914 | PRJ-001 | PRJ-001-ACT-10 | 2026-08-09 | Contractor | CON-002 | Electrical Contract | VEN-002 | 1 | Contract | 180483.5 | 170693.34 | 30724.8 | 201418.14 | Paid | Medium
EXP-00915 | PRJ-001 | PRJ-001-ACT-01 | 2026-08-09 | Material | MAT-007 | PVC Pipe | VEN-006 | 27.62 | Meter | 2883.15 | 2863.05 | 515.35 | 3378.4 | Paid | Low
EXP-00916 | PRJ-001 | PRJ-001-ACT-10 | 2026-08-09 | Labour | LAB-001 | Mason | VEN-006 | 18 | Worker | 33159.6 | 31739.92 | 5713.19 | 37453.11 | Paid | Medium
EXP-00917 | PRJ-001 | PRJ-001-ACT-06 | 2026-08-09 | Equipment | EQ-002 | Excavator | VEN-001 | 3 | Day | 42069.66 | 41832.91 | 7529.92 | 49362.83 | Paid | Low
EXP-00918 | PRJ-001 | PRJ-001-ACT-02 | 2026-08-09 | Labour | LAB-006 | Painter | VEN-006 | 25 | Worker | 33740.33 | 34317.16 | 6177.09 | 40494.25 | Paid | High
EXP-00919 | PRJ-001 | PRJ-001-ACT-09 | 2026-08-14 | Equipment | EQ-003 | Concrete Mixer | VEN-001 | 3 | Day | 13008.49 | 12664.12 | 2279.54 | 14943.66 | Paid | Medium
EXP-00920 | PRJ-001 | PRJ-001-ACT-02 | 2026-08-14 | Material | MAT-004 | Aggregate | VEN-006 | 1.72 | Ton | 2622.43 | 2441.23 | 439.42 | 2880.65 | Paid | Low
EXP-00921 | PRJ-001 | PRJ-001-ACT-01 | 2026-08-14 | Labour | LAB-006 | Painter | VEN-002 | 24 | Worker | 18962.58 | 18209.76 | 3277.76 | 21487.52 | Paid | Medium
EXP-00922 | PRJ-001 | PRJ-001-ACT-01 | 2026-08-14 | Material | MAT-005 | Bricks | VEN-006 | 7.59 | Piece | 62.36 | 62.32 | 11.22 | 73.54 | Paid | Low
EXP-00923 | PRJ-001 | PRJ-001-ACT-05 | 2026-08-14 | Contractor | CON-004 | Finishing Contract | VEN-001 | 1 | Contract | 97678.09 | 104247.7 | 18764.59 | 123012.29 | Paid | Low
EXP-00924 | PRJ-001 | PRJ-001-ACT-03 | 2026-08-14 | Other | OTH-001 | Site Office | VEN-001 | 1 | Lot | 33504.76 | 31178.93 | 5612.21 | 36791.14 | Paid | Medium
EXP-00925 | PRJ-001 | PRJ-001-ACT-01 | 2026-08-14 | Material | MAT-001 | Cement | VEN-001 | 6.12 | Bag | 3199.18 | 3458.59 | 622.55 | 4081.14 | Pending | Low
EXP-00926 | PRJ-001 | PRJ-001-ACT-08 | 2026-08-19 | Material | MAT-006 | Electrical Cable | VEN-002 | 17.11 | Meter | 1409.68 | 1500.96 | 270.17 | 1771.13 | Paid | Medium
EXP-00927 | PRJ-001 | PRJ-001-ACT-09 | 2026-08-19 | Material | MAT-003 | Sand | VEN-002 | 5.86 | Ton | 10739.48 | 11301.6 | 2034.29 | 13335.89 | Paid | Low
EXP-00928 | PRJ-001 | PRJ-001-ACT-03 | 2026-08-19 | Contractor | CON-001 | Civil Structure Contract | VEN-001 | 1 | Contract | 113565.17 | 105265.67 | 18947.82 | 124213.49 | Paid | High
EXP-00929 | PRJ-001 | PRJ-001-ACT-04 | 2026-08-19 | Material | MAT-004 | Aggregate | VEN-001 | 5.68 | Ton | 9137.7 | 9362.7 | 1685.29 | 11047.99 | Paid | Low
EXP-00930 | PRJ-001 | PRJ-001-ACT-06 | 2026-08-19 | Material | MAT-005 | Bricks | VEN-002 | 11.28 | Piece | 89.26 | 96.32 | 17.34 | 113.66 | Paid | Low
EXP-00931 | PRJ-001 | PRJ-001-ACT-03 | 2026-08-19 | Material | MAT-010 | Glass | VEN-010 | 10.02 | Sq Ft | 1497.6 | 1447.41 | 260.53 | 1707.94 | Paid | Low
EXP-00932 | PRJ-001 | PRJ-001-ACT-04 | 2026-08-19 | Material | MAT-005 | Bricks | VEN-010 | 14.4 | Piece | 122.76 | 116.15 | 20.91 | 137.06 | Paid | Low
EXP-00933 | PRJ-001 | PRJ-001-ACT-08 | 2026-08-19 | Equipment | EQ-003 | Concrete Mixer | VEN-002 | 6 | Day | 25890.97 | 27562.54 | 4961.26 | 32523.8 | Paid | Low
EXP-00934 | PRJ-001 | PRJ-001-ACT-09 | 2026-08-24 | Material | MAT-003 | Sand | VEN-006 | 4.87 | Ton | 8137.81 | 8584.5 | 1545.21 | 10129.71 | Pending | Medium
EXP-00935 | PRJ-001 | PRJ-001-ACT-01 | 2026-08-24 | Equipment | EQ-002 | Excavator | VEN-006 | 3 | Day | 39714.46 | 40204.58 | 7236.82 | 47441.4 | Paid | Low
EXP-00936 | PRJ-001 | PRJ-001-ACT-05 | 2026-08-24 | Contractor | CON-003 | Plumbing Contract | VEN-006 | 1 | Contract | 357163.44 | 379729.74 | 68351.35 | 448081.09 | Paid | Medium
EXP-00937 | PRJ-001 | PRJ-001-ACT-07 | 2026-08-24 | Material | MAT-006 | Electrical Cable | VEN-001 | 2.49 | Meter | 198.93 | 193.67 | 34.86 | 228.53 | Pending | Low
EXP-00938 | PRJ-001 | PRJ-001-ACT-04 | 2026-08-24 | Labour | LAB-005 | Plumber | VEN-002 | 15 | Worker | 18070.86 | 18653.33 | 3357.6 | 22010.93 | Paid | Medium
EXP-00939 | PRJ-001 | PRJ-001-ACT-10 | 2026-08-24 | Material | MAT-008 | Tiles | VEN-001 | 3.66 | Sq Ft | 256.41 | 269.88 | 48.58 | 318.46 | Paid | Low
EXP-00940 | PRJ-001 | PRJ-001-ACT-01 | 2026-08-24 | Labour | LAB-004 | Electrician | VEN-006 | 6 | Worker | 4545.89 | 4280.26 | 770.45 | 5050.71 | Paid | Low
EXP-00941 | PRJ-001 | PRJ-001-ACT-01 | 2026-08-24 | Material | MAT-003 | Sand | VEN-002 | 21.19 | Ton | 30067.16 | 32482.99 | 5846.94 | 38329.93 | Partially Paid | Medium
EXP-00942 | PRJ-001 | PRJ-001-ACT-01 | 2026-08-24 | Labour | LAB-006 | Painter | VEN-002 | 19 | Worker | 28074.26 | 27818.66 | 5007.36 | 32826.02 | Paid | Medium
EXP-00943 | PRJ-001 | PRJ-001-ACT-09 | 2026-08-29 | Material | MAT-010 | Glass | VEN-002 | 9.47 | Sq Ft | 1433.14 | 1409.68 | 253.74 | 1663.42 | Partially Paid | High
EXP-00944 | PRJ-001 | PRJ-001-ACT-04 | 2026-08-29 | Labour | LAB-005 | Plumber | VEN-001 | 25 | Worker | 23563.8 | 23641.51 | 4255.47 | 27896.98 | Paid | High
EXP-00945 | PRJ-001 | PRJ-001-ACT-01 | 2026-08-29 | Material | MAT-006 | Electrical Cable | VEN-010 | 12.66 | Meter | 1083.43 | 1112.96 | 200.33 | 1313.29 | Partially Paid | Low
EXP-00946 | PRJ-001 | PRJ-001-ACT-01 | 2026-08-29 | Contractor | CON-001 | Civil Structure Contract | VEN-001 | 1 | Contract | 372446.71 | 395199.75 | 71135.96 | 466335.71 | Paid | Low
EXP-00947 | PRJ-001 | PRJ-001-ACT-02 | 2026-08-29 | Material | MAT-001 | Cement | VEN-010 | 19.2 | Bag | 9796.92 | 9802.69 | 1764.48 | 11567.17 | Paid | Medium
EXP-00948 | PRJ-001 | PRJ-001-ACT-08 | 2026-08-29 | Labour | LAB-003 | Carpenter | VEN-001 | 32 | Worker | 47357.84 | 50515.19 | 9092.73 | 59607.92 | Paid | Low
EXP-00949 | PRJ-001 | PRJ-001-ACT-08 | 2026-08-29 | Labour | LAB-005 | Plumber | VEN-002 | 10 | Worker | 13013.55 | 12291.63 | 2212.49 | 14504.12 | Pending | Low
EXP-00950 | PRJ-001 | PRJ-001-ACT-01 | 2026-08-29 | Labour | LAB-001 | Mason | VEN-001 | 8 | Worker | 11940.92 | 12490 | 2248.2 | 14738.2 | Paid | Low
EXP-00951 | PRJ-001 | PRJ-001-ACT-04 | 2026-09-03 | Labour | LAB-005 | Plumber | VEN-010 | 16 | Worker | 10145.33 | 10815.26 | 1946.75 | 12762.01 | Paid | Medium
EXP-00952 | PRJ-001 | PRJ-001-ACT-01 | 2026-09-03 | Material | MAT-010 | Glass | VEN-010 | 5.47 | Sq Ft | 956.83 | 933.27 | 167.99 | 1101.26 | Pending | High
EXP-00953 | PRJ-001 | PRJ-001-ACT-01 | 2026-09-03 | Contractor | CON-002 | Electrical Contract | VEN-002 | 1 | Contract | 286657.69 | 280356.04 | 50464.09 | 330820.13 | Paid | Low
EXP-00954 | PRJ-001 | PRJ-001-ACT-06 | 2026-09-03 | Material | MAT-001 | Cement | VEN-006 | 20.32 | Bag | 12020.65 | 11645.58 | 2096.2 | 13741.78 | Paid | Low
EXP-00955 | PRJ-001 | PRJ-001-ACT-09 | 2026-09-03 | Material | MAT-009 | Paint | VEN-001 | 11.52 | Litre | 2453.4 | 2359.62 | 424.73 | 2784.35 | Pending | Low
EXP-00956 | PRJ-001 | PRJ-001-ACT-04 | 2026-09-03 | Material | MAT-003 | Sand | VEN-010 | 12.64 | Ton | 20290.96 | 20057.7 | 3610.39 | 23668.09 | Paid | Medium
EXP-00957 | PRJ-001 | PRJ-001-ACT-09 | 2026-09-03 | Labour | LAB-001 | Mason | VEN-001 | 30 | Worker | 37191.78 | 37022.46 | 6664.04 | 43686.5 | Partially Paid | Medium
EXP-00958 | PRJ-001 | PRJ-001-ACT-01 | 2026-09-08 | Labour | LAB-005 | Plumber | VEN-006 | 15 | Worker | 16481.81 | 15649.89 | 2816.98 | 18466.87 | Paid | Medium
EXP-00959 | PRJ-001 | PRJ-001-ACT-04 | 2026-09-08 | Material | MAT-008 | Tiles | VEN-010 | 12.62 | Sq Ft | 764.11 | 806.9 | 145.24 | 952.14 | Paid | Medium
EXP-00960 | PRJ-001 | PRJ-001-ACT-01 | 2026-09-08 | Contractor | CON-004 | Finishing Contract | VEN-010 | 1 | Contract | 221706.86 | 214164.78 | 38549.66 | 252714.44 | Paid | Medium
EXP-00961 | PRJ-001 | PRJ-001-ACT-08 | 2026-09-08 | Labour | LAB-002 | Helper | VEN-001 | 32 | Worker | 37278.95 | 40004.53 | 7200.82 | 47205.35 | Paid | Medium
EXP-00962 | PRJ-001 | PRJ-001-ACT-01 | 2026-09-08 | Equipment | EQ-002 | Excavator | VEN-002 | 1 | Day | 14657.87 | 15372.62 | 2767.07 | 18139.69 | Paid | High
EXP-00963 | PRJ-001 | PRJ-001-ACT-03 | 2026-09-08 | Material | MAT-002 | Steel | VEN-010 | 5.59 | Ton | 365082.73 | 376371.24 | 67746.82 | 444118.06 | Partially Paid | Medium
EXP-00964 | PRJ-001 | PRJ-001-ACT-06 | 2026-09-08 | Contractor | CON-001 | Civil Structure Contract | VEN-006 | 1 | Contract | 149593.83 | 154203.1 | 27756.56 | 181959.66 | Paid | High
EXP-00965 | PRJ-001 | PRJ-001-ACT-04 | 2026-09-08 | Material | MAT-001 | Cement | VEN-006 | 13.87 | Bag | 6562.64 | 6330.18 | 1139.43 | 7469.61 | Paid | Medium
EXP-00966 | PRJ-001 | PRJ-001-ACT-02 | 2026-09-13 | Material | MAT-007 | PVC Pipe | VEN-002 | 4.23 | Meter | 481.17 | 519.31 | 93.48 | 612.79 | Paid | Medium
EXP-00967 | PRJ-001 | PRJ-001-ACT-07 | 2026-09-13 | Contractor | CON-003 | Plumbing Contract | VEN-006 | 1 | Contract | 201379.61 | 197483.21 | 35546.98 | 233030.19 | Paid | Low
EXP-00968 | PRJ-001 | PRJ-001-ACT-09 | 2026-09-13 | Labour | LAB-002 | Helper | VEN-010 | 26 | Worker | 23426.57 | 24754.53 | 4455.82 | 29210.35 | Paid | Low
EXP-00969 | PRJ-001 | PRJ-001-ACT-04 | 2026-09-13 | Material | MAT-002 | Steel | VEN-001 | 10.24 | Ton | 728495.06 | 694287.46 | 124971.74 | 819259.2 | Paid | Low
EXP-00970 | PRJ-001 | PRJ-001-ACT-07 | 2026-09-13 | Equipment | EQ-003 | Concrete Mixer | VEN-001 | 7 | Day | 33252.54 | 33250.63 | 5985.11 | 39235.74 | Paid | Low
EXP-00971 | PRJ-001 | PRJ-001-ACT-10 | 2026-09-13 | Equipment | EQ-004 | Scaffolding | VEN-002 | 5 | Day | 12628.37 | 12105.84 | 2179.05 | 14284.89 | Paid | Medium
EXP-00972 | PRJ-001 | PRJ-001-ACT-04 | 2026-09-13 | Labour | LAB-002 | Helper | VEN-010 | 13 | Worker | 21113.41 | 19652.26 | 3537.41 | 23189.67 | Paid | Low
EXP-00973 | PRJ-001 | PRJ-001-ACT-04 | 2026-09-13 | Contractor | CON-003 | Plumbing Contract | VEN-006 | 1 | Contract | 294184.31 | 283321.9 | 50997.94 | 334319.84 | Paid | Low
EXP-00974 | PRJ-001 | PRJ-001-ACT-06 | 2026-09-13 | Material | MAT-008 | Tiles | VEN-010 | 18.38 | Sq Ft | 1414.33 | 1518.21 | 273.28 | 1791.49 | Partially Paid | Low
EXP-00975 | PRJ-001 | PRJ-001-ACT-09 | 2026-09-18 | Labour | LAB-003 | Carpenter | VEN-001 | 22 | Worker | 37942.4 | 35673.23 | 6421.18 | 42094.41 | Paid | Medium
EXP-00976 | PRJ-001 | PRJ-001-ACT-07 | 2026-09-18 | Material | MAT-008 | Tiles | VEN-002 | 28.83 | Sq Ft | 2305.72 | 2186.5 | 393.57 | 2580.07 | Paid | Low
EXP-00977 | PRJ-001 | PRJ-001-ACT-10 | 2026-09-18 | Material | MAT-005 | Bricks | VEN-002 | 11.47 | Piece | 95.1 | 92.22 | 16.6 | 108.82 | Paid | Medium
EXP-00978 | PRJ-001 | PRJ-001-ACT-03 | 2026-09-18 | Material | MAT-001 | Cement | VEN-010 | 7.99 | Bag | 4727.19 | 4695.35 | 845.16 | 5540.51 | Paid | Low
EXP-00979 | PRJ-001 | PRJ-001-ACT-02 | 2026-09-18 | Material | MAT-006 | Electrical Cable | VEN-002 | 4.7 | Meter | 408.22 | 407.15 | 73.29 | 480.44 | Paid | Medium
EXP-00980 | PRJ-001 | PRJ-001-ACT-05 | 2026-09-18 | Material | MAT-008 | Tiles | VEN-010 | 4.61 | Sq Ft | 347.39 | 341.95 | 61.55 | 403.5 | Paid | Medium
EXP-00981 | PRJ-001 | PRJ-001-ACT-04 | 2026-09-18 | Material | MAT-009 | Paint | VEN-001 | 20.03 | Litre | 4346.66 | 4137.88 | 744.82 | 4882.7 | Partially Paid | Low
EXP-00982 | PRJ-001 | PRJ-001-ACT-06 | 2026-09-18 | Labour | LAB-001 | Mason | VEN-002 | 32 | Worker | 43387.23 | 42978.25 | 7736.09 | 50714.34 | Paid | Low
EXP-00983 | PRJ-001 | PRJ-001-ACT-09 | 2026-09-18 | Labour | LAB-001 | Mason | VEN-006 | 21 | Worker | 20073.8 | 20473.36 | 3685.2 | 24158.56 | Paid | Medium
EXP-00984 | PRJ-001 | PRJ-001-ACT-05 | 2026-09-23 | Contractor | CON-002 | Electrical Contract | VEN-001 | 1 | Contract | 167612 | 161177.38 | 29011.93 | 190189.31 | Paid | Medium
EXP-00985 | PRJ-001 | PRJ-001-ACT-02 | 2026-09-23 | Labour | LAB-006 | Painter | VEN-002 | 11 | Worker | 11036.12 | 10796.94 | 1943.45 | 12740.39 | Paid | Low
EXP-00986 | PRJ-001 | PRJ-001-ACT-06 | 2026-09-23 | Material | MAT-005 | Bricks | VEN-002 | 24.43 | Piece | 199.07 | 201.36 | 36.24 | 237.6 | Paid | Medium
EXP-00987 | PRJ-001 | PRJ-001-ACT-06 | 2026-09-23 | Material | MAT-007 | PVC Pipe | VEN-002 | 47.32 | Meter | 5686.39 | 5986.6 | 1077.59 | 7064.19 | Paid | Medium
EXP-00988 | PRJ-001 | PRJ-001-ACT-05 | 2026-09-23 | Labour | LAB-005 | Plumber | VEN-002 | 34 | Worker | 53080.53 | 50230.88 | 9041.56 | 59272.44 | Paid | Low
EXP-00989 | PRJ-001 | PRJ-001-ACT-03 | 2026-09-23 | Material | MAT-002 | Steel | VEN-001 | 2.97 | Ton | 177723.47 | 185020.88 | 33303.76 | 218324.64 | Pending | High
EXP-00990 | PRJ-001 | PRJ-001-ACT-02 | 2026-09-23 | Labour | LAB-001 | Mason | VEN-010 | 5 | Worker | 5822.72 | 5618.15 | 1011.27 | 6629.42 | Paid | Medium
EXP-00991 | PRJ-001 | PRJ-001-ACT-09 | 2026-09-23 | Contractor | CON-004 | Finishing Contract | VEN-001 | 1 | Contract | 105343.49 | 110646.2 | 19916.32 | 130562.52 | Paid | Low
EXP-00992 | PRJ-001 | PRJ-001-ACT-01 | 2026-09-23 | Contractor | CON-003 | Plumbing Contract | VEN-006 | 1 | Contract | 311412.3 | 302137.22 | 54384.7 | 356521.92 | Paid | Medium
EXP-00993 | PRJ-001 | PRJ-001-ACT-03 | 2026-09-23 | Labour | LAB-003 | Carpenter | VEN-002 | 5 | Worker | 7553.76 | 7161.37 | 1289.05 | 8450.42 | Paid | Medium
EXP-00994 | PRJ-001 | PRJ-001-ACT-09 | 2026-09-28 | Material | MAT-010 | Glass | VEN-010 | 6.81 | Sq Ft | 1207.93 | 1154.32 | 207.78 | 1362.1 | Paid | Low
EXP-00995 | PRJ-001 | PRJ-001-ACT-07 | 2026-09-28 | Labour | LAB-005 | Plumber | VEN-010 | 11 | Worker | 8444.38 | 8875.09 | 1597.52 | 10472.61 | Paid | Low
EXP-00996 | PRJ-001 | PRJ-001-ACT-09 | 2026-09-28 | Material | MAT-006 | Electrical Cable | VEN-010 | 3.81 | Meter | 341.62 | 317.05 | 57.07 | 374.12 | Paid | Medium
EXP-00997 | PRJ-001 | PRJ-001-ACT-09 | 2026-09-28 | Contractor | CON-004 | Finishing Contract | VEN-006 | 1 | Contract | 411855.43 | 409527.88 | 73715.02 | 483242.9 | Paid | Medium
EXP-00998 | PRJ-001 | PRJ-001-ACT-09 | 2026-09-28 | Material | MAT-004 | Aggregate | VEN-010 | 6.42 | Ton | 9757.78 | 9387.29 | 1689.71 | 11077 | Paid | Low
EXP-00999 | PRJ-001 | PRJ-001-ACT-06 | 2026-09-28 | Labour | LAB-003 | Carpenter | VEN-001 | 19 | Worker | 22212.12 | 20735.84 | 3732.45 | 24468.29 | Paid | Medium
EXP-01000 | PRJ-001 | PRJ-001-ACT-07 | 2026-09-28 | Contractor | CON-003 | Plumbing Contract | VEN-006 | 1 | Contract | 240213.95 | 240575.25 | 43303.54 | 283878.79 | Partially Paid | Medium
EXP-01001 | PRJ-002 | PRJ-002-ACT-04 | 2025-04-01 | Material | MAT-003 | Sand | VEN-002 | 3.1 | Ton | 5445.4 | 5193.51 | 934.83 | 6128.34 | Paid | High
EXP-01002 | PRJ-002 | PRJ-002-ACT-07 | 2025-04-01 | Material | MAT-007 | PVC Pipe | VEN-002 | 12.13 | Meter | 1337.88 | 1275.5 | 229.59 | 1505.09 | Paid | Medium
EXP-01003 | PRJ-002 | PRJ-002-ACT-01 | 2025-04-01 | Labour | LAB-001 | Mason | VEN-007 | 12 | Worker | 16150.25 | 17192.05 | 3094.57 | 20286.62 | Paid | Low
EXP-01004 | PRJ-002 | PRJ-002-ACT-06 | 2025-04-01 | Equipment | EQ-004 | Scaffolding | VEN-011 | 7 | Day | 18312.23 | 19041.39 | 3427.45 | 22468.84 | Partially Paid | Medium
EXP-01005 | PRJ-002 | PRJ-002-ACT-04 | 2025-04-01 | Contractor | CON-002 | Electrical Contract | VEN-002 | 1 | Contract | 338274.67 | 348068.76 | 62652.38 | 410721.14 | Pending | Low
EXP-01006 | PRJ-002 | PRJ-002-ACT-06 | 2025-04-01 | Labour | LAB-002 | Helper | VEN-007 | 25 | Worker | 39894.08 | 42161.2 | 7589.02 | 49750.22 | Paid | Low
EXP-01007 | PRJ-002 | PRJ-002-ACT-03 | 2025-04-06 | Equipment | EQ-001 | Crane | VEN-007 | 2 | Day | 36499.4 | 39241.52 | 7063.47 | 46304.99 | Paid | Low
EXP-01008 | PRJ-002 | PRJ-002-ACT-02 | 2025-04-06 | Contractor | CON-003 | Plumbing Contract | VEN-007 | 1 | Contract | 365196.39 | 386840.22 | 69631.24 | 456471.46 | Paid | Medium
EXP-01009 | PRJ-002 | PRJ-002-ACT-07 | 2025-04-06 | Material | MAT-004 | Aggregate | VEN-011 | 14.63 | Ton | 18850.97 | 20193.82 | 3634.89 | 23828.71 | Paid | Low
EXP-01010 | PRJ-002 | PRJ-002-ACT-01 | 2025-04-06 | Material | MAT-009 | Paint | VEN-007 | 10.13 | Litre | 1910.84 | 2070.38 | 372.67 | 2443.05 | Paid | Medium
EXP-01011 | PRJ-002 | PRJ-002-ACT-08 | 2025-04-06 | Labour | LAB-004 | Electrician | VEN-007 | 13 | Worker | 14000.15 | 13279.91 | 2390.38 | 15670.29 | Paid | Medium
EXP-01012 | PRJ-002 | PRJ-002-ACT-06 | 2025-04-06 | Material | MAT-005 | Bricks | VEN-003 | 4.5 | Piece | 34.54 | 35.84 | 6.45 | 42.29 | Paid | Low
EXP-01013 | PRJ-002 | PRJ-002-ACT-09 | 2025-04-06 | Contractor | CON-002 | Electrical Contract | VEN-011 | 1 | Contract | 184138.97 | 188811.09 | 33986 | 222797.09 | Pending | Low
EXP-01014 | PRJ-002 | PRJ-002-ACT-04 | 2025-04-06 | Material | MAT-002 | Steel | VEN-011 | 3.86 | Ton | 234565.04 | 253213.23 | 45578.38 | 298791.61 | Partially Paid | Low
EXP-01015 | PRJ-002 | PRJ-002-ACT-06 | 2025-04-06 | Labour | LAB-002 | Helper | VEN-007 | 9 | Worker | 12157.91 | 12243.47 | 2203.82 | 14447.29 | Partially Paid | Low
EXP-01016 | PRJ-002 | PRJ-002-ACT-09 | 2025-04-11 | Material | MAT-004 | Aggregate | VEN-003 | 4.93 | Ton | 6588.62 | 6309.43 | 1135.7 | 7445.13 | Partially Paid | Low
EXP-01017 | PRJ-002 | PRJ-002-ACT-10 | 2025-04-11 | Labour | LAB-001 | Mason | VEN-007 | 32 | Worker | 55953.76 | 52978.46 | 9536.12 | 62514.58 | Paid | Low
EXP-01018 | PRJ-002 | PRJ-002-ACT-07 | 2025-04-11 | Contractor | CON-001 | Civil Structure Contract | VEN-007 | 1 | Contract | 263780.31 | 246352.07 | 44343.37 | 290695.44 | Partially Paid | Low
EXP-01019 | PRJ-002 | PRJ-002-ACT-03 | 2025-04-11 | Contractor | CON-001 | Civil Structure Contract | VEN-002 | 1 | Contract | 378120.99 | 401323.76 | 72238.28 | 473562.04 | Paid | Low
EXP-01020 | PRJ-002 | PRJ-002-ACT-01 | 2025-04-11 | Other | OTH-001 | Safety | VEN-011 | 1 | Lot | 28939.48 | 30223.45 | 5440.22 | 35663.67 | Paid | Medium
EXP-01021 | PRJ-002 | PRJ-002-ACT-04 | 2025-04-11 | Labour | LAB-006 | Painter | VEN-011 | 18 | Worker | 16347.51 | 15214 | 2738.52 | 17952.52 | Paid | Low
EXP-01022 | PRJ-002 | PRJ-002-ACT-04 | 2025-04-11 | Material | MAT-010 | Glass | VEN-002 | 15.15 | Sq Ft | 2103.19 | 2235.57 | 402.4 | 2637.97 | Paid | Low
EXP-01023 | PRJ-002 | PRJ-002-ACT-06 | 2025-04-11 | Material | MAT-010 | Glass | VEN-002 | 25.6 | Sq Ft | 3927.15 | 3935.93 | 708.47 | 4644.4 | Paid | Low
EXP-01024 | PRJ-002 | PRJ-002-ACT-04 | 2025-04-16 | Equipment | EQ-004 | Scaffolding | VEN-002 | 3 | Day | 8476.36 | 8175.91 | 1471.66 | 9647.57 | Paid | Medium
EXP-01025 | PRJ-002 | PRJ-002-ACT-04 | 2025-04-16 | Contractor | CON-002 | Electrical Contract | VEN-011 | 1 | Contract | 268688.23 | 285377.56 | 51367.96 | 336745.52 | Paid | High
EXP-01026 | PRJ-002 | PRJ-002-ACT-01 | 2025-04-16 | Material | MAT-004 | Aggregate | VEN-011 | 34.48 | Ton | 61050.37 | 56626.59 | 10192.79 | 66819.38 | Paid | Low
EXP-01027 | PRJ-002 | PRJ-002-ACT-10 | 2025-04-16 | Contractor | CON-003 | Plumbing Contract | VEN-007 | 1 | Contract | 224070.36 | 235468.01 | 42384.24 | 277852.25 | Paid | Medium
EXP-01028 | PRJ-002 | PRJ-002-ACT-10 | 2025-04-16 | Material | MAT-001 | Cement | VEN-003 | 1.91 | Bag | 1032.9 | 1064.8 | 191.66 | 1256.46 | Partially Paid | Medium
EXP-01029 | PRJ-002 | PRJ-002-ACT-05 | 2025-04-16 | Contractor | CON-001 | Civil Structure Contract | VEN-007 | 1 | Contract | 122182.71 | 119227 | 21460.86 | 140687.86 | Paid | Low
EXP-01030 | PRJ-002 | PRJ-002-ACT-04 | 2025-04-21 | Material | MAT-003 | Sand | VEN-002 | 7.7 | Ton | 14093.69 | 13943.92 | 2509.91 | 16453.83 | Paid | Low
EXP-01031 | PRJ-002 | PRJ-002-ACT-05 | 2025-04-21 | Contractor | CON-003 | Plumbing Contract | VEN-003 | 1 | Contract | 240185.76 | 223592.76 | 40246.7 | 263839.46 | Paid | Low
EXP-01032 | PRJ-002 | PRJ-002-ACT-03 | 2025-04-21 | Material | MAT-010 | Glass | VEN-003 | 13.07 | Sq Ft | 1735.19 | 1791.45 | 322.46 | 2113.91 | Partially Paid | Low
EXP-01033 | PRJ-002 | PRJ-002-ACT-02 | 2025-04-21 | Material | MAT-004 | Aggregate | VEN-007 | 8.14 | Ton | 11518.77 | 10756.33 | 1936.14 | 12692.47 | Paid | Low
EXP-01034 | PRJ-002 | PRJ-002-ACT-06 | 2025-04-21 | Equipment | EQ-003 | Concrete Mixer | VEN-011 | 6 | Day | 30642.27 | 28529.77 | 5135.36 | 33665.13 | Paid | Low
EXP-01035 | PRJ-002 | PRJ-002-ACT-07 | 2025-04-21 | Labour | LAB-006 | Painter | VEN-007 | 26 | Worker | 38420.75 | 40990.57 | 7378.3 | 48368.87 | Pending | Medium
EXP-01036 | PRJ-002 | PRJ-002-ACT-08 | 2025-04-21 | Equipment | EQ-003 | Concrete Mixer | VEN-003 | 7 | Day | 34634.75 | 32503.91 | 5850.7 | 38354.61 | Pending | Low
EXP-01037 | PRJ-002 | PRJ-002-ACT-09 | 2025-04-21 | Material | MAT-007 | PVC Pipe | VEN-011 | 5.46 | Meter | 754.54 | 751.71 | 135.31 | 887.02 | Paid | Low
EXP-01038 | PRJ-002 | PRJ-002-ACT-06 | 2025-04-21 | Material | MAT-001 | Cement | VEN-007 | 3.78 | Bag | 1954.28 | 2080.7 | 374.53 | 2455.23 | Paid | Low
EXP-01039 | PRJ-002 | PRJ-002-ACT-08 | 2025-04-21 | Contractor | CON-004 | Finishing Contract | VEN-002 | 1 | Contract | 94784.53 | 99709.56 | 17947.72 | 117657.28 | Paid | High
EXP-01040 | PRJ-002 | PRJ-002-ACT-01 | 2025-04-26 | Material | MAT-001 | Cement | VEN-003 | 8.05 | Bag | 3560.18 | 3756.09 | 676.1 | 4432.19 | Paid | Low
EXP-01041 | PRJ-002 | PRJ-002-ACT-04 | 2025-04-26 | Labour | LAB-002 | Helper | VEN-002 | 19 | Worker | 29495.07 | 27396.89 | 4931.44 | 32328.33 | Paid | High
EXP-01042 | PRJ-002 | PRJ-002-ACT-07 | 2025-04-26 | Contractor | CON-001 | Civil Structure Contract | VEN-003 | 1 | Contract | 401786.38 | 411673.43 | 74101.22 | 485774.65 | Paid | Low
EXP-01043 | PRJ-002 | PRJ-002-ACT-06 | 2025-04-26 | Material | MAT-004 | Aggregate | VEN-003 | 6.96 | Ton | 9436.55 | 9509.78 | 1711.76 | 11221.54 | Paid | Medium
EXP-01044 | PRJ-002 | PRJ-002-ACT-05 | 2025-04-26 | Material | MAT-005 | Bricks | VEN-011 | 23 | Piece | 210.12 | 204.1 | 36.74 | 240.84 | Paid | Medium
EXP-01045 | PRJ-002 | PRJ-002-ACT-04 | 2025-04-26 | Material | MAT-007 | PVC Pipe | VEN-007 | 17.31 | Meter | 2518.98 | 2339.84 | 421.17 | 2761.01 | Paid | Medium
EXP-01046 | PRJ-002 | PRJ-002-ACT-08 | 2025-04-26 | Material | MAT-001 | Cement | VEN-003 | 9.37 | Bag | 4949.96 | 5301.47 | 954.26 | 6255.73 | Paid | Medium
EXP-01047 | PRJ-002 | PRJ-002-ACT-03 | 2025-04-26 | Material | MAT-010 | Glass | VEN-011 | 10.55 | Sq Ft | 1729.41 | 1767.56 | 318.16 | 2085.72 | Paid | Medium
EXP-01048 | PRJ-002 | PRJ-002-ACT-07 | 2025-04-26 | Material | MAT-010 | Glass | VEN-003 | 11.42 | Sq Ft | 1520.19 | 1642.77 | 295.7 | 1938.47 | Paid | Medium
EXP-01049 | PRJ-002 | PRJ-002-ACT-09 | 2025-04-26 | Material | MAT-007 | PVC Pipe | VEN-011 | 16.6 | Meter | 2154.77 | 2215.24 | 398.74 | 2613.98 | Paid | Medium
EXP-01050 | PRJ-002 | PRJ-002-ACT-05 | 2025-05-01 | Contractor | CON-002 | Electrical Contract | VEN-003 | 1 | Contract | 249732.28 | 238858.07 | 42994.45 | 281852.52 | Paid | Low
EXP-01051 | PRJ-002 | PRJ-002-ACT-03 | 2025-05-01 | Contractor | CON-001 | Civil Structure Contract | VEN-003 | 1 | Contract | 292761.72 | 316658.69 | 56998.56 | 373657.25 | Partially Paid | Medium
EXP-01052 | PRJ-002 | PRJ-002-ACT-06 | 2025-05-01 | Material | MAT-005 | Bricks | VEN-011 | 6.13 | Piece | 53.89 | 53.82 | 9.69 | 63.51 | Paid | Low
EXP-01053 | PRJ-002 | PRJ-002-ACT-03 | 2025-05-01 | Material | MAT-010 | Glass | VEN-003 | 4.19 | Sq Ft | 742.49 | 756.85 | 136.23 | 893.08 | Paid | Low
EXP-01054 | PRJ-002 | PRJ-002-ACT-07 | 2025-05-01 | Material | MAT-009 | Paint | VEN-011 | 4.33 | Litre | 831.1 | 893.27 | 160.79 | 1054.06 | Partially Paid | Low
EXP-01055 | PRJ-002 | PRJ-002-ACT-08 | 2025-05-01 | Contractor | CON-003 | Plumbing Contract | VEN-011 | 1 | Contract | 110598.25 | 116623.06 | 20992.15 | 137615.21 | Paid | Low
EXP-01056 | PRJ-002 | PRJ-002-ACT-04 | 2025-05-01 | Labour | LAB-003 | Carpenter | VEN-002 | 20 | Worker | 24718.51 | 23640.24 | 4255.24 | 27895.48 | Partially Paid | Medium
EXP-01057 | PRJ-002 | PRJ-002-ACT-10 | 2025-05-01 | Material | MAT-005 | Bricks | VEN-007 | 14.74 | Piece | 137.02 | 147.78 | 26.6 | 174.38 | Paid | Medium
EXP-01058 | PRJ-002 | PRJ-002-ACT-04 | 2025-05-01 | Material | MAT-009 | Paint | VEN-002 | 30.03 | Litre | 6768.33 | 6937.01 | 1248.66 | 8185.67 | Partially Paid | Low
EXP-01059 | PRJ-002 | PRJ-002-ACT-08 | 2025-05-06 | Material | MAT-009 | Paint | VEN-011 | 8.61 | Litre | 1597.34 | 1733.12 | 311.96 | 2045.08 | Paid | Medium
EXP-01060 | PRJ-002 | PRJ-002-ACT-01 | 2025-05-06 | Equipment | EQ-002 | Excavator | VEN-002 | 7 | Day | 85445.01 | 90416.75 | 16275.01 | 106691.76 | Paid | Low
EXP-01061 | PRJ-002 | PRJ-002-ACT-02 | 2025-05-06 | Contractor | CON-002 | Electrical Contract | VEN-007 | 1 | Contract | 178564.44 | 185160.7 | 33328.93 | 218489.63 | Paid | Low
EXP-01062 | PRJ-002 | PRJ-002-ACT-08 | 2025-05-06 | Material | MAT-003 | Sand | VEN-002 | 37.23 | Ton | 68725.06 | 71097.04 | 12797.47 | 83894.51 | Paid | High
EXP-01063 | PRJ-002 | PRJ-002-ACT-03 | 2025-05-06 | Contractor | CON-003 | Plumbing Contract | VEN-011 | 1 | Contract | 359204.92 | 343373.49 | 61807.23 | 405180.72 | Paid | Medium
EXP-01064 | PRJ-002 | PRJ-002-ACT-05 | 2025-05-06 | Labour | LAB-005 | Plumber | VEN-011 | 25 | Worker | 43605.38 | 43031.63 | 7745.69 | 50777.32 | Paid | Low
EXP-01065 | PRJ-002 | PRJ-002-ACT-05 | 2025-05-06 | Material | MAT-005 | Bricks | VEN-007 | 15.14 | Piece | 109.09 | 118.54 | 21.34 | 139.88 | Paid | Low
EXP-01066 | PRJ-002 | PRJ-002-ACT-07 | 2025-05-06 | Other | OTH-001 | Safety | VEN-007 | 1 | Lot | 13927.78 | 15013.67 | 2702.46 | 17716.13 | Paid | Medium
EXP-01067 | PRJ-002 | PRJ-002-ACT-04 | 2025-05-11 | Material | MAT-010 | Glass | VEN-002 | 5.31 | Sq Ft | 943.63 | 973.44 | 175.22 | 1148.66 | Paid | Low
EXP-01068 | PRJ-002 | PRJ-002-ACT-09 | 2025-05-11 | Labour | LAB-004 | Electrician | VEN-011 | 17 | Worker | 14406.86 | 14800.4 | 2664.07 | 17464.47 | Paid | Medium
EXP-01069 | PRJ-002 | PRJ-002-ACT-05 | 2025-05-11 | Material | MAT-009 | Paint | VEN-007 | 6.93 | Litre | 1417.45 | 1474.04 | 265.33 | 1739.37 | Paid | Low
EXP-01070 | PRJ-002 | PRJ-002-ACT-01 | 2025-05-11 | Other | OTH-001 | Transport | VEN-011 | 1 | Lot | 52094.21 | 55513.76 | 9992.48 | 65506.24 | Paid | Low
EXP-01071 | PRJ-002 | PRJ-002-ACT-09 | 2025-05-11 | Contractor | CON-002 | Electrical Contract | VEN-011 | 1 | Contract | 234193.94 | 218242.52 | 39283.65 | 257526.17 | Paid | High
EXP-01072 | PRJ-002 | PRJ-002-ACT-06 | 2025-05-11 | Contractor | CON-003 | Plumbing Contract | VEN-002 | 1 | Contract | 337335.01 | 314522.32 | 56614.02 | 371136.34 | Paid | Low
EXP-01073 | PRJ-002 | PRJ-002-ACT-02 | 2025-05-16 | Material | MAT-004 | Aggregate | VEN-002 | 9.78 | Ton | 14538.34 | 15571.81 | 2802.93 | 18374.74 | Paid | Medium
EXP-01074 | PRJ-002 | PRJ-002-ACT-09 | 2025-05-16 | Other | OTH-001 | Site Office | VEN-003 | 1 | Lot | 61554.66 | 59043.98 | 10627.92 | 69671.9 | Paid | Low
EXP-01075 | PRJ-002 | PRJ-002-ACT-04 | 2025-05-16 | Material | MAT-004 | Aggregate | VEN-011 | 8.41 | Ton | 14624.27 | 13747.47 | 2474.54 | 16222.01 | Pending | Medium
EXP-01076 | PRJ-002 | PRJ-002-ACT-04 | 2025-05-16 | Material | MAT-008 | Tiles | VEN-003 | 3.53 | Sq Ft | 247.12 | 250.14 | 45.03 | 295.17 | Paid | Low
EXP-01077 | PRJ-002 | PRJ-002-ACT-06 | 2025-05-16 | Other | OTH-001 | Miscellaneous | VEN-002 | 1 | Lot | 13419.02 | 13726.13 | 2470.7 | 16196.83 | Pending | High
EXP-01078 | PRJ-002 | PRJ-002-ACT-08 | 2025-05-16 | Contractor | CON-003 | Plumbing Contract | VEN-007 | 1 | Contract | 323384.31 | 333011.44 | 59942.06 | 392953.5 | Paid | High
EXP-01079 | PRJ-002 | PRJ-002-ACT-05 | 2025-05-16 | Contractor | CON-001 | Civil Structure Contract | VEN-011 | 1 | Contract | 241661.93 | 244621.3 | 44031.83 | 288653.13 | Paid | Low
EXP-01080 | PRJ-002 | PRJ-002-ACT-08 | 2025-05-16 | Labour | LAB-001 | Mason | VEN-011 | 30 | Worker | 47795.09 | 46456.79 | 8362.22 | 54819.01 | Paid | High
EXP-01081 | PRJ-002 | PRJ-002-ACT-09 | 2025-05-21 | Material | MAT-005 | Bricks | VEN-007 | 10.57 | Piece | 93.6 | 96.31 | 17.34 | 113.65 | Paid | Medium
EXP-01082 | PRJ-002 | PRJ-002-ACT-01 | 2025-05-21 | Labour | LAB-004 | Electrician | VEN-011 | 8 | Worker | 6740.14 | 6373.7 | 1147.27 | 7520.97 | Paid | Low
EXP-01083 | PRJ-002 | PRJ-002-ACT-07 | 2025-05-21 | Contractor | CON-004 | Finishing Contract | VEN-007 | 1 | Contract | 127204.72 | 118319.21 | 21297.46 | 139616.67 | Pending | Low
EXP-01084 | PRJ-002 | PRJ-002-ACT-10 | 2025-05-21 | Material | MAT-010 | Glass | VEN-007 | 25.9 | Sq Ft | 4312.07 | 4552.03 | 819.37 | 5371.4 | Partially Paid | Medium
EXP-01085 | PRJ-002 | PRJ-002-ACT-07 | 2025-05-21 | Contractor | CON-001 | Civil Structure Contract | VEN-007 | 1 | Contract | 446490.19 | 419639.35 | 75535.08 | 495174.43 | Paid | Low
EXP-01086 | PRJ-002 | PRJ-002-ACT-04 | 2025-05-21 | Material | MAT-002 | Steel | VEN-003 | 12.98 | Ton | 811880.32 | 751817.19 | 135327.09 | 887144.28 | Paid | Low
EXP-01087 | PRJ-002 | PRJ-002-ACT-04 | 2025-05-21 | Equipment | EQ-004 | Scaffolding | VEN-002 | 2 | Day | 4519.02 | 4658.64 | 838.56 | 5497.2 | Paid | Low
EXP-01088 | PRJ-002 | PRJ-002-ACT-07 | 2025-05-21 | Contractor | CON-002 | Electrical Contract | VEN-007 | 1 | Contract | 361805.08 | 361049.64 | 64988.94 | 426038.58 | Paid | Medium
EXP-01089 | PRJ-002 | PRJ-002-ACT-08 | 2025-05-21 | Material | MAT-005 | Bricks | VEN-011 | 7.87 | Piece | 63.27 | 68.76 | 12.38 | 81.14 | Paid | Medium
EXP-01090 | PRJ-002 | PRJ-002-ACT-09 | 2025-05-21 | Contractor | CON-004 | Finishing Contract | VEN-011 | 1 | Contract | 290532.6 | 311488.57 | 56067.94 | 367556.51 | Paid | Low
EXP-01091 | PRJ-002 | PRJ-002-ACT-05 | 2025-05-26 | Material | MAT-001 | Cement | VEN-002 | 5.77 | Bag | 3262.44 | 3064.88 | 551.68 | 3616.56 | Paid | High
EXP-01092 | PRJ-002 | PRJ-002-ACT-05 | 2025-05-26 | Contractor | CON-001 | Civil Structure Contract | VEN-002 | 1 | Contract | 425541.32 | 448504.79 | 80730.86 | 529235.65 | Paid | Medium
EXP-01093 | PRJ-002 | PRJ-002-ACT-09 | 2025-05-26 | Material | MAT-010 | Glass | VEN-003 | 18.77 | Sq Ft | 3019.34 | 3160.16 | 568.83 | 3728.99 | Paid | Low
EXP-01094 | PRJ-002 | PRJ-002-ACT-03 | 2025-05-26 | Material | MAT-003 | Sand | VEN-007 | 3.86 | Ton | 6975.3 | 6858.42 | 1234.52 | 8092.94 | Paid | Medium
EXP-01095 | PRJ-002 | PRJ-002-ACT-04 | 2025-05-26 | Labour | LAB-005 | Plumber | VEN-002 | 12 | Worker | 15075.78 | 15199.45 | 2735.9 | 17935.35 | Paid | Low
EXP-01096 | PRJ-002 | PRJ-002-ACT-05 | 2025-05-26 | Equipment | EQ-003 | Concrete Mixer | VEN-011 | 4 | Day | 16915.61 | 17685.93 | 3183.47 | 20869.4 | Paid | Low
EXP-01097 | PRJ-002 | PRJ-002-ACT-07 | 2025-05-31 | Labour | LAB-002 | Helper | VEN-011 | 19 | Worker | 33101.21 | 33180.14 | 5972.43 | 39152.57 | Pending | Low
EXP-01098 | PRJ-002 | PRJ-002-ACT-08 | 2025-05-31 | Contractor | CON-002 | Electrical Contract | VEN-007 | 1 | Contract | 293991.55 | 284565.33 | 51221.76 | 335787.09 | Paid | Low
EXP-01099 | PRJ-002 | PRJ-002-ACT-10 | 2025-05-31 | Contractor | CON-002 | Electrical Contract | VEN-011 | 1 | Contract | 269127.08 | 267164.91 | 48089.68 | 315254.59 | Paid | Low
EXP-01100 | PRJ-002 | PRJ-002-ACT-01 | 2025-05-31 | Labour | LAB-004 | Electrician | VEN-007 | 22 | Worker | 16530.41 | 17939.01 | 3229.02 | 21168.03 | Paid | Low
EXP-01101 | PRJ-002 | PRJ-002-ACT-02 | 2025-05-31 | Labour | LAB-004 | Electrician | VEN-003 | 22 | Worker | 20813.16 | 22286.04 | 4011.49 | 26297.53 | Paid | Low
EXP-01102 | PRJ-002 | PRJ-002-ACT-01 | 2025-05-31 | Labour | LAB-004 | Electrician | VEN-011 | 5 | Worker | 3329.46 | 3319.4 | 597.49 | 3916.89 | Paid | High
EXP-01103 | PRJ-002 | PRJ-002-ACT-03 | 2025-05-31 | Labour | LAB-001 | Mason | VEN-011 | 31 | Worker | 33287.68 | 32622.16 | 5871.99 | 38494.15 | Paid | Medium
EXP-01104 | PRJ-002 | PRJ-002-ACT-06 | 2025-05-31 | Contractor | CON-002 | Electrical Contract | VEN-002 | 1 | Contract | 158915.05 | 155489.24 | 27988.06 | 183477.3 | Paid | Medium
EXP-01105 | PRJ-002 | PRJ-002-ACT-10 | 2025-05-31 | Contractor | CON-003 | Plumbing Contract | VEN-007 | 1 | Contract | 393554.51 | 391959.58 | 70552.72 | 462512.3 | Paid | Medium
EXP-01106 | PRJ-002 | PRJ-002-ACT-08 | 2025-05-31 | Labour | LAB-005 | Plumber | VEN-002 | 5 | Worker | 4434.85 | 4515.38 | 812.77 | 5328.15 | Partially Paid | Medium
EXP-01107 | PRJ-002 | PRJ-002-ACT-08 | 2025-06-05 | Equipment | EQ-002 | Excavator | VEN-011 | 4 | Day | 52093.78 | 55156.4 | 9928.15 | 65084.55 | Paid | Low
EXP-01108 | PRJ-002 | PRJ-002-ACT-07 | 2025-06-05 | Other | OTH-001 | Site Office | VEN-002 | 1 | Lot | 36257.61 | 38599.66 | 6947.94 | 45547.6 | Paid | Low
EXP-01109 | PRJ-002 | PRJ-002-ACT-02 | 2025-06-05 | Material | MAT-003 | Sand | VEN-003 | 9.64 | Ton | 18651.2 | 18708.9 | 3367.6 | 22076.5 | Pending | Medium
EXP-01110 | PRJ-002 | PRJ-002-ACT-06 | 2025-06-05 | Contractor | CON-001 | Civil Structure Contract | VEN-011 | 1 | Contract | 150351.62 | 140089.55 | 25216.12 | 165305.67 | Partially Paid | Low
EXP-01111 | PRJ-002 | PRJ-002-ACT-06 | 2025-06-05 | Material | MAT-007 | PVC Pipe | VEN-002 | 6.92 | Meter | 730.22 | 710.73 | 127.93 | 838.66 | Paid | Medium
EXP-01112 | PRJ-002 | PRJ-002-ACT-05 | 2025-06-05 | Material | MAT-001 | Cement | VEN-003 | 17.6 | Bag | 10087.73 | 10103.17 | 1818.57 | 11921.74 | Paid | Low
EXP-01113 | PRJ-002 | PRJ-002-ACT-09 | 2025-06-10 | Material | MAT-008 | Tiles | VEN-002 | 9.61 | Sq Ft | 760.92 | 779.47 | 140.3 | 919.77 | Partially Paid | Low
EXP-01114 | PRJ-002 | PRJ-002-ACT-03 | 2025-06-10 | Material | MAT-008 | Tiles | VEN-002 | 8.48 | Sq Ft | 650.79 | 605.76 | 109.04 | 714.8 | Paid | Medium
EXP-01115 | PRJ-002 | PRJ-002-ACT-08 | 2025-06-10 | Material | MAT-002 | Steel | VEN-011 | 8.58 | Ton | 530618.01 | 532013.25 | 95762.38 | 627775.63 | Paid | Medium
EXP-01116 | PRJ-002 | PRJ-002-ACT-07 | 2025-06-10 | Labour | LAB-002 | Helper | VEN-003 | 25 | Worker | 37956.93 | 35991.2 | 6478.42 | 42469.62 | Paid | Medium
EXP-01117 | PRJ-002 | PRJ-002-ACT-07 | 2025-06-10 | Material | MAT-007 | PVC Pipe | VEN-011 | 6.54 | Meter | 848.7 | 821.2 | 147.82 | 969.02 | Paid | Low
EXP-01118 | PRJ-002 | PRJ-002-ACT-07 | 2025-06-10 | Labour | LAB-005 | Plumber | VEN-007 | 27 | Worker | 45490.86 | 48376.56 | 8707.78 | 57084.34 | Paid | Medium
EXP-01119 | PRJ-002 | PRJ-002-ACT-06 | 2025-06-10 | Material | MAT-008 | Tiles | VEN-007 | 18.61 | Sq Ft | 1263.59 | 1296.14 | 233.31 | 1529.45 | Paid | Medium
EXP-01120 | PRJ-002 | PRJ-002-ACT-07 | 2025-06-10 | Labour | LAB-005 | Plumber | VEN-007 | 24 | Worker | 39338.35 | 37632.33 | 6773.82 | 44406.15 | Paid | Low
EXP-01121 | PRJ-002 | PRJ-002-ACT-09 | 2025-06-10 | Labour | LAB-002 | Helper | VEN-002 | 7 | Worker | 11170.17 | 10446.26 | 1880.33 | 12326.59 | Paid | Low
EXP-01122 | PRJ-002 | PRJ-002-ACT-01 | 2025-06-10 | Material | MAT-006 | Electrical Cable | VEN-002 | 3.76 | Meter | 356.49 | 359.9 | 64.78 | 424.68 | Pending | Low
EXP-01123 | PRJ-002 | PRJ-002-ACT-07 | 2025-06-15 | Material | MAT-010 | Glass | VEN-003 | 8.95 | Sq Ft | 1647.76 | 1576.16 | 283.71 | 1859.87 | Partially Paid | Medium
EXP-01124 | PRJ-002 | PRJ-002-ACT-03 | 2025-06-15 | Contractor | CON-004 | Finishing Contract | VEN-011 | 1 | Contract | 310775.56 | 318405.23 | 57312.94 | 375718.17 | Partially Paid | Low
EXP-01125 | PRJ-002 | PRJ-002-ACT-07 | 2025-06-15 | Equipment | EQ-003 | Concrete Mixer | VEN-002 | 2 | Day | 7764.35 | 8302.51 | 1494.45 | 9796.96 | Paid | Low
EXP-01126 | PRJ-002 | PRJ-002-ACT-10 | 2025-06-15 | Material | MAT-009 | Paint | VEN-002 | 8.87 | Litre | 2097.97 | 2036.17 | 366.51 | 2402.68 | Paid | Medium
EXP-01127 | PRJ-002 | PRJ-002-ACT-04 | 2025-06-15 | Material | MAT-002 | Steel | VEN-011 | 8.64 | Ton | 510371.59 | 483394.96 | 87011.09 | 570406.05 | Paid | Medium
EXP-01128 | PRJ-002 | PRJ-002-ACT-01 | 2025-06-15 | Labour | LAB-005 | Plumber | VEN-011 | 26 | Worker | 25163.16 | 26619.22 | 4791.46 | 31410.68 | Paid | Low
EXP-01129 | PRJ-002 | PRJ-002-ACT-08 | 2025-06-15 | Material | MAT-009 | Paint | VEN-011 | 7.6 | Litre | 1340.74 | 1450.3 | 261.05 | 1711.35 | Paid | Low
EXP-01130 | PRJ-002 | PRJ-002-ACT-09 | 2025-06-15 | Contractor | CON-001 | Civil Structure Contract | VEN-002 | 1 | Contract | 382471.76 | 385943.17 | 69469.77 | 455412.94 | Paid | Low
EXP-01131 | PRJ-002 | PRJ-002-ACT-09 | 2025-06-15 | Material | MAT-009 | Paint | VEN-002 | 3.88 | Litre | 742.11 | 731.08 | 131.59 | 862.67 | Paid | Low
EXP-01132 | PRJ-002 | PRJ-002-ACT-04 | 2025-06-20 | Material | MAT-007 | PVC Pipe | VEN-002 | 13.14 | Meter | 1665.98 | 1628.57 | 293.14 | 1921.71 | Paid | Medium
EXP-01133 | PRJ-002 | PRJ-002-ACT-04 | 2025-06-20 | Material | MAT-009 | Paint | VEN-003 | 4.32 | Litre | 1075.25 | 1006.15 | 181.11 | 1187.26 | Paid | Medium
EXP-01134 | PRJ-002 | PRJ-002-ACT-10 | 2025-06-20 | Contractor | CON-004 | Finishing Contract | VEN-007 | 1 | Contract | 176358.86 | 179268.28 | 32268.29 | 211536.57 | Paid | Medium
EXP-01135 | PRJ-002 | PRJ-002-ACT-04 | 2025-06-20 | Contractor | CON-002 | Electrical Contract | VEN-002 | 1 | Contract | 334658.16 | 316839.87 | 57031.18 | 373871.05 | Paid | Medium
EXP-01136 | PRJ-002 | PRJ-002-ACT-09 | 2025-06-20 | Material | MAT-010 | Glass | VEN-007 | 10.07 | Sq Ft | 1442.41 | 1459.8 | 262.76 | 1722.56 | Paid | Medium
EXP-01137 | PRJ-002 | PRJ-002-ACT-04 | 2025-06-20 | Labour | LAB-001 | Mason | VEN-003 | 12 | Worker | 17779.28 | 17375.07 | 3127.51 | 20502.58 | Paid | Low
EXP-01138 | PRJ-002 | PRJ-002-ACT-09 | 2025-06-20 | Material | MAT-008 | Tiles | VEN-002 | 25.74 | Sq Ft | 2027.28 | 2010.1 | 361.82 | 2371.92 | Paid | Medium
EXP-01139 | PRJ-002 | PRJ-002-ACT-02 | 2025-06-20 | Material | MAT-005 | Bricks | VEN-011 | 2.9 | Piece | 23.17 | 23.78 | 4.28 | 28.06 | Paid | Low
EXP-01140 | PRJ-002 | PRJ-002-ACT-01 | 2025-06-20 | Labour | LAB-005 | Plumber | VEN-002 | 23 | Worker | 42220.34 | 39599.92 | 7127.99 | 46727.91 | Paid | Medium
EXP-01141 | PRJ-002 | PRJ-002-ACT-01 | 2025-06-25 | Contractor | CON-004 | Finishing Contract | VEN-003 | 1 | Contract | 190286.96 | 187934.63 | 33828.23 | 221762.86 | Paid | Medium
EXP-01142 | PRJ-002 | PRJ-002-ACT-01 | 2025-06-25 | Material | MAT-009 | Paint | VEN-003 | 13.48 | Litre | 3162.91 | 2966.21 | 533.92 | 3500.13 | Paid | Medium
EXP-01143 | PRJ-002 | PRJ-002-ACT-03 | 2025-06-25 | Labour | LAB-002 | Helper | VEN-003 | 22 | Worker | 32277.03 | 34408.38 | 6193.51 | 40601.89 | Paid | Low
EXP-01144 | PRJ-002 | PRJ-002-ACT-04 | 2025-06-25 | Contractor | CON-004 | Finishing Contract | VEN-003 | 1 | Contract | 127329.02 | 117949.83 | 21230.97 | 139180.8 | Paid | Low
EXP-01145 | PRJ-002 | PRJ-002-ACT-03 | 2025-06-25 | Equipment | EQ-001 | Crane | VEN-003 | 5 | Day | 92309.6 | 89176.87 | 16051.84 | 105228.71 | Paid | Medium
EXP-01146 | PRJ-002 | PRJ-002-ACT-01 | 2025-06-25 | Equipment | EQ-004 | Scaffolding | VEN-003 | 6 | Day | 15549.47 | 14448.88 | 2600.8 | 17049.68 | Paid | Low
EXP-01147 | PRJ-002 | PRJ-002-ACT-04 | 2025-06-30 | Labour | LAB-002 | Helper | VEN-002 | 5 | Worker | 8319.42 | 8583.48 | 1545.03 | 10128.51 | Paid | Medium
EXP-01148 | PRJ-002 | PRJ-002-ACT-01 | 2025-06-30 | Other | OTH-001 | Miscellaneous | VEN-007 | 1 | Lot | 66416.93 | 69434.78 | 12498.26 | 81933.04 | Paid | Low
EXP-01149 | PRJ-002 | PRJ-002-ACT-08 | 2025-06-30 | Contractor | CON-004 | Finishing Contract | VEN-002 | 1 | Contract | 366579.92 | 353187.27 | 63573.71 | 416760.98 | Paid | Medium
EXP-01150 | PRJ-002 | PRJ-002-ACT-09 | 2025-06-30 | Material | MAT-002 | Steel | VEN-011 | 9.79 | Ton | 549112.5 | 535396.17 | 96371.31 | 631767.48 | Partially Paid | Medium
EXP-01151 | PRJ-002 | PRJ-002-ACT-01 | 2025-06-30 | Labour | LAB-001 | Mason | VEN-007 | 16 | Worker | 16538.47 | 16618.65 | 2991.36 | 19610.01 | Paid | Medium
EXP-01152 | PRJ-002 | PRJ-002-ACT-09 | 2025-06-30 | Material | MAT-006 | Electrical Cable | VEN-002 | 2.45 | Meter | 227.78 | 238.23 | 42.88 | 281.11 | Paid | Low
EXP-01153 | PRJ-002 | PRJ-002-ACT-10 | 2025-06-30 | Material | MAT-008 | Tiles | VEN-003 | 17.25 | Sq Ft | 1420.2 | 1415.74 | 254.83 | 1670.57 | Paid | Low
EXP-01154 | PRJ-002 | PRJ-002-ACT-10 | 2025-06-30 | Material | MAT-007 | PVC Pipe | VEN-007 | 8.36 | Meter | 863.64 | 893.48 | 160.83 | 1054.31 | Paid | Medium
EXP-01155 | PRJ-002 | PRJ-002-ACT-07 | 2025-07-05 | Labour | LAB-002 | Helper | VEN-011 | 32 | Worker | 48238.74 | 50341.78 | 9061.52 | 59403.3 | Paid | Medium
EXP-01156 | PRJ-002 | PRJ-002-ACT-03 | 2025-07-05 | Labour | LAB-003 | Carpenter | VEN-011 | 11 | Worker | 13551.96 | 14115.26 | 2540.75 | 16656.01 | Paid | Low
EXP-01157 | PRJ-002 | PRJ-002-ACT-01 | 2025-07-05 | Contractor | CON-002 | Electrical Contract | VEN-011 | 1 | Contract | 429790.73 | 435660.93 | 78418.97 | 514079.9 | Paid | Medium
EXP-01158 | PRJ-002 | PRJ-002-ACT-04 | 2025-07-05 | Other | OTH-001 | Miscellaneous | VEN-002 | 1 | Lot | 58347.32 | 56720.6 | 10209.71 | 66930.31 | Paid | Medium
EXP-01159 | PRJ-002 | PRJ-002-ACT-02 | 2025-07-05 | Contractor | CON-004 | Finishing Contract | VEN-007 | 1 | Contract | 260274.75 | 255477.73 | 45985.99 | 301463.72 | Paid | Low
EXP-01160 | PRJ-002 | PRJ-002-ACT-05 | 2025-07-05 | Other | OTH-001 | Safety | VEN-003 | 1 | Lot | 36537.94 | 36490.28 | 6568.25 | 43058.53 | Paid | Medium
EXP-01161 | PRJ-002 | PRJ-002-ACT-02 | 2025-07-05 | Contractor | CON-002 | Electrical Contract | VEN-003 | 1 | Contract | 390474.23 | 381868.2 | 68736.28 | 450604.48 | Paid | Medium
EXP-01162 | PRJ-002 | PRJ-002-ACT-01 | 2025-07-05 | Material | MAT-005 | Bricks | VEN-002 | 4.4 | Piece | 43.56 | 44.75 | 8.05 | 52.8 | Paid | Low
EXP-01163 | PRJ-002 | PRJ-002-ACT-08 | 2025-07-05 | Material | MAT-001 | Cement | VEN-007 | 10.02 | Bag | 4461.66 | 4635.28 | 834.35 | 5469.63 | Paid | Low
EXP-01164 | PRJ-002 | PRJ-002-ACT-05 | 2025-07-05 | Contractor | CON-004 | Finishing Contract | VEN-002 | 1 | Contract | 143519.04 | 149952.37 | 26991.43 | 176943.8 | Paid | Medium
EXP-01165 | PRJ-002 | PRJ-002-ACT-09 | 2025-07-10 | Labour | LAB-006 | Painter | VEN-007 | 29 | Worker | 42738 | 41399.33 | 7451.88 | 48851.21 | Paid | Medium
EXP-01166 | PRJ-002 | PRJ-002-ACT-01 | 2025-07-10 | Material | MAT-009 | Paint | VEN-002 | 8.28 | Litre | 1864.32 | 1767.28 | 318.11 | 2085.39 | Paid | Low
EXP-01167 | PRJ-002 | PRJ-002-ACT-04 | 2025-07-10 | Contractor | CON-004 | Finishing Contract | VEN-003 | 1 | Contract | 333174.74 | 329455.25 | 59301.94 | 388757.19 | Pending | Low
EXP-01168 | PRJ-002 | PRJ-002-ACT-03 | 2025-07-10 | Labour | LAB-001 | Mason | VEN-011 | 24 | Worker | 20715.17 | 20070.29 | 3612.65 | 23682.94 | Partially Paid | Low
EXP-01169 | PRJ-002 | PRJ-002-ACT-09 | 2025-07-10 | Material | MAT-001 | Cement | VEN-003 | 23.38 | Bag | 10403.46 | 10568.55 | 1902.34 | 12470.89 | Paid | Low
EXP-01170 | PRJ-002 | PRJ-002-ACT-06 | 2025-07-10 | Labour | LAB-006 | Painter | VEN-007 | 16 | Worker | 22190.98 | 22075.44 | 3973.58 | 26049.02 | Paid | Low
EXP-01171 | PRJ-002 | PRJ-002-ACT-03 | 2025-07-10 | Contractor | CON-003 | Plumbing Contract | VEN-007 | 1 | Contract | 240091.34 | 225979.29 | 40676.27 | 266655.56 | Paid | Medium
EXP-01172 | PRJ-002 | PRJ-002-ACT-04 | 2025-07-10 | Labour | LAB-004 | Electrician | VEN-007 | 26 | Worker | 31620.94 | 30477.49 | 5485.95 | 35963.44 | Paid | Low
EXP-01173 | PRJ-002 | PRJ-002-ACT-05 | 2025-07-15 | Material | MAT-002 | Steel | VEN-007 | 20.44 | Ton | 1343204.1 | 1344813.17 | 242066.37 | 1586879.54 | Partially Paid | Low
EXP-01174 | PRJ-002 | PRJ-002-ACT-09 | 2025-07-15 | Labour | LAB-003 | Carpenter | VEN-002 | 11 | Worker | 12657.96 | 12233.27 | 2201.99 | 14435.26 | Partially Paid | Low
EXP-01175 | PRJ-002 | PRJ-002-ACT-04 | 2025-07-15 | Contractor | CON-002 | Electrical Contract | VEN-003 | 1 | Contract | 144482.98 | 138396.66 | 24911.4 | 163308.06 | Paid | Low
EXP-01176 | PRJ-002 | PRJ-002-ACT-10 | 2025-07-15 | Labour | LAB-001 | Mason | VEN-007 | 22 | Worker | 21033.06 | 21799.95 | 3923.99 | 25723.94 | Paid | Low
EXP-01177 | PRJ-002 | PRJ-002-ACT-07 | 2025-07-15 | Material | MAT-007 | PVC Pipe | VEN-002 | 20.17 | Meter | 2217.95 | 2112.97 | 380.33 | 2493.3 | Pending | Medium
EXP-01178 | PRJ-002 | PRJ-002-ACT-06 | 2025-07-15 | Material | MAT-004 | Aggregate | VEN-011 | 9.64 | Ton | 13375.53 | 12673.29 | 2281.19 | 14954.48 | Paid | Medium
EXP-01179 | PRJ-002 | PRJ-002-ACT-04 | 2025-07-15 | Contractor | CON-002 | Electrical Contract | VEN-003 | 1 | Contract | 269095.36 | 267008.77 | 48061.58 | 315070.35 | Paid | Medium
EXP-01180 | PRJ-002 | PRJ-002-ACT-05 | 2025-07-15 | Contractor | CON-001 | Civil Structure Contract | VEN-002 | 1 | Contract | 82225.65 | 81687.67 | 14703.78 | 96391.45 | Paid | Low
EXP-01181 | PRJ-002 | PRJ-002-ACT-08 | 2025-07-20 | Labour | LAB-005 | Plumber | VEN-007 | 33 | Worker | 25664.91 | 26723.53 | 4810.24 | 31533.77 | Paid | Low
EXP-01182 | PRJ-002 | PRJ-002-ACT-05 | 2025-07-20 | Material | MAT-006 | Electrical Cable | VEN-011 | 10.29 | Meter | 938.67 | 930.48 | 167.49 | 1097.97 | Partially Paid | Medium
EXP-01183 | PRJ-002 | PRJ-002-ACT-01 | 2025-07-20 | Labour | LAB-003 | Carpenter | VEN-007 | 16 | Worker | 22644.01 | 23747.17 | 4274.49 | 28021.66 | Partially Paid | Medium
EXP-01184 | PRJ-002 | PRJ-002-ACT-06 | 2025-07-20 | Labour | LAB-001 | Mason | VEN-007 | 19 | Worker | 27500.56 | 28848.24 | 5192.68 | 34040.92 | Paid | Medium
EXP-01185 | PRJ-002 | PRJ-002-ACT-01 | 2025-07-20 | Equipment | EQ-003 | Concrete Mixer | VEN-011 | 3 | Day | 13828.7 | 14084.49 | 2535.21 | 16619.7 | Paid | Medium
EXP-01186 | PRJ-002 | PRJ-002-ACT-06 | 2025-07-20 | Other | OTH-001 | Safety | VEN-003 | 1 | Lot | 55919.01 | 55550.1 | 9999.02 | 65549.12 | Partially Paid | Medium
EXP-01187 | PRJ-002 | PRJ-002-ACT-04 | 2025-07-25 | Material | MAT-001 | Cement | VEN-007 | 4.38 | Bag | 2235.34 | 2213.8 | 398.48 | 2612.28 | Paid | Medium
EXP-01188 | PRJ-002 | PRJ-002-ACT-10 | 2025-07-25 | Material | MAT-009 | Paint | VEN-002 | 2.66 | Litre | 581.63 | 614.82 | 110.67 | 725.49 | Partially Paid | Medium
EXP-01189 | PRJ-002 | PRJ-002-ACT-09 | 2025-07-25 | Labour | LAB-006 | Painter | VEN-007 | 24 | Worker | 20232.91 | 20954.23 | 3771.76 | 24725.99 | Paid | Low
EXP-01190 | PRJ-002 | PRJ-002-ACT-10 | 2025-07-25 | Contractor | CON-004 | Finishing Contract | VEN-011 | 1 | Contract | 246313.38 | 241192.53 | 43414.66 | 284607.19 | Partially Paid | Low
EXP-01191 | PRJ-002 | PRJ-002-ACT-10 | 2025-07-25 | Contractor | CON-004 | Finishing Contract | VEN-007 | 1 | Contract | 330880.23 | 335744.61 | 60434.03 | 396178.64 | Partially Paid | Low
EXP-01192 | PRJ-002 | PRJ-002-ACT-09 | 2025-07-25 | Material | MAT-007 | PVC Pipe | VEN-007 | 16.41 | Meter | 1804.83 | 1701.61 | 306.29 | 2007.9 | Partially Paid | Medium
EXP-01193 | PRJ-002 | PRJ-002-ACT-05 | 2025-07-25 | Material | MAT-005 | Bricks | VEN-002 | 27.72 | Piece | 248.66 | 265.92 | 47.87 | 313.79 | Paid | Low
EXP-01194 | PRJ-002 | PRJ-002-ACT-08 | 2025-07-30 | Labour | LAB-003 | Carpenter | VEN-011 | 13 | Worker | 11755.38 | 11146.32 | 2006.34 | 13152.66 | Paid | Low
EXP-01195 | PRJ-002 | PRJ-002-ACT-01 | 2025-07-30 | Material | MAT-005 | Bricks | VEN-003 | 9.94 | Piece | 80.9 | 78.37 | 14.11 | 92.48 | Paid | Low
EXP-01196 | PRJ-002 | PRJ-002-ACT-03 | 2025-07-30 | Material | MAT-002 | Steel | VEN-011 | 5.79 | Ton | 335082.28 | 333607.76 | 60049.4 | 393657.16 | Paid | High
EXP-01197 | PRJ-002 | PRJ-002-ACT-01 | 2025-07-30 | Labour | LAB-005 | Plumber | VEN-007 | 33 | Worker | 24404.41 | 22601.37 | 4068.25 | 26669.62 | Paid | Medium
EXP-01198 | PRJ-002 | PRJ-002-ACT-02 | 2025-07-30 | Material | MAT-007 | PVC Pipe | VEN-002 | 24.93 | Meter | 3309.49 | 3439.89 | 619.18 | 4059.07 | Paid | Medium
EXP-01199 | PRJ-002 | PRJ-002-ACT-06 | 2025-07-30 | Material | MAT-002 | Steel | VEN-003 | 3.61 | Ton | 221796.57 | 238203.71 | 42876.67 | 281080.38 | Pending | Low
EXP-01200 | PRJ-002 | PRJ-002-ACT-10 | 2025-07-30 | Labour | LAB-002 | Helper | VEN-011 | 24 | Worker | 20690.86 | 19765.28 | 3557.75 | 23323.03 | Partially Paid | Low
EXP-01201 | PRJ-002 | PRJ-002-ACT-10 | 2025-07-30 | Labour | LAB-001 | Mason | VEN-011 | 34 | Worker | 57632.89 | 56166.73 | 10110.01 | 66276.74 | Paid | Medium
EXP-01202 | PRJ-002 | PRJ-002-ACT-04 | 2025-08-04 | Labour | LAB-002 | Helper | VEN-011 | 7 | Worker | 6861.14 | 6632.39 | 1193.83 | 7826.22 | Paid | Low
EXP-01203 | PRJ-002 | PRJ-002-ACT-06 | 2025-08-04 | Contractor | CON-001 | Civil Structure Contract | VEN-011 | 1 | Contract | 354214.09 | 333711 | 60067.98 | 393778.98 | Paid | High
EXP-01204 | PRJ-002 | PRJ-002-ACT-07 | 2025-08-04 | Contractor | CON-003 | Plumbing Contract | VEN-011 | 1 | Contract | 102083.13 | 104189.68 | 18754.14 | 122943.82 | Paid | Medium
EXP-01205 | PRJ-002 | PRJ-002-ACT-03 | 2025-08-04 | Material | MAT-006 | Electrical Cable | VEN-002 | 9.18 | Meter | 657.08 | 673.41 | 121.21 | 794.62 | Paid | Medium
EXP-01206 | PRJ-002 | PRJ-002-ACT-06 | 2025-08-04 | Labour | LAB-002 | Helper | VEN-007 | 14 | Worker | 23374.05 | 24491.92 | 4408.55 | 28900.47 | Paid | Medium
EXP-01207 | PRJ-002 | PRJ-002-ACT-01 | 2025-08-04 | Labour | LAB-005 | Plumber | VEN-011 | 17 | Worker | 18790.57 | 20114.86 | 3620.67 | 23735.53 | Paid | Low
EXP-01208 | PRJ-002 | PRJ-002-ACT-02 | 2025-08-04 | Material | MAT-001 | Cement | VEN-007 | 1.64 | Bag | 840.46 | 884.47 | 159.2 | 1043.67 | Paid | Medium
EXP-01209 | PRJ-002 | PRJ-002-ACT-04 | 2025-08-04 | Labour | LAB-002 | Helper | VEN-003 | 16 | Worker | 23151.01 | 21631.25 | 3893.62 | 25524.87 | Paid | Low
EXP-01210 | PRJ-002 | PRJ-002-ACT-02 | 2025-08-04 | Labour | LAB-005 | Plumber | VEN-011 | 28 | Worker | 45469.89 | 48760.03 | 8776.81 | 57536.84 | Pending | Low
EXP-01211 | PRJ-002 | PRJ-002-ACT-01 | 2025-08-04 | Contractor | CON-003 | Plumbing Contract | VEN-011 | 1 | Contract | 309779.26 | 301543.36 | 54277.8 | 355821.16 | Paid | Low
EXP-01212 | PRJ-002 | PRJ-002-ACT-07 | 2025-08-09 | Material | MAT-007 | PVC Pipe | VEN-011 | 6.1 | Meter | 621.16 | 631.88 | 113.74 | 745.62 | Paid | Low
EXP-01213 | PRJ-002 | PRJ-002-ACT-01 | 2025-08-09 | Contractor | CON-003 | Plumbing Contract | VEN-007 | 1 | Contract | 195596.37 | 201729.59 | 36311.33 | 238040.92 | Pending | Low
EXP-01214 | PRJ-002 | PRJ-002-ACT-10 | 2025-08-09 | Equipment | EQ-001 | Crane | VEN-011 | 2 | Day | 38575.2 | 36625.11 | 6592.52 | 43217.63 | Paid | Medium
EXP-01215 | PRJ-002 | PRJ-002-ACT-10 | 2025-08-09 | Labour | LAB-001 | Mason | VEN-003 | 29 | Worker | 48534.99 | 48564.7 | 8741.65 | 57306.35 | Partially Paid | Low
EXP-01216 | PRJ-002 | PRJ-002-ACT-01 | 2025-08-09 | Material | MAT-006 | Electrical Cable | VEN-003 | 12.54 | Meter | 1049.2 | 1013.85 | 182.49 | 1196.34 | Paid | Low
EXP-01217 | PRJ-002 | PRJ-002-ACT-06 | 2025-08-09 | Material | MAT-003 | Sand | VEN-002 | 6.9 | Ton | 12435.29 | 11882.05 | 2138.77 | 14020.82 | Paid | Low
EXP-01218 | PRJ-002 | PRJ-002-ACT-06 | 2025-08-09 | Equipment | EQ-001 | Crane | VEN-002 | 7 | Day | 122818.47 | 122862.57 | 22115.26 | 144977.83 | Paid | Low
EXP-01219 | PRJ-002 | PRJ-002-ACT-04 | 2025-08-09 | Material | MAT-007 | PVC Pipe | VEN-002 | 3.6 | Meter | 448.88 | 469.32 | 84.48 | 553.8 | Paid | Low
EXP-01220 | PRJ-002 | PRJ-002-ACT-03 | 2025-08-09 | Contractor | CON-004 | Finishing Contract | VEN-011 | 1 | Contract | 157782.94 | 152013.07 | 27362.35 | 179375.42 | Paid | Low
EXP-01221 | PRJ-002 | PRJ-002-ACT-01 | 2025-08-09 | Contractor | CON-002 | Electrical Contract | VEN-007 | 1 | Contract | 409546.08 | 397592.93 | 71566.73 | 469159.66 | Pending | Medium
EXP-01222 | PRJ-002 | PRJ-002-ACT-03 | 2025-08-14 | Labour | LAB-001 | Mason | VEN-007 | 16 | Worker | 17697.66 | 17522.04 | 3153.97 | 20676.01 | Paid | Low
EXP-01223 | PRJ-002 | PRJ-002-ACT-08 | 2025-08-14 | Material | MAT-003 | Sand | VEN-011 | 12.89 | Ton | 23214.41 | 21774.14 | 3919.35 | 25693.49 | Paid | Medium
EXP-01224 | PRJ-002 | PRJ-002-ACT-03 | 2025-08-14 | Contractor | CON-004 | Finishing Contract | VEN-003 | 1 | Contract | 82891.95 | 83110.12 | 14959.82 | 98069.94 | Paid | Low
EXP-01225 | PRJ-002 | PRJ-002-ACT-02 | 2025-08-14 | Material | MAT-005 | Bricks | VEN-003 | 17.28 | Piece | 159.7 | 151.62 | 27.29 | 178.91 | Pending | Low
EXP-01226 | PRJ-002 | PRJ-002-ACT-08 | 2025-08-14 | Labour | LAB-004 | Electrician | VEN-002 | 17 | Worker | 21056.39 | 20406.31 | 3673.14 | 24079.45 | Partially Paid | Low
EXP-01227 | PRJ-002 | PRJ-002-ACT-10 | 2025-08-14 | Contractor | CON-003 | Plumbing Contract | VEN-007 | 1 | Contract | 385149.1 | 381472.23 | 68665 | 450137.23 | Paid | Low
EXP-01228 | PRJ-002 | PRJ-002-ACT-01 | 2025-08-14 | Material | MAT-010 | Glass | VEN-003 | 18.62 | Sq Ft | 3032.42 | 2939.27 | 529.07 | 3468.34 | Paid | Low
EXP-01229 | PRJ-002 | PRJ-002-ACT-02 | 2025-08-14 | Material | MAT-007 | PVC Pipe | VEN-011 | 15.31 | Meter | 1773.37 | 1824.24 | 328.36 | 2152.6 | Paid | Low
EXP-01230 | PRJ-002 | PRJ-002-ACT-03 | 2025-08-14 | Contractor | CON-002 | Electrical Contract | VEN-011 | 1 | Contract | 244912.74 | 248383.35 | 44709 | 293092.35 | Paid | Low
EXP-01231 | PRJ-002 | PRJ-002-ACT-02 | 2025-08-19 | Material | MAT-005 | Bricks | VEN-007 | 10.05 | Piece | 85.45 | 91.07 | 16.39 | 107.46 | Paid | Low
EXP-01232 | PRJ-002 | PRJ-002-ACT-04 | 2025-08-19 | Material | MAT-008 | Tiles | VEN-011 | 8.34 | Sq Ft | 665.02 | 681.81 | 122.73 | 804.54 | Paid | Low
EXP-01233 | PRJ-002 | PRJ-002-ACT-08 | 2025-08-19 | Labour | LAB-005 | Plumber | VEN-003 | 17 | Worker | 15573.64 | 14726.2 | 2650.72 | 17376.92 | Paid | Low
EXP-01234 | PRJ-002 | PRJ-002-ACT-06 | 2025-08-19 | Labour | LAB-005 | Plumber | VEN-002 | 22 | Worker | 20058.88 | 21178.08 | 3812.05 | 24990.13 | Paid | Medium
EXP-01235 | PRJ-002 | PRJ-002-ACT-05 | 2025-08-19 | Labour | LAB-006 | Painter | VEN-003 | 8 | Worker | 14812.51 | 14088.84 | 2535.99 | 16624.83 | Paid | Low
EXP-01236 | PRJ-002 | PRJ-002-ACT-03 | 2025-08-19 | Material | MAT-005 | Bricks | VEN-011 | 14.35 | Piece | 125.86 | 136.37 | 24.55 | 160.92 | Paid | Medium
EXP-01237 | PRJ-002 | PRJ-002-ACT-09 | 2025-08-24 | Labour | LAB-005 | Plumber | VEN-007 | 19 | Worker | 26111.66 | 26757.43 | 4816.34 | 31573.77 | Paid | Medium
EXP-01238 | PRJ-002 | PRJ-002-ACT-05 | 2025-08-24 | Contractor | CON-002 | Electrical Contract | VEN-011 | 1 | Contract | 114780.92 | 114930.66 | 20687.52 | 135618.18 | Paid | Low
EXP-01239 | PRJ-002 | PRJ-002-ACT-01 | 2025-08-24 | Material | MAT-001 | Cement | VEN-003 | 26.89 | Bag | 12867.08 | 12713.46 | 2288.42 | 15001.88 | Partially Paid | Low
EXP-01240 | PRJ-002 | PRJ-002-ACT-02 | 2025-08-24 | Other | OTH-001 | Safety | VEN-002 | 1 | Lot | 21544.13 | 21091.74 | 3796.51 | 24888.25 | Paid | High
EXP-01241 | PRJ-002 | PRJ-002-ACT-01 | 2025-08-24 | Material | MAT-002 | Steel | VEN-003 | 7.21 | Ton | 483689.49 | 486425.16 | 87556.53 | 573981.69 | Paid | High
EXP-01242 | PRJ-002 | PRJ-002-ACT-04 | 2025-08-24 | Material | MAT-001 | Cement | VEN-007 | 3.57 | Bag | 1929.64 | 2082.5 | 374.85 | 2457.35 | Paid | Low
EXP-01243 | PRJ-002 | PRJ-002-ACT-04 | 2025-08-24 | Material | MAT-005 | Bricks | VEN-002 | 9.1 | Piece | 67.34 | 70.11 | 12.62 | 82.73 | Paid | Low
EXP-01244 | PRJ-002 | PRJ-002-ACT-04 | 2025-08-24 | Material | MAT-006 | Electrical Cable | VEN-003 | 2.97 | Meter | 299.86 | 280.39 | 50.47 | 330.86 | Paid | Low
EXP-01245 | PRJ-002 | PRJ-002-ACT-08 | 2025-08-24 | Material | MAT-004 | Aggregate | VEN-002 | 2.17 | Ton | 3086.36 | 3185.85 | 573.45 | 3759.3 | Paid | Medium
EXP-01246 | PRJ-002 | PRJ-002-ACT-08 | 2025-08-29 | Labour | LAB-006 | Painter | VEN-011 | 21 | Worker | 20607.75 | 19732.26 | 3551.81 | 23284.07 | Pending | Medium
EXP-01247 | PRJ-002 | PRJ-002-ACT-10 | 2025-08-29 | Labour | LAB-004 | Electrician | VEN-007 | 13 | Worker | 14026.95 | 13727.42 | 2470.94 | 16198.36 | Paid | Medium
EXP-01248 | PRJ-002 | PRJ-002-ACT-04 | 2025-08-29 | Material | MAT-003 | Sand | VEN-007 | 7.06 | Ton | 12689.29 | 12615.37 | 2270.77 | 14886.14 | Paid | Medium
EXP-01249 | PRJ-002 | PRJ-002-ACT-01 | 2025-08-29 | Material | MAT-005 | Bricks | VEN-007 | 16.7 | Piece | 173.76 | 164.32 | 29.58 | 193.9 | Pending | Low
EXP-01250 | PRJ-002 | PRJ-002-ACT-01 | 2025-08-29 | Equipment | EQ-001 | Crane | VEN-011 | 1 | Day | 16829.77 | 16505.02 | 2970.9 | 19475.92 | Paid | Low
EXP-01251 | PRJ-002 | PRJ-002-ACT-05 | 2025-08-29 | Contractor | CON-004 | Finishing Contract | VEN-003 | 1 | Contract | 307093.79 | 290235.57 | 52242.4 | 342477.97 | Paid | Low
EXP-01252 | PRJ-002 | PRJ-002-ACT-07 | 2025-08-29 | Labour | LAB-006 | Painter | VEN-002 | 8 | Worker | 13056.09 | 13011.12 | 2342 | 15353.12 | Pending | Medium
EXP-01253 | PRJ-002 | PRJ-002-ACT-08 | 2025-09-03 | Equipment | EQ-003 | Concrete Mixer | VEN-002 | 5 | Day | 22472.02 | 21546.56 | 3878.38 | 25424.94 | Paid | Medium
EXP-01254 | PRJ-002 | PRJ-002-ACT-02 | 2025-09-03 | Labour | LAB-004 | Electrician | VEN-003 | 16 | Worker | 19276.9 | 19531.99 | 3515.76 | 23047.75 | Paid | Medium
EXP-01255 | PRJ-002 | PRJ-002-ACT-02 | 2025-09-03 | Labour | LAB-006 | Painter | VEN-011 | 34 | Worker | 57101.68 | 59807.62 | 10765.37 | 70572.99 | Paid | Low
EXP-01256 | PRJ-002 | PRJ-002-ACT-07 | 2025-09-03 | Material | MAT-008 | Tiles | VEN-007 | 4.56 | Sq Ft | 387.1 | 374 | 67.32 | 441.32 | Paid | Low
EXP-01257 | PRJ-002 | PRJ-002-ACT-10 | 2025-09-03 | Equipment | EQ-004 | Scaffolding | VEN-002 | 1 | Day | 2097.53 | 2270.8 | 408.74 | 2679.54 | Paid | Low
EXP-01258 | PRJ-002 | PRJ-002-ACT-06 | 2025-09-03 | Labour | LAB-003 | Carpenter | VEN-002 | 29 | Worker | 50235.18 | 49207.56 | 8857.36 | 58064.92 | Paid | Low
EXP-01259 | PRJ-002 | PRJ-002-ACT-03 | 2025-09-08 | Material | MAT-009 | Paint | VEN-011 | 6.39 | Litre | 1489.83 | 1522.19 | 273.99 | 1796.18 | Partially Paid | Low
EXP-01260 | PRJ-002 | PRJ-002-ACT-08 | 2025-09-08 | Labour | LAB-001 | Mason | VEN-002 | 32 | Worker | 42358.8 | 44239.47 | 7963.1 | 52202.57 | Paid | Medium
EXP-01261 | PRJ-002 | PRJ-002-ACT-04 | 2025-09-08 | Equipment | EQ-004 | Scaffolding | VEN-011 | 1 | Day | 2201.15 | 2301.52 | 414.27 | 2715.79 | Paid | Low
EXP-01262 | PRJ-002 | PRJ-002-ACT-09 | 2025-09-08 | Material | MAT-007 | PVC Pipe | VEN-003 | 5.41 | Meter | 732.48 | 712.3 | 128.21 | 840.51 | Paid | Low
EXP-01263 | PRJ-002 | PRJ-002-ACT-08 | 2025-09-08 | Contractor | CON-004 | Finishing Contract | VEN-002 | 1 | Contract | 165461.31 | 170062.88 | 30611.32 | 200674.2 | Paid | Low
EXP-01264 | PRJ-002 | PRJ-002-ACT-10 | 2025-09-08 | Labour | LAB-003 | Carpenter | VEN-007 | 18 | Worker | 19923.61 | 19019.34 | 3423.48 | 22442.82 | Paid | Low
EXP-01265 | PRJ-002 | PRJ-002-ACT-09 | 2025-09-13 | Contractor | CON-004 | Finishing Contract | VEN-002 | 1 | Contract | 461883.93 | 441627.91 | 79493.02 | 521120.93 | Paid | Medium
EXP-01266 | PRJ-002 | PRJ-002-ACT-05 | 2025-09-13 | Material | MAT-002 | Steel | VEN-011 | 11.28 | Ton | 579769.84 | 622966 | 112133.88 | 735099.88 | Pending | High
EXP-01267 | PRJ-002 | PRJ-002-ACT-07 | 2025-09-13 | Material | MAT-004 | Aggregate | VEN-002 | 6.37 | Ton | 9302.28 | 9469.28 | 1704.47 | 11173.75 | Paid | Medium
EXP-01268 | PRJ-002 | PRJ-002-ACT-04 | 2025-09-13 | Material | MAT-007 | PVC Pipe | VEN-011 | 13.99 | Meter | 1882.73 | 1865.35 | 335.76 | 2201.11 | Paid | Low
EXP-01269 | PRJ-002 | PRJ-002-ACT-07 | 2025-09-13 | Material | MAT-009 | Paint | VEN-003 | 7.38 | Litre | 1702.43 | 1588.59 | 285.95 | 1874.54 | Paid | High
EXP-01270 | PRJ-002 | PRJ-002-ACT-08 | 2025-09-13 | Contractor | CON-001 | Civil Structure Contract | VEN-003 | 1 | Contract | 422962.39 | 430015.47 | 77402.78 | 507418.25 | Paid | Low
EXP-01271 | PRJ-002 | PRJ-002-ACT-03 | 2025-09-13 | Material | MAT-009 | Paint | VEN-002 | 7.95 | Litre | 1506.96 | 1446.11 | 260.3 | 1706.41 | Paid | Medium
EXP-01272 | PRJ-002 | PRJ-002-ACT-08 | 2025-09-18 | Material | MAT-006 | Electrical Cable | VEN-007 | 13.77 | Meter | 1178.11 | 1191.59 | 214.49 | 1406.08 | Pending | Medium
EXP-01273 | PRJ-002 | PRJ-002-ACT-08 | 2025-09-18 | Contractor | CON-004 | Finishing Contract | VEN-007 | 1 | Contract | 81033.14 | 78083.67 | 14055.06 | 92138.73 | Paid | High
EXP-01274 | PRJ-002 | PRJ-002-ACT-06 | 2025-09-18 | Contractor | CON-004 | Finishing Contract | VEN-007 | 1 | Contract | 82975.97 | 77002.18 | 13860.39 | 90862.57 | Partially Paid | Medium
EXP-01275 | PRJ-002 | PRJ-002-ACT-03 | 2025-09-18 | Equipment | EQ-003 | Concrete Mixer | VEN-011 | 5 | Day | 21778.18 | 21561.83 | 3881.13 | 25442.96 | Paid | High
EXP-01276 | PRJ-002 | PRJ-002-ACT-10 | 2025-09-18 | Material | MAT-008 | Tiles | VEN-007 | 4.2 | Sq Ft | 279.54 | 302.51 | 54.45 | 356.96 | Paid | Medium
EXP-01277 | PRJ-002 | PRJ-002-ACT-05 | 2025-09-18 | Contractor | CON-003 | Plumbing Contract | VEN-007 | 1 | Contract | 229605.24 | 228692.88 | 41164.72 | 269857.6 | Paid | Low
EXP-01278 | PRJ-002 | PRJ-002-ACT-03 | 2025-09-18 | Contractor | CON-001 | Civil Structure Contract | VEN-003 | 1 | Contract | 286416.9 | 276346.22 | 49742.32 | 326088.54 | Paid | Medium
EXP-01279 | PRJ-002 | PRJ-002-ACT-06 | 2025-09-18 | Equipment | EQ-004 | Scaffolding | VEN-002 | 5 | Day | 13945.84 | 13107.27 | 2359.31 | 15466.58 | Partially Paid | High
EXP-01280 | PRJ-002 | PRJ-002-ACT-04 | 2025-09-23 | Labour | LAB-006 | Painter | VEN-003 | 22 | Worker | 20225.37 | 21235.65 | 3822.42 | 25058.07 | Paid | Low
EXP-01281 | PRJ-002 | PRJ-002-ACT-09 | 2025-09-23 | Other | OTH-001 | Site Office | VEN-003 | 1 | Lot | 54158.92 | 54184.72 | 9753.25 | 63937.97 | Paid | Medium
EXP-01282 | PRJ-002 | PRJ-002-ACT-04 | 2025-09-23 | Equipment | EQ-003 | Concrete Mixer | VEN-003 | 6 | Day | 24387.47 | 25525.81 | 4594.65 | 30120.46 | Paid | Low
EXP-01283 | PRJ-002 | PRJ-002-ACT-04 | 2025-09-23 | Contractor | CON-001 | Civil Structure Contract | VEN-003 | 1 | Contract | 222427.05 | 231097.87 | 41597.62 | 272695.49 | Paid | Low
EXP-01284 | PRJ-002 | PRJ-002-ACT-02 | 2025-09-23 | Labour | LAB-005 | Plumber | VEN-007 | 26 | Worker | 27875.96 | 26998.9 | 4859.8 | 31858.7 | Paid | Low
EXP-01285 | PRJ-002 | PRJ-002-ACT-02 | 2025-09-23 | Labour | LAB-001 | Mason | VEN-007 | 17 | Worker | 14986.77 | 16189.32 | 2914.08 | 19103.4 | Paid | Low
EXP-01286 | PRJ-002 | PRJ-002-ACT-01 | 2025-09-23 | Material | MAT-002 | Steel | VEN-007 | 8.49 | Ton | 603011.66 | 565386.1 | 101769.5 | 667155.6 | Pending | Low
EXP-01287 | PRJ-002 | PRJ-002-ACT-06 | 2025-09-28 | Material | MAT-008 | Tiles | VEN-007 | 10.5 | Sq Ft | 688.77 | 673.05 | 121.15 | 794.2 | Paid | Low
EXP-01288 | PRJ-002 | PRJ-002-ACT-04 | 2025-09-28 | Material | MAT-009 | Paint | VEN-007 | 7.7 | Litre | 1285.33 | 1393.59 | 250.85 | 1644.44 | Paid | Medium
EXP-01289 | PRJ-002 | PRJ-002-ACT-07 | 2025-09-28 | Labour | LAB-002 | Helper | VEN-011 | 16 | Worker | 20328.42 | 19035.18 | 3426.33 | 22461.51 | Paid | Medium
EXP-01290 | PRJ-002 | PRJ-002-ACT-02 | 2025-09-28 | Contractor | CON-003 | Plumbing Contract | VEN-011 | 1 | Contract | 417368.21 | 395529.8 | 71195.36 | 466725.16 | Paid | Low
EXP-01291 | PRJ-002 | PRJ-002-ACT-04 | 2025-09-28 | Labour | LAB-004 | Electrician | VEN-011 | 24 | Worker | 22225.28 | 22711.33 | 4088.04 | 26799.37 | Paid | Low
EXP-01292 | PRJ-002 | PRJ-002-ACT-07 | 2025-09-28 | Labour | LAB-002 | Helper | VEN-002 | 15 | Worker | 16900.19 | 16849.48 | 3032.91 | 19882.39 | Paid | Medium
EXP-01293 | PRJ-002 | PRJ-002-ACT-08 | 2025-09-28 | Material | MAT-006 | Electrical Cable | VEN-003 | 6.69 | Meter | 520.12 | 522.16 | 93.99 | 616.15 | Paid | Medium
EXP-01294 | PRJ-002 | PRJ-002-ACT-08 | 2025-10-03 | Equipment | EQ-002 | Excavator | VEN-007 | 2 | Day | 28867.27 | 29004.17 | 5220.75 | 34224.92 | Paid | Low
EXP-01295 | PRJ-002 | PRJ-002-ACT-03 | 2025-10-03 | Equipment | EQ-003 | Concrete Mixer | VEN-011 | 7 | Day | 32075.82 | 33860.62 | 6094.91 | 39955.53 | Paid | Medium
EXP-01296 | PRJ-002 | PRJ-002-ACT-02 | 2025-10-03 | Material | MAT-008 | Tiles | VEN-011 | 8.81 | Sq Ft | 575.02 | 578.64 | 104.16 | 682.8 | Paid | High
EXP-01297 | PRJ-002 | PRJ-002-ACT-03 | 2025-10-03 | Equipment | EQ-002 | Excavator | VEN-007 | 3 | Day | 40847.97 | 42822.61 | 7708.07 | 50530.68 | Partially Paid | Low
EXP-01298 | PRJ-002 | PRJ-002-ACT-07 | 2025-10-03 | Other | OTH-001 | Miscellaneous | VEN-011 | 1 | Lot | 56177.15 | 52201.62 | 9396.29 | 61597.91 | Paid | Low
EXP-01299 | PRJ-002 | PRJ-002-ACT-07 | 2025-10-03 | Labour | LAB-005 | Plumber | VEN-002 | 9 | Worker | 10458.92 | 11048.82 | 1988.79 | 13037.61 | Paid | Low
EXP-01300 | PRJ-002 | PRJ-002-ACT-08 | 2025-10-03 | Material | MAT-008 | Tiles | VEN-002 | 9.26 | Sq Ft | 771.85 | 737.58 | 132.76 | 870.34 | Paid | Low
EXP-01301 | PRJ-002 | PRJ-002-ACT-03 | 2025-10-08 | Material | MAT-006 | Electrical Cable | VEN-011 | 6.88 | Meter | 622.62 | 667.03 | 120.07 | 787.1 | Paid | Low
EXP-01302 | PRJ-002 | PRJ-002-ACT-10 | 2025-10-08 | Material | MAT-004 | Aggregate | VEN-007 | 9.57 | Ton | 13271.12 | 12760.57 | 2296.9 | 15057.47 | Paid | Medium
EXP-01303 | PRJ-002 | PRJ-002-ACT-01 | 2025-10-08 | Contractor | CON-004 | Finishing Contract | VEN-002 | 1 | Contract | 88781.7 | 90182.93 | 16232.93 | 106415.86 | Pending | Low
EXP-01304 | PRJ-002 | PRJ-002-ACT-07 | 2025-10-08 | Labour | LAB-003 | Carpenter | VEN-003 | 20 | Worker | 29501.45 | 28675.1 | 5161.52 | 33836.62 | Paid | High
EXP-01305 | PRJ-002 | PRJ-002-ACT-05 | 2025-10-08 | Contractor | CON-001 | Civil Structure Contract | VEN-007 | 1 | Contract | 93121.03 | 95249.73 | 17144.95 | 112394.68 | Partially Paid | Medium
EXP-01306 | PRJ-002 | PRJ-002-ACT-05 | 2025-10-08 | Contractor | CON-001 | Civil Structure Contract | VEN-003 | 1 | Contract | 419505.84 | 420836.58 | 75750.58 | 496587.16 | Paid | Medium
EXP-01307 | PRJ-002 | PRJ-002-ACT-10 | 2025-10-08 | Material | MAT-010 | Glass | VEN-011 | 34.26 | Sq Ft | 5634.79 | 5275.6 | 949.61 | 6225.21 | Partially Paid | Low
EXP-01308 | PRJ-002 | PRJ-002-ACT-06 | 2025-10-08 | Material | MAT-007 | PVC Pipe | VEN-002 | 9.87 | Meter | 1053.73 | 1027.82 | 185.01 | 1212.83 | Partially Paid | Medium
EXP-01309 | PRJ-002 | PRJ-002-ACT-03 | 2025-10-08 | Material | MAT-007 | PVC Pipe | VEN-002 | 11.5 | Meter | 1500.27 | 1534.88 | 276.28 | 1811.16 | Paid | Medium
EXP-01310 | PRJ-002 | PRJ-002-ACT-06 | 2025-10-13 | Contractor | CON-002 | Electrical Contract | VEN-007 | 1 | Contract | 178138.09 | 171969.08 | 30954.43 | 202923.51 | Partially Paid | Low
EXP-01311 | PRJ-002 | PRJ-002-ACT-02 | 2025-10-13 | Contractor | CON-001 | Civil Structure Contract | VEN-003 | 1 | Contract | 396753.76 | 417262.88 | 75107.32 | 492370.2 | Paid | High
EXP-01312 | PRJ-002 | PRJ-002-ACT-05 | 2025-10-13 | Labour | LAB-001 | Mason | VEN-011 | 26 | Worker | 30960.87 | 29540.49 | 5317.29 | 34857.78 | Paid | Low
EXP-01313 | PRJ-002 | PRJ-002-ACT-07 | 2025-10-13 | Contractor | CON-002 | Electrical Contract | VEN-011 | 1 | Contract | 220428.12 | 230275.43 | 41449.58 | 271725.01 | Paid | Medium
EXP-01314 | PRJ-002 | PRJ-002-ACT-08 | 2025-10-13 | Equipment | EQ-002 | Excavator | VEN-003 | 2 | Day | 23976.99 | 25412.45 | 4574.24 | 29986.69 | Partially Paid | High
EXP-01315 | PRJ-002 | PRJ-002-ACT-06 | 2025-10-13 | Contractor | CON-002 | Electrical Contract | VEN-007 | 1 | Contract | 270673.61 | 287116.83 | 51681.03 | 338797.86 | Paid | High
EXP-01316 | PRJ-002 | PRJ-002-ACT-10 | 2025-10-13 | Labour | LAB-006 | Painter | VEN-011 | 34 | Worker | 41681.01 | 41165.1 | 7409.72 | 48574.82 | Paid | Low
EXP-01317 | PRJ-002 | PRJ-002-ACT-09 | 2025-10-13 | Contractor | CON-003 | Plumbing Contract | VEN-011 | 1 | Contract | 316024.61 | 308484.76 | 55527.26 | 364012.02 | Paid | Low
EXP-01318 | PRJ-002 | PRJ-002-ACT-01 | 2025-10-18 | Other | OTH-001 | Permit | VEN-011 | 1 | Lot | 29531.17 | 29778.57 | 5360.14 | 35138.71 | Paid | Low
EXP-01319 | PRJ-002 | PRJ-002-ACT-01 | 2025-10-18 | Contractor | CON-002 | Electrical Contract | VEN-002 | 1 | Contract | 262224.75 | 263710.63 | 47467.91 | 311178.54 | Pending | Low
EXP-01320 | PRJ-002 | PRJ-002-ACT-04 | 2025-10-18 | Material | MAT-010 | Glass | VEN-002 | 12.26 | Sq Ft | 1875.76 | 1923.01 | 346.14 | 2269.15 | Paid | Medium
EXP-01321 | PRJ-002 | PRJ-002-ACT-07 | 2025-10-18 | Material | MAT-005 | Bricks | VEN-002 | 17.95 | Piece | 169.4 | 161.41 | 29.05 | 190.46 | Paid | High
EXP-01322 | PRJ-002 | PRJ-002-ACT-09 | 2025-10-18 | Contractor | CON-001 | Civil Structure Contract | VEN-007 | 1 | Contract | 318025.17 | 317890.9 | 57220.36 | 375111.26 | Paid | Low
EXP-01323 | PRJ-002 | PRJ-002-ACT-03 | 2025-10-18 | Material | MAT-001 | Cement | VEN-011 | 14.28 | Bag | 7246.34 | 7671.04 | 1380.79 | 9051.83 | Paid | Medium
EXP-01324 | PRJ-002 | PRJ-002-ACT-04 | 2025-10-18 | Material | MAT-008 | Tiles | VEN-011 | 2.8 | Sq Ft | 192.33 | 190.69 | 34.32 | 225.01 | Paid | Low
EXP-01325 | PRJ-002 | PRJ-002-ACT-03 | 2025-10-18 | Equipment | EQ-003 | Concrete Mixer | VEN-003 | 6 | Day | 27948.06 | 26890.77 | 4840.34 | 31731.11 | Paid | Low
EXP-01326 | PRJ-002 | PRJ-002-ACT-07 | 2025-10-23 | Material | MAT-002 | Steel | VEN-007 | 2.99 | Ton | 223580.75 | 207038.69 | 37266.96 | 244305.65 | Paid | High
EXP-01327 | PRJ-002 | PRJ-002-ACT-08 | 2025-10-23 | Equipment | EQ-003 | Concrete Mixer | VEN-011 | 7 | Day | 29308.19 | 31077.7 | 5593.99 | 36671.69 | Partially Paid | High
EXP-01328 | PRJ-002 | PRJ-002-ACT-02 | 2025-10-23 | Labour | LAB-006 | Painter | VEN-003 | 30 | Worker | 28825.93 | 28311.66 | 5096.1 | 33407.76 | Pending | Low
EXP-01329 | PRJ-002 | PRJ-002-ACT-07 | 2025-10-23 | Material | MAT-003 | Sand | VEN-011 | 4.61 | Ton | 9720.55 | 9131.87 | 1643.74 | 10775.61 | Partially Paid | Low
EXP-01330 | PRJ-002 | PRJ-002-ACT-06 | 2025-10-23 | Material | MAT-009 | Paint | VEN-002 | 7.34 | Litre | 1406.48 | 1523.35 | 274.2 | 1797.55 | Paid | Low
EXP-01331 | PRJ-002 | PRJ-002-ACT-08 | 2025-10-23 | Equipment | EQ-001 | Crane | VEN-011 | 7 | Day | 113538.73 | 114712.62 | 20648.27 | 135360.89 | Paid | Medium
EXP-01332 | PRJ-002 | PRJ-002-ACT-03 | 2025-10-23 | Equipment | EQ-002 | Excavator | VEN-003 | 3 | Day | 44187.06 | 45446.91 | 8180.44 | 53627.35 | Paid | High
EXP-01333 | PRJ-002 | PRJ-002-ACT-03 | 2025-10-23 | Equipment | EQ-003 | Concrete Mixer | VEN-002 | 5 | Day | 20638.22 | 22116.14 | 3980.91 | 26097.05 | Paid | Low
EXP-01334 | PRJ-002 | PRJ-002-ACT-10 | 2025-10-23 | Contractor | CON-001 | Civil Structure Contract | VEN-011 | 1 | Contract | 187754.51 | 195692.49 | 35224.65 | 230917.14 | Paid | Low
EXP-01335 | PRJ-002 | PRJ-002-ACT-10 | 2025-10-23 | Material | MAT-002 | Steel | VEN-003 | 3.64 | Ton | 224291.62 | 231781.24 | 41720.62 | 273501.86 | Paid | Low
EXP-01336 | PRJ-002 | PRJ-002-ACT-07 | 2025-10-28 | Material | MAT-009 | Paint | VEN-002 | 2.89 | Litre | 630.02 | 609.25 | 109.66 | 718.91 | Paid | Low
EXP-01337 | PRJ-002 | PRJ-002-ACT-09 | 2025-10-28 | Labour | LAB-001 | Mason | VEN-007 | 4 | Worker | 4120.33 | 4082.57 | 734.86 | 4817.43 | Partially Paid | Low
EXP-01338 | PRJ-002 | PRJ-002-ACT-06 | 2025-10-28 | Contractor | CON-003 | Plumbing Contract | VEN-007 | 1 | Contract | 398222.2 | 402584.85 | 72465.27 | 475050.12 | Paid | Medium
EXP-01339 | PRJ-002 | PRJ-002-ACT-05 | 2025-10-28 | Labour | LAB-006 | Painter | VEN-011 | 24 | Worker | 16988.99 | 16790.33 | 3022.26 | 19812.59 | Partially Paid | Low
EXP-01340 | PRJ-002 | PRJ-002-ACT-05 | 2025-10-28 | Material | MAT-001 | Cement | VEN-003 | 1.72 | Bag | 817.05 | 761.09 | 137 | 898.09 | Paid | Medium
EXP-01341 | PRJ-002 | PRJ-002-ACT-04 | 2025-10-28 | Contractor | CON-001 | Civil Structure Contract | VEN-011 | 1 | Contract | 386255.88 | 362729.36 | 65291.28 | 428020.64 | Paid | High
EXP-01342 | PRJ-002 | PRJ-002-ACT-03 | 2025-10-28 | Contractor | CON-001 | Civil Structure Contract | VEN-003 | 1 | Contract | 219766.06 | 218243.8 | 39283.88 | 257527.68 | Paid | Low
EXP-01343 | PRJ-002 | PRJ-002-ACT-07 | 2025-10-28 | Equipment | EQ-003 | Concrete Mixer | VEN-011 | 6 | Day | 28054.06 | 28934.77 | 5208.26 | 34143.03 | Pending | Low
EXP-01344 | PRJ-002 | PRJ-002-ACT-06 | 2025-11-02 | Material | MAT-006 | Electrical Cable | VEN-007 | 9.42 | Meter | 875.52 | 884.85 | 159.27 | 1044.12 | Partially Paid | Medium
EXP-01345 | PRJ-002 | PRJ-002-ACT-06 | 2025-11-02 | Labour | LAB-002 | Helper | VEN-003 | 11 | Worker | 9629.34 | 9994.67 | 1799.04 | 11793.71 | Paid | Medium
EXP-01346 | PRJ-002 | PRJ-002-ACT-04 | 2025-11-02 | Contractor | CON-003 | Plumbing Contract | VEN-003 | 1 | Contract | 246648 | 228689.43 | 41164.1 | 269853.53 | Paid | Medium
EXP-01347 | PRJ-002 | PRJ-002-ACT-01 | 2025-11-02 | Labour | LAB-005 | Plumber | VEN-003 | 9 | Worker | 8672.63 | 8178.23 | 1472.08 | 9650.31 | Paid | Medium
EXP-01348 | PRJ-002 | PRJ-002-ACT-09 | 2025-11-02 | Labour | LAB-001 | Mason | VEN-003 | 9 | Worker | 5875.4 | 6034.99 | 1086.3 | 7121.29 | Paid | Medium
EXP-01349 | PRJ-002 | PRJ-002-ACT-10 | 2025-11-02 | Material | MAT-002 | Steel | VEN-011 | 8.22 | Ton | 563048.79 | 578264.94 | 104087.69 | 682352.63 | Paid | High
EXP-01350 | PRJ-002 | PRJ-002-ACT-06 | 2025-11-02 | Material | MAT-007 | PVC Pipe | VEN-007 | 30.56 | Meter | 3191.8 | 3271.21 | 588.82 | 3860.03 | Paid | Low
EXP-01351 | PRJ-002 | PRJ-002-ACT-04 | 2025-11-02 | Contractor | CON-004 | Finishing Contract | VEN-011 | 1 | Contract | 424761.09 | 424925.95 | 76486.67 | 501412.62 | Paid | Low
EXP-01352 | PRJ-002 | PRJ-002-ACT-01 | 2025-11-07 | Other | OTH-001 | Site Office | VEN-003 | 1 | Lot | 44742.51 | 44351.63 | 7983.29 | 52334.92 | Paid | Low
EXP-01353 | PRJ-002 | PRJ-002-ACT-04 | 2025-11-07 | Material | MAT-009 | Paint | VEN-011 | 10.77 | Litre | 2314.43 | 2223.67 | 400.26 | 2623.93 | Paid | Low
EXP-01354 | PRJ-002 | PRJ-002-ACT-01 | 2025-11-07 | Labour | LAB-001 | Mason | VEN-002 | 19 | Worker | 23098.64 | 23898.6 | 4301.75 | 28200.35 | Paid | Low
EXP-01355 | PRJ-002 | PRJ-002-ACT-05 | 2025-11-07 | Labour | LAB-003 | Carpenter | VEN-007 | 5 | Worker | 5178.41 | 5333.2 | 959.98 | 6293.18 | Partially Paid | Low
EXP-01356 | PRJ-002 | PRJ-002-ACT-04 | 2025-11-07 | Labour | LAB-002 | Helper | VEN-011 | 27 | Worker | 31727.52 | 31401.85 | 5652.33 | 37054.18 | Paid | Low
EXP-01357 | PRJ-002 | PRJ-002-ACT-09 | 2025-11-07 | Contractor | CON-003 | Plumbing Contract | VEN-003 | 1 | Contract | 73162.15 | 76270.44 | 13728.68 | 89999.12 | Paid | Low
EXP-01358 | PRJ-002 | PRJ-002-ACT-08 | 2025-11-07 | Contractor | CON-001 | Civil Structure Contract | VEN-007 | 1 | Contract | 98030.89 | 102581.43 | 18464.66 | 121046.09 | Paid | Low
EXP-01359 | PRJ-002 | PRJ-002-ACT-07 | 2025-11-07 | Equipment | EQ-004 | Scaffolding | VEN-011 | 7 | Day | 16457.35 | 17842.29 | 3211.61 | 21053.9 | Paid | Low
EXP-01360 | PRJ-002 | PRJ-002-ACT-06 | 2025-11-07 | Contractor | CON-002 | Electrical Contract | VEN-011 | 1 | Contract | 229093.34 | 245968.48 | 44274.33 | 290242.81 | Paid | Low
EXP-01361 | PRJ-002 | PRJ-002-ACT-07 | 2025-11-12 | Material | MAT-005 | Bricks | VEN-003 | 33.83 | Piece | 277.88 | 292.66 | 52.68 | 345.34 | Paid | Low
EXP-01362 | PRJ-002 | PRJ-002-ACT-05 | 2025-11-12 | Other | OTH-001 | Safety | VEN-011 | 1 | Lot | 52301.52 | 51984.79 | 9357.26 | 61342.05 | Paid | Low
EXP-01363 | PRJ-002 | PRJ-002-ACT-09 | 2025-11-12 | Labour | LAB-006 | Painter | VEN-007 | 21 | Worker | 34477.39 | 32054.03 | 5769.73 | 37823.76 | Paid | Low
EXP-01364 | PRJ-002 | PRJ-002-ACT-02 | 2025-11-12 | Material | MAT-010 | Glass | VEN-007 | 7.94 | Sq Ft | 1169.59 | 1167.91 | 210.22 | 1378.13 | Partially Paid | Medium
EXP-01365 | PRJ-002 | PRJ-002-ACT-08 | 2025-11-12 | Material | MAT-001 | Cement | VEN-011 | 12.73 | Bag | 6707.81 | 6349.82 | 1142.97 | 7492.79 | Paid | Medium
EXP-01366 | PRJ-002 | PRJ-002-ACT-08 | 2025-11-12 | Material | MAT-004 | Aggregate | VEN-007 | 3.94 | Ton | 5157.54 | 5421.98 | 975.96 | 6397.94 | Paid | Medium
EXP-01367 | PRJ-002 | PRJ-002-ACT-08 | 2025-11-12 | Material | MAT-008 | Tiles | VEN-011 | 19.08 | Sq Ft | 1576.43 | 1588.87 | 286 | 1874.87 | Paid | Low
EXP-01368 | PRJ-002 | PRJ-002-ACT-04 | 2025-11-12 | Labour | LAB-005 | Plumber | VEN-003 | 19 | Worker | 16085.03 | 15716.55 | 2828.98 | 18545.53 | Paid | Medium
EXP-01369 | PRJ-002 | PRJ-002-ACT-08 | 2025-11-12 | Material | MAT-005 | Bricks | VEN-002 | 10.57 | Piece | 95.53 | 92.5 | 16.65 | 109.15 | Paid | Medium
EXP-01370 | PRJ-002 | PRJ-002-ACT-06 | 2025-11-17 | Labour | LAB-002 | Helper | VEN-002 | 5 | Worker | 6655.31 | 6684.76 | 1203.26 | 7888.02 | Paid | Low
EXP-01371 | PRJ-002 | PRJ-002-ACT-06 | 2025-11-17 | Material | MAT-004 | Aggregate | VEN-003 | 5.75 | Ton | 9816.55 | 9812.78 | 1766.3 | 11579.08 | Partially Paid | Medium
EXP-01372 | PRJ-002 | PRJ-002-ACT-10 | 2025-11-17 | Equipment | EQ-002 | Excavator | VEN-003 | 1 | Day | 13061.25 | 12624.68 | 2272.44 | 14897.12 | Paid | Medium
EXP-01373 | PRJ-002 | PRJ-002-ACT-08 | 2025-11-17 | Material | MAT-001 | Cement | VEN-002 | 14.09 | Bag | 6440.6 | 6608.86 | 1189.59 | 7798.45 | Paid | Low
EXP-01374 | PRJ-002 | PRJ-002-ACT-06 | 2025-11-17 | Contractor | CON-002 | Electrical Contract | VEN-002 | 1 | Contract | 229994.83 | 229053.47 | 41229.62 | 270283.09 | Pending | Medium
EXP-01375 | PRJ-002 | PRJ-002-ACT-03 | 2025-11-17 | Equipment | EQ-004 | Scaffolding | VEN-007 | 6 | Day | 15787.19 | 15118.14 | 2721.27 | 17839.41 | Paid | Low
EXP-01376 | PRJ-002 | PRJ-002-ACT-07 | 2025-11-22 | Contractor | CON-003 | Plumbing Contract | VEN-003 | 1 | Contract | 296047.65 | 313296.44 | 56393.36 | 369689.8 | Paid | Medium
EXP-01377 | PRJ-002 | PRJ-002-ACT-02 | 2025-11-22 | Equipment | EQ-003 | Concrete Mixer | VEN-011 | 4 | Day | 17424.47 | 16584.32 | 2985.18 | 19569.5 | Paid | Low
EXP-01378 | PRJ-002 | PRJ-002-ACT-09 | 2025-11-22 | Material | MAT-006 | Electrical Cable | VEN-002 | 2.81 | Meter | 207.11 | 211.74 | 38.11 | 249.85 | Paid | Low
EXP-01379 | PRJ-002 | PRJ-002-ACT-07 | 2025-11-22 | Other | OTH-001 | Miscellaneous | VEN-007 | 1 | Lot | 58252.24 | 62897.33 | 11321.52 | 74218.85 | Paid | Medium
EXP-01380 | PRJ-002 | PRJ-002-ACT-06 | 2025-11-22 | Labour | LAB-004 | Electrician | VEN-002 | 19 | Worker | 26752.91 | 25185.02 | 4533.3 | 29718.32 | Pending | Low
EXP-01381 | PRJ-002 | PRJ-002-ACT-05 | 2025-11-22 | Labour | LAB-003 | Carpenter | VEN-002 | 11 | Worker | 12396.45 | 12833.59 | 2310.05 | 15143.64 | Paid | Medium
EXP-01382 | PRJ-002 | PRJ-002-ACT-06 | 2025-11-22 | Labour | LAB-002 | Helper | VEN-007 | 27 | Worker | 26331.07 | 28092.37 | 5056.63 | 33149 | Paid | Low
EXP-01383 | PRJ-002 | PRJ-002-ACT-02 | 2025-11-22 | Other | OTH-001 | Miscellaneous | VEN-007 | 1 | Lot | 56389.99 | 53431.97 | 9617.75 | 63049.72 | Paid | Medium
EXP-01384 | PRJ-002 | PRJ-002-ACT-10 | 2025-11-27 | Other | OTH-001 | Miscellaneous | VEN-003 | 1 | Lot | 27584.56 | 27808.25 | 5005.48 | 32813.73 | Paid | Low
EXP-01385 | PRJ-002 | PRJ-002-ACT-02 | 2025-11-27 | Contractor | CON-001 | Civil Structure Contract | VEN-007 | 1 | Contract | 279138.97 | 283440.18 | 51019.23 | 334459.41 | Paid | Medium
EXP-01386 | PRJ-002 | PRJ-002-ACT-04 | 2025-11-27 | Contractor | CON-001 | Civil Structure Contract | VEN-011 | 1 | Contract | 356520.36 | 382211.47 | 68798.06 | 451009.53 | Partially Paid | Low
EXP-01387 | PRJ-002 | PRJ-002-ACT-08 | 2025-11-27 | Contractor | CON-004 | Finishing Contract | VEN-003 | 1 | Contract | 265615.79 | 274271.92 | 49368.95 | 323640.87 | Paid | Low
EXP-01388 | PRJ-002 | PRJ-002-ACT-08 | 2025-11-27 | Other | OTH-001 | Permit | VEN-007 | 1 | Lot | 47485.24 | 45364.58 | 8165.62 | 53530.2 | Paid | Low
EXP-01389 | PRJ-002 | PRJ-002-ACT-08 | 2025-11-27 | Material | MAT-005 | Bricks | VEN-007 | 10.02 | Piece | 95.14 | 99.44 | 17.9 | 117.34 | Paid | Medium
EXP-01390 | PRJ-002 | PRJ-002-ACT-03 | 2025-12-02 | Contractor | CON-004 | Finishing Contract | VEN-003 | 1 | Contract | 256445.04 | 275855.54 | 49654 | 325509.54 | Paid | Medium
EXP-01391 | PRJ-002 | PRJ-002-ACT-02 | 2025-12-02 | Labour | LAB-004 | Electrician | VEN-003 | 19 | Worker | 27429.07 | 28740.78 | 5173.34 | 33914.12 | Partially Paid | Low
EXP-01392 | PRJ-002 | PRJ-002-ACT-04 | 2025-12-02 | Labour | LAB-005 | Plumber | VEN-007 | 23 | Worker | 23622.65 | 24776.69 | 4459.8 | 29236.49 | Paid | Low
EXP-01393 | PRJ-002 | PRJ-002-ACT-06 | 2025-12-02 | Material | MAT-010 | Glass | VEN-002 | 8.1 | Sq Ft | 1162.28 | 1196 | 215.28 | 1411.28 | Pending | High
EXP-01394 | PRJ-002 | PRJ-002-ACT-02 | 2025-12-02 | Contractor | CON-003 | Plumbing Contract | VEN-007 | 1 | Contract | 404620.27 | 423418.63 | 76215.35 | 499633.98 | Pending | Low
EXP-01395 | PRJ-002 | PRJ-002-ACT-04 | 2025-12-02 | Contractor | CON-004 | Finishing Contract | VEN-002 | 1 | Contract | 93456.75 | 87234.08 | 15702.13 | 102936.21 | Partially Paid | Low
EXP-01396 | PRJ-002 | PRJ-002-ACT-02 | 2025-12-07 | Labour | LAB-002 | Helper | VEN-011 | 16 | Worker | 19988.68 | 20035.57 | 3606.4 | 23641.97 | Paid | Medium
EXP-01397 | PRJ-002 | PRJ-002-ACT-02 | 2025-12-07 | Material | MAT-006 | Electrical Cable | VEN-003 | 8.99 | Meter | 761.15 | 800.25 | 144.04 | 944.29 | Paid | High
EXP-01398 | PRJ-002 | PRJ-002-ACT-04 | 2025-12-07 | Material | MAT-010 | Glass | VEN-011 | 15.33 | Sq Ft | 2609.26 | 2626.94 | 472.85 | 3099.79 | Paid | Medium
EXP-01399 | PRJ-002 | PRJ-002-ACT-10 | 2025-12-07 | Labour | LAB-006 | Painter | VEN-011 | 34 | Worker | 28208.36 | 30461.1 | 5483 | 35944.1 | Paid | Medium
EXP-01400 | PRJ-002 | PRJ-002-ACT-03 | 2025-12-07 | Equipment | EQ-003 | Concrete Mixer | VEN-002 | 1 | Day | 4272.34 | 4207.45 | 757.34 | 4964.79 | Partially Paid | Medium
EXP-01401 | PRJ-002 | PRJ-002-ACT-03 | 2025-12-07 | Contractor | CON-003 | Plumbing Contract | VEN-002 | 1 | Contract | 288046.14 | 286531.85 | 51575.73 | 338107.58 | Paid | Medium
EXP-01402 | PRJ-002 | PRJ-002-ACT-10 | 2025-12-07 | Material | MAT-007 | PVC Pipe | VEN-007 | 8.48 | Meter | 1164.58 | 1132.67 | 203.88 | 1336.55 | Paid | Low
EXP-01403 | PRJ-002 | PRJ-002-ACT-07 | 2025-12-12 | Contractor | CON-002 | Electrical Contract | VEN-002 | 1 | Contract | 399133.27 | 397744.46 | 71594 | 469338.46 | Paid | Medium
EXP-01404 | PRJ-002 | PRJ-002-ACT-02 | 2025-12-12 | Material | MAT-007 | PVC Pipe | VEN-007 | 1.01 | Meter | 116.69 | 123.62 | 22.25 | 145.87 | Paid | Medium
EXP-01405 | PRJ-002 | PRJ-002-ACT-01 | 2025-12-12 | Material | MAT-007 | PVC Pipe | VEN-007 | 3.83 | Meter | 387.67 | 392.82 | 70.71 | 463.53 | Paid | Low
EXP-01406 | PRJ-002 | PRJ-002-ACT-04 | 2025-12-12 | Material | MAT-006 | Electrical Cable | VEN-003 | 33.39 | Meter | 3308.16 | 3199.43 | 575.9 | 3775.33 | Paid | Medium
EXP-01407 | PRJ-002 | PRJ-002-ACT-06 | 2025-12-12 | Material | MAT-008 | Tiles | VEN-002 | 14.85 | Sq Ft | 1251.15 | 1203.13 | 216.56 | 1419.69 | Paid | Medium
EXP-01408 | PRJ-002 | PRJ-002-ACT-10 | 2025-12-12 | Material | MAT-004 | Aggregate | VEN-003 | 2.83 | Ton | 3826.4 | 4082.35 | 734.82 | 4817.17 | Paid | Low
EXP-01409 | PRJ-002 | PRJ-002-ACT-05 | 2025-12-12 | Equipment | EQ-003 | Concrete Mixer | VEN-007 | 2 | Day | 7929.97 | 8498.54 | 1529.74 | 10028.28 | Paid | Low
EXP-01410 | PRJ-002 | PRJ-002-ACT-04 | 2025-12-12 | Labour | LAB-004 | Electrician | VEN-002 | 22 | Worker | 38329.48 | 38677.8 | 6962 | 45639.8 | Paid | Low
EXP-01411 | PRJ-002 | PRJ-002-ACT-03 | 2025-12-12 | Labour | LAB-005 | Plumber | VEN-007 | 18 | Worker | 19969.72 | 19599.56 | 3527.92 | 23127.48 | Paid | Low
EXP-01412 | PRJ-002 | PRJ-002-ACT-03 | 2025-12-12 | Contractor | CON-004 | Finishing Contract | VEN-003 | 1 | Contract | 374322.66 | 363356.43 | 65404.16 | 428760.59 | Paid | Medium
EXP-01413 | PRJ-002 | PRJ-002-ACT-04 | 2025-12-17 | Labour | LAB-006 | Painter | VEN-011 | 11 | Worker | 6776.21 | 7289.75 | 1312.15 | 8601.9 | Pending | Low
EXP-01414 | PRJ-002 | PRJ-002-ACT-09 | 2025-12-17 | Material | MAT-006 | Electrical Cable | VEN-007 | 6.27 | Meter | 496.69 | 503.96 | 90.71 | 594.67 | Paid | Low
EXP-01415 | PRJ-002 | PRJ-002-ACT-10 | 2025-12-17 | Contractor | CON-001 | Civil Structure Contract | VEN-011 | 1 | Contract | 85481.44 | 86399.03 | 15551.83 | 101950.86 | Paid | Medium
EXP-01416 | PRJ-002 | PRJ-002-ACT-05 | 2025-12-17 | Contractor | CON-004 | Finishing Contract | VEN-011 | 1 | Contract | 338023.89 | 354780.81 | 63860.55 | 418641.36 | Paid | Medium
EXP-01417 | PRJ-002 | PRJ-002-ACT-05 | 2025-12-17 | Material | MAT-006 | Electrical Cable | VEN-003 | 15.82 | Meter | 1328.77 | 1348.07 | 242.65 | 1590.72 | Partially Paid | Medium
EXP-01418 | PRJ-002 | PRJ-002-ACT-06 | 2025-12-17 | Contractor | CON-003 | Plumbing Contract | VEN-003 | 1 | Contract | 131705.15 | 135836.09 | 24450.5 | 160286.59 | Partially Paid | Medium
EXP-01419 | PRJ-002 | PRJ-002-ACT-06 | 2025-12-17 | Other | OTH-001 | Site Office | VEN-003 | 1 | Lot | 22135.63 | 21214.14 | 3818.55 | 25032.69 | Paid | Medium
EXP-01420 | PRJ-002 | PRJ-002-ACT-03 | 2025-12-17 | Labour | LAB-006 | Painter | VEN-011 | 34 | Worker | 51259.77 | 55501.87 | 9990.34 | 65492.21 | Paid | Low
EXP-01421 | PRJ-002 | PRJ-002-ACT-05 | 2025-12-22 | Material | MAT-002 | Steel | VEN-011 | 11.03 | Ton | 736994.42 | 717243.81 | 129103.89 | 846347.7 | Paid | Low
EXP-01422 | PRJ-002 | PRJ-002-ACT-10 | 2025-12-22 | Contractor | CON-004 | Finishing Contract | VEN-011 | 1 | Contract | 208903.61 | 206252.61 | 37125.47 | 243378.08 | Paid | Low
EXP-01423 | PRJ-002 | PRJ-002-ACT-01 | 2025-12-22 | Labour | LAB-004 | Electrician | VEN-003 | 13 | Worker | 17098.13 | 16847.14 | 3032.49 | 19879.63 | Paid | Low
EXP-01424 | PRJ-002 | PRJ-002-ACT-03 | 2025-12-22 | Material | MAT-009 | Paint | VEN-002 | 19.18 | Litre | 3777.64 | 3885.93 | 699.47 | 4585.4 | Paid | Low
EXP-01425 | PRJ-002 | PRJ-002-ACT-09 | 2025-12-22 | Contractor | CON-002 | Electrical Contract | VEN-007 | 1 | Contract | 286066.25 | 302858.84 | 54514.59 | 357373.43 | Paid | Medium
EXP-01426 | PRJ-002 | PRJ-002-ACT-04 | 2025-12-22 | Material | MAT-005 | Bricks | VEN-003 | 38.87 | Piece | 331.05 | 331.68 | 59.7 | 391.38 | Pending | Low
EXP-01427 | PRJ-002 | PRJ-002-ACT-01 | 2025-12-22 | Material | MAT-006 | Electrical Cable | VEN-003 | 2.71 | Meter | 217.52 | 204.08 | 36.73 | 240.81 | Pending | Low
EXP-01428 | PRJ-002 | PRJ-002-ACT-07 | 2025-12-27 | Equipment | EQ-001 | Crane | VEN-002 | 3 | Day | 45690.72 | 49214.54 | 8858.62 | 58073.16 | Paid | High
EXP-01429 | PRJ-002 | PRJ-002-ACT-02 | 2025-12-27 | Material | MAT-010 | Glass | VEN-002 | 6.63 | Sq Ft | 1221.16 | 1145.09 | 206.12 | 1351.21 | Paid | Low
EXP-01430 | PRJ-002 | PRJ-002-ACT-06 | 2025-12-27 | Equipment | EQ-001 | Crane | VEN-007 | 7 | Day | 130387.02 | 124491.63 | 22408.49 | 146900.12 | Paid | Low
EXP-01431 | PRJ-002 | PRJ-002-ACT-03 | 2025-12-27 | Labour | LAB-005 | Plumber | VEN-007 | 34 | Worker | 40475.58 | 40193.91 | 7234.9 | 47428.81 | Paid | Low
EXP-01432 | PRJ-002 | PRJ-002-ACT-03 | 2025-12-27 | Labour | LAB-004 | Electrician | VEN-002 | 30 | Worker | 26572.3 | 27372.13 | 4926.98 | 32299.11 | Pending | Low
EXP-01433 | PRJ-002 | PRJ-002-ACT-01 | 2025-12-27 | Material | MAT-009 | Paint | VEN-003 | 11.64 | Litre | 2054.68 | 2095.98 | 377.28 | 2473.26 | Partially Paid | Low
EXP-01434 | PRJ-002 | PRJ-002-ACT-03 | 2025-12-27 | Material | MAT-007 | PVC Pipe | VEN-002 | 8.2 | Meter | 924.12 | 910.46 | 163.88 | 1074.34 | Paid | Low
EXP-01435 | PRJ-002 | PRJ-002-ACT-07 | 2026-01-01 | Contractor | CON-003 | Plumbing Contract | VEN-003 | 1 | Contract | 374803.09 | 359664.9 | 64739.68 | 424404.58 | Paid | Low
EXP-01436 | PRJ-002 | PRJ-002-ACT-07 | 2026-01-01 | Contractor | CON-003 | Plumbing Contract | VEN-002 | 1 | Contract | 316874.16 | 301589.82 | 54286.17 | 355875.99 | Paid | Low
EXP-01437 | PRJ-002 | PRJ-002-ACT-06 | 2026-01-01 | Material | MAT-008 | Tiles | VEN-011 | 6.17 | Sq Ft | 457.39 | 478.4 | 86.11 | 564.51 | Partially Paid | Low
EXP-01438 | PRJ-002 | PRJ-002-ACT-07 | 2026-01-01 | Material | MAT-009 | Paint | VEN-003 | 9.94 | Litre | 2226.47 | 2296.73 | 413.41 | 2710.14 | Paid | Low
EXP-01439 | PRJ-002 | PRJ-002-ACT-02 | 2026-01-01 | Material | MAT-008 | Tiles | VEN-011 | 12.53 | Sq Ft | 766.66 | 817.94 | 147.23 | 965.17 | Paid | Low
EXP-01440 | PRJ-002 | PRJ-002-ACT-09 | 2026-01-01 | Other | OTH-001 | Transport | VEN-011 | 1 | Lot | 61414.47 | 59841.04 | 10771.39 | 70612.43 | Paid | Medium
EXP-01441 | PRJ-002 | PRJ-002-ACT-02 | 2026-01-01 | Contractor | CON-003 | Plumbing Contract | VEN-002 | 1 | Contract | 150216.02 | 161962.92 | 29153.33 | 191116.25 | Pending | Low
EXP-01442 | PRJ-002 | PRJ-002-ACT-01 | 2026-01-01 | Labour | LAB-006 | Painter | VEN-007 | 17 | Worker | 12209.56 | 11590.2 | 2086.24 | 13676.44 | Paid | Medium
EXP-01443 | PRJ-002 | PRJ-002-ACT-02 | 2026-01-01 | Equipment | EQ-002 | Excavator | VEN-002 | 2 | Day | 27703.69 | 26198.11 | 4715.66 | 30913.77 | Paid | Low
EXP-01444 | PRJ-002 | PRJ-002-ACT-04 | 2026-01-01 | Material | MAT-003 | Sand | VEN-003 | 5.14 | Ton | 11255.66 | 10505.47 | 1890.98 | 12396.45 | Paid | Low
EXP-01445 | PRJ-002 | PRJ-002-ACT-04 | 2026-01-06 | Material | MAT-003 | Sand | VEN-002 | 11.42 | Ton | 22766.95 | 23441.87 | 4219.54 | 27661.41 | Paid | Low
EXP-01446 | PRJ-002 | PRJ-002-ACT-06 | 2026-01-06 | Material | MAT-003 | Sand | VEN-007 | 6.61 | Ton | 11387.07 | 10984.57 | 1977.22 | 12961.79 | Paid | High
EXP-01447 | PRJ-002 | PRJ-002-ACT-08 | 2026-01-06 | Material | MAT-002 | Steel | VEN-003 | 5.37 | Ton | 307321.53 | 326369.62 | 58746.53 | 385116.15 | Paid | Low
EXP-01448 | PRJ-002 | PRJ-002-ACT-04 | 2026-01-06 | Contractor | CON-002 | Electrical Contract | VEN-011 | 1 | Contract | 147969.56 | 149756.3 | 26956.13 | 176712.43 | Paid | Medium
EXP-01449 | PRJ-002 | PRJ-002-ACT-01 | 2026-01-06 | Equipment | EQ-004 | Scaffolding | VEN-002 | 5 | Day | 11938.19 | 11360.99 | 2044.98 | 13405.97 | Pending | Low
EXP-01450 | PRJ-002 | PRJ-002-ACT-10 | 2026-01-06 | Material | MAT-006 | Electrical Cable | VEN-011 | 9.9 | Meter | 823.08 | 875.36 | 157.56 | 1032.92 | Paid | Low
EXP-01451 | PRJ-002 | PRJ-002-ACT-09 | 2026-01-06 | Labour | LAB-002 | Helper | VEN-011 | 12 | Worker | 14352.01 | 13612.44 | 2450.24 | 16062.68 | Paid | Low
EXP-01452 | PRJ-002 | PRJ-002-ACT-09 | 2026-01-06 | Labour | LAB-004 | Electrician | VEN-007 | 13 | Worker | 10102.04 | 10238.48 | 1842.93 | 12081.41 | Paid | Low
EXP-01453 | PRJ-002 | PRJ-002-ACT-07 | 2026-01-06 | Material | MAT-009 | Paint | VEN-011 | 24.76 | Litre | 5418.11 | 5246.78 | 944.42 | 6191.2 | Paid | High
EXP-01454 | PRJ-002 | PRJ-002-ACT-07 | 2026-01-06 | Labour | LAB-001 | Mason | VEN-003 | 32 | Worker | 42001.79 | 45592.59 | 8206.67 | 53799.26 | Paid | Low
EXP-01455 | PRJ-002 | PRJ-002-ACT-02 | 2026-01-11 | Contractor | CON-001 | Civil Structure Contract | VEN-002 | 1 | Contract | 382037.07 | 381561.85 | 68681.13 | 450242.98 | Paid | High
EXP-01456 | PRJ-002 | PRJ-002-ACT-06 | 2026-01-11 | Contractor | CON-003 | Plumbing Contract | VEN-002 | 1 | Contract | 201030.27 | 187255.04 | 33705.91 | 220960.95 | Paid | Medium
EXP-01457 | PRJ-002 | PRJ-002-ACT-09 | 2026-01-11 | Equipment | EQ-004 | Scaffolding | VEN-007 | 3 | Day | 7723.12 | 7339.85 | 1321.17 | 8661.02 | Paid | Low
EXP-01458 | PRJ-002 | PRJ-002-ACT-08 | 2026-01-11 | Labour | LAB-006 | Painter | VEN-011 | 7 | Worker | 7159.95 | 7482.54 | 1346.86 | 8829.4 | Paid | Medium
EXP-01459 | PRJ-002 | PRJ-002-ACT-09 | 2026-01-11 | Material | MAT-009 | Paint | VEN-007 | 5.55 | Litre | 1163.46 | 1088.34 | 195.9 | 1284.24 | Paid | Low
EXP-01460 | PRJ-002 | PRJ-002-ACT-10 | 2026-01-11 | Equipment | EQ-004 | Scaffolding | VEN-003 | 3 | Day | 7342.19 | 6981.62 | 1256.69 | 8238.31 | Paid | Low
EXP-01461 | PRJ-002 | PRJ-002-ACT-07 | 2026-01-11 | Material | MAT-006 | Electrical Cable | VEN-002 | 4.37 | Meter | 348.55 | 362.29 | 65.21 | 427.5 | Paid | Low
EXP-01462 | PRJ-002 | PRJ-002-ACT-04 | 2026-01-11 | Contractor | CON-003 | Plumbing Contract | VEN-003 | 1 | Contract | 234752.64 | 225338.52 | 40560.93 | 265899.45 | Paid | High
EXP-01463 | PRJ-002 | PRJ-002-ACT-05 | 2026-01-11 | Material | MAT-010 | Glass | VEN-003 | 10.4 | Sq Ft | 1706.12 | 1587.94 | 285.83 | 1873.77 | Paid | Low
EXP-01464 | PRJ-002 | PRJ-002-ACT-04 | 2026-01-16 | Material | MAT-004 | Aggregate | VEN-007 | 7.08 | Ton | 10048.52 | 9375.11 | 1687.52 | 11062.63 | Paid | Low
EXP-01465 | PRJ-002 | PRJ-002-ACT-02 | 2026-01-16 | Labour | LAB-002 | Helper | VEN-007 | 9 | Worker | 9432.86 | 9591.02 | 1726.38 | 11317.4 | Paid | Low
EXP-01466 | PRJ-002 | PRJ-002-ACT-07 | 2026-01-16 | Contractor | CON-001 | Civil Structure Contract | VEN-002 | 1 | Contract | 407221.68 | 395461.94 | 71183.15 | 466645.09 | Paid | Low
EXP-01467 | PRJ-002 | PRJ-002-ACT-02 | 2026-01-16 | Material | MAT-010 | Glass | VEN-002 | 17.09 | Sq Ft | 2497.42 | 2600.42 | 468.08 | 3068.5 | Paid | High
EXP-01468 | PRJ-002 | PRJ-002-ACT-04 | 2026-01-16 | Material | MAT-006 | Electrical Cable | VEN-003 | 20.02 | Meter | 1911.05 | 1909.1 | 343.64 | 2252.74 | Paid | Medium
EXP-01469 | PRJ-002 | PRJ-002-ACT-07 | 2026-01-16 | Contractor | CON-002 | Electrical Contract | VEN-011 | 1 | Contract | 101778.6 | 102396.99 | 18431.46 | 120828.45 | Paid | Medium
EXP-01470 | PRJ-002 | PRJ-002-ACT-06 | 2026-01-16 | Material | MAT-010 | Glass | VEN-011 | 7.08 | Sq Ft | 1220.99 | 1286.81 | 231.63 | 1518.44 | Paid | Medium
EXP-01471 | PRJ-002 | PRJ-002-ACT-09 | 2026-01-16 | Equipment | EQ-003 | Concrete Mixer | VEN-007 | 5 | Day | 25365.7 | 24124.19 | 4342.35 | 28466.54 | Paid | Medium
EXP-01472 | PRJ-002 | PRJ-002-ACT-10 | 2026-01-16 | Material | MAT-006 | Electrical Cable | VEN-007 | 19.6 | Meter | 1603.89 | 1510.14 | 271.83 | 1781.97 | Paid | Low
EXP-01473 | PRJ-002 | PRJ-002-ACT-07 | 2026-01-16 | Equipment | EQ-004 | Scaffolding | VEN-007 | 3 | Day | 7623.73 | 8106.5 | 1459.17 | 9565.67 | Pending | Medium
EXP-01474 | PRJ-002 | PRJ-002-ACT-10 | 2026-01-21 | Material | MAT-007 | PVC Pipe | VEN-003 | 2.48 | Meter | 295.63 | 284.7 | 51.25 | 335.95 | Paid | Low
EXP-01475 | PRJ-002 | PRJ-002-ACT-04 | 2026-01-21 | Material | MAT-008 | Tiles | VEN-002 | 13.72 | Sq Ft | 970.52 | 973.71 | 175.27 | 1148.98 | Partially Paid | Medium
EXP-01476 | PRJ-002 | PRJ-002-ACT-01 | 2026-01-21 | Material | MAT-006 | Electrical Cable | VEN-003 | 9.26 | Meter | 808.83 | 823.99 | 148.32 | 972.31 | Partially Paid | High
EXP-01477 | PRJ-002 | PRJ-002-ACT-04 | 2026-01-21 | Contractor | CON-003 | Plumbing Contract | VEN-002 | 1 | Contract | 335407.35 | 313452.95 | 56421.53 | 369874.48 | Paid | Low
EXP-01478 | PRJ-002 | PRJ-002-ACT-10 | 2026-01-21 | Contractor | CON-001 | Civil Structure Contract | VEN-011 | 1 | Contract | 366354.1 | 374611.84 | 67430.13 | 442041.97 | Paid | High
EXP-01479 | PRJ-002 | PRJ-002-ACT-02 | 2026-01-21 | Material | MAT-007 | PVC Pipe | VEN-007 | 2.5 | Meter | 242.08 | 260.87 | 46.96 | 307.83 | Paid | Low
EXP-01480 | PRJ-002 | PRJ-002-ACT-01 | 2026-01-21 | Contractor | CON-004 | Finishing Contract | VEN-011 | 1 | Contract | 247027.25 | 243760.69 | 43876.92 | 287637.61 | Paid | Low
EXP-01481 | PRJ-002 | PRJ-002-ACT-01 | 2026-01-21 | Material | MAT-009 | Paint | VEN-003 | 12.11 | Litre | 2629.7 | 2637.42 | 474.74 | 3112.16 | Paid | High
EXP-01482 | PRJ-002 | PRJ-002-ACT-07 | 2026-01-26 | Contractor | CON-003 | Plumbing Contract | VEN-003 | 1 | Contract | 280173.18 | 272399.55 | 49031.92 | 321431.47 | Paid | Low
EXP-01483 | PRJ-002 | PRJ-002-ACT-02 | 2026-01-26 | Material | MAT-004 | Aggregate | VEN-002 | 5.61 | Ton | 7524.74 | 7578.18 | 1364.07 | 8942.25 | Partially Paid | Low
EXP-01484 | PRJ-002 | PRJ-002-ACT-10 | 2026-01-26 | Labour | LAB-001 | Mason | VEN-011 | 17 | Worker | 25723.63 | 26333.13 | 4739.96 | 31073.09 | Paid | Medium
EXP-01485 | PRJ-002 | PRJ-002-ACT-01 | 2026-01-26 | Equipment | EQ-001 | Crane | VEN-002 | 1 | Day | 20381.35 | 18893.32 | 3400.8 | 22294.12 | Paid | Low
EXP-01486 | PRJ-002 | PRJ-002-ACT-01 | 2026-01-26 | Material | MAT-003 | Sand | VEN-007 | 8.37 | Ton | 14534.05 | 15220.13 | 2739.62 | 17959.75 | Paid | Low
EXP-01487 | PRJ-002 | PRJ-002-ACT-05 | 2026-01-26 | Labour | LAB-005 | Plumber | VEN-011 | 30 | Worker | 32997.07 | 35503.35 | 6390.6 | 41893.95 | Paid | Low
EXP-01488 | PRJ-002 | PRJ-002-ACT-05 | 2026-01-26 | Equipment | EQ-004 | Scaffolding | VEN-002 | 5 | Day | 14082.99 | 13180.38 | 2372.47 | 15552.85 | Paid | Low
EXP-01489 | PRJ-002 | PRJ-002-ACT-07 | 2026-01-26 | Labour | LAB-003 | Carpenter | VEN-011 | 30 | Worker | 21269.81 | 22600.8 | 4068.14 | 26668.94 | Paid | Low
EXP-01490 | PRJ-002 | PRJ-002-ACT-02 | 2026-01-31 | Material | MAT-008 | Tiles | VEN-011 | 24.47 | Sq Ft | 1907.07 | 2031.4 | 365.65 | 2397.05 | Paid | Low
EXP-01491 | PRJ-002 | PRJ-002-ACT-09 | 2026-01-31 | Material | MAT-007 | PVC Pipe | VEN-002 | 2.57 | Meter | 275.42 | 274.6 | 49.43 | 324.03 | Paid | Low
EXP-01492 | PRJ-002 | PRJ-002-ACT-03 | 2026-01-31 | Contractor | CON-004 | Finishing Contract | VEN-011 | 1 | Contract | 292771.81 | 289555.08 | 52119.91 | 341674.99 | Paid | Low
EXP-01493 | PRJ-002 | PRJ-002-ACT-01 | 2026-01-31 | Contractor | CON-002 | Electrical Contract | VEN-003 | 1 | Contract | 123673.13 | 123738.91 | 22273 | 146011.91 | Paid | Medium
EXP-01494 | PRJ-002 | PRJ-002-ACT-04 | 2026-01-31 | Contractor | CON-001 | Civil Structure Contract | VEN-007 | 1 | Contract | 315920.94 | 308786.92 | 55581.65 | 364368.57 | Paid | Low
EXP-01495 | PRJ-002 | PRJ-002-ACT-01 | 2026-01-31 | Material | MAT-001 | Cement | VEN-007 | 11.64 | Bag | 5152.55 | 5211.49 | 938.07 | 6149.56 | Paid | Medium
EXP-01496 | PRJ-002 | PRJ-002-ACT-02 | 2026-01-31 | Contractor | CON-002 | Electrical Contract | VEN-011 | 1 | Contract | 415215.43 | 389670.6 | 70140.71 | 459811.31 | Paid | Medium
EXP-01497 | PRJ-002 | PRJ-002-ACT-08 | 2026-02-05 | Labour | LAB-001 | Mason | VEN-007 | 19 | Worker | 27705.35 | 26818.48 | 4827.33 | 31645.81 | Partially Paid | High
EXP-01498 | PRJ-002 | PRJ-002-ACT-10 | 2026-02-05 | Labour | LAB-006 | Painter | VEN-011 | 5 | Worker | 4874.23 | 4522.02 | 813.96 | 5335.98 | Paid | Low
EXP-01499 | PRJ-002 | PRJ-002-ACT-06 | 2026-02-05 | Labour | LAB-004 | Electrician | VEN-003 | 26 | Worker | 26006.74 | 25752.85 | 4635.51 | 30388.36 | Paid | Medium
EXP-01500 | PRJ-002 | PRJ-002-ACT-01 | 2026-02-05 | Equipment | EQ-004 | Scaffolding | VEN-011 | 4 | Day | 9871.11 | 10319.49 | 1857.51 | 12177 | Paid | Medium
EXP-01501 | PRJ-002 | PRJ-002-ACT-07 | 2026-02-05 | Equipment | EQ-003 | Concrete Mixer | VEN-007 | 3 | Day | 13917.79 | 13363.88 | 2405.5 | 15769.38 | Paid | Medium
EXP-01502 | PRJ-002 | PRJ-002-ACT-01 | 2026-02-05 | Other | OTH-001 | Site Office | VEN-002 | 1 | Lot | 31618.71 | 32272.08 | 5808.97 | 38081.05 | Pending | High
EXP-01503 | PRJ-002 | PRJ-002-ACT-08 | 2026-02-05 | Material | MAT-004 | Aggregate | VEN-007 | 14.26 | Ton | 24383.23 | 22688.15 | 4083.87 | 26772.02 | Paid | Medium
EXP-01504 | PRJ-002 | PRJ-002-ACT-08 | 2026-02-05 | Labour | LAB-002 | Helper | VEN-011 | 16 | Worker | 19952.35 | 20882.57 | 3758.86 | 24641.43 | Paid | Low
EXP-01505 | PRJ-002 | PRJ-002-ACT-07 | 2026-02-10 | Equipment | EQ-003 | Concrete Mixer | VEN-011 | 5 | Day | 22465.67 | 23876.79 | 4297.82 | 28174.61 | Paid | Low
EXP-01506 | PRJ-002 | PRJ-002-ACT-10 | 2026-02-10 | Contractor | CON-002 | Electrical Contract | VEN-007 | 1 | Contract | 391773.52 | 375453.71 | 67581.67 | 443035.38 | Partially Paid | Low
EXP-01507 | PRJ-002 | PRJ-002-ACT-05 | 2026-02-10 | Material | MAT-001 | Cement | VEN-007 | 6.29 | Bag | 2929.4 | 2876.05 | 517.69 | 3393.74 | Paid | Low
EXP-01508 | PRJ-002 | PRJ-002-ACT-08 | 2026-02-10 | Labour | LAB-003 | Carpenter | VEN-007 | 23 | Worker | 16943.3 | 15758.53 | 2836.54 | 18595.07 | Partially Paid | High
EXP-01509 | PRJ-002 | PRJ-002-ACT-10 | 2026-02-10 | Material | MAT-004 | Aggregate | VEN-007 | 15.17 | Ton | 21778.44 | 23188.28 | 4173.89 | 27362.17 | Paid | Low
EXP-01510 | PRJ-002 | PRJ-002-ACT-09 | 2026-02-10 | Contractor | CON-001 | Civil Structure Contract | VEN-011 | 1 | Contract | 398270.36 | 385475.37 | 69385.57 | 454860.94 | Paid | Medium
EXP-01511 | PRJ-002 | PRJ-002-ACT-04 | 2026-02-10 | Other | OTH-001 | Miscellaneous | VEN-007 | 1 | Lot | 53238 | 52155.89 | 9388.06 | 61543.95 | Pending | Low
EXP-01512 | PRJ-002 | PRJ-002-ACT-09 | 2026-02-10 | Material | MAT-007 | PVC Pipe | VEN-011 | 37.79 | Meter | 5011.98 | 5019.52 | 903.51 | 5923.03 | Paid | Low
EXP-01513 | PRJ-002 | PRJ-002-ACT-09 | 2026-02-10 | Material | MAT-007 | PVC Pipe | VEN-007 | 4.14 | Meter | 606.61 | 565.13 | 101.72 | 666.85 | Paid | Medium
EXP-01514 | PRJ-002 | PRJ-002-ACT-03 | 2026-02-15 | Equipment | EQ-004 | Scaffolding | VEN-007 | 1 | Day | 2434.41 | 2499.61 | 449.93 | 2949.54 | Paid | Low
EXP-01515 | PRJ-002 | PRJ-002-ACT-07 | 2026-02-15 | Contractor | CON-002 | Electrical Contract | VEN-011 | 1 | Contract | 343181.36 | 334455.39 | 60201.97 | 394657.36 | Paid | Low
EXP-01516 | PRJ-002 | PRJ-002-ACT-03 | 2026-02-15 | Material | MAT-003 | Sand | VEN-007 | 8.25 | Ton | 13400.27 | 14537.63 | 2616.77 | 17154.4 | Partially Paid | Medium
EXP-01517 | PRJ-002 | PRJ-002-ACT-10 | 2026-02-15 | Material | MAT-002 | Steel | VEN-011 | 28.1 | Ton | 2117448.04 | 1997877 | 359617.86 | 2357494.86 | Pending | Low
EXP-01518 | PRJ-002 | PRJ-002-ACT-06 | 2026-02-15 | Contractor | CON-003 | Plumbing Contract | VEN-002 | 1 | Contract | 184244.38 | 194291.53 | 34972.48 | 229264.01 | Paid | Medium
EXP-01519 | PRJ-002 | PRJ-002-ACT-08 | 2026-02-15 | Labour | LAB-002 | Helper | VEN-003 | 6 | Worker | 9485.24 | 9029.32 | 1625.28 | 10654.6 | Paid | Low
EXP-01520 | PRJ-002 | PRJ-002-ACT-04 | 2026-02-15 | Material | MAT-010 | Glass | VEN-002 | 4.79 | Sq Ft | 712.86 | 762.8 | 137.3 | 900.1 | Paid | Low
EXP-01521 | PRJ-002 | PRJ-002-ACT-04 | 2026-02-15 | Contractor | CON-003 | Plumbing Contract | VEN-011 | 1 | Contract | 131023.47 | 140020.98 | 25203.78 | 165224.76 | Paid | Low
EXP-01522 | PRJ-002 | PRJ-002-ACT-03 | 2026-02-20 | Equipment | EQ-001 | Crane | VEN-007 | 2 | Day | 37431.97 | 38483.38 | 6927.01 | 45410.39 | Paid | Medium
EXP-01523 | PRJ-002 | PRJ-002-ACT-05 | 2026-02-20 | Material | MAT-005 | Bricks | VEN-011 | 7.92 | Piece | 64.43 | 63.52 | 11.43 | 74.95 | Partially Paid | Medium
EXP-01524 | PRJ-002 | PRJ-002-ACT-08 | 2026-02-20 | Labour | LAB-001 | Mason | VEN-011 | 24 | Worker | 33994.12 | 36349.65 | 6542.94 | 42892.59 | Paid | Low
EXP-01525 | PRJ-002 | PRJ-002-ACT-01 | 2026-02-20 | Labour | LAB-004 | Electrician | VEN-007 | 5 | Worker | 6211.93 | 5823.37 | 1048.21 | 6871.58 | Paid | Low
EXP-01526 | PRJ-002 | PRJ-002-ACT-04 | 2026-02-20 | Material | MAT-008 | Tiles | VEN-011 | 3.18 | Sq Ft | 281.71 | 271.97 | 48.95 | 320.92 | Paid | Low
EXP-01527 | PRJ-002 | PRJ-002-ACT-02 | 2026-02-20 | Material | MAT-006 | Electrical Cable | VEN-007 | 2.12 | Meter | 189.69 | 206.02 | 37.08 | 243.1 | Partially Paid | Low
EXP-01528 | PRJ-002 | PRJ-002-ACT-06 | 2026-02-20 | Contractor | CON-004 | Finishing Contract | VEN-002 | 1 | Contract | 100682.85 | 105012.21 | 18902.2 | 123914.41 | Paid | Low
EXP-01529 | PRJ-002 | PRJ-002-ACT-02 | 2026-02-25 | Material | MAT-004 | Aggregate | VEN-003 | 12.01 | Ton | 19939.73 | 20500.17 | 3690.03 | 24190.2 | Partially Paid | Medium
EXP-01530 | PRJ-002 | PRJ-002-ACT-09 | 2026-02-25 | Material | MAT-007 | PVC Pipe | VEN-007 | 8.75 | Meter | 1095.86 | 1156.06 | 208.09 | 1364.15 | Paid | Low
EXP-01531 | PRJ-002 | PRJ-002-ACT-05 | 2026-02-25 | Labour | LAB-005 | Plumber | VEN-007 | 15 | Worker | 16112.37 | 17331.25 | 3119.62 | 20450.87 | Paid | Medium
EXP-01532 | PRJ-002 | PRJ-002-ACT-02 | 2026-02-25 | Labour | LAB-001 | Mason | VEN-007 | 33 | Worker | 24250.67 | 22594.62 | 4067.03 | 26661.65 | Paid | Low
EXP-01533 | PRJ-002 | PRJ-002-ACT-03 | 2026-02-25 | Material | MAT-007 | PVC Pipe | VEN-011 | 13.35 | Meter | 1618.13 | 1533.62 | 276.05 | 1809.67 | Paid | Medium
EXP-01534 | PRJ-002 | PRJ-002-ACT-01 | 2026-02-25 | Material | MAT-003 | Sand | VEN-011 | 3.56 | Ton | 6620.06 | 7000.98 | 1260.18 | 8261.16 | Paid | Low
EXP-01535 | PRJ-002 | PRJ-002-ACT-07 | 2026-03-02 | Equipment | EQ-002 | Excavator | VEN-003 | 3 | Day | 39392.69 | 41196.75 | 7415.41 | 48612.16 | Paid | Medium
EXP-01536 | PRJ-002 | PRJ-002-ACT-02 | 2026-03-02 | Material | MAT-003 | Sand | VEN-007 | 13.96 | Ton | 23924.52 | 24587.82 | 4425.81 | 29013.63 | Pending | Medium
EXP-01537 | PRJ-002 | PRJ-002-ACT-06 | 2026-03-02 | Material | MAT-003 | Sand | VEN-003 | 10.47 | Ton | 17344.49 | 17409.36 | 3133.68 | 20543.04 | Partially Paid | Medium
EXP-01538 | PRJ-002 | PRJ-002-ACT-09 | 2026-03-02 | Equipment | EQ-001 | Crane | VEN-011 | 6 | Day | 111953.05 | 109747.74 | 19754.59 | 129502.33 | Paid | Low
EXP-01539 | PRJ-002 | PRJ-002-ACT-03 | 2026-03-02 | Material | MAT-001 | Cement | VEN-002 | 40.38 | Bag | 20534.05 | 21307.85 | 3835.41 | 25143.26 | Paid | Low
EXP-01540 | PRJ-002 | PRJ-002-ACT-05 | 2026-03-02 | Contractor | CON-003 | Plumbing Contract | VEN-003 | 1 | Contract | 199239.9 | 204477.94 | 36806.03 | 241283.97 | Partially Paid | Low
EXP-01541 | PRJ-002 | PRJ-002-ACT-02 | 2026-03-02 | Material | MAT-001 | Cement | VEN-003 | 21.85 | Bag | 9931.96 | 10042.43 | 1807.64 | 11850.07 | Paid | Low
EXP-01542 | PRJ-002 | PRJ-002-ACT-01 | 2026-03-07 | Labour | LAB-004 | Electrician | VEN-003 | 25 | Worker | 35651.99 | 37029.41 | 6665.29 | 43694.7 | Partially Paid | High
EXP-01543 | PRJ-002 | PRJ-002-ACT-08 | 2026-03-07 | Material | MAT-010 | Glass | VEN-011 | 14.93 | Sq Ft | 2263.74 | 2280.58 | 410.5 | 2691.08 | Paid | High
EXP-01544 | PRJ-002 | PRJ-002-ACT-04 | 2026-03-07 | Material | MAT-005 | Bricks | VEN-007 | 15.79 | Piece | 138.65 | 145.47 | 26.18 | 171.65 | Paid | Medium
EXP-01545 | PRJ-002 | PRJ-002-ACT-08 | 2026-03-07 | Material | MAT-001 | Cement | VEN-003 | 7.11 | Bag | 4057.66 | 3988.75 | 717.98 | 4706.73 | Paid | Medium
EXP-01546 | PRJ-002 | PRJ-002-ACT-02 | 2026-03-07 | Labour | LAB-002 | Helper | VEN-003 | 24 | Worker | 21210.57 | 21370.74 | 3846.73 | 25217.47 | Paid | High
EXP-01547 | PRJ-002 | PRJ-002-ACT-06 | 2026-03-07 | Contractor | CON-001 | Civil Structure Contract | VEN-002 | 1 | Contract | 249582.01 | 233751.17 | 42075.21 | 275826.38 | Paid | Medium
EXP-01548 | PRJ-002 | PRJ-002-ACT-07 | 2026-03-12 | Material | MAT-002 | Steel | VEN-003 | 4.94 | Ton | 341905.95 | 337385.94 | 60729.47 | 398115.41 | Paid | High
EXP-01549 | PRJ-002 | PRJ-002-ACT-04 | 2026-03-12 | Material | MAT-006 | Electrical Cable | VEN-003 | 11.6 | Meter | 924.86 | 945.27 | 170.15 | 1115.42 | Partially Paid | Low
EXP-01550 | PRJ-002 | PRJ-002-ACT-03 | 2026-03-12 | Other | OTH-001 | Transport | VEN-003 | 1 | Lot | 50291.91 | 50414.7 | 9074.65 | 59489.35 | Paid | Low
EXP-01551 | PRJ-002 | PRJ-002-ACT-05 | 2026-03-12 | Contractor | CON-002 | Electrical Contract | VEN-007 | 1 | Contract | 251374.86 | 239018.72 | 43023.37 | 282042.09 | Partially Paid | Medium
EXP-01552 | PRJ-002 | PRJ-002-ACT-07 | 2026-03-12 | Contractor | CON-001 | Civil Structure Contract | VEN-002 | 1 | Contract | 284787.28 | 297476.66 | 53545.8 | 351022.46 | Pending | Medium
EXP-01553 | PRJ-002 | PRJ-002-ACT-08 | 2026-03-12 | Material | MAT-005 | Bricks | VEN-003 | 29.7 | Piece | 232.2 | 240.16 | 43.23 | 283.39 | Paid | Low
EXP-01554 | PRJ-002 | PRJ-002-ACT-05 | 2026-03-17 | Material | MAT-008 | Tiles | VEN-002 | 15.65 | Sq Ft | 1112.1 | 1090.92 | 196.37 | 1287.29 | Paid | Medium
EXP-01555 | PRJ-002 | PRJ-002-ACT-02 | 2026-03-17 | Labour | LAB-002 | Helper | VEN-003 | 18 | Worker | 25937.45 | 25731.97 | 4631.75 | 30363.72 | Paid | Low
EXP-01556 | PRJ-002 | PRJ-002-ACT-08 | 2026-03-17 | Labour | LAB-003 | Carpenter | VEN-002 | 20 | Worker | 23530.26 | 24166.41 | 4349.95 | 28516.36 | Paid | Medium
EXP-01557 | PRJ-002 | PRJ-002-ACT-09 | 2026-03-17 | Material | MAT-003 | Sand | VEN-011 | 18.12 | Ton | 27485.67 | 28812.79 | 5186.3 | 33999.09 | Paid | High
EXP-01558 | PRJ-002 | PRJ-002-ACT-01 | 2026-03-17 | Contractor | CON-002 | Electrical Contract | VEN-003 | 1 | Contract | 418608.12 | 447014.43 | 80462.6 | 527477.03 | Paid | Medium
EXP-01559 | PRJ-002 | PRJ-002-ACT-08 | 2026-03-17 | Contractor | CON-002 | Electrical Contract | VEN-011 | 1 | Contract | 107837.11 | 105860.08 | 19054.81 | 124914.89 | Paid | Medium
EXP-01560 | PRJ-002 | PRJ-002-ACT-05 | 2026-03-22 | Contractor | CON-001 | Civil Structure Contract | VEN-007 | 1 | Contract | 80342.44 | 77927.51 | 14026.95 | 91954.46 | Paid | Medium
EXP-01561 | PRJ-002 | PRJ-002-ACT-09 | 2026-03-22 | Other | OTH-001 | Site Office | VEN-007 | 1 | Lot | 50290.05 | 52454.63 | 9441.83 | 61896.46 | Paid | Medium
EXP-01562 | PRJ-002 | PRJ-002-ACT-01 | 2026-03-22 | Labour | LAB-002 | Helper | VEN-002 | 21 | Worker | 33537.55 | 32759.84 | 5896.77 | 38656.61 | Paid | Low
EXP-01563 | PRJ-002 | PRJ-002-ACT-04 | 2026-03-22 | Contractor | CON-003 | Plumbing Contract | VEN-007 | 1 | Contract | 195169.82 | 198642.07 | 35755.57 | 234397.64 | Paid | Medium
EXP-01564 | PRJ-002 | PRJ-002-ACT-03 | 2026-03-22 | Equipment | EQ-002 | Excavator | VEN-007 | 7 | Day | 104870.61 | 102481.39 | 18446.65 | 120928.04 | Pending | Low
EXP-01565 | PRJ-002 | PRJ-002-ACT-09 | 2026-03-22 | Labour | LAB-006 | Painter | VEN-003 | 25 | Worker | 28851.82 | 27165.79 | 4889.84 | 32055.63 | Paid | Medium
EXP-01566 | PRJ-002 | PRJ-002-ACT-03 | 2026-03-22 | Contractor | CON-004 | Finishing Contract | VEN-003 | 1 | Contract | 408626.23 | 409211.04 | 73657.99 | 482869.03 | Paid | Low
EXP-01567 | PRJ-002 | PRJ-002-ACT-06 | 2026-03-22 | Material | MAT-002 | Steel | VEN-011 | 7.07 | Ton | 439808.66 | 428197.27 | 77075.51 | 505272.78 | Paid | Medium
EXP-01568 | PRJ-002 | PRJ-002-ACT-03 | 2026-03-27 | Labour | LAB-005 | Plumber | VEN-002 | 13 | Worker | 9219.02 | 8574.16 | 1543.35 | 10117.51 | Paid | High
EXP-01569 | PRJ-002 | PRJ-002-ACT-07 | 2026-03-27 | Material | MAT-008 | Tiles | VEN-011 | 15.68 | Sq Ft | 1336.37 | 1278.34 | 230.1 | 1508.44 | Paid | High
EXP-01570 | PRJ-002 | PRJ-002-ACT-01 | 2026-03-27 | Material | MAT-004 | Aggregate | VEN-007 | 13.61 | Ton | 22113.8 | 22441.21 | 4039.42 | 26480.63 | Paid | Low
EXP-01571 | PRJ-002 | PRJ-002-ACT-05 | 2026-03-27 | Other | OTH-001 | Safety | VEN-011 | 1 | Lot | 80331.71 | 75902.48 | 13662.45 | 89564.93 | Paid | Medium
EXP-01572 | PRJ-002 | PRJ-002-ACT-09 | 2026-03-27 | Material | MAT-009 | Paint | VEN-002 | 4.48 | Litre | 1127.41 | 1058.25 | 190.48 | 1248.73 | Paid | Low
EXP-01573 | PRJ-002 | PRJ-002-ACT-04 | 2026-03-27 | Other | OTH-001 | Transport | VEN-007 | 1 | Lot | 68719.17 | 65836.72 | 11850.61 | 77687.33 | Paid | Low
EXP-01574 | PRJ-002 | PRJ-002-ACT-04 | 2026-03-27 | Contractor | CON-004 | Finishing Contract | VEN-002 | 1 | Contract | 184091.4 | 197427.27 | 35536.91 | 232964.18 | Paid | Low
EXP-01575 | PRJ-002 | PRJ-002-ACT-08 | 2026-03-27 | Contractor | CON-003 | Plumbing Contract | VEN-002 | 1 | Contract | 92252.25 | 93804.01 | 16884.72 | 110688.73 | Paid | Low
EXP-01576 | PRJ-002 | PRJ-002-ACT-10 | 2026-03-27 | Contractor | CON-002 | Electrical Contract | VEN-007 | 1 | Contract | 411498.3 | 399154.87 | 71847.88 | 471002.75 | Paid | Low
EXP-01577 | PRJ-002 | PRJ-002-ACT-06 | 2026-03-27 | Contractor | CON-002 | Electrical Contract | VEN-002 | 1 | Contract | 234451.23 | 246039.52 | 44287.11 | 290326.63 | Paid | Low
EXP-01578 | PRJ-002 | PRJ-002-ACT-10 | 2026-04-01 | Equipment | EQ-003 | Concrete Mixer | VEN-002 | 3 | Day | 12948.71 | 12473.88 | 2245.3 | 14719.18 | Paid | Low
EXP-01579 | PRJ-002 | PRJ-002-ACT-01 | 2026-04-01 | Labour | LAB-005 | Plumber | VEN-011 | 34 | Worker | 32486.73 | 32289.38 | 5812.09 | 38101.47 | Paid | Medium
EXP-01580 | PRJ-002 | PRJ-002-ACT-04 | 2026-04-01 | Material | MAT-003 | Sand | VEN-003 | 16.73 | Ton | 29609.11 | 27529.87 | 4955.38 | 32485.25 | Paid | Low
EXP-01581 | PRJ-002 | PRJ-002-ACT-01 | 2026-04-01 | Material | MAT-001 | Cement | VEN-011 | 11.61 | Bag | 6429.79 | 6382.3 | 1148.81 | 7531.11 | Paid | High
EXP-01582 | PRJ-002 | PRJ-002-ACT-06 | 2026-04-01 | Equipment | EQ-001 | Crane | VEN-011 | 2 | Day | 36237.86 | 35703.13 | 6426.56 | 42129.69 | Paid | Medium
EXP-01583 | PRJ-002 | PRJ-002-ACT-05 | 2026-04-01 | Other | OTH-001 | Site Office | VEN-003 | 1 | Lot | 33973.08 | 36827.28 | 6628.91 | 43456.19 | Paid | Low
EXP-01584 | PRJ-002 | PRJ-002-ACT-02 | 2026-04-01 | Material | MAT-006 | Electrical Cable | VEN-011 | 5.71 | Meter | 459.97 | 486.95 | 87.65 | 574.6 | Paid | Low
EXP-01585 | PRJ-002 | PRJ-002-ACT-05 | 2026-04-01 | Labour | LAB-002 | Helper | VEN-007 | 23 | Worker | 39862.22 | 38142.91 | 6865.72 | 45008.63 | Paid | Medium
EXP-01586 | PRJ-002 | PRJ-002-ACT-04 | 2026-04-01 | Material | MAT-001 | Cement | VEN-011 | 6.75 | Bag | 3435.11 | 3476.91 | 625.84 | 4102.75 | Paid | Low
EXP-01587 | PRJ-002 | PRJ-002-ACT-06 | 2026-04-06 | Contractor | CON-003 | Plumbing Contract | VEN-007 | 1 | Contract | 178382.84 | 185976.36 | 33475.74 | 219452.1 | Paid | Low
EXP-01588 | PRJ-002 | PRJ-002-ACT-07 | 2026-04-06 | Labour | LAB-001 | Mason | VEN-011 | 33 | Worker | 45693.67 | 47264.1 | 8507.54 | 55771.64 | Paid | Medium
EXP-01589 | PRJ-002 | PRJ-002-ACT-06 | 2026-04-06 | Material | MAT-008 | Tiles | VEN-002 | 6.69 | Sq Ft | 452.91 | 436.24 | 78.52 | 514.76 | Paid | Low
EXP-01590 | PRJ-002 | PRJ-002-ACT-05 | 2026-04-06 | Material | MAT-002 | Steel | VEN-002 | 13.17 | Ton | 849342.63 | 891105.56 | 160399 | 1051504.56 | Paid | Low
EXP-01591 | PRJ-002 | PRJ-002-ACT-09 | 2026-04-06 | Material | MAT-004 | Aggregate | VEN-003 | 21.09 | Ton | 32854.28 | 31747.05 | 5714.47 | 37461.52 | Paid | Low
EXP-01592 | PRJ-002 | PRJ-002-ACT-06 | 2026-04-06 | Equipment | EQ-004 | Scaffolding | VEN-003 | 7 | Day | 16452.85 | 16536.94 | 2976.65 | 19513.59 | Paid | Low
EXP-01593 | PRJ-002 | PRJ-002-ACT-05 | 2026-04-06 | Material | MAT-009 | Paint | VEN-007 | 12.61 | Litre | 2431.29 | 2486.83 | 447.63 | 2934.46 | Pending | Medium
EXP-01594 | PRJ-002 | PRJ-002-ACT-07 | 2026-04-06 | Material | MAT-007 | PVC Pipe | VEN-002 | 5.84 | Meter | 791.07 | 772.75 | 139.09 | 911.84 | Paid | Low
EXP-01595 | PRJ-002 | PRJ-002-ACT-07 | 2026-04-06 | Labour | LAB-006 | Painter | VEN-007 | 24 | Worker | 30982.02 | 32604.32 | 5868.78 | 38473.1 | Paid | Medium
EXP-01596 | PRJ-002 | PRJ-002-ACT-04 | 2026-04-06 | Material | MAT-005 | Bricks | VEN-011 | 9.99 | Piece | 82.12 | 81.64 | 14.7 | 96.34 | Partially Paid | Low
EXP-01597 | PRJ-002 | PRJ-002-ACT-06 | 2026-04-11 | Material | MAT-006 | Electrical Cable | VEN-002 | 3.02 | Meter | 262.15 | 250.17 | 45.03 | 295.2 | Paid | Low
EXP-01598 | PRJ-002 | PRJ-002-ACT-08 | 2026-04-11 | Material | MAT-009 | Paint | VEN-007 | 17.75 | Litre | 3524.31 | 3755.86 | 676.05 | 4431.91 | Pending | Low
EXP-01599 | PRJ-002 | PRJ-002-ACT-09 | 2026-04-11 | Labour | LAB-005 | Plumber | VEN-002 | 14 | Worker | 14397.12 | 13830.77 | 2489.54 | 16320.31 | Paid | Low
EXP-01600 | PRJ-002 | PRJ-002-ACT-04 | 2026-04-11 | Equipment | EQ-002 | Excavator | VEN-007 | 2 | Day | 28514.54 | 26796.89 | 4823.44 | 31620.33 | Paid | Medium
EXP-01601 | PRJ-002 | PRJ-002-ACT-08 | 2026-04-11 | Labour | LAB-003 | Carpenter | VEN-011 | 34 | Worker | 27831 | 28425.34 | 5116.56 | 33541.9 | Paid | Medium
EXP-01602 | PRJ-002 | PRJ-002-ACT-05 | 2026-04-11 | Material | MAT-009 | Paint | VEN-007 | 20.19 | Litre | 4431.58 | 4757.46 | 856.34 | 5613.8 | Paid | Medium
EXP-01603 | PRJ-002 | PRJ-002-ACT-08 | 2026-04-11 | Labour | LAB-003 | Carpenter | VEN-002 | 13 | Worker | 13355.26 | 14293.59 | 2572.85 | 16866.44 | Paid | Low
EXP-01604 | PRJ-002 | PRJ-002-ACT-07 | 2026-04-11 | Material | MAT-008 | Tiles | VEN-003 | 6.82 | Sq Ft | 501.82 | 520.35 | 93.66 | 614.01 | Paid | Low
EXP-01605 | PRJ-002 | PRJ-002-ACT-09 | 2026-04-11 | Material | MAT-008 | Tiles | VEN-003 | 54.61 | Sq Ft | 4836.73 | 4631.23 | 833.62 | 5464.85 | Paid | Low
EXP-01606 | PRJ-002 | PRJ-002-ACT-09 | 2026-04-11 | Material | MAT-010 | Glass | VEN-003 | 15.68 | Sq Ft | 2884.99 | 2874.86 | 517.47 | 3392.33 | Partially Paid | Medium
EXP-01607 | PRJ-002 | PRJ-002-ACT-10 | 2026-04-16 | Equipment | EQ-001 | Crane | VEN-003 | 4 | Day | 74243.92 | 75210.78 | 13537.94 | 88748.72 | Paid | Low
EXP-01608 | PRJ-002 | PRJ-002-ACT-09 | 2026-04-16 | Labour | LAB-005 | Plumber | VEN-002 | 9 | Worker | 8568.32 | 8819.45 | 1587.5 | 10406.95 | Paid | Low
EXP-01609 | PRJ-002 | PRJ-002-ACT-10 | 2026-04-16 | Material | MAT-009 | Paint | VEN-002 | 6.89 | Litre | 1530 | 1553.86 | 279.69 | 1833.55 | Paid | Medium
EXP-01610 | PRJ-002 | PRJ-002-ACT-05 | 2026-04-16 | Other | OTH-001 | Transport | VEN-002 | 1 | Lot | 20933.8 | 20305.48 | 3654.99 | 23960.47 | Partially Paid | Low
EXP-01611 | PRJ-002 | PRJ-002-ACT-05 | 2026-04-16 | Material | MAT-001 | Cement | VEN-011 | 23.43 | Bag | 14571.13 | 13798.69 | 2483.76 | 16282.45 | Partially Paid | High
EXP-01612 | PRJ-002 | PRJ-002-ACT-04 | 2026-04-16 | Labour | LAB-002 | Helper | VEN-007 | 22 | Worker | 34441.86 | 32487.26 | 5847.71 | 38334.97 | Paid | Low
EXP-01613 | PRJ-002 | PRJ-002-ACT-01 | 2026-04-21 | Material | MAT-010 | Glass | VEN-007 | 2.91 | Sq Ft | 484.48 | 479.98 | 86.4 | 566.38 | Paid | Medium
EXP-01614 | PRJ-002 | PRJ-002-ACT-06 | 2026-04-21 | Equipment | EQ-004 | Scaffolding | VEN-007 | 6 | Day | 15289.16 | 16149.5 | 2906.91 | 19056.41 | Paid | Low
EXP-01615 | PRJ-002 | PRJ-002-ACT-06 | 2026-04-21 | Labour | LAB-001 | Mason | VEN-007 | 7 | Worker | 11574.99 | 11360.83 | 2044.95 | 13405.78 | Paid | Low
EXP-01616 | PRJ-002 | PRJ-002-ACT-10 | 2026-04-21 | Equipment | EQ-002 | Excavator | VEN-003 | 4 | Day | 61632.13 | 59516.62 | 10712.99 | 70229.61 | Paid | Low
EXP-01617 | PRJ-002 | PRJ-002-ACT-03 | 2026-04-21 | Contractor | CON-003 | Plumbing Contract | VEN-003 | 1 | Contract | 248133.86 | 258090.42 | 46456.28 | 304546.7 | Paid | Medium
EXP-01618 | PRJ-002 | PRJ-002-ACT-02 | 2026-04-21 | Material | MAT-003 | Sand | VEN-003 | 8.46 | Ton | 16471.84 | 16586 | 2985.48 | 19571.48 | Paid | Low
EXP-01619 | PRJ-002 | PRJ-002-ACT-10 | 2026-04-21 | Material | MAT-006 | Electrical Cable | VEN-003 | 17.3 | Meter | 1288 | 1275.7 | 229.63 | 1505.33 | Paid | High
EXP-01620 | PRJ-002 | PRJ-002-ACT-03 | 2026-04-21 | Contractor | CON-001 | Civil Structure Contract | VEN-002 | 1 | Contract | 399232.97 | 379294.89 | 68273.08 | 447567.97 | Paid | Low
EXP-01621 | PRJ-002 | PRJ-002-ACT-07 | 2026-04-21 | Material | MAT-007 | PVC Pipe | VEN-007 | 19.08 | Meter | 1985.01 | 2064.75 | 371.65 | 2436.4 | Paid | Low
EXP-01622 | PRJ-002 | PRJ-002-ACT-08 | 2026-04-26 | Contractor | CON-003 | Plumbing Contract | VEN-007 | 1 | Contract | 292954.54 | 293520.55 | 52833.7 | 346354.25 | Paid | Medium
EXP-01623 | PRJ-002 | PRJ-002-ACT-08 | 2026-04-26 | Material | MAT-007 | PVC Pipe | VEN-011 | 6.48 | Meter | 628.8 | 667.56 | 120.16 | 787.72 | Paid | Low
EXP-01624 | PRJ-002 | PRJ-002-ACT-05 | 2026-04-26 | Equipment | EQ-004 | Scaffolding | VEN-002 | 6 | Day | 15384.22 | 16123.73 | 2902.27 | 19026 | Paid | Low
EXP-01625 | PRJ-002 | PRJ-002-ACT-05 | 2026-04-26 | Labour | LAB-005 | Plumber | VEN-002 | 31 | Worker | 32290.97 | 30011.58 | 5402.08 | 35413.66 | Paid | Low
EXP-01626 | PRJ-002 | PRJ-002-ACT-07 | 2026-04-26 | Material | MAT-001 | Cement | VEN-007 | 3.91 | Bag | 1993.02 | 2101.09 | 378.2 | 2479.29 | Paid | Low
EXP-01627 | PRJ-002 | PRJ-002-ACT-10 | 2026-04-26 | Material | MAT-005 | Bricks | VEN-003 | 3.49 | Piece | 26.37 | 28.07 | 5.05 | 33.12 | Paid | Low
EXP-01628 | PRJ-002 | PRJ-002-ACT-01 | 2026-04-26 | Material | MAT-003 | Sand | VEN-002 | 13.06 | Ton | 24605.28 | 24883.5 | 4479.03 | 29362.53 | Paid | Low
EXP-01629 | PRJ-002 | PRJ-002-ACT-05 | 2026-04-26 | Other | OTH-001 | Miscellaneous | VEN-003 | 1 | Lot | 39797.4 | 41842.91 | 7531.72 | 49374.63 | Paid | Low
EXP-01630 | PRJ-002 | PRJ-002-ACT-03 | 2026-04-26 | Material | MAT-010 | Glass | VEN-011 | 5.45 | Sq Ft | 857.28 | 923.34 | 166.2 | 1089.54 | Partially Paid | Medium
EXP-01631 | PRJ-002 | PRJ-002-ACT-06 | 2026-04-26 | Material | MAT-006 | Electrical Cable | VEN-003 | 9.65 | Meter | 897.59 | 881.86 | 158.73 | 1040.59 | Paid | Low
EXP-01632 | PRJ-002 | PRJ-002-ACT-07 | 2026-05-01 | Material | MAT-005 | Bricks | VEN-011 | 8.82 | Piece | 71.25 | 72.24 | 13 | 85.24 | Paid | Low
EXP-01633 | PRJ-002 | PRJ-002-ACT-09 | 2026-05-01 | Material | MAT-010 | Glass | VEN-011 | 9.88 | Sq Ft | 1480.61 | 1414.27 | 254.57 | 1668.84 | Paid | Low
EXP-01634 | PRJ-002 | PRJ-002-ACT-06 | 2026-05-01 | Contractor | CON-001 | Civil Structure Contract | VEN-007 | 1 | Contract | 224182.68 | 231571.05 | 41682.79 | 273253.84 | Paid | High
EXP-01635 | PRJ-002 | PRJ-002-ACT-10 | 2026-05-01 | Material | MAT-001 | Cement | VEN-007 | 3.12 | Bag | 1440.19 | 1451.87 | 261.34 | 1713.21 | Paid | High
EXP-01636 | PRJ-002 | PRJ-002-ACT-01 | 2026-05-01 | Contractor | CON-003 | Plumbing Contract | VEN-003 | 1 | Contract | 242851.62 | 229041.41 | 41227.45 | 270268.86 | Paid | Low
EXP-01637 | PRJ-002 | PRJ-002-ACT-07 | 2026-05-01 | Material | MAT-001 | Cement | VEN-007 | 49.07 | Bag | 22734.41 | 23353.77 | 4203.68 | 27557.45 | Pending | Low
EXP-01638 | PRJ-002 | PRJ-002-ACT-08 | 2026-05-01 | Material | MAT-004 | Aggregate | VEN-011 | 28.3 | Ton | 45101.03 | 42848.2 | 7712.68 | 50560.88 | Paid | Low
EXP-01639 | PRJ-002 | PRJ-002-ACT-10 | 2026-05-01 | Labour | LAB-004 | Electrician | VEN-002 | 15 | Worker | 19001.56 | 18840.11 | 3391.22 | 22231.33 | Partially Paid | Medium
EXP-01640 | PRJ-002 | PRJ-002-ACT-04 | 2026-05-01 | Material | MAT-008 | Tiles | VEN-011 | 5.49 | Sq Ft | 453.08 | 449.27 | 80.87 | 530.14 | Paid | Low
EXP-01641 | PRJ-002 | PRJ-002-ACT-09 | 2026-05-01 | Material | MAT-002 | Steel | VEN-003 | 10.75 | Ton | 645921.23 | 599990.14 | 107998.23 | 707988.37 | Paid | Low
EXP-01642 | PRJ-002 | PRJ-002-ACT-04 | 2026-05-06 | Contractor | CON-002 | Electrical Contract | VEN-007 | 1 | Contract | 192147.18 | 201950.65 | 36351.12 | 238301.77 | Partially Paid | Low
EXP-01643 | PRJ-002 | PRJ-002-ACT-05 | 2026-05-06 | Contractor | CON-001 | Civil Structure Contract | VEN-007 | 1 | Contract | 304962.11 | 290412.66 | 52274.28 | 342686.94 | Paid | Medium
EXP-01644 | PRJ-002 | PRJ-002-ACT-09 | 2026-05-06 | Labour | LAB-002 | Helper | VEN-011 | 19 | Worker | 15729.62 | 14896.5 | 2681.37 | 17577.87 | Paid | Low
EXP-01645 | PRJ-002 | PRJ-002-ACT-06 | 2026-05-06 | Labour | LAB-005 | Plumber | VEN-003 | 18 | Worker | 25912.61 | 25064.01 | 4511.52 | 29575.53 | Partially Paid | Low
EXP-01646 | PRJ-002 | PRJ-002-ACT-03 | 2026-05-06 | Labour | LAB-004 | Electrician | VEN-003 | 18 | Worker | 25974.51 | 24782.22 | 4460.8 | 29243.02 | Paid | Medium
EXP-01647 | PRJ-002 | PRJ-002-ACT-06 | 2026-05-06 | Labour | LAB-003 | Carpenter | VEN-003 | 8 | Worker | 5418.69 | 5720.86 | 1029.75 | 6750.61 | Paid | Low
EXP-01648 | PRJ-002 | PRJ-002-ACT-09 | 2026-05-06 | Equipment | EQ-002 | Excavator | VEN-002 | 4 | Day | 51749.52 | 53371.84 | 9606.93 | 62978.77 | Paid | Low
EXP-01649 | PRJ-002 | PRJ-002-ACT-04 | 2026-05-11 | Material | MAT-006 | Electrical Cable | VEN-002 | 44.15 | Meter | 4222.99 | 4146.14 | 746.31 | 4892.45 | Paid | Low
EXP-01650 | PRJ-002 | PRJ-002-ACT-01 | 2026-05-11 | Equipment | EQ-002 | Excavator | VEN-011 | 7 | Day | 102477.25 | 94911.68 | 17084.1 | 111995.78 | Paid | Low
EXP-01651 | PRJ-002 | PRJ-002-ACT-04 | 2026-05-11 | Contractor | CON-002 | Electrical Contract | VEN-003 | 1 | Contract | 127941 | 126137.12 | 22704.68 | 148841.8 | Paid | High
EXP-01652 | PRJ-002 | PRJ-002-ACT-01 | 2026-05-11 | Contractor | CON-001 | Civil Structure Contract | VEN-002 | 1 | Contract | 443616.26 | 422330.29 | 76019.45 | 498349.74 | Paid | High
EXP-01653 | PRJ-002 | PRJ-002-ACT-05 | 2026-05-11 | Equipment | EQ-001 | Crane | VEN-002 | 4 | Day | 69675.89 | 67225.07 | 12100.51 | 79325.58 | Paid | Low
EXP-01654 | PRJ-002 | PRJ-002-ACT-09 | 2026-05-11 | Material | MAT-006 | Electrical Cable | VEN-011 | 15.93 | Meter | 1162.62 | 1198.94 | 215.81 | 1414.75 | Paid | Low
EXP-01655 | PRJ-002 | PRJ-002-ACT-03 | 2026-05-11 | Contractor | CON-001 | Civil Structure Contract | VEN-003 | 1 | Contract | 234228.72 | 218815.88 | 39386.86 | 258202.74 | Paid | Medium
EXP-01656 | PRJ-002 | PRJ-002-ACT-09 | 2026-05-11 | Material | MAT-007 | PVC Pipe | VEN-011 | 7.35 | Meter | 954.97 | 912.67 | 164.28 | 1076.95 | Partially Paid | Low
EXP-01657 | PRJ-002 | PRJ-002-ACT-03 | 2026-05-11 | Material | MAT-009 | Paint | VEN-003 | 6.85 | Litre | 1499 | 1466.78 | 264.02 | 1730.8 | Paid | Low
EXP-01658 | PRJ-002 | PRJ-002-ACT-03 | 2026-05-11 | Other | OTH-001 | Site Office | VEN-002 | 1 | Lot | 79317.39 | 78288.72 | 14091.97 | 92380.69 | Partially Paid | High
EXP-01659 | PRJ-002 | PRJ-002-ACT-02 | 2026-05-16 | Labour | LAB-002 | Helper | VEN-003 | 5 | Worker | 4009.27 | 3897.19 | 701.49 | 4598.68 | Paid | Low
EXP-01660 | PRJ-002 | PRJ-002-ACT-07 | 2026-05-16 | Material | MAT-001 | Cement | VEN-002 | 6.73 | Bag | 3684.11 | 3765 | 677.7 | 4442.7 | Paid | Low
EXP-01661 | PRJ-002 | PRJ-002-ACT-04 | 2026-05-16 | Labour | LAB-001 | Mason | VEN-007 | 33 | Worker | 52682.52 | 53313.75 | 9596.48 | 62910.23 | Paid | Low
EXP-01662 | PRJ-002 | PRJ-002-ACT-05 | 2026-05-16 | Labour | LAB-002 | Helper | VEN-003 | 32 | Worker | 38646.51 | 35789.93 | 6442.19 | 42232.12 | Paid | Low
EXP-01663 | PRJ-002 | PRJ-002-ACT-07 | 2026-05-16 | Labour | LAB-003 | Carpenter | VEN-007 | 7 | Worker | 9077.21 | 9198.15 | 1655.67 | 10853.82 | Paid | Low
EXP-01664 | PRJ-002 | PRJ-002-ACT-10 | 2026-05-16 | Equipment | EQ-001 | Crane | VEN-002 | 2 | Day | 35461.52 | 37966.67 | 6834 | 44800.67 | Paid | Low
EXP-01665 | PRJ-002 | PRJ-002-ACT-09 | 2026-05-16 | Material | MAT-001 | Cement | VEN-011 | 10.35 | Bag | 6232.04 | 6109.46 | 1099.7 | 7209.16 | Partially Paid | Medium
EXP-01666 | PRJ-002 | PRJ-002-ACT-07 | 2026-05-16 | Contractor | CON-004 | Finishing Contract | VEN-011 | 1 | Contract | 155094.39 | 146729.62 | 26411.33 | 173140.95 | Partially Paid | Low
EXP-01667 | PRJ-002 | PRJ-002-ACT-03 | 2026-05-16 | Contractor | CON-002 | Electrical Contract | VEN-003 | 1 | Contract | 451995.62 | 438322.25 | 78898 | 517220.25 | Paid | Low
EXP-01668 | PRJ-002 | PRJ-002-ACT-03 | 2026-05-21 | Material | MAT-008 | Tiles | VEN-011 | 3.37 | Sq Ft | 259.67 | 272.1 | 48.98 | 321.08 | Pending | Low
EXP-01669 | PRJ-002 | PRJ-002-ACT-02 | 2026-05-21 | Material | MAT-004 | Aggregate | VEN-003 | 14.34 | Ton | 23375.84 | 22881.77 | 4118.72 | 27000.49 | Paid | High
EXP-01670 | PRJ-002 | PRJ-002-ACT-01 | 2026-05-21 | Other | OTH-001 | Permit | VEN-002 | 1 | Lot | 8209.13 | 8418.57 | 1515.34 | 9933.91 | Paid | Low
EXP-01671 | PRJ-002 | PRJ-002-ACT-09 | 2026-05-21 | Equipment | EQ-002 | Excavator | VEN-011 | 4 | Day | 59441.47 | 57733.89 | 10392.1 | 68125.99 | Pending | Low
EXP-01672 | PRJ-002 | PRJ-002-ACT-09 | 2026-05-21 | Equipment | EQ-003 | Concrete Mixer | VEN-007 | 1 | Day | 4145.11 | 4375.62 | 787.61 | 5163.23 | Partially Paid | Low
EXP-01673 | PRJ-002 | PRJ-002-ACT-10 | 2026-05-21 | Contractor | CON-004 | Finishing Contract | VEN-002 | 1 | Contract | 300749.51 | 305046.53 | 54908.38 | 359954.91 | Paid | High
EXP-01674 | PRJ-002 | PRJ-002-ACT-03 | 2026-05-21 | Contractor | CON-004 | Finishing Contract | VEN-002 | 1 | Contract | 162425.74 | 163438.52 | 29418.93 | 192857.45 | Paid | Low
EXP-01675 | PRJ-002 | PRJ-002-ACT-04 | 2026-05-21 | Other | OTH-001 | Transport | VEN-007 | 1 | Lot | 77168.52 | 75824.92 | 13648.49 | 89473.41 | Paid | Medium
EXP-01676 | PRJ-002 | PRJ-002-ACT-05 | 2026-05-21 | Material | MAT-001 | Cement | VEN-011 | 5.45 | Bag | 2595.04 | 2707.02 | 487.26 | 3194.28 | Paid | Low
EXP-01677 | PRJ-002 | PRJ-002-ACT-06 | 2026-05-26 | Equipment | EQ-004 | Scaffolding | VEN-002 | 7 | Day | 16586.23 | 16469.62 | 2964.53 | 19434.15 | Paid | Low
EXP-01678 | PRJ-002 | PRJ-002-ACT-10 | 2026-05-26 | Contractor | CON-001 | Civil Structure Contract | VEN-003 | 1 | Contract | 292987.29 | 285658.29 | 51418.49 | 337076.78 | Partially Paid | Medium
EXP-01679 | PRJ-002 | PRJ-002-ACT-08 | 2026-05-26 | Contractor | CON-002 | Electrical Contract | VEN-002 | 1 | Contract | 354414 | 359055.87 | 64630.06 | 423685.93 | Paid | Low
EXP-01680 | PRJ-002 | PRJ-002-ACT-09 | 2026-05-26 | Material | MAT-001 | Cement | VEN-003 | 6.11 | Bag | 3050.04 | 3102.49 | 558.45 | 3660.94 | Pending | Low
EXP-01681 | PRJ-002 | PRJ-002-ACT-06 | 2026-05-26 | Material | MAT-001 | Cement | VEN-003 | 7.79 | Bag | 4831.32 | 4476.1 | 805.7 | 5281.8 | Paid | Low
EXP-01682 | PRJ-002 | PRJ-002-ACT-01 | 2026-05-26 | Material | MAT-004 | Aggregate | VEN-007 | 23.44 | Ton | 37554.38 | 35208.28 | 6337.49 | 41545.77 | Paid | Medium
EXP-01683 | PRJ-002 | PRJ-002-ACT-04 | 2026-05-26 | Material | MAT-010 | Glass | VEN-002 | 10.62 | Sq Ft | 1640.42 | 1554.74 | 279.85 | 1834.59 | Paid | Low
EXP-01684 | PRJ-002 | PRJ-002-ACT-04 | 2026-05-26 | Labour | LAB-001 | Mason | VEN-007 | 22 | Worker | 39692.62 | 38098.33 | 6857.7 | 44956.03 | Paid | Low
EXP-01685 | PRJ-002 | PRJ-002-ACT-10 | 2026-05-26 | Material | MAT-009 | Paint | VEN-003 | 2.89 | Litre | 611.28 | 590.85 | 106.35 | 697.2 | Paid | Low
EXP-01686 | PRJ-002 | PRJ-002-ACT-09 | 2026-05-31 | Labour | LAB-003 | Carpenter | VEN-003 | 13 | Worker | 15273.48 | 14923.42 | 2686.22 | 17609.64 | Paid | Low
EXP-01687 | PRJ-002 | PRJ-002-ACT-09 | 2026-05-31 | Equipment | EQ-001 | Crane | VEN-002 | 3 | Day | 47448.8 | 48707.69 | 8767.38 | 57475.07 | Paid | Low
EXP-01688 | PRJ-002 | PRJ-002-ACT-01 | 2026-05-31 | Labour | LAB-006 | Painter | VEN-002 | 30 | Worker | 35921.64 | 37013.86 | 6662.49 | 43676.35 | Pending | Low
EXP-01689 | PRJ-002 | PRJ-002-ACT-07 | 2026-05-31 | Contractor | CON-002 | Electrical Contract | VEN-003 | 1 | Contract | 404838.45 | 430405.02 | 77472.9 | 507877.92 | Paid | Low
EXP-01690 | PRJ-002 | PRJ-002-ACT-09 | 2026-05-31 | Material | MAT-004 | Aggregate | VEN-003 | 6.95 | Ton | 11462.65 | 10678.91 | 1922.2 | 12601.11 | Paid | Medium
EXP-01691 | PRJ-002 | PRJ-002-ACT-02 | 2026-05-31 | Other | OTH-001 | Permit | VEN-003 | 1 | Lot | 15123.37 | 15322.92 | 2758.13 | 18081.05 | Partially Paid | High
EXP-01692 | PRJ-002 | PRJ-002-ACT-06 | 2026-05-31 | Labour | LAB-003 | Carpenter | VEN-011 | 24 | Worker | 17721.69 | 17384.77 | 3129.26 | 20514.03 | Paid | Medium
EXP-01693 | PRJ-002 | PRJ-002-ACT-08 | 2026-05-31 | Other | OTH-001 | Safety | VEN-011 | 1 | Lot | 60520.96 | 61061.97 | 10991.15 | 72053.12 | Pending | Medium
EXP-01694 | PRJ-002 | PRJ-002-ACT-10 | 2026-05-31 | Labour | LAB-001 | Mason | VEN-003 | 32 | Worker | 53297.86 | 54346.13 | 9782.3 | 64128.43 | Partially Paid | Low
EXP-01695 | PRJ-002 | PRJ-002-ACT-08 | 2026-05-31 | Labour | LAB-006 | Painter | VEN-002 | 25 | Worker | 39855.95 | 41623.29 | 7492.19 | 49115.48 | Paid | Medium
EXP-01696 | PRJ-002 | PRJ-002-ACT-04 | 2026-06-05 | Labour | LAB-005 | Plumber | VEN-003 | 32 | Worker | 47594.22 | 45781.55 | 8240.68 | 54022.23 | Paid | Low
EXP-01697 | PRJ-002 | PRJ-002-ACT-02 | 2026-06-05 | Material | MAT-009 | Paint | VEN-007 | 19.18 | Litre | 4227.34 | 4108.02 | 739.44 | 4847.46 | Paid | Medium
EXP-01698 | PRJ-002 | PRJ-002-ACT-10 | 2026-06-05 | Labour | LAB-003 | Carpenter | VEN-011 | 9 | Worker | 10598.05 | 10955.66 | 1972.02 | 12927.68 | Paid | High
EXP-01699 | PRJ-002 | PRJ-002-ACT-03 | 2026-06-05 | Material | MAT-008 | Tiles | VEN-007 | 8.67 | Sq Ft | 531.88 | 560.26 | 100.85 | 661.11 | Partially Paid | High
EXP-01700 | PRJ-002 | PRJ-002-ACT-10 | 2026-06-05 | Contractor | CON-002 | Electrical Contract | VEN-002 | 1 | Contract | 219823.76 | 208708.58 | 37567.54 | 246276.12 | Paid | Low
EXP-01701 | PRJ-002 | PRJ-002-ACT-08 | 2026-06-05 | Equipment | EQ-003 | Concrete Mixer | VEN-003 | 5 | Day | 21582.38 | 22679.77 | 4082.36 | 26762.13 | Paid | Low
EXP-01702 | PRJ-002 | PRJ-002-ACT-05 | 2026-06-05 | Contractor | CON-004 | Finishing Contract | VEN-002 | 1 | Contract | 106714.61 | 113400.23 | 20412.04 | 133812.27 | Paid | Low
EXP-01703 | PRJ-002 | PRJ-002-ACT-02 | 2026-06-10 | Contractor | CON-003 | Plumbing Contract | VEN-011 | 1 | Contract | 250682.86 | 254507.55 | 45811.36 | 300318.91 | Partially Paid | Low
EXP-01704 | PRJ-002 | PRJ-002-ACT-06 | 2026-06-10 | Contractor | CON-002 | Electrical Contract | VEN-011 | 1 | Contract | 378222.42 | 379650.93 | 68337.17 | 447988.1 | Partially Paid | Low
EXP-01705 | PRJ-002 | PRJ-002-ACT-01 | 2026-06-10 | Material | MAT-008 | Tiles | VEN-003 | 15.1 | Sq Ft | 1074.83 | 1023.55 | 184.24 | 1207.79 | Pending | Low
EXP-01706 | PRJ-002 | PRJ-002-ACT-10 | 2026-06-10 | Labour | LAB-002 | Helper | VEN-011 | 9 | Worker | 10719.18 | 10963.74 | 1973.47 | 12937.21 | Partially Paid | Medium
EXP-01707 | PRJ-002 | PRJ-002-ACT-05 | 2026-06-10 | Equipment | EQ-002 | Excavator | VEN-011 | 2 | Day | 26833.24 | 27249.53 | 4904.92 | 32154.45 | Paid | High
EXP-01708 | PRJ-002 | PRJ-002-ACT-10 | 2026-06-10 | Equipment | EQ-001 | Crane | VEN-002 | 2 | Day | 36363.62 | 35070.41 | 6312.67 | 41383.08 | Paid | Low
EXP-01709 | PRJ-002 | PRJ-002-ACT-07 | 2026-06-10 | Labour | LAB-001 | Mason | VEN-011 | 29 | Worker | 38880.35 | 37709.45 | 6787.7 | 44497.15 | Paid | Medium
EXP-01710 | PRJ-002 | PRJ-002-ACT-10 | 2026-06-15 | Contractor | CON-002 | Electrical Contract | VEN-002 | 1 | Contract | 382226.95 | 370388.21 | 66669.88 | 437058.09 | Paid | Low
EXP-01711 | PRJ-002 | PRJ-002-ACT-05 | 2026-06-15 | Equipment | EQ-002 | Excavator | VEN-007 | 1 | Day | 15733.55 | 14713.11 | 2648.36 | 17361.47 | Paid | Medium
EXP-01712 | PRJ-002 | PRJ-002-ACT-02 | 2026-06-15 | Equipment | EQ-001 | Crane | VEN-007 | 2 | Day | 36426.77 | 34894.76 | 6281.06 | 41175.82 | Paid | Low
EXP-01713 | PRJ-002 | PRJ-002-ACT-08 | 2026-06-15 | Material | MAT-005 | Bricks | VEN-002 | 5.76 | Piece | 48.2 | 50.61 | 9.11 | 59.72 | Paid | Low
EXP-01714 | PRJ-002 | PRJ-002-ACT-09 | 2026-06-15 | Material | MAT-003 | Sand | VEN-003 | 4.75 | Ton | 7586.45 | 8234.6 | 1482.23 | 9716.83 | Paid | Medium
EXP-01715 | PRJ-002 | PRJ-002-ACT-10 | 2026-06-15 | Contractor | CON-002 | Electrical Contract | VEN-007 | 1 | Contract | 152278.17 | 145648.04 | 26216.65 | 171864.69 | Paid | Medium
EXP-01716 | PRJ-002 | PRJ-002-ACT-02 | 2026-06-15 | Material | MAT-007 | PVC Pipe | VEN-007 | 14.92 | Meter | 1913.79 | 1900.55 | 342.1 | 2242.65 | Paid | Low
EXP-01717 | PRJ-002 | PRJ-002-ACT-05 | 2026-06-15 | Labour | LAB-006 | Painter | VEN-007 | 6 | Worker | 8708.26 | 8963.7 | 1613.47 | 10577.17 | Paid | Low
EXP-01718 | PRJ-002 | PRJ-002-ACT-02 | 2026-06-20 | Contractor | CON-004 | Finishing Contract | VEN-002 | 1 | Contract | 271172.08 | 272671.47 | 49080.86 | 321752.33 | Pending | Low
EXP-01719 | PRJ-002 | PRJ-002-ACT-05 | 2026-06-20 | Material | MAT-009 | Paint | VEN-002 | 10.44 | Litre | 2083.32 | 1989.89 | 358.18 | 2348.07 | Paid | High
EXP-01720 | PRJ-002 | PRJ-002-ACT-01 | 2026-06-20 | Contractor | CON-004 | Finishing Contract | VEN-007 | 1 | Contract | 150231.62 | 155727.29 | 28030.91 | 183758.2 | Paid | Low
EXP-01721 | PRJ-002 | PRJ-002-ACT-05 | 2026-06-20 | Contractor | CON-002 | Electrical Contract | VEN-003 | 1 | Contract | 173051.7 | 174575.85 | 31423.65 | 205999.5 | Paid | Low
EXP-01722 | PRJ-002 | PRJ-002-ACT-08 | 2026-06-20 | Contractor | CON-001 | Civil Structure Contract | VEN-003 | 1 | Contract | 436466.73 | 422749.73 | 76094.95 | 498844.68 | Paid | Low
EXP-01723 | PRJ-002 | PRJ-002-ACT-02 | 2026-06-20 | Material | MAT-002 | Steel | VEN-011 | 19.3 | Ton | 1272795.57 | 1215177.53 | 218731.96 | 1433909.49 | Paid | Medium
EXP-01724 | PRJ-002 | PRJ-002-ACT-04 | 2026-06-20 | Labour | LAB-005 | Plumber | VEN-007 | 26 | Worker | 18431.28 | 18285.96 | 3291.47 | 21577.43 | Paid | High
EXP-01725 | PRJ-002 | PRJ-002-ACT-04 | 2026-06-20 | Material | MAT-003 | Sand | VEN-011 | 22.5 | Ton | 38060.95 | 35910.37 | 6463.87 | 42374.24 | Paid | Low
EXP-01726 | PRJ-002 | PRJ-002-ACT-04 | 2026-06-20 | Other | OTH-001 | Permit | VEN-002 | 1 | Lot | 33436.11 | 34525.71 | 6214.63 | 40740.34 | Paid | Low
EXP-01727 | PRJ-002 | PRJ-002-ACT-06 | 2026-06-25 | Material | MAT-007 | PVC Pipe | VEN-002 | 19.61 | Meter | 2203.98 | 2214.96 | 398.69 | 2613.65 | Partially Paid | Low
EXP-01728 | PRJ-002 | PRJ-002-ACT-10 | 2026-06-25 | Contractor | CON-003 | Plumbing Contract | VEN-003 | 1 | Contract | 323690.98 | 343984.01 | 61917.12 | 405901.13 | Pending | Medium
EXP-01729 | PRJ-002 | PRJ-002-ACT-01 | 2026-06-25 | Material | MAT-002 | Steel | VEN-002 | 13.27 | Ton | 671489.84 | 712325.6 | 128218.61 | 840544.21 | Paid | Medium
EXP-01730 | PRJ-002 | PRJ-002-ACT-04 | 2026-06-25 | Material | MAT-009 | Paint | VEN-003 | 11.27 | Litre | 2301.39 | 2264.76 | 407.66 | 2672.42 | Paid | Low
EXP-01731 | PRJ-002 | PRJ-002-ACT-07 | 2026-06-25 | Labour | LAB-004 | Electrician | VEN-003 | 9 | Worker | 13820.49 | 14652.19 | 2637.39 | 17289.58 | Paid | High
EXP-01732 | PRJ-002 | PRJ-002-ACT-08 | 2026-06-25 | Labour | LAB-003 | Carpenter | VEN-007 | 5 | Worker | 9062.74 | 8819.81 | 1587.57 | 10407.38 | Paid | Low
EXP-01733 | PRJ-002 | PRJ-002-ACT-02 | 2026-06-25 | Material | MAT-002 | Steel | VEN-003 | 5.07 | Ton | 327633.48 | 306984.94 | 55257.29 | 362242.23 | Partially Paid | Low
EXP-01734 | PRJ-002 | PRJ-002-ACT-10 | 2026-06-30 | Labour | LAB-003 | Carpenter | VEN-002 | 32 | Worker | 26335.25 | 27670.52 | 4980.69 | 32651.21 | Paid | Low
EXP-01735 | PRJ-002 | PRJ-002-ACT-05 | 2026-06-30 | Material | MAT-003 | Sand | VEN-007 | 5.1 | Ton | 8223.92 | 8482.82 | 1526.91 | 10009.73 | Partially Paid | Low
EXP-01736 | PRJ-002 | PRJ-002-ACT-05 | 2026-06-30 | Contractor | CON-004 | Finishing Contract | VEN-003 | 1 | Contract | 268680.58 | 258477.08 | 46525.87 | 305002.95 | Paid | Low
EXP-01737 | PRJ-002 | PRJ-002-ACT-07 | 2026-06-30 | Material | MAT-009 | Paint | VEN-003 | 19.1 | Litre | 4480.48 | 4359.3 | 784.67 | 5143.97 | Paid | Low
EXP-01738 | PRJ-002 | PRJ-002-ACT-06 | 2026-06-30 | Contractor | CON-001 | Civil Structure Contract | VEN-011 | 1 | Contract | 113292.11 | 120143.61 | 21625.85 | 141769.46 | Paid | Medium
EXP-01739 | PRJ-002 | PRJ-002-ACT-10 | 2026-06-30 | Contractor | CON-003 | Plumbing Contract | VEN-007 | 1 | Contract | 314003.65 | 304820.76 | 54867.74 | 359688.5 | Paid | Low
EXP-01740 | PRJ-002 | PRJ-002-ACT-04 | 2026-06-30 | Equipment | EQ-002 | Excavator | VEN-007 | 4 | Day | 59272.3 | 57263.97 | 10307.51 | 67571.48 | Paid | Low
EXP-01741 | PRJ-002 | PRJ-002-ACT-05 | 2026-06-30 | Equipment | EQ-002 | Excavator | VEN-011 | 1 | Day | 14373.4 | 14167.9 | 2550.22 | 16718.12 | Pending | Low
EXP-01742 | PRJ-002 | PRJ-002-ACT-07 | 2026-07-05 | Material | MAT-001 | Cement | VEN-007 | 10.78 | Bag | 4675.11 | 5067.88 | 912.22 | 5980.1 | Paid | Low
EXP-01743 | PRJ-002 | PRJ-002-ACT-07 | 2026-07-05 | Labour | LAB-001 | Mason | VEN-003 | 32 | Worker | 50192.4 | 48202.78 | 8676.5 | 56879.28 | Pending | High
EXP-01744 | PRJ-002 | PRJ-002-ACT-06 | 2026-07-05 | Contractor | CON-002 | Electrical Contract | VEN-003 | 1 | Contract | 125615.86 | 123204.73 | 22176.85 | 145381.58 | Paid | Medium
EXP-01745 | PRJ-002 | PRJ-002-ACT-02 | 2026-07-05 | Labour | LAB-003 | Carpenter | VEN-002 | 10 | Worker | 12965.11 | 12391.27 | 2230.43 | 14621.7 | Paid | Medium
EXP-01746 | PRJ-002 | PRJ-002-ACT-08 | 2026-07-05 | Other | OTH-001 | Transport | VEN-007 | 1 | Lot | 69160.49 | 69734.82 | 12552.27 | 82287.09 | Paid | High
EXP-01747 | PRJ-002 | PRJ-002-ACT-06 | 2026-07-05 | Labour | LAB-006 | Painter | VEN-003 | 20 | Worker | 20466.06 | 20835.56 | 3750.4 | 24585.96 | Paid | Low
EXP-01748 | PRJ-002 | PRJ-002-ACT-06 | 2026-07-05 | Contractor | CON-003 | Plumbing Contract | VEN-007 | 1 | Contract | 345613.58 | 359053.56 | 64629.64 | 423683.2 | Partially Paid | High
EXP-01749 | PRJ-002 | PRJ-002-ACT-04 | 2026-07-05 | Labour | LAB-006 | Painter | VEN-003 | 16 | Worker | 15429.71 | 16131.52 | 2903.67 | 19035.19 | Paid | Low
EXP-01750 | PRJ-002 | PRJ-002-ACT-02 | 2026-07-05 | Contractor | CON-004 | Finishing Contract | VEN-007 | 1 | Contract | 259094.65 | 249201.92 | 44856.35 | 294058.27 | Paid | Low
EXP-01751 | PRJ-002 | PRJ-002-ACT-05 | 2026-07-05 | Contractor | CON-004 | Finishing Contract | VEN-003 | 1 | Contract | 352535.18 | 345282.08 | 62150.77 | 407432.85 | Paid | High
EXP-01752 | PRJ-002 | PRJ-002-ACT-10 | 2026-07-10 | Material | MAT-006 | Electrical Cable | VEN-002 | 6.78 | Meter | 618.26 | 603.41 | 108.61 | 712.02 | Paid | Low
EXP-01753 | PRJ-002 | PRJ-002-ACT-08 | 2026-07-10 | Other | OTH-001 | Site Office | VEN-011 | 1 | Lot | 19555.61 | 20968.8 | 3774.38 | 24743.18 | Paid | Low
EXP-01754 | PRJ-002 | PRJ-002-ACT-10 | 2026-07-10 | Material | MAT-002 | Steel | VEN-003 | 7.73 | Ton | 477842.86 | 454545.06 | 81818.11 | 536363.17 | Paid | Low
EXP-01755 | PRJ-002 | PRJ-002-ACT-05 | 2026-07-10 | Material | MAT-009 | Paint | VEN-007 | 6.97 | Litre | 1447.03 | 1368.04 | 246.25 | 1614.29 | Paid | Low
EXP-01756 | PRJ-002 | PRJ-002-ACT-01 | 2026-07-10 | Equipment | EQ-004 | Scaffolding | VEN-002 | 2 | Day | 5523.65 | 5268.25 | 948.28 | 6216.53 | Partially Paid | High
EXP-01757 | PRJ-002 | PRJ-002-ACT-04 | 2026-07-10 | Material | MAT-003 | Sand | VEN-011 | 4.29 | Ton | 7524.45 | 7044.16 | 1267.95 | 8312.11 | Paid | Low
EXP-01758 | PRJ-002 | PRJ-002-ACT-07 | 2026-07-10 | Material | MAT-001 | Cement | VEN-003 | 13.38 | Bag | 8176.53 | 7854.07 | 1413.73 | 9267.8 | Paid | Medium
EXP-01759 | PRJ-002 | PRJ-002-ACT-02 | 2026-07-10 | Contractor | CON-003 | Plumbing Contract | VEN-002 | 1 | Contract | 426426.49 | 403682.1 | 72662.78 | 476344.88 | Pending | Medium
EXP-01760 | PRJ-002 | PRJ-002-ACT-05 | 2026-07-15 | Contractor | CON-001 | Civil Structure Contract | VEN-007 | 1 | Contract | 72524.02 | 78331.43 | 14099.66 | 92431.09 | Paid | Low
EXP-01761 | PRJ-002 | PRJ-002-ACT-05 | 2026-07-15 | Contractor | CON-004 | Finishing Contract | VEN-002 | 1 | Contract | 173258.26 | 184372.04 | 33186.97 | 217559.01 | Paid | Low
EXP-01762 | PRJ-002 | PRJ-002-ACT-09 | 2026-07-15 | Material | MAT-006 | Electrical Cable | VEN-003 | 14.04 | Meter | 1228.07 | 1307.06 | 235.27 | 1542.33 | Paid | High
EXP-01763 | PRJ-002 | PRJ-002-ACT-09 | 2026-07-15 | Contractor | CON-004 | Finishing Contract | VEN-011 | 1 | Contract | 432912.56 | 440155.58 | 79228 | 519383.58 | Paid | Low
EXP-01764 | PRJ-002 | PRJ-002-ACT-03 | 2026-07-15 | Labour | LAB-006 | Painter | VEN-003 | 31 | Worker | 36262.68 | 36860.35 | 6634.86 | 43495.21 | Paid | Medium
EXP-01765 | PRJ-002 | PRJ-002-ACT-01 | 2026-07-15 | Other | OTH-001 | Transport | VEN-002 | 1 | Lot | 12802.12 | 13670.89 | 2460.76 | 16131.65 | Paid | Low
EXP-01766 | PRJ-002 | PRJ-002-ACT-03 | 2026-07-15 | Material | MAT-001 | Cement | VEN-011 | 7.33 | Bag | 4287.1 | 4071.47 | 732.86 | 4804.33 | Paid | Low
EXP-01767 | PRJ-002 | PRJ-002-ACT-05 | 2026-07-20 | Material | MAT-007 | PVC Pipe | VEN-007 | 8.56 | Meter | 921.74 | 934.98 | 168.3 | 1103.28 | Paid | Low
EXP-01768 | PRJ-002 | PRJ-002-ACT-03 | 2026-07-20 | Material | MAT-002 | Steel | VEN-011 | 1.39 | Ton | 78621.7 | 81259.48 | 14626.71 | 95886.19 | Paid | Medium
EXP-01769 | PRJ-002 | PRJ-002-ACT-05 | 2026-07-20 | Equipment | EQ-002 | Excavator | VEN-002 | 2 | Day | 28055.61 | 30261.85 | 5447.13 | 35708.98 | Paid | Medium
EXP-01770 | PRJ-002 | PRJ-002-ACT-06 | 2026-07-20 | Labour | LAB-003 | Carpenter | VEN-003 | 16 | Worker | 11655.71 | 11625.85 | 2092.65 | 13718.5 | Paid | Medium
EXP-01771 | PRJ-002 | PRJ-002-ACT-03 | 2026-07-20 | Other | OTH-001 | Site Office | VEN-011 | 1 | Lot | 44182.08 | 43045.46 | 7748.18 | 50793.64 | Paid | Medium
EXP-01772 | PRJ-002 | PRJ-002-ACT-06 | 2026-07-20 | Material | MAT-009 | Paint | VEN-002 | 14.8 | Litre | 2915.45 | 2832.59 | 509.87 | 3342.46 | Paid | Medium
EXP-01773 | PRJ-002 | PRJ-002-ACT-04 | 2026-07-20 | Material | MAT-002 | Steel | VEN-011 | 3.15 | Ton | 178369.39 | 188628.5 | 33953.13 | 222581.63 | Paid | Low
EXP-01774 | PRJ-002 | PRJ-002-ACT-10 | 2026-07-20 | Equipment | EQ-004 | Scaffolding | VEN-002 | 3 | Day | 7529.32 | 8132.77 | 1463.9 | 9596.67 | Partially Paid | Low
EXP-01775 | PRJ-002 | PRJ-002-ACT-04 | 2026-07-25 | Material | MAT-001 | Cement | VEN-007 | 4.97 | Bag | 2665.03 | 2563.88 | 461.5 | 3025.38 | Paid | Medium
EXP-01776 | PRJ-002 | PRJ-002-ACT-06 | 2026-07-25 | Contractor | CON-003 | Plumbing Contract | VEN-011 | 1 | Contract | 211796.98 | 203778.79 | 36680.18 | 240458.97 | Paid | Low
EXP-01777 | PRJ-002 | PRJ-002-ACT-05 | 2026-07-25 | Other | OTH-001 | Site Office | VEN-007 | 1 | Lot | 68353.43 | 67367.71 | 12126.19 | 79493.9 | Paid | Medium
EXP-01778 | PRJ-002 | PRJ-002-ACT-09 | 2026-07-25 | Material | MAT-007 | PVC Pipe | VEN-003 | 6.87 | Meter | 824.75 | 854 | 153.72 | 1007.72 | Partially Paid | Medium
EXP-01779 | PRJ-002 | PRJ-002-ACT-01 | 2026-07-25 | Material | MAT-005 | Bricks | VEN-003 | 16.83 | Piece | 150.1 | 162.51 | 29.25 | 191.76 | Pending | Low
EXP-01780 | PRJ-002 | PRJ-002-ACT-03 | 2026-07-25 | Material | MAT-001 | Cement | VEN-011 | 6.41 | Bag | 3311 | 3235.12 | 582.32 | 3817.44 | Paid | Low
EXP-01781 | PRJ-002 | PRJ-002-ACT-10 | 2026-07-25 | Labour | LAB-004 | Electrician | VEN-002 | 15 | Worker | 16670.39 | 17444.14 | 3139.95 | 20584.09 | Paid | Medium
EXP-01782 | PRJ-002 | PRJ-002-ACT-03 | 2026-07-25 | Equipment | EQ-003 | Concrete Mixer | VEN-003 | 6 | Day | 30232.9 | 28432.9 | 5117.92 | 33550.82 | Paid | Low
EXP-01783 | PRJ-002 | PRJ-002-ACT-10 | 2026-07-30 | Material | MAT-003 | Sand | VEN-003 | 10.69 | Ton | 20400.45 | 21220.38 | 3819.67 | 25040.05 | Paid | High
EXP-01784 | PRJ-002 | PRJ-002-ACT-07 | 2026-07-30 | Material | MAT-008 | Tiles | VEN-007 | 10.21 | Sq Ft | 678.97 | 694.39 | 124.99 | 819.38 | Partially Paid | Low
EXP-01785 | PRJ-002 | PRJ-002-ACT-09 | 2026-07-30 | Contractor | CON-002 | Electrical Contract | VEN-003 | 1 | Contract | 194620.22 | 182626.16 | 32872.71 | 215498.87 | Paid | Low
EXP-01786 | PRJ-002 | PRJ-002-ACT-10 | 2026-07-30 | Labour | LAB-001 | Mason | VEN-011 | 17 | Worker | 12286.55 | 11458.72 | 2062.57 | 13521.29 | Paid | Medium
EXP-01787 | PRJ-002 | PRJ-002-ACT-10 | 2026-07-30 | Other | OTH-001 | Permit | VEN-002 | 1 | Lot | 55559.82 | 57049.03 | 10268.83 | 67317.86 | Paid | Medium
EXP-01788 | PRJ-002 | PRJ-002-ACT-08 | 2026-07-30 | Labour | LAB-002 | Helper | VEN-007 | 33 | Worker | 48237.92 | 47666.15 | 8579.91 | 56246.06 | Paid | Medium
EXP-01789 | PRJ-002 | PRJ-002-ACT-07 | 2026-08-04 | Labour | LAB-006 | Painter | VEN-003 | 20 | Worker | 24059.95 | 23659.99 | 4258.8 | 27918.79 | Paid | Low
EXP-01790 | PRJ-002 | PRJ-002-ACT-10 | 2026-08-04 | Material | MAT-009 | Paint | VEN-003 | 5.17 | Litre | 1157.58 | 1109.92 | 199.79 | 1309.71 | Paid | Low
EXP-01791 | PRJ-002 | PRJ-002-ACT-01 | 2026-08-04 | Labour | LAB-001 | Mason | VEN-002 | 13 | Worker | 10952.32 | 10734.45 | 1932.2 | 12666.65 | Paid | Low
EXP-01792 | PRJ-002 | PRJ-002-ACT-06 | 2026-08-04 | Material | MAT-004 | Aggregate | VEN-002 | 26.45 | Ton | 40246.06 | 41815.99 | 7526.88 | 49342.87 | Paid | Low
EXP-01793 | PRJ-002 | PRJ-002-ACT-05 | 2026-08-04 | Material | MAT-005 | Bricks | VEN-003 | 20.89 | Piece | 203.1 | 206.2 | 37.12 | 243.32 | Pending | Medium
EXP-01794 | PRJ-002 | PRJ-002-ACT-03 | 2026-08-04 | Other | OTH-001 | Site Office | VEN-002 | 1 | Lot | 49169.16 | 46235.39 | 8322.37 | 54557.76 | Paid | Low
EXP-01795 | PRJ-002 | PRJ-002-ACT-06 | 2026-08-04 | Labour | LAB-005 | Plumber | VEN-002 | 15 | Worker | 25085.94 | 24662.44 | 4439.24 | 29101.68 | Paid | Medium
EXP-01796 | PRJ-002 | PRJ-002-ACT-03 | 2026-08-04 | Material | MAT-004 | Aggregate | VEN-002 | 15.01 | Ton | 21383.38 | 20402.05 | 3672.37 | 24074.42 | Pending | Low
EXP-01797 | PRJ-002 | PRJ-002-ACT-06 | 2026-08-04 | Material | MAT-004 | Aggregate | VEN-011 | 2.21 | Ton | 2775.67 | 2926.34 | 526.74 | 3453.08 | Paid | Medium
EXP-01798 | PRJ-002 | PRJ-002-ACT-08 | 2026-08-09 | Labour | LAB-004 | Electrician | VEN-011 | 17 | Worker | 25361.72 | 25109.81 | 4519.77 | 29629.58 | Pending | Medium
EXP-01799 | PRJ-002 | PRJ-002-ACT-02 | 2026-08-09 | Contractor | CON-004 | Finishing Contract | VEN-003 | 1 | Contract | 130279.83 | 133618.96 | 24051.41 | 157670.37 | Paid | Low
EXP-01800 | PRJ-002 | PRJ-002-ACT-03 | 2026-08-09 | Material | MAT-005 | Bricks | VEN-003 | 11.85 | Piece | 97.28 | 96.63 | 17.39 | 114.02 | Paid | Low
EXP-01801 | PRJ-002 | PRJ-002-ACT-06 | 2026-08-09 | Material | MAT-002 | Steel | VEN-002 | 21.58 | Ton | 1122438.44 | 1193900.96 | 214902.17 | 1408803.13 | Paid | Low
EXP-01802 | PRJ-002 | PRJ-002-ACT-08 | 2026-08-09 | Material | MAT-007 | PVC Pipe | VEN-011 | 5.36 | Meter | 649.76 | 673.47 | 121.22 | 794.69 | Paid | Low
EXP-01803 | PRJ-002 | PRJ-002-ACT-02 | 2026-08-09 | Labour | LAB-002 | Helper | VEN-011 | 16 | Worker | 15607.4 | 16082.73 | 2894.89 | 18977.62 | Paid | Medium
EXP-01804 | PRJ-002 | PRJ-002-ACT-02 | 2026-08-14 | Contractor | CON-002 | Electrical Contract | VEN-011 | 1 | Contract | 275148.51 | 276509.16 | 49771.65 | 326280.81 | Paid | Medium
EXP-01805 | PRJ-002 | PRJ-002-ACT-10 | 2026-08-14 | Equipment | EQ-004 | Scaffolding | VEN-002 | 1 | Day | 2500.47 | 2713.27 | 488.39 | 3201.66 | Paid | Low
EXP-01806 | PRJ-002 | PRJ-002-ACT-09 | 2026-08-14 | Contractor | CON-003 | Plumbing Contract | VEN-003 | 1 | Contract | 397538.24 | 387144.51 | 69686.01 | 456830.52 | Paid | Medium
EXP-01807 | PRJ-002 | PRJ-002-ACT-02 | 2026-08-14 | Equipment | EQ-003 | Concrete Mixer | VEN-002 | 1 | Day | 4727.54 | 4857.67 | 874.38 | 5732.05 | Pending | Low
EXP-01808 | PRJ-002 | PRJ-002-ACT-05 | 2026-08-14 | Material | MAT-008 | Tiles | VEN-011 | 11.67 | Sq Ft | 876.07 | 947.24 | 170.5 | 1117.74 | Paid | Medium
EXP-01809 | PRJ-002 | PRJ-002-ACT-09 | 2026-08-14 | Contractor | CON-002 | Electrical Contract | VEN-007 | 1 | Contract | 357477.74 | 385889.11 | 69460.04 | 455349.15 | Pending | Medium
EXP-01810 | PRJ-002 | PRJ-002-ACT-10 | 2026-08-14 | Other | OTH-001 | Site Office | VEN-002 | 1 | Lot | 42380.33 | 39418.74 | 7095.37 | 46514.11 | Paid | Medium
EXP-01811 | PRJ-002 | PRJ-002-ACT-10 | 2026-08-14 | Labour | LAB-002 | Helper | VEN-002 | 7 | Worker | 10384.96 | 11097.41 | 1997.53 | 13094.94 | Paid | Low
EXP-01812 | PRJ-002 | PRJ-002-ACT-08 | 2026-08-14 | Contractor | CON-003 | Plumbing Contract | VEN-003 | 1 | Contract | 131618.47 | 130096.14 | 23417.31 | 153513.45 | Pending | Low
EXP-01813 | PRJ-002 | PRJ-002-ACT-03 | 2026-08-19 | Material | MAT-009 | Paint | VEN-007 | 9.44 | Litre | 1784.92 | 1766.51 | 317.97 | 2084.48 | Paid | Medium
EXP-01814 | PRJ-002 | PRJ-002-ACT-01 | 2026-08-19 | Labour | LAB-003 | Carpenter | VEN-002 | 17 | Worker | 21385.59 | 21251.5 | 3825.27 | 25076.77 | Paid | Low
EXP-01815 | PRJ-002 | PRJ-002-ACT-08 | 2026-08-19 | Material | MAT-005 | Bricks | VEN-003 | 18.66 | Piece | 169.84 | 178.26 | 32.09 | 210.35 | Partially Paid | High
EXP-01816 | PRJ-002 | PRJ-002-ACT-04 | 2026-08-19 | Other | OTH-001 | Transport | VEN-011 | 1 | Lot | 71980.19 | 67822.77 | 12208.1 | 80030.87 | Paid | Low
EXP-01817 | PRJ-002 | PRJ-002-ACT-09 | 2026-08-19 | Contractor | CON-003 | Plumbing Contract | VEN-003 | 1 | Contract | 109795.1 | 110847.65 | 19952.58 | 130800.23 | Paid | Low
EXP-01818 | PRJ-002 | PRJ-002-ACT-10 | 2026-08-19 | Labour | LAB-003 | Carpenter | VEN-011 | 34 | Worker | 39106.26 | 38896.06 | 7001.29 | 45897.35 | Pending | Low
EXP-01819 | PRJ-002 | PRJ-002-ACT-10 | 2026-08-19 | Material | MAT-002 | Steel | VEN-003 | 34.01 | Ton | 1831528.6 | 1934841.6 | 348271.49 | 2283113.09 | Partially Paid | Low
EXP-01820 | PRJ-002 | PRJ-002-ACT-09 | 2026-08-19 | Labour | LAB-004 | Electrician | VEN-003 | 25 | Worker | 40374.01 | 38400.09 | 6912.02 | 45312.11 | Paid | Medium
EXP-01821 | PRJ-002 | PRJ-002-ACT-08 | 2026-08-19 | Labour | LAB-002 | Helper | VEN-007 | 12 | Worker | 11786.44 | 10994.94 | 1979.09 | 12974.03 | Paid | Low
EXP-01822 | PRJ-002 | PRJ-002-ACT-01 | 2026-08-24 | Equipment | EQ-001 | Crane | VEN-007 | 7 | Day | 138090.31 | 131137.09 | 23604.68 | 154741.77 | Paid | Low
EXP-01823 | PRJ-002 | PRJ-002-ACT-03 | 2026-08-24 | Material | MAT-010 | Glass | VEN-002 | 11.56 | Sq Ft | 1926.77 | 1868.26 | 336.29 | 2204.55 | Paid | Low
EXP-01824 | PRJ-002 | PRJ-002-ACT-06 | 2026-08-24 | Labour | LAB-002 | Helper | VEN-002 | 19 | Worker | 21826.12 | 21832.37 | 3929.83 | 25762.2 | Partially Paid | Medium
EXP-01825 | PRJ-002 | PRJ-002-ACT-01 | 2026-08-24 | Labour | LAB-004 | Electrician | VEN-007 | 12 | Worker | 13579.17 | 13253.06 | 2385.55 | 15638.61 | Paid | Medium
EXP-01826 | PRJ-002 | PRJ-002-ACT-03 | 2026-08-24 | Equipment | EQ-004 | Scaffolding | VEN-011 | 4 | Day | 10032.79 | 10755.88 | 1936.06 | 12691.94 | Paid | Low
EXP-01827 | PRJ-002 | PRJ-002-ACT-07 | 2026-08-24 | Labour | LAB-003 | Carpenter | VEN-011 | 33 | Worker | 54322.94 | 55109.08 | 9919.63 | 65028.71 | Paid | Low
EXP-01828 | PRJ-002 | PRJ-002-ACT-02 | 2026-08-24 | Material | MAT-005 | Bricks | VEN-007 | 6.68 | Piece | 70.44 | 67.12 | 12.08 | 79.2 | Paid | Low
EXP-01829 | PRJ-002 | PRJ-002-ACT-04 | 2026-08-29 | Material | MAT-007 | PVC Pipe | VEN-003 | 30.6 | Meter | 3512.41 | 3278.91 | 590.2 | 3869.11 | Pending | Low
EXP-01830 | PRJ-002 | PRJ-002-ACT-04 | 2026-08-29 | Material | MAT-004 | Aggregate | VEN-003 | 19.48 | Ton | 29709.44 | 31783.94 | 5721.11 | 37505.05 | Paid | Medium
EXP-01831 | PRJ-002 | PRJ-002-ACT-05 | 2026-08-29 | Material | MAT-010 | Glass | VEN-003 | 15.75 | Sq Ft | 2286.16 | 2172.45 | 391.04 | 2563.49 | Paid | Low
EXP-01832 | PRJ-002 | PRJ-002-ACT-09 | 2026-08-29 | Contractor | CON-003 | Plumbing Contract | VEN-007 | 1 | Contract | 465208.51 | 445971.09 | 80274.8 | 526245.89 | Pending | Medium
EXP-01833 | PRJ-002 | PRJ-002-ACT-08 | 2026-08-29 | Contractor | CON-001 | Civil Structure Contract | VEN-011 | 1 | Contract | 289599.71 | 271191.75 | 48814.51 | 320006.26 | Partially Paid | Medium
EXP-01834 | PRJ-002 | PRJ-002-ACT-05 | 2026-08-29 | Equipment | EQ-001 | Crane | VEN-011 | 6 | Day | 119027.97 | 117410.15 | 21133.83 | 138543.98 | Paid | Low
EXP-01835 | PRJ-002 | PRJ-002-ACT-07 | 2026-08-29 | Contractor | CON-003 | Plumbing Contract | VEN-002 | 1 | Contract | 405883.62 | 420141.13 | 75625.4 | 495766.53 | Paid | Medium
EXP-01836 | PRJ-002 | PRJ-002-ACT-07 | 2026-08-29 | Contractor | CON-004 | Finishing Contract | VEN-011 | 1 | Contract | 311736.24 | 311533.12 | 56075.96 | 367609.08 | Paid | High
EXP-01837 | PRJ-002 | PRJ-002-ACT-07 | 2026-08-29 | Material | MAT-004 | Aggregate | VEN-011 | 3.26 | Ton | 5556.85 | 5474.93 | 985.49 | 6460.42 | Paid | Low
EXP-01838 | PRJ-002 | PRJ-002-ACT-07 | 2026-09-03 | Material | MAT-009 | Paint | VEN-002 | 19.23 | Litre | 3988.44 | 4172.18 | 750.99 | 4923.17 | Paid | Medium
EXP-01839 | PRJ-002 | PRJ-002-ACT-05 | 2026-09-03 | Equipment | EQ-002 | Excavator | VEN-003 | 3 | Day | 42305.03 | 39457.22 | 7102.3 | 46559.52 | Paid | Medium
EXP-01840 | PRJ-002 | PRJ-002-ACT-07 | 2026-09-03 | Material | MAT-003 | Sand | VEN-002 | 3.27 | Ton | 5720.42 | 5872.17 | 1056.99 | 6929.16 | Paid | Low
EXP-01841 | PRJ-002 | PRJ-002-ACT-02 | 2026-09-03 | Labour | LAB-003 | Carpenter | VEN-002 | 19 | Worker | 21304.24 | 21805.61 | 3925.01 | 25730.62 | Paid | Medium
EXP-01842 | PRJ-002 | PRJ-002-ACT-10 | 2026-09-03 | Contractor | CON-001 | Civil Structure Contract | VEN-011 | 1 | Contract | 191483.88 | 177682.73 | 31982.89 | 209665.62 | Partially Paid | High
EXP-01843 | PRJ-002 | PRJ-002-ACT-01 | 2026-09-03 | Material | MAT-005 | Bricks | VEN-007 | 8.54 | Piece | 75.85 | 80.06 | 14.41 | 94.47 | Partially Paid | Low
EXP-01844 | PRJ-002 | PRJ-002-ACT-09 | 2026-09-03 | Material | MAT-004 | Aggregate | VEN-002 | 17.09 | Ton | 30521.18 | 29241.94 | 5263.55 | 34505.49 | Paid | Low
EXP-01845 | PRJ-002 | PRJ-002-ACT-05 | 2026-09-03 | Other | OTH-001 | Miscellaneous | VEN-002 | 1 | Lot | 73939.88 | 72946.64 | 13130.4 | 86077.04 | Paid | Medium
EXP-01846 | PRJ-002 | PRJ-002-ACT-06 | 2026-09-08 | Material | MAT-010 | Glass | VEN-011 | 15.93 | Sq Ft | 2513.06 | 2695.25 | 485.14 | 3180.39 | Paid | Low
EXP-01847 | PRJ-002 | PRJ-002-ACT-01 | 2026-09-08 | Material | MAT-002 | Steel | VEN-002 | 6.2 | Ton | 435737.72 | 404266.58 | 72767.98 | 477034.56 | Partially Paid | Medium
EXP-01848 | PRJ-002 | PRJ-002-ACT-08 | 2026-09-08 | Material | MAT-005 | Bricks | VEN-002 | 8.17 | Piece | 84.91 | 81.69 | 14.7 | 96.39 | Paid | Low
EXP-01849 | PRJ-002 | PRJ-002-ACT-09 | 2026-09-08 | Equipment | EQ-002 | Excavator | VEN-002 | 3 | Day | 40516.94 | 41540.48 | 7477.29 | 49017.77 | Paid | Medium
EXP-01850 | PRJ-002 | PRJ-002-ACT-01 | 2026-09-08 | Contractor | CON-003 | Plumbing Contract | VEN-007 | 1 | Contract | 186254.86 | 180772.59 | 32539.07 | 213311.66 | Partially Paid | High
EXP-01851 | PRJ-002 | PRJ-002-ACT-09 | 2026-09-08 | Material | MAT-001 | Cement | VEN-002 | 6.7 | Bag | 3148.76 | 3203 | 576.54 | 3779.54 | Paid | Low
EXP-01852 | PRJ-002 | PRJ-002-ACT-04 | 2026-09-08 | Labour | LAB-005 | Plumber | VEN-002 | 25 | Worker | 36029.29 | 37163.78 | 6689.48 | 43853.26 | Paid | Low
EXP-01853 | PRJ-002 | PRJ-002-ACT-03 | 2026-09-08 | Labour | LAB-005 | Plumber | VEN-011 | 31 | Worker | 49229.81 | 49609.71 | 8929.75 | 58539.46 | Paid | High
EXP-01854 | PRJ-002 | PRJ-002-ACT-02 | 2026-09-13 | Labour | LAB-001 | Mason | VEN-002 | 16 | Worker | 21682.07 | 22270.52 | 4008.69 | 26279.21 | Partially Paid | Medium
EXP-01855 | PRJ-002 | PRJ-002-ACT-06 | 2026-09-13 | Material | MAT-002 | Steel | VEN-003 | 10.95 | Ton | 651674.03 | 649090.42 | 116836.28 | 765926.7 | Paid | Medium
EXP-01856 | PRJ-002 | PRJ-002-ACT-01 | 2026-09-13 | Equipment | EQ-002 | Excavator | VEN-011 | 5 | Day | 77772.2 | 72186.03 | 12993.49 | 85179.52 | Paid | Low
EXP-01857 | PRJ-002 | PRJ-002-ACT-06 | 2026-09-13 | Labour | LAB-001 | Mason | VEN-007 | 27 | Worker | 37151.85 | 39951.86 | 7191.33 | 47143.19 | Paid | Medium
EXP-01858 | PRJ-002 | PRJ-002-ACT-02 | 2026-09-13 | Labour | LAB-004 | Electrician | VEN-003 | 6 | Worker | 10471.74 | 10036.07 | 1806.49 | 11842.56 | Paid | Low
EXP-01859 | PRJ-002 | PRJ-002-ACT-06 | 2026-09-13 | Contractor | CON-003 | Plumbing Contract | VEN-011 | 1 | Contract | 197928.27 | 203285.63 | 36591.41 | 239877.04 | Pending | Low
EXP-01860 | PRJ-002 | PRJ-002-ACT-06 | 2026-09-18 | Material | MAT-007 | PVC Pipe | VEN-003 | 26.06 | Meter | 3222.05 | 2991.11 | 538.4 | 3529.51 | Paid | Medium
EXP-01861 | PRJ-002 | PRJ-002-ACT-08 | 2026-09-18 | Material | MAT-010 | Glass | VEN-011 | 6.63 | Sq Ft | 1213.91 | 1180.47 | 212.48 | 1392.95 | Paid | Low
EXP-01862 | PRJ-002 | PRJ-002-ACT-08 | 2026-09-18 | Material | MAT-008 | Tiles | VEN-002 | 6.32 | Sq Ft | 400.38 | 415.56 | 74.8 | 490.36 | Paid | Medium
EXP-01863 | PRJ-002 | PRJ-002-ACT-07 | 2026-09-18 | Contractor | CON-003 | Plumbing Contract | VEN-003 | 1 | Contract | 334812.11 | 340764.11 | 61337.54 | 402101.65 | Partially Paid | Medium
EXP-01864 | PRJ-002 | PRJ-002-ACT-04 | 2026-09-18 | Equipment | EQ-001 | Crane | VEN-011 | 7 | Day | 117473.54 | 119750.77 | 21555.14 | 141305.91 | Paid | Low
EXP-01865 | PRJ-002 | PRJ-002-ACT-03 | 2026-09-18 | Contractor | CON-001 | Civil Structure Contract | VEN-011 | 1 | Contract | 183070.37 | 197049.79 | 35468.96 | 232518.75 | Partially Paid | Low
EXP-01866 | PRJ-002 | PRJ-002-ACT-06 | 2026-09-18 | Equipment | EQ-004 | Scaffolding | VEN-002 | 7 | Day | 16927.28 | 16417.62 | 2955.17 | 19372.79 | Paid | Low
EXP-01867 | PRJ-002 | PRJ-002-ACT-01 | 2026-09-18 | Material | MAT-008 | Tiles | VEN-003 | 5.49 | Sq Ft | 339.09 | 352.16 | 63.39 | 415.55 | Paid | Medium
EXP-01868 | PRJ-002 | PRJ-002-ACT-05 | 2026-09-18 | Other | OTH-001 | Transport | VEN-002 | 1 | Lot | 52316.71 | 53046.62 | 9548.39 | 62595.01 | Paid | High
EXP-01869 | PRJ-002 | PRJ-002-ACT-07 | 2026-09-18 | Material | MAT-008 | Tiles | VEN-011 | 9.13 | Sq Ft | 675.3 | 681.52 | 122.67 | 804.19 | Paid | High
EXP-01870 | PRJ-002 | PRJ-002-ACT-10 | 2026-09-23 | Labour | LAB-002 | Helper | VEN-003 | 19 | Worker | 15669.53 | 15537.68 | 2796.78 | 18334.46 | Paid | Low
EXP-01871 | PRJ-002 | PRJ-002-ACT-04 | 2026-09-23 | Labour | LAB-005 | Plumber | VEN-011 | 4 | Worker | 3154.88 | 2973.89 | 535.3 | 3509.19 | Paid | Medium
EXP-01872 | PRJ-002 | PRJ-002-ACT-07 | 2026-09-23 | Contractor | CON-003 | Plumbing Contract | VEN-002 | 1 | Contract | 250991.6 | 271765.33 | 48917.76 | 320683.09 | Paid | Low
EXP-01873 | PRJ-002 | PRJ-002-ACT-07 | 2026-09-23 | Contractor | CON-003 | Plumbing Contract | VEN-007 | 1 | Contract | 95855.25 | 93235.3 | 16782.35 | 110017.65 | Paid | High
EXP-01874 | PRJ-002 | PRJ-002-ACT-07 | 2026-09-23 | Material | MAT-003 | Sand | VEN-003 | 6.53 | Ton | 13092.39 | 12836.09 | 2310.5 | 15146.59 | Paid | Low
EXP-01875 | PRJ-002 | PRJ-002-ACT-08 | 2026-09-23 | Material | MAT-010 | Glass | VEN-003 | 36.25 | Sq Ft | 5441.6 | 5573.11 | 1003.16 | 6576.27 | Paid | Low
EXP-01876 | PRJ-002 | PRJ-002-ACT-10 | 2026-09-23 | Material | MAT-003 | Sand | VEN-007 | 30.01 | Ton | 62916.91 | 61577.47 | 11083.94 | 72661.41 | Paid | Low
EXP-01877 | PRJ-002 | PRJ-002-ACT-01 | 2026-09-23 | Labour | LAB-003 | Carpenter | VEN-011 | 5 | Worker | 7683.03 | 7810.1 | 1405.82 | 9215.92 | Pending | Low
EXP-01878 | PRJ-002 | PRJ-002-ACT-05 | 2026-09-23 | Material | MAT-008 | Tiles | VEN-002 | 10.9 | Sq Ft | 879.17 | 822.49 | 148.05 | 970.54 | Pending | High
EXP-01879 | PRJ-002 | PRJ-002-ACT-09 | 2026-09-28 | Material | MAT-007 | PVC Pipe | VEN-003 | 20.77 | Meter | 2464.37 | 2351.41 | 423.25 | 2774.66 | Paid | Low
EXP-01880 | PRJ-002 | PRJ-002-ACT-01 | 2026-09-28 | Material | MAT-009 | Paint | VEN-003 | 23.53 | Litre | 4534.72 | 4833.72 | 870.07 | 5703.79 | Paid | Low
EXP-01881 | PRJ-002 | PRJ-002-ACT-08 | 2026-09-28 | Labour | LAB-003 | Carpenter | VEN-007 | 12 | Worker | 10585.22 | 10540.02 | 1897.2 | 12437.22 | Paid | Low
EXP-01882 | PRJ-002 | PRJ-002-ACT-10 | 2026-09-28 | Contractor | CON-001 | Civil Structure Contract | VEN-003 | 1 | Contract | 252193.41 | 261617 | 47091.06 | 308708.06 | Paid | Low
EXP-01883 | PRJ-002 | PRJ-002-ACT-05 | 2026-09-28 | Labour | LAB-003 | Carpenter | VEN-003 | 10 | Worker | 12440.11 | 12336.94 | 2220.65 | 14557.59 | Paid | Low
EXP-01884 | PRJ-002 | PRJ-002-ACT-09 | 2026-09-28 | Material | MAT-010 | Glass | VEN-002 | 12.1 | Sq Ft | 1937.82 | 1883.68 | 339.06 | 2222.74 | Pending | Medium
EXP-01885 | PRJ-002 | PRJ-002-ACT-04 | 2026-09-28 | Equipment | EQ-004 | Scaffolding | VEN-002 | 5 | Day | 14474.28 | 13489.59 | 2428.13 | 15917.72 | Partially Paid | Medium
EXP-01886 | PRJ-002 | PRJ-002-ACT-06 | 2026-09-28 | Labour | LAB-005 | Plumber | VEN-002 | 13 | Worker | 16375.1 | 16278.71 | 2930.17 | 19208.88 | Paid | Low
EXP-01887 | PRJ-002 | PRJ-002-ACT-07 | 2026-09-28 | Equipment | EQ-002 | Excavator | VEN-011 | 3 | Day | 40482.4 | 42343.22 | 7621.78 | 49965 | Pending | Low
EXP-01888 | PRJ-002 | PRJ-002-ACT-09 | 2026-09-28 | Contractor | CON-001 | Civil Structure Contract | VEN-007 | 1 | Contract | 405146.59 | 378480.47 | 68126.48 | 446606.95 | Paid | Low
EXP-01889 | PRJ-003 | PRJ-003-ACT-05 | 2024-07-01 | Material | MAT-006 | Electrical Cable | VEN-008 | 11.54 | Meter | 917.18 | 904.15 | 162.75 | 1066.9 | Paid | Low
EXP-01890 | PRJ-003 | PRJ-003-ACT-04 | 2024-07-01 | Material | MAT-009 | Paint | VEN-008 | 1 | Litre | 173.09 | 178.58 | 32.14 | 210.72 | Paid | Low
EXP-01891 | PRJ-003 | PRJ-003-ACT-08 | 2024-07-01 | Material | MAT-010 | Glass | VEN-010 | 7.05 | Sq Ft | 1263.99 | 1274.02 | 229.32 | 1503.34 | Paid | Low
EXP-01892 | PRJ-003 | PRJ-003-ACT-10 | 2024-07-01 | Material | MAT-003 | Sand | VEN-010 | 14.51 | Ton | 22961.49 | 23570.22 | 4242.64 | 27812.86 | Paid | Low
EXP-01893 | PRJ-003 | PRJ-003-ACT-05 | 2024-07-01 | Material | MAT-002 | Steel | VEN-010 | 15.14 | Ton | 846371.1 | 886737.43 | 159612.74 | 1046350.17 | Paid | Low
EXP-01894 | PRJ-003 | PRJ-003-ACT-02 | 2024-07-01 | Equipment | EQ-001 | Crane | VEN-010 | 1 | Day | 19420.42 | 19413.64 | 3494.46 | 22908.1 | Paid | Low
EXP-01895 | PRJ-003 | PRJ-003-ACT-01 | 2024-07-01 | Material | MAT-003 | Sand | VEN-010 | 11.5 | Ton | 19437.72 | 20020.47 | 3603.68 | 23624.15 | Paid | Low
EXP-01896 | PRJ-003 | PRJ-003-ACT-02 | 2024-07-01 | Material | MAT-001 | Cement | VEN-010 | 4.28 | Bag | 2065.85 | 2172.12 | 390.98 | 2563.1 | Paid | Low
EXP-01897 | PRJ-003 | PRJ-003-ACT-08 | 2024-07-01 | Equipment | EQ-003 | Concrete Mixer | VEN-001 | 5 | Day | 21755.64 | 20352.09 | 3663.38 | 24015.47 | Paid | Low
EXP-01898 | PRJ-003 | PRJ-003-ACT-05 | 2024-07-01 | Contractor | CON-004 | Finishing Contract | VEN-001 | 1 | Contract | 109883.08 | 102634.22 | 18474.16 | 121108.38 | Paid | Low
EXP-01899 | PRJ-003 | PRJ-003-ACT-09 | 2024-07-06 | Contractor | CON-002 | Electrical Contract | VEN-008 | 1 | Contract | 234144.13 | 250459.7 | 45082.75 | 295542.45 | Paid | Low
EXP-01900 | PRJ-003 | PRJ-003-ACT-02 | 2024-07-06 | Material | MAT-002 | Steel | VEN-005 | 7.62 | Ton | 517171.57 | 484660.23 | 87238.84 | 571899.07 | Paid | Low
EXP-01901 | PRJ-003 | PRJ-003-ACT-07 | 2024-07-06 | Material | MAT-008 | Tiles | VEN-001 | 2.45 | Sq Ft | 175.06 | 186.56 | 33.58 | 220.14 | Pending | Low
EXP-01902 | PRJ-003 | PRJ-003-ACT-02 | 2024-07-06 | Contractor | CON-004 | Finishing Contract | VEN-008 | 1 | Contract | 124734.14 | 119371.53 | 21486.88 | 140858.41 | Paid | Medium
EXP-01903 | PRJ-003 | PRJ-003-ACT-06 | 2024-07-06 | Labour | LAB-005 | Plumber | VEN-010 | 10 | Worker | 12677.03 | 12653.73 | 2277.67 | 14931.4 | Paid | High
EXP-01904 | PRJ-003 | PRJ-003-ACT-06 | 2024-07-06 | Labour | LAB-005 | Plumber | VEN-005 | 28 | Worker | 46604.13 | 47469.74 | 8544.55 | 56014.29 | Partially Paid | Medium
EXP-01905 | PRJ-003 | PRJ-003-ACT-05 | 2024-07-06 | Contractor | CON-001 | Civil Structure Contract | VEN-010 | 1 | Contract | 221447.06 | 212575.65 | 38263.62 | 250839.27 | Paid | Low
EXP-01906 | PRJ-003 | PRJ-003-ACT-06 | 2024-07-06 | Material | MAT-004 | Aggregate | VEN-008 | 11.76 | Ton | 18814.28 | 20276.84 | 3649.83 | 23926.67 | Paid | Low
EXP-01907 | PRJ-003 | PRJ-003-ACT-09 | 2024-07-06 | Material | MAT-004 | Aggregate | VEN-010 | 5.52 | Ton | 8800.4 | 8506.89 | 1531.24 | 10038.13 | Partially Paid | Medium
EXP-01908 | PRJ-003 | PRJ-003-ACT-08 | 2024-07-11 | Material | MAT-008 | Tiles | VEN-010 | 20.77 | Sq Ft | 1624.25 | 1734.19 | 312.15 | 2046.34 | Paid | Medium
EXP-01909 | PRJ-003 | PRJ-003-ACT-01 | 2024-07-11 | Labour | LAB-003 | Carpenter | VEN-001 | 29 | Worker | 42070.05 | 38954.87 | 7011.88 | 45966.75 | Paid | Low
EXP-01910 | PRJ-003 | PRJ-003-ACT-02 | 2024-07-11 | Material | MAT-010 | Glass | VEN-005 | 3.11 | Sq Ft | 547.08 | 526.76 | 94.82 | 621.58 | Paid | Low
EXP-01911 | PRJ-003 | PRJ-003-ACT-04 | 2024-07-11 | Other | OTH-001 | Permit | VEN-008 | 1 | Lot | 64531.88 | 68127.93 | 12263.03 | 80390.96 | Paid | Medium
EXP-01912 | PRJ-003 | PRJ-003-ACT-01 | 2024-07-11 | Labour | LAB-003 | Carpenter | VEN-001 | 11 | Worker | 13413.66 | 14094.53 | 2537.02 | 16631.55 | Paid | High
EXP-01913 | PRJ-003 | PRJ-003-ACT-10 | 2024-07-11 | Labour | LAB-006 | Painter | VEN-005 | 5 | Worker | 4693.45 | 4693.7 | 844.87 | 5538.57 | Paid | Medium
EXP-01914 | PRJ-003 | PRJ-003-ACT-07 | 2024-07-11 | Material | MAT-003 | Sand | VEN-008 | 10.6 | Ton | 18171.1 | 17686.93 | 3183.65 | 20870.58 | Pending | Medium
EXP-01915 | PRJ-003 | PRJ-003-ACT-03 | 2024-07-11 | Labour | LAB-006 | Painter | VEN-010 | 31 | Worker | 20697.69 | 22372.47 | 4027.04 | 26399.51 | Paid | Medium
EXP-01916 | PRJ-003 | PRJ-003-ACT-09 | 2024-07-11 | Labour | LAB-006 | Painter | VEN-001 | 18 | Worker | 18390.47 | 19378.76 | 3488.18 | 22866.94 | Partially Paid | Low
EXP-01917 | PRJ-003 | PRJ-003-ACT-10 | 2024-07-16 | Contractor | CON-002 | Electrical Contract | VEN-008 | 1 | Contract | 303548.32 | 317188.07 | 57093.85 | 374281.92 | Partially Paid | Low
EXP-01918 | PRJ-003 | PRJ-003-ACT-04 | 2024-07-16 | Equipment | EQ-002 | Excavator | VEN-008 | 7 | Day | 101350.64 | 105906.64 | 19063.2 | 124969.84 | Paid | Low
EXP-01919 | PRJ-003 | PRJ-003-ACT-02 | 2024-07-16 | Contractor | CON-003 | Plumbing Contract | VEN-008 | 1 | Contract | 78062.6 | 82573.1 | 14863.16 | 97436.26 | Paid | Medium
EXP-01920 | PRJ-003 | PRJ-003-ACT-02 | 2024-07-16 | Labour | LAB-001 | Mason | VEN-008 | 10 | Worker | 10576.24 | 10583.59 | 1905.05 | 12488.64 | Partially Paid | Medium
EXP-01921 | PRJ-003 | PRJ-003-ACT-03 | 2024-07-16 | Material | MAT-004 | Aggregate | VEN-005 | 20.49 | Ton | 25370.84 | 27515.47 | 4952.78 | 32468.25 | Paid | Low
EXP-01922 | PRJ-003 | PRJ-003-ACT-02 | 2024-07-16 | Labour | LAB-002 | Helper | VEN-010 | 16 | Worker | 23157.37 | 23203.89 | 4176.7 | 27380.59 | Paid | Low
EXP-01923 | PRJ-003 | PRJ-003-ACT-07 | 2024-07-16 | Labour | LAB-002 | Helper | VEN-001 | 17 | Worker | 15647.71 | 16491.29 | 2968.43 | 19459.72 | Partially Paid | Low
EXP-01924 | PRJ-003 | PRJ-003-ACT-08 | 2024-07-16 | Contractor | CON-004 | Finishing Contract | VEN-001 | 1 | Contract | 270069.24 | 252774.08 | 45499.33 | 298273.41 | Paid | Medium
EXP-01925 | PRJ-003 | PRJ-003-ACT-02 | 2024-07-16 | Material | MAT-008 | Tiles | VEN-008 | 8.09 | Sq Ft | 612.52 | 625.99 | 112.68 | 738.67 | Paid | Medium
EXP-01926 | PRJ-003 | PRJ-003-ACT-05 | 2024-07-21 | Labour | LAB-006 | Painter | VEN-008 | 30 | Worker | 52915.9 | 53772.99 | 9679.14 | 63452.13 | Paid | Medium
EXP-01927 | PRJ-003 | PRJ-003-ACT-02 | 2024-07-21 | Material | MAT-007 | PVC Pipe | VEN-001 | 3.94 | Meter | 530.4 | 510.45 | 91.88 | 602.33 | Partially Paid | Low
EXP-01928 | PRJ-003 | PRJ-003-ACT-06 | 2024-07-21 | Material | MAT-005 | Bricks | VEN-010 | 10.96 | Piece | 102.49 | 110.31 | 19.86 | 130.17 | Paid | Medium
EXP-01929 | PRJ-003 | PRJ-003-ACT-10 | 2024-07-21 | Material | MAT-001 | Cement | VEN-010 | 12.66 | Bag | 6208.24 | 6004.76 | 1080.86 | 7085.62 | Paid | Low
EXP-01930 | PRJ-003 | PRJ-003-ACT-08 | 2024-07-21 | Contractor | CON-003 | Plumbing Contract | VEN-005 | 1 | Contract | 341327.68 | 364023.23 | 65524.18 | 429547.41 | Paid | Low
EXP-01931 | PRJ-003 | PRJ-003-ACT-02 | 2024-07-21 | Material | MAT-002 | Steel | VEN-008 | 10.04 | Ton | 517003.96 | 550483.57 | 99087.04 | 649570.61 | Partially Paid | Low
EXP-01932 | PRJ-003 | PRJ-003-ACT-05 | 2024-07-21 | Equipment | EQ-004 | Scaffolding | VEN-001 | 6 | Day | 13402.1 | 13678.91 | 2462.2 | 16141.11 | Paid | Medium
EXP-01933 | PRJ-003 | PRJ-003-ACT-10 | 2024-07-21 | Equipment | EQ-003 | Concrete Mixer | VEN-001 | 4 | Day | 17763.61 | 17964.15 | 3233.55 | 21197.7 | Paid | Low
EXP-01934 | PRJ-003 | PRJ-003-ACT-08 | 2024-07-21 | Other | OTH-001 | Miscellaneous | VEN-001 | 1 | Lot | 27987.25 | 29770.05 | 5358.61 | 35128.66 | Paid | Medium
EXP-01935 | PRJ-003 | PRJ-003-ACT-02 | 2024-07-21 | Material | MAT-009 | Paint | VEN-008 | 5.96 | Litre | 1148.68 | 1104.62 | 198.83 | 1303.45 | Paid | High
EXP-01936 | PRJ-003 | PRJ-003-ACT-05 | 2024-07-26 | Material | MAT-007 | PVC Pipe | VEN-010 | 12.92 | Meter | 1271.78 | 1354.65 | 243.84 | 1598.49 | Paid | Medium
EXP-01937 | PRJ-003 | PRJ-003-ACT-01 | 2024-07-26 | Labour | LAB-002 | Helper | VEN-001 | 19 | Worker | 21645.15 | 21607.63 | 3889.37 | 25497 | Paid | Medium
EXP-01938 | PRJ-003 | PRJ-003-ACT-06 | 2024-07-26 | Other | OTH-001 | Miscellaneous | VEN-005 | 1 | Lot | 67876.1 | 63874.2 | 11497.36 | 75371.56 | Paid | Low
EXP-01939 | PRJ-003 | PRJ-003-ACT-06 | 2024-07-26 | Labour | LAB-004 | Electrician | VEN-010 | 21 | Worker | 22943.57 | 24132.94 | 4343.93 | 28476.87 | Paid | Low
EXP-01940 | PRJ-003 | PRJ-003-ACT-03 | 2024-07-26 | Contractor | CON-003 | Plumbing Contract | VEN-001 | 1 | Contract | 262877.42 | 279908.03 | 50383.45 | 330291.48 | Pending | Low
EXP-01941 | PRJ-003 | PRJ-003-ACT-05 | 2024-07-26 | Contractor | CON-002 | Electrical Contract | VEN-005 | 1 | Contract | 293287.7 | 277284.94 | 49911.29 | 327196.23 | Paid | Low
EXP-01942 | PRJ-003 | PRJ-003-ACT-09 | 2024-07-26 | Material | MAT-009 | Paint | VEN-001 | 19.53 | Litre | 4354.71 | 4584.42 | 825.2 | 5409.62 | Paid | High
EXP-01943 | PRJ-003 | PRJ-003-ACT-10 | 2024-07-31 | Other | OTH-001 | Safety | VEN-010 | 1 | Lot | 33596.95 | 33184.62 | 5973.23 | 39157.85 | Paid | Low
EXP-01944 | PRJ-003 | PRJ-003-ACT-06 | 2024-07-31 | Other | OTH-001 | Safety | VEN-005 | 1 | Lot | 75902.11 | 73405.09 | 13212.92 | 86618.01 | Paid | Low
EXP-01945 | PRJ-003 | PRJ-003-ACT-01 | 2024-07-31 | Contractor | CON-003 | Plumbing Contract | VEN-010 | 1 | Contract | 163618 | 176825.06 | 31828.51 | 208653.57 | Paid | Low
EXP-01946 | PRJ-003 | PRJ-003-ACT-02 | 2024-07-31 | Contractor | CON-002 | Electrical Contract | VEN-001 | 1 | Contract | 349793.02 | 368620.63 | 66351.71 | 434972.34 | Paid | Medium
EXP-01947 | PRJ-003 | PRJ-003-ACT-04 | 2024-07-31 | Equipment | EQ-004 | Scaffolding | VEN-005 | 5 | Day | 12686.43 | 12415.01 | 2234.7 | 14649.71 | Paid | Low
EXP-01948 | PRJ-003 | PRJ-003-ACT-03 | 2024-07-31 | Labour | LAB-006 | Painter | VEN-010 | 13 | Worker | 15413.39 | 14369.08 | 2586.43 | 16955.51 | Partially Paid | Low
EXP-01949 | PRJ-003 | PRJ-003-ACT-02 | 2024-07-31 | Contractor | CON-003 | Plumbing Contract | VEN-001 | 1 | Contract | 198014.72 | 208789.14 | 37582.05 | 246371.19 | Paid | Medium
EXP-01950 | PRJ-003 | PRJ-003-ACT-01 | 2024-07-31 | Material | MAT-010 | Glass | VEN-008 | 6.34 | Sq Ft | 922.74 | 888.78 | 159.98 | 1048.76 | Paid | Low
EXP-01951 | PRJ-003 | PRJ-003-ACT-05 | 2024-08-05 | Other | OTH-001 | Site Office | VEN-001 | 1 | Lot | 76069.78 | 72071.2 | 12972.82 | 85044.02 | Paid | Medium
EXP-01952 | PRJ-003 | PRJ-003-ACT-09 | 2024-08-05 | Material | MAT-004 | Aggregate | VEN-001 | 5.85 | Ton | 8557.34 | 9179.98 | 1652.4 | 10832.38 | Paid | High
EXP-01953 | PRJ-003 | PRJ-003-ACT-01 | 2024-08-05 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 147865.96 | 146986.5 | 26457.57 | 173444.07 | Paid | Low
EXP-01954 | PRJ-003 | PRJ-003-ACT-01 | 2024-08-05 | Equipment | EQ-002 | Excavator | VEN-001 | 3 | Day | 44656.04 | 42723.33 | 7690.2 | 50413.53 | Paid | Low
EXP-01955 | PRJ-003 | PRJ-003-ACT-01 | 2024-08-05 | Contractor | CON-002 | Electrical Contract | VEN-005 | 1 | Contract | 83118.91 | 82505.51 | 14850.99 | 97356.5 | Paid | Low
EXP-01956 | PRJ-003 | PRJ-003-ACT-01 | 2024-08-05 | Material | MAT-005 | Bricks | VEN-001 | 3.34 | Piece | 31.82 | 30.84 | 5.55 | 36.39 | Paid | Medium
EXP-01957 | PRJ-003 | PRJ-003-ACT-07 | 2024-08-10 | Material | MAT-008 | Tiles | VEN-010 | 7.98 | Sq Ft | 505.33 | 536.04 | 96.49 | 632.53 | Pending | Low
EXP-01958 | PRJ-003 | PRJ-003-ACT-03 | 2024-08-10 | Material | MAT-003 | Sand | VEN-005 | 8.65 | Ton | 14880.87 | 16140.79 | 2905.34 | 19046.13 | Paid | Medium
EXP-01959 | PRJ-003 | PRJ-003-ACT-06 | 2024-08-10 | Contractor | CON-002 | Electrical Contract | VEN-010 | 1 | Contract | 319569.96 | 299132.64 | 53843.88 | 352976.52 | Paid | Low
EXP-01960 | PRJ-003 | PRJ-003-ACT-04 | 2024-08-10 | Contractor | CON-001 | Civil Structure Contract | VEN-010 | 1 | Contract | 312035.53 | 289479.51 | 52106.31 | 341585.82 | Partially Paid | Low
EXP-01961 | PRJ-003 | PRJ-003-ACT-03 | 2024-08-10 | Equipment | EQ-001 | Crane | VEN-001 | 5 | Day | 93686.57 | 89523.97 | 16114.31 | 105638.28 | Paid | Medium
EXP-01962 | PRJ-003 | PRJ-003-ACT-10 | 2024-08-10 | Equipment | EQ-003 | Concrete Mixer | VEN-001 | 5 | Day | 23314.45 | 24416.96 | 4395.05 | 28812.01 | Paid | Medium
EXP-01963 | PRJ-003 | PRJ-003-ACT-09 | 2024-08-10 | Contractor | CON-003 | Plumbing Contract | VEN-008 | 1 | Contract | 435218.48 | 413445.95 | 74420.27 | 487866.22 | Paid | Low
EXP-01964 | PRJ-003 | PRJ-003-ACT-01 | 2024-08-10 | Material | MAT-001 | Cement | VEN-001 | 5.99 | Bag | 3632 | 3403.16 | 612.57 | 4015.73 | Paid | Low
EXP-01965 | PRJ-003 | PRJ-003-ACT-07 | 2024-08-15 | Labour | LAB-003 | Carpenter | VEN-005 | 4 | Worker | 5125.9 | 4895.34 | 881.16 | 5776.5 | Paid | Low
EXP-01966 | PRJ-003 | PRJ-003-ACT-10 | 2024-08-15 | Labour | LAB-003 | Carpenter | VEN-008 | 9 | Worker | 9417.81 | 9058.52 | 1630.53 | 10689.05 | Paid | Medium
EXP-01967 | PRJ-003 | PRJ-003-ACT-08 | 2024-08-15 | Material | MAT-003 | Sand | VEN-010 | 17.1 | Ton | 27227.14 | 29372.41 | 5287.03 | 34659.44 | Paid | Low
EXP-01968 | PRJ-003 | PRJ-003-ACT-03 | 2024-08-15 | Material | MAT-001 | Cement | VEN-005 | 15.26 | Bag | 9064.43 | 8970.85 | 1614.75 | 10585.6 | Paid | Low
EXP-01969 | PRJ-003 | PRJ-003-ACT-01 | 2024-08-15 | Contractor | CON-001 | Civil Structure Contract | VEN-010 | 1 | Contract | 448923.56 | 442167.06 | 79590.07 | 521757.13 | Paid | Low
EXP-01970 | PRJ-003 | PRJ-003-ACT-03 | 2024-08-15 | Material | MAT-008 | Tiles | VEN-010 | 4.43 | Sq Ft | 370.22 | 371.99 | 66.96 | 438.95 | Paid | Medium
EXP-01971 | PRJ-003 | PRJ-003-ACT-09 | 2024-08-20 | Contractor | CON-002 | Electrical Contract | VEN-008 | 1 | Contract | 242874 | 250430.36 | 45077.46 | 295507.82 | Paid | Low
EXP-01972 | PRJ-003 | PRJ-003-ACT-08 | 2024-08-20 | Labour | LAB-001 | Mason | VEN-005 | 29 | Worker | 33814.21 | 35554.01 | 6399.72 | 41953.73 | Paid | Medium
EXP-01973 | PRJ-003 | PRJ-003-ACT-04 | 2024-08-20 | Material | MAT-004 | Aggregate | VEN-005 | 12.27 | Ton | 17097.72 | 17681.05 | 3182.59 | 20863.64 | Partially Paid | Medium
EXP-01974 | PRJ-003 | PRJ-003-ACT-01 | 2024-08-20 | Contractor | CON-001 | Civil Structure Contract | VEN-005 | 1 | Contract | 435595.62 | 416223.64 | 74920.26 | 491143.9 | Paid | Low
EXP-01975 | PRJ-003 | PRJ-003-ACT-06 | 2024-08-20 | Equipment | EQ-001 | Crane | VEN-005 | 2 | Day | 37780.31 | 38752.22 | 6975.4 | 45727.62 | Paid | Medium
EXP-01976 | PRJ-003 | PRJ-003-ACT-09 | 2024-08-20 | Labour | LAB-002 | Helper | VEN-010 | 28 | Worker | 20190.77 | 21241.81 | 3823.53 | 25065.34 | Paid | Low
EXP-01977 | PRJ-003 | PRJ-003-ACT-08 | 2024-08-20 | Material | MAT-003 | Sand | VEN-005 | 6.56 | Ton | 12343.99 | 11950.85 | 2151.15 | 14102 | Paid | Medium
EXP-01978 | PRJ-003 | PRJ-003-ACT-08 | 2024-08-20 | Labour | LAB-005 | Plumber | VEN-001 | 34 | Worker | 45830.28 | 46378.99 | 8348.22 | 54727.21 | Partially Paid | Low
EXP-01979 | PRJ-003 | PRJ-003-ACT-10 | 2024-08-20 | Material | MAT-001 | Cement | VEN-008 | 12.71 | Bag | 6347.85 | 6369.56 | 1146.52 | 7516.08 | Paid | Low
EXP-01980 | PRJ-003 | PRJ-003-ACT-09 | 2024-08-25 | Material | MAT-001 | Cement | VEN-008 | 14.06 | Bag | 5950.28 | 6404.27 | 1152.77 | 7557.04 | Paid | Low
EXP-01981 | PRJ-003 | PRJ-003-ACT-09 | 2024-08-25 | Labour | LAB-004 | Electrician | VEN-001 | 11 | Worker | 12408.46 | 11753.83 | 2115.69 | 13869.52 | Paid | Low
EXP-01982 | PRJ-003 | PRJ-003-ACT-03 | 2024-08-25 | Contractor | CON-004 | Finishing Contract | VEN-008 | 1 | Contract | 250271.35 | 267957.41 | 48232.33 | 316189.74 | Paid | High
EXP-01983 | PRJ-003 | PRJ-003-ACT-06 | 2024-08-25 | Material | MAT-004 | Aggregate | VEN-005 | 16.64 | Ton | 27667.81 | 28642.58 | 5155.66 | 33798.24 | Paid | Medium
EXP-01984 | PRJ-003 | PRJ-003-ACT-03 | 2024-08-25 | Labour | LAB-001 | Mason | VEN-008 | 32 | Worker | 57383.3 | 55557.04 | 10000.27 | 65557.31 | Paid | Low
EXP-01985 | PRJ-003 | PRJ-003-ACT-01 | 2024-08-25 | Material | MAT-003 | Sand | VEN-008 | 9.66 | Ton | 19448.14 | 19676.93 | 3541.85 | 23218.78 | Paid | Low
EXP-01986 | PRJ-003 | PRJ-003-ACT-07 | 2024-08-30 | Contractor | CON-004 | Finishing Contract | VEN-008 | 1 | Contract | 146356.16 | 151065.3 | 27191.75 | 178257.05 | Paid | Low
EXP-01987 | PRJ-003 | PRJ-003-ACT-10 | 2024-08-30 | Contractor | CON-004 | Finishing Contract | VEN-010 | 1 | Contract | 154480.36 | 144011.2 | 25922.02 | 169933.22 | Paid | Medium
EXP-01988 | PRJ-003 | PRJ-003-ACT-05 | 2024-08-30 | Material | MAT-003 | Sand | VEN-010 | 6.32 | Ton | 11565.67 | 11633.93 | 2094.11 | 13728.04 | Paid | Medium
EXP-01989 | PRJ-003 | PRJ-003-ACT-09 | 2024-08-30 | Contractor | CON-002 | Electrical Contract | VEN-005 | 1 | Contract | 229241.99 | 224434.69 | 40398.24 | 264832.93 | Partially Paid | High
EXP-01990 | PRJ-003 | PRJ-003-ACT-08 | 2024-08-30 | Labour | LAB-004 | Electrician | VEN-005 | 20 | Worker | 13524.41 | 13293 | 2392.74 | 15685.74 | Paid | Low
EXP-01991 | PRJ-003 | PRJ-003-ACT-02 | 2024-08-30 | Material | MAT-003 | Sand | VEN-001 | 6.52 | Ton | 10348.37 | 11000.43 | 1980.08 | 12980.51 | Partially Paid | Medium
EXP-01992 | PRJ-003 | PRJ-003-ACT-10 | 2024-09-04 | Labour | LAB-003 | Carpenter | VEN-008 | 13 | Worker | 9005.61 | 9713.96 | 1748.51 | 11462.47 | Paid | Medium
EXP-01993 | PRJ-003 | PRJ-003-ACT-09 | 2024-09-04 | Material | MAT-007 | PVC Pipe | VEN-001 | 16.98 | Meter | 2521.64 | 2341.63 | 421.49 | 2763.12 | Paid | Low
EXP-01994 | PRJ-003 | PRJ-003-ACT-03 | 2024-09-04 | Labour | LAB-001 | Mason | VEN-005 | 29 | Worker | 29884.28 | 27974.04 | 5035.33 | 33009.37 | Paid | Medium
EXP-01995 | PRJ-003 | PRJ-003-ACT-10 | 2024-09-04 | Labour | LAB-005 | Plumber | VEN-001 | 22 | Worker | 34363.2 | 36659.57 | 6598.72 | 43258.29 | Paid | Low
EXP-01996 | PRJ-003 | PRJ-003-ACT-05 | 2024-09-04 | Other | OTH-001 | Site Office | VEN-001 | 1 | Lot | 24522.79 | 24010.2 | 4321.84 | 28332.04 | Paid | Low
EXP-01997 | PRJ-003 | PRJ-003-ACT-04 | 2024-09-04 | Contractor | CON-001 | Civil Structure Contract | VEN-010 | 1 | Contract | 149646.57 | 151691.39 | 27304.45 | 178995.84 | Paid | Medium
EXP-01998 | PRJ-003 | PRJ-003-ACT-03 | 2024-09-04 | Labour | LAB-005 | Plumber | VEN-005 | 15 | Worker | 15439.26 | 16673.59 | 3001.25 | 19674.84 | Paid | Medium
EXP-01999 | PRJ-003 | PRJ-003-ACT-09 | 2024-09-09 | Equipment | EQ-001 | Crane | VEN-008 | 7 | Day | 132533.96 | 138175.69 | 24871.62 | 163047.31 | Paid | Low
EXP-02000 | PRJ-003 | PRJ-003-ACT-08 | 2024-09-09 | Material | MAT-002 | Steel | VEN-010 | 37.06 | Ton | 2396618 | 2261440.25 | 407059.24 | 2668499.49 | Paid | Low
EXP-02001 | PRJ-003 | PRJ-003-ACT-10 | 2024-09-09 | Labour | LAB-003 | Carpenter | VEN-008 | 23 | Worker | 31469.91 | 33069.04 | 5952.43 | 39021.47 | Partially Paid | High
EXP-02002 | PRJ-003 | PRJ-003-ACT-08 | 2024-09-09 | Contractor | CON-001 | Civil Structure Contract | VEN-008 | 1 | Contract | 189514.78 | 179073.3 | 32233.19 | 211306.49 | Paid | Low
EXP-02003 | PRJ-003 | PRJ-003-ACT-06 | 2024-09-09 | Labour | LAB-006 | Painter | VEN-008 | 10 | Worker | 16644.75 | 15573.24 | 2803.18 | 18376.42 | Paid | Low
EXP-02004 | PRJ-003 | PRJ-003-ACT-01 | 2024-09-09 | Contractor | CON-003 | Plumbing Contract | VEN-001 | 1 | Contract | 180285.26 | 175962.44 | 31673.24 | 207635.68 | Paid | Medium
EXP-02005 | PRJ-003 | PRJ-003-ACT-06 | 2024-09-09 | Labour | LAB-001 | Mason | VEN-005 | 24 | Worker | 22391.1 | 23843.68 | 4291.86 | 28135.54 | Paid | Low
EXP-02006 | PRJ-003 | PRJ-003-ACT-08 | 2024-09-09 | Material | MAT-001 | Cement | VEN-008 | 15.42 | Bag | 6826.44 | 7375.42 | 1327.58 | 8703 | Paid | Medium
EXP-02007 | PRJ-003 | PRJ-003-ACT-04 | 2024-09-14 | Material | MAT-010 | Glass | VEN-005 | 8.61 | Sq Ft | 1452.85 | 1476.05 | 265.69 | 1741.74 | Paid | Medium
EXP-02008 | PRJ-003 | PRJ-003-ACT-09 | 2024-09-14 | Material | MAT-007 | PVC Pipe | VEN-008 | 34.41 | Meter | 3816.13 | 3996.96 | 719.45 | 4716.41 | Paid | Medium
EXP-02009 | PRJ-003 | PRJ-003-ACT-10 | 2024-09-14 | Contractor | CON-001 | Civil Structure Contract | VEN-008 | 1 | Contract | 303517.08 | 300108.92 | 54019.61 | 354128.53 | Paid | Medium
EXP-02010 | PRJ-003 | PRJ-003-ACT-10 | 2024-09-14 | Contractor | CON-002 | Electrical Contract | VEN-008 | 1 | Contract | 430357.31 | 419173.36 | 75451.2 | 494624.56 | Paid | Medium
EXP-02011 | PRJ-003 | PRJ-003-ACT-03 | 2024-09-14 | Equipment | EQ-002 | Excavator | VEN-010 | 7 | Day | 88328.63 | 88943.17 | 16009.77 | 104952.94 | Partially Paid | Low
EXP-02012 | PRJ-003 | PRJ-003-ACT-09 | 2024-09-14 | Material | MAT-003 | Sand | VEN-005 | 7.97 | Ton | 16843.45 | 16436.67 | 2958.6 | 19395.27 | Paid | Medium
EXP-02013 | PRJ-003 | PRJ-003-ACT-10 | 2024-09-14 | Equipment | EQ-004 | Scaffolding | VEN-001 | 1 | Day | 2149.18 | 2282 | 410.76 | 2692.76 | Paid | Medium
EXP-02014 | PRJ-003 | PRJ-003-ACT-04 | 2024-09-14 | Labour | LAB-006 | Painter | VEN-001 | 26 | Worker | 37074.53 | 39966.05 | 7193.89 | 47159.94 | Paid | High
EXP-02015 | PRJ-003 | PRJ-003-ACT-10 | 2024-09-14 | Material | MAT-004 | Aggregate | VEN-008 | 7.23 | Ton | 11661.61 | 12461.22 | 2243.02 | 14704.24 | Paid | Low
EXP-02016 | PRJ-003 | PRJ-003-ACT-09 | 2024-09-19 | Material | MAT-007 | PVC Pipe | VEN-010 | 9.66 | Meter | 1227.7 | 1259.73 | 226.75 | 1486.48 | Paid | Medium
EXP-02017 | PRJ-003 | PRJ-003-ACT-04 | 2024-09-19 | Labour | LAB-002 | Helper | VEN-001 | 30 | Worker | 41397.85 | 43334.37 | 7800.19 | 51134.56 | Paid | Medium
EXP-02018 | PRJ-003 | PRJ-003-ACT-05 | 2024-09-19 | Equipment | EQ-004 | Scaffolding | VEN-001 | 5 | Day | 13454.88 | 12797.9 | 2303.62 | 15101.52 | Paid | Medium
EXP-02019 | PRJ-003 | PRJ-003-ACT-09 | 2024-09-19 | Material | MAT-006 | Electrical Cable | VEN-008 | 6.59 | Meter | 493.51 | 485.1 | 87.32 | 572.42 | Paid | Low
EXP-02020 | PRJ-003 | PRJ-003-ACT-06 | 2024-09-19 | Equipment | EQ-004 | Scaffolding | VEN-005 | 1 | Day | 2170.07 | 2282.44 | 410.84 | 2693.28 | Paid | Medium
EXP-02021 | PRJ-003 | PRJ-003-ACT-07 | 2024-09-19 | Contractor | CON-001 | Civil Structure Contract | VEN-005 | 1 | Contract | 399204.28 | 380175.82 | 68431.65 | 448607.47 | Paid | Medium
EXP-02022 | PRJ-003 | PRJ-003-ACT-10 | 2024-09-24 | Material | MAT-004 | Aggregate | VEN-010 | 7.28 | Ton | 10122.73 | 10763.98 | 1937.52 | 12701.5 | Paid | Medium
EXP-02023 | PRJ-003 | PRJ-003-ACT-07 | 2024-09-24 | Contractor | CON-001 | Civil Structure Contract | VEN-001 | 1 | Contract | 332389.73 | 357101.05 | 64278.19 | 421379.24 | Paid | Low
EXP-02024 | PRJ-003 | PRJ-003-ACT-07 | 2024-09-24 | Labour | LAB-001 | Mason | VEN-001 | 30 | Worker | 19362.7 | 20927.75 | 3766.99 | 24694.74 | Paid | Low
EXP-02025 | PRJ-003 | PRJ-003-ACT-02 | 2024-09-24 | Labour | LAB-002 | Helper | VEN-001 | 10 | Worker | 9251.97 | 9401.35 | 1692.24 | 11093.59 | Paid | Low
EXP-02026 | PRJ-003 | PRJ-003-ACT-03 | 2024-09-24 | Material | MAT-009 | Paint | VEN-001 | 2.87 | Litre | 572.64 | 614.22 | 110.56 | 724.78 | Paid | High
EXP-02027 | PRJ-003 | PRJ-003-ACT-06 | 2024-09-24 | Contractor | CON-002 | Electrical Contract | VEN-005 | 1 | Contract | 233595.61 | 246899.67 | 44441.94 | 291341.61 | Partially Paid | Low
EXP-02028 | PRJ-003 | PRJ-003-ACT-10 | 2024-09-24 | Material | MAT-008 | Tiles | VEN-010 | 13.65 | Sq Ft | 853.19 | 892.7 | 160.69 | 1053.39 | Paid | Low
EXP-02029 | PRJ-003 | PRJ-003-ACT-04 | 2024-09-24 | Material | MAT-001 | Cement | VEN-008 | 1.22 | Bag | 534.15 | 564.55 | 101.62 | 666.17 | Paid | Medium
EXP-02030 | PRJ-003 | PRJ-003-ACT-05 | 2024-09-24 | Labour | LAB-005 | Plumber | VEN-008 | 32 | Worker | 47375.74 | 47930.76 | 8627.54 | 56558.3 | Paid | Low
EXP-02031 | PRJ-003 | PRJ-003-ACT-10 | 2024-09-24 | Material | MAT-010 | Glass | VEN-008 | 7.73 | Sq Ft | 1212.39 | 1188.47 | 213.92 | 1402.39 | Paid | Low
EXP-02032 | PRJ-003 | PRJ-003-ACT-07 | 2024-09-29 | Contractor | CON-001 | Civil Structure Contract | VEN-005 | 1 | Contract | 178534.61 | 166370.25 | 29946.65 | 196316.9 | Paid | Low
EXP-02033 | PRJ-003 | PRJ-003-ACT-06 | 2024-09-29 | Material | MAT-003 | Sand | VEN-008 | 8.68 | Ton | 14039.46 | 13776.8 | 2479.82 | 16256.62 | Paid | Low
EXP-02034 | PRJ-003 | PRJ-003-ACT-06 | 2024-09-29 | Material | MAT-005 | Bricks | VEN-010 | 6.5 | Piece | 59 | 54.77 | 9.86 | 64.63 | Paid | High
EXP-02035 | PRJ-003 | PRJ-003-ACT-04 | 2024-09-29 | Material | MAT-010 | Glass | VEN-008 | 20.56 | Sq Ft | 3626.51 | 3491.21 | 628.42 | 4119.63 | Paid | Low
EXP-02036 | PRJ-003 | PRJ-003-ACT-02 | 2024-09-29 | Material | MAT-006 | Electrical Cable | VEN-005 | 2.02 | Meter | 141.32 | 152.96 | 27.53 | 180.49 | Pending | High
EXP-02037 | PRJ-003 | PRJ-003-ACT-05 | 2024-09-29 | Material | MAT-001 | Cement | VEN-001 | 10.68 | Bag | 5161.08 | 5430.27 | 977.45 | 6407.72 | Paid | Low
EXP-02038 | PRJ-003 | PRJ-003-ACT-02 | 2024-09-29 | Contractor | CON-003 | Plumbing Contract | VEN-001 | 1 | Contract | 287391 | 299979.11 | 53996.24 | 353975.35 | Paid | Low
EXP-02039 | PRJ-003 | PRJ-003-ACT-07 | 2024-09-29 | Material | MAT-010 | Glass | VEN-010 | 12.49 | Sq Ft | 2199.96 | 2211.6 | 398.09 | 2609.69 | Partially Paid | Low
EXP-02040 | PRJ-003 | PRJ-003-ACT-01 | 2024-09-29 | Material | MAT-005 | Bricks | VEN-005 | 12.51 | Piece | 101.28 | 106.02 | 19.08 | 125.1 | Paid | Low
EXP-02041 | PRJ-003 | PRJ-003-ACT-05 | 2024-09-29 | Labour | LAB-002 | Helper | VEN-001 | 33 | Worker | 46167.5 | 43145.34 | 7766.16 | 50911.5 | Paid | Medium
EXP-02042 | PRJ-003 | PRJ-003-ACT-03 | 2024-10-04 | Contractor | CON-004 | Finishing Contract | VEN-008 | 1 | Contract | 70522.6 | 76650.6 | 13797.11 | 90447.71 | Paid | Low
EXP-02043 | PRJ-003 | PRJ-003-ACT-02 | 2024-10-04 | Other | OTH-001 | Safety | VEN-001 | 1 | Lot | 43305.57 | 44153.63 | 7947.65 | 52101.28 | Paid | Low
EXP-02044 | PRJ-003 | PRJ-003-ACT-06 | 2024-10-04 | Material | MAT-001 | Cement | VEN-001 | 29.67 | Bag | 16854.78 | 15635.66 | 2814.42 | 18450.08 | Paid | High
EXP-02045 | PRJ-003 | PRJ-003-ACT-02 | 2024-10-04 | Other | OTH-001 | Transport | VEN-008 | 1 | Lot | 44075.3 | 47844.27 | 8611.97 | 56456.24 | Paid | Medium
EXP-02046 | PRJ-003 | PRJ-003-ACT-03 | 2024-10-04 | Equipment | EQ-004 | Scaffolding | VEN-008 | 5 | Day | 12742.08 | 11868.44 | 2136.32 | 14004.76 | Paid | Low
EXP-02047 | PRJ-003 | PRJ-003-ACT-01 | 2024-10-04 | Contractor | CON-002 | Electrical Contract | VEN-010 | 1 | Contract | 229020.41 | 218201.91 | 39276.34 | 257478.25 | Paid | Low
EXP-02048 | PRJ-003 | PRJ-003-ACT-04 | 2024-10-04 | Material | MAT-005 | Bricks | VEN-001 | 25.02 | Piece | 239.56 | 253.7 | 45.67 | 299.37 | Paid | Medium
EXP-02049 | PRJ-003 | PRJ-003-ACT-09 | 2024-10-04 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 383083.88 | 412721.96 | 74289.95 | 487011.91 | Paid | Low
EXP-02050 | PRJ-003 | PRJ-003-ACT-02 | 2024-10-09 | Other | OTH-001 | Site Office | VEN-005 | 1 | Lot | 65218.27 | 66537.45 | 11976.74 | 78514.19 | Partially Paid | High
EXP-02051 | PRJ-003 | PRJ-003-ACT-09 | 2024-10-09 | Labour | LAB-002 | Helper | VEN-001 | 6 | Worker | 9947.51 | 10350.36 | 1863.06 | 12213.42 | Paid | Low
EXP-02052 | PRJ-003 | PRJ-003-ACT-02 | 2024-10-09 | Material | MAT-002 | Steel | VEN-010 | 3.24 | Ton | 218582.16 | 223906 | 40303.08 | 264209.08 | Paid | Medium
EXP-02053 | PRJ-003 | PRJ-003-ACT-10 | 2024-10-09 | Material | MAT-004 | Aggregate | VEN-001 | 2.75 | Ton | 4106.46 | 3807.51 | 685.35 | 4492.86 | Paid | Medium
EXP-02054 | PRJ-003 | PRJ-003-ACT-06 | 2024-10-09 | Labour | LAB-005 | Plumber | VEN-001 | 21 | Worker | 35223.1 | 36500.09 | 6570.02 | 43070.11 | Paid | Medium
EXP-02055 | PRJ-003 | PRJ-003-ACT-03 | 2024-10-09 | Material | MAT-009 | Paint | VEN-010 | 11.79 | Litre | 2428.03 | 2471.27 | 444.83 | 2916.1 | Paid | Medium
EXP-02056 | PRJ-003 | PRJ-003-ACT-08 | 2024-10-09 | Equipment | EQ-003 | Concrete Mixer | VEN-008 | 1 | Day | 4311.63 | 4201.57 | 756.28 | 4957.85 | Paid | Medium
EXP-02057 | PRJ-003 | PRJ-003-ACT-08 | 2024-10-09 | Contractor | CON-003 | Plumbing Contract | VEN-008 | 1 | Contract | 214545.5 | 224235.14 | 40362.33 | 264597.47 | Paid | High
EXP-02058 | PRJ-003 | PRJ-003-ACT-04 | 2024-10-09 | Contractor | CON-001 | Civil Structure Contract | VEN-001 | 1 | Contract | 196264.86 | 202850.96 | 36513.17 | 239364.13 | Paid | Medium
EXP-02059 | PRJ-003 | PRJ-003-ACT-04 | 2024-10-14 | Material | MAT-008 | Tiles | VEN-008 | 12.76 | Sq Ft | 1001.31 | 967.57 | 174.16 | 1141.73 | Paid | Low
EXP-02060 | PRJ-003 | PRJ-003-ACT-08 | 2024-10-14 | Equipment | EQ-001 | Crane | VEN-001 | 5 | Day | 83588.45 | 89127.21 | 16042.9 | 105170.11 | Paid | Low
EXP-02061 | PRJ-003 | PRJ-003-ACT-03 | 2024-10-14 | Material | MAT-002 | Steel | VEN-001 | 34.57 | Ton | 2068241.26 | 1945559.68 | 350200.74 | 2295760.42 | Pending | Low
EXP-02062 | PRJ-003 | PRJ-003-ACT-09 | 2024-10-14 | Material | MAT-009 | Paint | VEN-010 | 16.63 | Litre | 4027.76 | 3990.82 | 718.35 | 4709.17 | Paid | Low
EXP-02063 | PRJ-003 | PRJ-003-ACT-03 | 2024-10-14 | Labour | LAB-005 | Plumber | VEN-008 | 9 | Worker | 10787.38 | 10328.15 | 1859.07 | 12187.22 | Paid | Medium
EXP-02064 | PRJ-003 | PRJ-003-ACT-10 | 2024-10-14 | Material | MAT-010 | Glass | VEN-010 | 7.18 | Sq Ft | 1287.08 | 1259.54 | 226.72 | 1486.26 | Paid | Low
EXP-02065 | PRJ-003 | PRJ-003-ACT-05 | 2024-10-19 | Equipment | EQ-001 | Crane | VEN-001 | 1 | Day | 17863.1 | 16983.41 | 3057.01 | 20040.42 | Paid | Medium
EXP-02066 | PRJ-003 | PRJ-003-ACT-10 | 2024-10-19 | Contractor | CON-001 | Civil Structure Contract | VEN-010 | 1 | Contract | 141683.26 | 134044.86 | 24128.07 | 158172.93 | Partially Paid | Low
EXP-02067 | PRJ-003 | PRJ-003-ACT-04 | 2024-10-19 | Material | MAT-005 | Bricks | VEN-001 | 5.78 | Piece | 52.86 | 50.18 | 9.03 | 59.21 | Paid | Low
EXP-02068 | PRJ-003 | PRJ-003-ACT-09 | 2024-10-19 | Material | MAT-004 | Aggregate | VEN-008 | 6.86 | Ton | 12034.4 | 11527.44 | 2074.94 | 13602.38 | Paid | Low
EXP-02069 | PRJ-003 | PRJ-003-ACT-07 | 2024-10-19 | Material | MAT-002 | Steel | VEN-008 | 8.04 | Ton | 513141.35 | 526786.3 | 94821.53 | 621607.83 | Pending | Low
EXP-02070 | PRJ-003 | PRJ-003-ACT-08 | 2024-10-19 | Labour | LAB-004 | Electrician | VEN-010 | 13 | Worker | 17032.22 | 18100.73 | 3258.13 | 21358.86 | Paid | High
EXP-02071 | PRJ-003 | PRJ-003-ACT-08 | 2024-10-19 | Contractor | CON-002 | Electrical Contract | VEN-001 | 1 | Contract | 275654.28 | 290551.96 | 52299.35 | 342851.31 | Paid | Low
EXP-02072 | PRJ-003 | PRJ-003-ACT-03 | 2024-10-24 | Material | MAT-002 | Steel | VEN-005 | 11.46 | Ton | 829549.45 | 772160.59 | 138988.91 | 911149.5 | Paid | Low
EXP-02073 | PRJ-003 | PRJ-003-ACT-04 | 2024-10-24 | Contractor | CON-004 | Finishing Contract | VEN-001 | 1 | Contract | 123809.47 | 115802.77 | 20844.5 | 136647.27 | Paid | Medium
EXP-02074 | PRJ-003 | PRJ-003-ACT-09 | 2024-10-24 | Labour | LAB-005 | Plumber | VEN-008 | 4 | Worker | 3545.65 | 3521.66 | 633.9 | 4155.56 | Paid | Low
EXP-02075 | PRJ-003 | PRJ-003-ACT-10 | 2024-10-24 | Equipment | EQ-004 | Scaffolding | VEN-001 | 3 | Day | 6892.46 | 7367.65 | 1326.18 | 8693.83 | Paid | Low
EXP-02076 | PRJ-003 | PRJ-003-ACT-05 | 2024-10-24 | Other | OTH-001 | Safety | VEN-001 | 1 | Lot | 59347.9 | 61162.65 | 11009.28 | 72171.93 | Paid | Medium
EXP-02077 | PRJ-003 | PRJ-003-ACT-07 | 2024-10-24 | Equipment | EQ-002 | Excavator | VEN-010 | 6 | Day | 82717.54 | 81871.52 | 14736.87 | 96608.39 | Paid | Medium
EXP-02078 | PRJ-003 | PRJ-003-ACT-08 | 2024-10-24 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 431642.32 | 422914.16 | 76124.55 | 499038.71 | Paid | Low
EXP-02079 | PRJ-003 | PRJ-003-ACT-08 | 2024-10-29 | Labour | LAB-004 | Electrician | VEN-010 | 6 | Worker | 9421.06 | 9475.96 | 1705.67 | 11181.63 | Paid | Medium
EXP-02080 | PRJ-003 | PRJ-003-ACT-04 | 2024-10-29 | Other | OTH-001 | Safety | VEN-005 | 1 | Lot | 6116.06 | 6297.05 | 1133.47 | 7430.52 | Paid | Medium
EXP-02081 | PRJ-003 | PRJ-003-ACT-01 | 2024-10-29 | Contractor | CON-004 | Finishing Contract | VEN-001 | 1 | Contract | 174281.95 | 163592.61 | 29446.67 | 193039.28 | Paid | Medium
EXP-02082 | PRJ-003 | PRJ-003-ACT-04 | 2024-10-29 | Material | MAT-007 | PVC Pipe | VEN-005 | 22.19 | Meter | 2645.17 | 2735.54 | 492.4 | 3227.94 | Paid | Low
EXP-02083 | PRJ-003 | PRJ-003-ACT-07 | 2024-10-29 | Material | MAT-003 | Sand | VEN-008 | 3.09 | Ton | 4882.66 | 5134.27 | 924.17 | 6058.44 | Paid | Low
EXP-02084 | PRJ-003 | PRJ-003-ACT-03 | 2024-10-29 | Equipment | EQ-004 | Scaffolding | VEN-005 | 4 | Day | 10071.35 | 10593.37 | 1906.81 | 12500.18 | Paid | High
EXP-02085 | PRJ-003 | PRJ-003-ACT-07 | 2024-10-29 | Material | MAT-004 | Aggregate | VEN-005 | 12.32 | Ton | 15314.08 | 15835.01 | 2850.3 | 18685.31 | Paid | High
EXP-02086 | PRJ-003 | PRJ-003-ACT-06 | 2024-10-29 | Material | MAT-004 | Aggregate | VEN-008 | 15.75 | Ton | 21983.28 | 22524.12 | 4054.34 | 26578.46 | Paid | Low
EXP-02087 | PRJ-003 | PRJ-003-ACT-08 | 2024-10-29 | Material | MAT-004 | Aggregate | VEN-001 | 30.88 | Ton | 38580.4 | 41837.32 | 7530.72 | 49368.04 | Paid | Medium
EXP-02088 | PRJ-003 | PRJ-003-ACT-01 | 2024-10-29 | Labour | LAB-004 | Electrician | VEN-008 | 27 | Worker | 29017.73 | 27206.64 | 4897.2 | 32103.84 | Paid | Low
EXP-02089 | PRJ-003 | PRJ-003-ACT-01 | 2024-11-03 | Material | MAT-002 | Steel | VEN-010 | 7.64 | Ton | 397910.46 | 405020.08 | 72903.61 | 477923.69 | Paid | Low
EXP-02090 | PRJ-003 | PRJ-003-ACT-01 | 2024-11-03 | Labour | LAB-005 | Plumber | VEN-010 | 23 | Worker | 34469.19 | 34954 | 6291.72 | 41245.72 | Paid | Low
EXP-02091 | PRJ-003 | PRJ-003-ACT-05 | 2024-11-03 | Material | MAT-009 | Paint | VEN-001 | 14.68 | Litre | 2731.06 | 2688.11 | 483.86 | 3171.97 | Paid | Low
EXP-02092 | PRJ-003 | PRJ-003-ACT-04 | 2024-11-03 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 163051.77 | 166957.34 | 30052.32 | 197009.66 | Paid | Medium
EXP-02093 | PRJ-003 | PRJ-003-ACT-05 | 2024-11-03 | Material | MAT-006 | Electrical Cable | VEN-005 | 9.32 | Meter | 704.45 | 714.39 | 128.59 | 842.98 | Paid | Low
EXP-02094 | PRJ-003 | PRJ-003-ACT-07 | 2024-11-03 | Other | OTH-001 | Transport | VEN-010 | 1 | Lot | 35035.37 | 33944.11 | 6109.94 | 40054.05 | Paid | Low
EXP-02095 | PRJ-003 | PRJ-003-ACT-03 | 2024-11-03 | Material | MAT-008 | Tiles | VEN-008 | 3.26 | Sq Ft | 237.14 | 251.14 | 45.21 | 296.35 | Paid | Low
EXP-02096 | PRJ-003 | PRJ-003-ACT-01 | 2024-11-03 | Labour | LAB-002 | Helper | VEN-001 | 8 | Worker | 12000.5 | 11184.03 | 2013.13 | 13197.16 | Paid | Low
EXP-02097 | PRJ-003 | PRJ-003-ACT-06 | 2024-11-03 | Contractor | CON-001 | Civil Structure Contract | VEN-008 | 1 | Contract | 172645.67 | 166911.34 | 30044.04 | 196955.38 | Paid | Medium
EXP-02098 | PRJ-003 | PRJ-003-ACT-01 | 2024-11-08 | Material | MAT-009 | Paint | VEN-001 | 5.01 | Litre | 1020.09 | 986.1 | 177.5 | 1163.6 | Paid | Low
EXP-02099 | PRJ-003 | PRJ-003-ACT-10 | 2024-11-08 | Material | MAT-010 | Glass | VEN-008 | 11.68 | Sq Ft | 1659.86 | 1711.83 | 308.13 | 2019.96 | Paid | Low
EXP-02100 | PRJ-003 | PRJ-003-ACT-08 | 2024-11-08 | Contractor | CON-004 | Finishing Contract | VEN-001 | 1 | Contract | 448974.18 | 426672.11 | 76800.98 | 503473.09 | Partially Paid | High
EXP-02101 | PRJ-003 | PRJ-003-ACT-01 | 2024-11-08 | Material | MAT-002 | Steel | VEN-005 | 10.35 | Ton | 663080.34 | 662851.25 | 119313.22 | 782164.47 | Paid | Low
EXP-02102 | PRJ-003 | PRJ-003-ACT-08 | 2024-11-08 | Contractor | CON-002 | Electrical Contract | VEN-010 | 1 | Contract | 171827.04 | 167176.45 | 30091.76 | 197268.21 | Paid | Medium
EXP-02103 | PRJ-003 | PRJ-003-ACT-07 | 2024-11-08 | Material | MAT-008 | Tiles | VEN-005 | 3.45 | Sq Ft | 264.95 | 276.56 | 49.78 | 326.34 | Paid | Medium
EXP-02104 | PRJ-003 | PRJ-003-ACT-06 | 2024-11-08 | Material | MAT-010 | Glass | VEN-010 | 8.55 | Sq Ft | 1233.76 | 1169.52 | 210.51 | 1380.03 | Paid | Medium
EXP-02105 | PRJ-003 | PRJ-003-ACT-10 | 2024-11-08 | Labour | LAB-004 | Electrician | VEN-005 | 22 | Worker | 31591.39 | 32630.41 | 5873.47 | 38503.88 | Paid | Low
EXP-02106 | PRJ-003 | PRJ-003-ACT-04 | 2024-11-13 | Other | OTH-001 | Safety | VEN-010 | 1 | Lot | 10795.95 | 10596.81 | 1907.43 | 12504.24 | Pending | Low
EXP-02107 | PRJ-003 | PRJ-003-ACT-03 | 2024-11-13 | Labour | LAB-005 | Plumber | VEN-005 | 28 | Worker | 23933.17 | 23961.5 | 4313.07 | 28274.57 | Paid | Low
EXP-02108 | PRJ-003 | PRJ-003-ACT-05 | 2024-11-13 | Contractor | CON-001 | Civil Structure Contract | VEN-001 | 1 | Contract | 417550.87 | 414578.12 | 74624.06 | 489202.18 | Partially Paid | Medium
EXP-02109 | PRJ-003 | PRJ-003-ACT-01 | 2024-11-13 | Material | MAT-006 | Electrical Cable | VEN-010 | 41.81 | Meter | 3754.87 | 3543.63 | 637.85 | 4181.48 | Paid | Low
EXP-02110 | PRJ-003 | PRJ-003-ACT-01 | 2024-11-13 | Contractor | CON-002 | Electrical Contract | VEN-005 | 1 | Contract | 112055.69 | 121014.64 | 21782.64 | 142797.28 | Paid | Low
EXP-02111 | PRJ-003 | PRJ-003-ACT-06 | 2024-11-13 | Material | MAT-006 | Electrical Cable | VEN-008 | 4.35 | Meter | 446.95 | 418.73 | 75.37 | 494.1 | Partially Paid | Low
EXP-02112 | PRJ-003 | PRJ-003-ACT-06 | 2024-11-13 | Labour | LAB-002 | Helper | VEN-008 | 20 | Worker | 24262.11 | 26291.86 | 4732.53 | 31024.39 | Pending | Low
EXP-02113 | PRJ-003 | PRJ-003-ACT-06 | 2024-11-13 | Material | MAT-007 | PVC Pipe | VEN-010 | 5.07 | Meter | 682.29 | 696.99 | 125.46 | 822.45 | Paid | Medium
EXP-02114 | PRJ-003 | PRJ-003-ACT-07 | 2024-11-18 | Material | MAT-009 | Paint | VEN-005 | 3.82 | Litre | 735.31 | 713.16 | 128.37 | 841.53 | Partially Paid | Medium
EXP-02115 | PRJ-003 | PRJ-003-ACT-09 | 2024-11-18 | Material | MAT-006 | Electrical Cable | VEN-010 | 11.44 | Meter | 788.62 | 856.98 | 154.26 | 1011.24 | Paid | Low
EXP-02116 | PRJ-003 | PRJ-003-ACT-08 | 2024-11-18 | Equipment | EQ-002 | Excavator | VEN-008 | 3 | Day | 44391.76 | 41122.89 | 7402.12 | 48525.01 | Paid | High
EXP-02117 | PRJ-003 | PRJ-003-ACT-07 | 2024-11-18 | Material | MAT-009 | Paint | VEN-001 | 7.41 | Litre | 1846.81 | 1781 | 320.58 | 2101.58 | Partially Paid | Low
EXP-02118 | PRJ-003 | PRJ-003-ACT-07 | 2024-11-18 | Labour | LAB-002 | Helper | VEN-005 | 24 | Worker | 37405.8 | 38173.32 | 6871.2 | 45044.52 | Partially Paid | Low
EXP-02119 | PRJ-003 | PRJ-003-ACT-01 | 2024-11-18 | Material | MAT-005 | Bricks | VEN-005 | 22.34 | Piece | 208.17 | 210.3 | 37.85 | 248.15 | Paid | Low
EXP-02120 | PRJ-003 | PRJ-003-ACT-09 | 2024-11-18 | Material | MAT-005 | Bricks | VEN-008 | 6.32 | Piece | 60.6 | 61.56 | 11.08 | 72.64 | Paid | Medium
EXP-02121 | PRJ-003 | PRJ-003-ACT-10 | 2024-11-18 | Other | OTH-001 | Safety | VEN-010 | 1 | Lot | 49901.22 | 52318.28 | 9417.29 | 61735.57 | Paid | Low
EXP-02122 | PRJ-003 | PRJ-003-ACT-01 | 2024-11-18 | Contractor | CON-001 | Civil Structure Contract | VEN-010 | 1 | Contract | 150318.85 | 162048.23 | 29168.68 | 191216.91 | Paid | Low
EXP-02123 | PRJ-003 | PRJ-003-ACT-10 | 2024-11-18 | Material | MAT-004 | Aggregate | VEN-001 | 16.67 | Ton | 21877.68 | 23174.29 | 4171.37 | 27345.66 | Paid | Medium
EXP-02124 | PRJ-003 | PRJ-003-ACT-06 | 2024-11-23 | Labour | LAB-004 | Electrician | VEN-001 | 7 | Worker | 6354.33 | 6736.37 | 1212.55 | 7948.92 | Paid | Low
EXP-02125 | PRJ-003 | PRJ-003-ACT-04 | 2024-11-23 | Material | MAT-004 | Aggregate | VEN-008 | 5.27 | Ton | 8098.91 | 8590.06 | 1546.21 | 10136.27 | Partially Paid | Medium
EXP-02126 | PRJ-003 | PRJ-003-ACT-07 | 2024-11-23 | Equipment | EQ-004 | Scaffolding | VEN-010 | 5 | Day | 12680.29 | 12441.2 | 2239.42 | 14680.62 | Paid | Medium
EXP-02127 | PRJ-003 | PRJ-003-ACT-05 | 2024-11-23 | Material | MAT-001 | Cement | VEN-010 | 14.26 | Bag | 8256.4 | 8241.31 | 1483.44 | 9724.75 | Paid | Low
EXP-02128 | PRJ-003 | PRJ-003-ACT-03 | 2024-11-23 | Material | MAT-010 | Glass | VEN-008 | 8.1 | Sq Ft | 1453.67 | 1426.41 | 256.75 | 1683.16 | Paid | Low
EXP-02129 | PRJ-003 | PRJ-003-ACT-02 | 2024-11-23 | Labour | LAB-002 | Helper | VEN-005 | 26 | Worker | 31792.31 | 30901.3 | 5562.23 | 36463.53 | Paid | Medium
EXP-02130 | PRJ-003 | PRJ-003-ACT-07 | 2024-11-28 | Contractor | CON-002 | Electrical Contract | VEN-008 | 1 | Contract | 451272.8 | 433737.87 | 78072.82 | 511810.69 | Paid | Medium
EXP-02131 | PRJ-003 | PRJ-003-ACT-04 | 2024-11-28 | Labour | LAB-002 | Helper | VEN-010 | 7 | Worker | 6439.17 | 6714.44 | 1208.6 | 7923.04 | Paid | Medium
EXP-02132 | PRJ-003 | PRJ-003-ACT-01 | 2024-11-28 | Labour | LAB-002 | Helper | VEN-010 | 21 | Worker | 22255.41 | 21294.39 | 3832.99 | 25127.38 | Paid | Medium
EXP-02133 | PRJ-003 | PRJ-003-ACT-08 | 2024-11-28 | Equipment | EQ-002 | Excavator | VEN-001 | 7 | Day | 94464.38 | 101273.23 | 18229.18 | 119502.41 | Partially Paid | Low
EXP-02134 | PRJ-003 | PRJ-003-ACT-01 | 2024-11-28 | Material | MAT-006 | Electrical Cable | VEN-001 | 27.92 | Meter | 2314.6 | 2283.38 | 411.01 | 2694.39 | Paid | Low
EXP-02135 | PRJ-003 | PRJ-003-ACT-02 | 2024-11-28 | Equipment | EQ-004 | Scaffolding | VEN-008 | 6 | Day | 17485.34 | 16366.97 | 2946.05 | 19313.02 | Paid | Low
EXP-02136 | PRJ-003 | PRJ-003-ACT-06 | 2024-12-03 | Equipment | EQ-004 | Scaffolding | VEN-008 | 2 | Day | 4828.4 | 4732.62 | 851.87 | 5584.49 | Partially Paid | Low
EXP-02137 | PRJ-003 | PRJ-003-ACT-09 | 2024-12-03 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 372982.27 | 371018.61 | 66783.35 | 437801.96 | Paid | Low
EXP-02138 | PRJ-003 | PRJ-003-ACT-06 | 2024-12-03 | Material | MAT-007 | PVC Pipe | VEN-008 | 15.64 | Meter | 1637.09 | 1724.44 | 310.4 | 2034.84 | Paid | Low
EXP-02139 | PRJ-003 | PRJ-003-ACT-02 | 2024-12-03 | Contractor | CON-003 | Plumbing Contract | VEN-005 | 1 | Contract | 433630.51 | 414406.51 | 74593.17 | 488999.68 | Partially Paid | Low
EXP-02140 | PRJ-003 | PRJ-003-ACT-10 | 2024-12-03 | Labour | LAB-004 | Electrician | VEN-010 | 16 | Worker | 23752.57 | 25021.78 | 4503.92 | 29525.7 | Paid | Medium
EXP-02141 | PRJ-003 | PRJ-003-ACT-07 | 2024-12-03 | Material | MAT-007 | PVC Pipe | VEN-005 | 12.81 | Meter | 1587.8 | 1527.06 | 274.87 | 1801.93 | Paid | Low
EXP-02142 | PRJ-003 | PRJ-003-ACT-02 | 2024-12-08 | Material | MAT-010 | Glass | VEN-010 | 5.26 | Sq Ft | 916.51 | 907.17 | 163.29 | 1070.46 | Partially Paid | Medium
EXP-02143 | PRJ-003 | PRJ-003-ACT-02 | 2024-12-08 | Equipment | EQ-003 | Concrete Mixer | VEN-005 | 7 | Day | 27321.86 | 29170.4 | 5250.67 | 34421.07 | Paid | High
EXP-02144 | PRJ-003 | PRJ-003-ACT-07 | 2024-12-08 | Material | MAT-001 | Cement | VEN-008 | 9.01 | Bag | 4743.4 | 4677.21 | 841.9 | 5519.11 | Paid | Medium
EXP-02145 | PRJ-003 | PRJ-003-ACT-04 | 2024-12-08 | Contractor | CON-004 | Finishing Contract | VEN-010 | 1 | Contract | 102375.84 | 103218.01 | 18579.24 | 121797.25 | Paid | Medium
EXP-02146 | PRJ-003 | PRJ-003-ACT-07 | 2024-12-08 | Material | MAT-007 | PVC Pipe | VEN-010 | 4.96 | Meter | 547.14 | 514.06 | 92.53 | 606.59 | Paid | Medium
EXP-02147 | PRJ-003 | PRJ-003-ACT-09 | 2024-12-08 | Contractor | CON-001 | Civil Structure Contract | VEN-010 | 1 | Contract | 377521.87 | 387298.75 | 69713.77 | 457012.52 | Paid | Medium
EXP-02148 | PRJ-003 | PRJ-003-ACT-06 | 2024-12-13 | Labour | LAB-005 | Plumber | VEN-005 | 8 | Worker | 10203.99 | 9968.64 | 1794.36 | 11763 | Paid | Low
EXP-02149 | PRJ-003 | PRJ-003-ACT-01 | 2024-12-13 | Labour | LAB-006 | Painter | VEN-008 | 19 | Worker | 22743.92 | 23874.59 | 4297.43 | 28172.02 | Paid | Low
EXP-02150 | PRJ-003 | PRJ-003-ACT-10 | 2024-12-13 | Material | MAT-004 | Aggregate | VEN-010 | 13.54 | Ton | 23281.71 | 21976.48 | 3955.77 | 25932.25 | Paid | Medium
EXP-02151 | PRJ-003 | PRJ-003-ACT-09 | 2024-12-13 | Material | MAT-002 | Steel | VEN-008 | 7.23 | Ton | 444093.09 | 480644 | 86515.92 | 567159.92 | Partially Paid | Low
EXP-02152 | PRJ-003 | PRJ-003-ACT-07 | 2024-12-13 | Material | MAT-008 | Tiles | VEN-005 | 9.58 | Sq Ft | 787.83 | 815.17 | 146.73 | 961.9 | Paid | Medium
EXP-02153 | PRJ-003 | PRJ-003-ACT-07 | 2024-12-13 | Contractor | CON-001 | Civil Structure Contract | VEN-001 | 1 | Contract | 123226.74 | 119245.2 | 21464.14 | 140709.34 | Paid | Low
EXP-02154 | PRJ-003 | PRJ-003-ACT-02 | 2024-12-13 | Material | MAT-002 | Steel | VEN-001 | 19.32 | Ton | 1178894.47 | 1154269.09 | 207768.44 | 1362037.53 | Partially Paid | Low
EXP-02155 | PRJ-003 | PRJ-003-ACT-07 | 2024-12-13 | Material | MAT-007 | PVC Pipe | VEN-008 | 12.88 | Meter | 1704.48 | 1688.03 | 303.85 | 1991.88 | Pending | Medium
EXP-02156 | PRJ-003 | PRJ-003-ACT-01 | 2024-12-18 | Labour | LAB-004 | Electrician | VEN-010 | 10 | Worker | 16461.2 | 15843.24 | 2851.78 | 18695.02 | Paid | Low
EXP-02157 | PRJ-003 | PRJ-003-ACT-07 | 2024-12-18 | Labour | LAB-006 | Painter | VEN-005 | 29 | Worker | 26139.96 | 27319.78 | 4917.56 | 32237.34 | Paid | Low
EXP-02158 | PRJ-003 | PRJ-003-ACT-01 | 2024-12-18 | Material | MAT-004 | Aggregate | VEN-005 | 2.63 | Ton | 4141.15 | 4085.94 | 735.47 | 4821.41 | Paid | Medium
EXP-02159 | PRJ-003 | PRJ-003-ACT-08 | 2024-12-18 | Contractor | CON-003 | Plumbing Contract | VEN-001 | 1 | Contract | 237793.25 | 243407.98 | 43813.44 | 287221.42 | Paid | High
EXP-02160 | PRJ-003 | PRJ-003-ACT-05 | 2024-12-18 | Material | MAT-008 | Tiles | VEN-008 | 12.7 | Sq Ft | 802.99 | 866.68 | 156 | 1022.68 | Paid | Low
EXP-02161 | PRJ-003 | PRJ-003-ACT-06 | 2024-12-18 | Material | MAT-003 | Sand | VEN-010 | 10.25 | Ton | 18300.87 | 19344.36 | 3481.98 | 22826.34 | Paid | Medium
EXP-02162 | PRJ-003 | PRJ-003-ACT-10 | 2024-12-23 | Labour | LAB-003 | Carpenter | VEN-010 | 30 | Worker | 22706.16 | 21681.24 | 3902.62 | 25583.86 | Paid | Low
EXP-02163 | PRJ-003 | PRJ-003-ACT-07 | 2024-12-23 | Material | MAT-002 | Steel | VEN-008 | 3.02 | Ton | 168650.05 | 170081.14 | 30614.61 | 200695.75 | Paid | Low
EXP-02164 | PRJ-003 | PRJ-003-ACT-02 | 2024-12-23 | Other | OTH-001 | Site Office | VEN-005 | 1 | Lot | 15744.99 | 15099.42 | 2717.9 | 17817.32 | Paid | Medium
EXP-02165 | PRJ-003 | PRJ-003-ACT-05 | 2024-12-23 | Labour | LAB-002 | Helper | VEN-001 | 10 | Worker | 17161.86 | 16592.19 | 2986.59 | 19578.78 | Paid | Low
EXP-02166 | PRJ-003 | PRJ-003-ACT-07 | 2024-12-23 | Contractor | CON-002 | Electrical Contract | VEN-008 | 1 | Contract | 435514.74 | 408600.52 | 73548.09 | 482148.61 | Paid | Medium
EXP-02167 | PRJ-003 | PRJ-003-ACT-10 | 2024-12-23 | Equipment | EQ-003 | Concrete Mixer | VEN-001 | 2 | Day | 9384.51 | 9333.73 | 1680.07 | 11013.8 | Paid | Medium
EXP-02168 | PRJ-003 | PRJ-003-ACT-03 | 2024-12-23 | Labour | LAB-006 | Painter | VEN-001 | 5 | Worker | 8177.22 | 8639.7 | 1555.15 | 10194.85 | Paid | Low
EXP-02169 | PRJ-003 | PRJ-003-ACT-10 | 2024-12-28 | Material | MAT-004 | Aggregate | VEN-010 | 3.18 | Ton | 4893.9 | 4562.39 | 821.23 | 5383.62 | Partially Paid | Low
EXP-02170 | PRJ-003 | PRJ-003-ACT-06 | 2024-12-28 | Material | MAT-007 | PVC Pipe | VEN-005 | 13.3 | Meter | 1563.4 | 1474.4 | 265.39 | 1739.79 | Paid | Low
EXP-02171 | PRJ-003 | PRJ-003-ACT-08 | 2024-12-28 | Material | MAT-010 | Glass | VEN-010 | 3.51 | Sq Ft | 607.93 | 588.76 | 105.98 | 694.74 | Paid | Medium
EXP-02172 | PRJ-003 | PRJ-003-ACT-01 | 2024-12-28 | Equipment | EQ-002 | Excavator | VEN-010 | 7 | Day | 111907.4 | 105720.24 | 19029.64 | 124749.88 | Paid | Low
EXP-02173 | PRJ-003 | PRJ-003-ACT-09 | 2024-12-28 | Contractor | CON-002 | Electrical Contract | VEN-010 | 1 | Contract | 380403.55 | 373865.54 | 67295.8 | 441161.34 | Paid | Low
EXP-02174 | PRJ-003 | PRJ-003-ACT-06 | 2024-12-28 | Other | OTH-001 | Site Office | VEN-010 | 1 | Lot | 64682.25 | 61064.62 | 10991.63 | 72056.25 | Paid | Medium
EXP-02175 | PRJ-003 | PRJ-003-ACT-04 | 2024-12-28 | Contractor | CON-002 | Electrical Contract | VEN-010 | 1 | Contract | 360138.63 | 370996.13 | 66779.3 | 437775.43 | Partially Paid | Medium
EXP-02176 | PRJ-003 | PRJ-003-ACT-08 | 2024-12-28 | Equipment | EQ-002 | Excavator | VEN-005 | 7 | Day | 94420.19 | 96918.65 | 17445.36 | 114364.01 | Partially Paid | Low
EXP-02177 | PRJ-003 | PRJ-003-ACT-10 | 2025-01-02 | Labour | LAB-001 | Mason | VEN-005 | 29 | Worker | 29943.26 | 31534.48 | 5676.21 | 37210.69 | Paid | Low
EXP-02178 | PRJ-003 | PRJ-003-ACT-01 | 2025-01-02 | Equipment | EQ-001 | Crane | VEN-001 | 6 | Day | 99092.35 | 102623.76 | 18472.28 | 121096.04 | Paid | Low
EXP-02179 | PRJ-003 | PRJ-003-ACT-09 | 2025-01-02 | Contractor | CON-004 | Finishing Contract | VEN-010 | 1 | Contract | 249704.08 | 267485.09 | 48147.32 | 315632.41 | Paid | High
EXP-02180 | PRJ-003 | PRJ-003-ACT-08 | 2025-01-02 | Equipment | EQ-004 | Scaffolding | VEN-005 | 1 | Day | 2280.55 | 2468.54 | 444.34 | 2912.88 | Partially Paid | Low
EXP-02181 | PRJ-003 | PRJ-003-ACT-06 | 2025-01-02 | Labour | LAB-004 | Electrician | VEN-001 | 16 | Worker | 17060.64 | 16913.52 | 3044.43 | 19957.95 | Paid | Low
EXP-02182 | PRJ-003 | PRJ-003-ACT-05 | 2025-01-02 | Labour | LAB-004 | Electrician | VEN-010 | 32 | Worker | 39390.51 | 40663.7 | 7319.47 | 47983.17 | Paid | Low
EXP-02183 | PRJ-003 | PRJ-003-ACT-04 | 2025-01-02 | Contractor | CON-001 | Civil Structure Contract | VEN-005 | 1 | Contract | 300272.43 | 325406.24 | 58573.12 | 383979.36 | Paid | Medium
EXP-02184 | PRJ-003 | PRJ-003-ACT-03 | 2025-01-07 | Material | MAT-003 | Sand | VEN-010 | 16.04 | Ton | 33918.09 | 32628.17 | 5873.07 | 38501.24 | Paid | Low
EXP-02185 | PRJ-003 | PRJ-003-ACT-09 | 2025-01-07 | Material | MAT-008 | Tiles | VEN-001 | 6.57 | Sq Ft | 424.02 | 439.07 | 79.03 | 518.1 | Paid | Medium
EXP-02186 | PRJ-003 | PRJ-003-ACT-03 | 2025-01-07 | Labour | LAB-004 | Electrician | VEN-010 | 19 | Worker | 13992.51 | 14329.35 | 2579.28 | 16908.63 | Paid | Low
EXP-02187 | PRJ-003 | PRJ-003-ACT-09 | 2025-01-07 | Material | MAT-003 | Sand | VEN-008 | 5.1 | Ton | 8663.79 | 8603.6 | 1548.65 | 10152.25 | Paid | Low
EXP-02188 | PRJ-003 | PRJ-003-ACT-04 | 2025-01-07 | Labour | LAB-001 | Mason | VEN-005 | 23 | Worker | 28089.63 | 27761.54 | 4997.08 | 32758.62 | Paid | Low
EXP-02189 | PRJ-003 | PRJ-003-ACT-05 | 2025-01-07 | Material | MAT-008 | Tiles | VEN-008 | 7.85 | Sq Ft | 500.97 | 511.24 | 92.02 | 603.26 | Paid | High
EXP-02190 | PRJ-003 | PRJ-003-ACT-10 | 2025-01-12 | Labour | LAB-005 | Plumber | VEN-001 | 24 | Worker | 36634.57 | 35499.56 | 6389.92 | 41889.48 | Pending | Medium
EXP-02191 | PRJ-003 | PRJ-003-ACT-05 | 2025-01-12 | Labour | LAB-003 | Carpenter | VEN-010 | 20 | Worker | 12675.49 | 13691.34 | 2464.44 | 16155.78 | Pending | Medium
EXP-02192 | PRJ-003 | PRJ-003-ACT-02 | 2025-01-12 | Material | MAT-008 | Tiles | VEN-008 | 5.57 | Sq Ft | 467.76 | 459.3 | 82.67 | 541.97 | Paid | Low
EXP-02193 | PRJ-003 | PRJ-003-ACT-10 | 2025-01-12 | Labour | LAB-003 | Carpenter | VEN-010 | 21 | Worker | 38030.17 | 35751.93 | 6435.35 | 42187.28 | Pending | Medium
EXP-02194 | PRJ-003 | PRJ-003-ACT-05 | 2025-01-12 | Other | OTH-001 | Safety | VEN-008 | 1 | Lot | 40277.92 | 37500.04 | 6750.01 | 44250.05 | Paid | Low
EXP-02195 | PRJ-003 | PRJ-003-ACT-03 | 2025-01-12 | Equipment | EQ-003 | Concrete Mixer | VEN-005 | 5 | Day | 22918.13 | 23393.75 | 4210.88 | 27604.63 | Paid | Low
EXP-02196 | PRJ-003 | PRJ-003-ACT-06 | 2025-01-12 | Equipment | EQ-003 | Concrete Mixer | VEN-008 | 6 | Day | 28431.61 | 29342.32 | 5281.62 | 34623.94 | Paid | Low
EXP-02197 | PRJ-003 | PRJ-003-ACT-08 | 2025-01-12 | Material | MAT-005 | Bricks | VEN-010 | 20.77 | Piece | 156.48 | 161.84 | 29.13 | 190.97 | Paid | Low
EXP-02198 | PRJ-003 | PRJ-003-ACT-10 | 2025-01-12 | Material | MAT-004 | Aggregate | VEN-005 | 9.76 | Ton | 15467.61 | 14932.51 | 2687.85 | 17620.36 | Paid | Low
EXP-02199 | PRJ-003 | PRJ-003-ACT-05 | 2025-01-17 | Other | OTH-001 | Miscellaneous | VEN-001 | 1 | Lot | 70296.15 | 70863.58 | 12755.44 | 83619.02 | Paid | Low
EXP-02200 | PRJ-003 | PRJ-003-ACT-07 | 2025-01-17 | Material | MAT-007 | PVC Pipe | VEN-008 | 8.1 | Meter | 1009.3 | 1028.75 | 185.17 | 1213.92 | Paid | Medium
EXP-02201 | PRJ-003 | PRJ-003-ACT-07 | 2025-01-17 | Labour | LAB-004 | Electrician | VEN-010 | 15 | Worker | 20306.47 | 19018.6 | 3423.35 | 22441.95 | Paid | High
EXP-02202 | PRJ-003 | PRJ-003-ACT-02 | 2025-01-17 | Material | MAT-005 | Bricks | VEN-008 | 22.84 | Piece | 234.75 | 227.37 | 40.93 | 268.3 | Paid | Low
EXP-02203 | PRJ-003 | PRJ-003-ACT-07 | 2025-01-17 | Material | MAT-004 | Aggregate | VEN-005 | 6.65 | Ton | 11584.94 | 10801.32 | 1944.24 | 12745.56 | Paid | Low
EXP-02204 | PRJ-003 | PRJ-003-ACT-07 | 2025-01-17 | Material | MAT-010 | Glass | VEN-005 | 4.68 | Sq Ft | 792.34 | 793.42 | 142.82 | 936.24 | Partially Paid | Low
EXP-02205 | PRJ-003 | PRJ-003-ACT-07 | 2025-01-17 | Labour | LAB-006 | Painter | VEN-005 | 5 | Worker | 7102.73 | 7463.26 | 1343.39 | 8806.65 | Paid | Medium
EXP-02206 | PRJ-003 | PRJ-003-ACT-01 | 2025-01-17 | Material | MAT-004 | Aggregate | VEN-008 | 17.17 | Ton | 26376.17 | 25747.92 | 4634.63 | 30382.55 | Paid | Medium
EXP-02207 | PRJ-003 | PRJ-003-ACT-06 | 2025-01-22 | Material | MAT-004 | Aggregate | VEN-001 | 21.23 | Ton | 32004.23 | 32671.94 | 5880.95 | 38552.89 | Paid | Low
EXP-02208 | PRJ-003 | PRJ-003-ACT-09 | 2025-01-22 | Material | MAT-010 | Glass | VEN-008 | 11.2 | Sq Ft | 1906.34 | 1926.07 | 346.69 | 2272.76 | Paid | Low
EXP-02209 | PRJ-003 | PRJ-003-ACT-06 | 2025-01-22 | Material | MAT-004 | Aggregate | VEN-010 | 16.06 | Ton | 24222.44 | 24430.47 | 4397.48 | 28827.95 | Paid | Low
EXP-02210 | PRJ-003 | PRJ-003-ACT-04 | 2025-01-22 | Contractor | CON-003 | Plumbing Contract | VEN-001 | 1 | Contract | 161455.5 | 174379.42 | 31388.3 | 205767.72 | Partially Paid | Low
EXP-02211 | PRJ-003 | PRJ-003-ACT-01 | 2025-01-22 | Material | MAT-010 | Glass | VEN-001 | 4.46 | Sq Ft | 658.78 | 625.8 | 112.64 | 738.44 | Paid | Low
EXP-02212 | PRJ-003 | PRJ-003-ACT-06 | 2025-01-22 | Contractor | CON-001 | Civil Structure Contract | VEN-008 | 1 | Contract | 230917.44 | 223146.29 | 40166.33 | 263312.62 | Pending | Medium
EXP-02213 | PRJ-003 | PRJ-003-ACT-07 | 2025-01-22 | Material | MAT-009 | Paint | VEN-001 | 3.96 | Litre | 831.08 | 881.12 | 158.6 | 1039.72 | Paid | Medium
EXP-02214 | PRJ-003 | PRJ-003-ACT-08 | 2025-01-22 | Material | MAT-008 | Tiles | VEN-005 | 11 | Sq Ft | 959.68 | 935.07 | 168.31 | 1103.38 | Paid | Low
EXP-02215 | PRJ-003 | PRJ-003-ACT-05 | 2025-01-27 | Material | MAT-008 | Tiles | VEN-008 | 17.83 | Sq Ft | 1397.91 | 1454.53 | 261.82 | 1716.35 | Paid | Medium
EXP-02216 | PRJ-003 | PRJ-003-ACT-03 | 2025-01-27 | Labour | LAB-001 | Mason | VEN-001 | 25 | Worker | 20425.05 | 19546.12 | 3518.3 | 23064.42 | Paid | Medium
EXP-02217 | PRJ-003 | PRJ-003-ACT-06 | 2025-01-27 | Material | MAT-010 | Glass | VEN-001 | 20.44 | Sq Ft | 3657.29 | 3583.01 | 644.94 | 4227.95 | Paid | Low
EXP-02218 | PRJ-003 | PRJ-003-ACT-05 | 2025-01-27 | Contractor | CON-002 | Electrical Contract | VEN-001 | 1 | Contract | 118756.3 | 127416.36 | 22934.94 | 150351.3 | Paid | Low
EXP-02219 | PRJ-003 | PRJ-003-ACT-10 | 2025-01-27 | Material | MAT-001 | Cement | VEN-001 | 5.66 | Bag | 2580.93 | 2508.02 | 451.44 | 2959.46 | Paid | Medium
EXP-02220 | PRJ-003 | PRJ-003-ACT-06 | 2025-01-27 | Material | MAT-002 | Steel | VEN-010 | 4.1 | Ton | 242840.85 | 234538.05 | 42216.85 | 276754.9 | Paid | Low
EXP-02221 | PRJ-003 | PRJ-003-ACT-05 | 2025-01-27 | Labour | LAB-001 | Mason | VEN-008 | 6 | Worker | 8163.64 | 8195.13 | 1475.12 | 9670.25 | Paid | Low
EXP-02222 | PRJ-003 | PRJ-003-ACT-05 | 2025-02-01 | Labour | LAB-004 | Electrician | VEN-005 | 31 | Worker | 25395.01 | 25450.72 | 4581.13 | 30031.85 | Paid | Low
EXP-02223 | PRJ-003 | PRJ-003-ACT-06 | 2025-02-01 | Material | MAT-009 | Paint | VEN-010 | 8.74 | Litre | 1950.69 | 1938.46 | 348.92 | 2287.38 | Paid | Low
EXP-02224 | PRJ-003 | PRJ-003-ACT-10 | 2025-02-01 | Material | MAT-008 | Tiles | VEN-001 | 12.26 | Sq Ft | 830.48 | 877.87 | 158.02 | 1035.89 | Paid | Low
EXP-02225 | PRJ-003 | PRJ-003-ACT-05 | 2025-02-01 | Contractor | CON-003 | Plumbing Contract | VEN-010 | 1 | Contract | 433859.64 | 444422.33 | 79996.02 | 524418.35 | Paid | Low
EXP-02226 | PRJ-003 | PRJ-003-ACT-03 | 2025-02-01 | Material | MAT-008 | Tiles | VEN-010 | 7.75 | Sq Ft | 480.42 | 519.81 | 93.57 | 613.38 | Pending | Low
EXP-02227 | PRJ-003 | PRJ-003-ACT-01 | 2025-02-01 | Contractor | CON-003 | Plumbing Contract | VEN-005 | 1 | Contract | 429454.63 | 398465.38 | 71723.77 | 470189.15 | Paid | Medium
EXP-02228 | PRJ-003 | PRJ-003-ACT-08 | 2025-02-06 | Contractor | CON-004 | Finishing Contract | VEN-008 | 1 | Contract | 284067.68 | 275527.39 | 49594.93 | 325122.32 | Partially Paid | Low
EXP-02229 | PRJ-003 | PRJ-003-ACT-04 | 2025-02-06 | Material | MAT-007 | PVC Pipe | VEN-005 | 8.66 | Meter | 971.36 | 983.45 | 177.02 | 1160.47 | Pending | Low
EXP-02230 | PRJ-003 | PRJ-003-ACT-10 | 2025-02-06 | Labour | LAB-002 | Helper | VEN-010 | 4 | Worker | 6833.48 | 6954.51 | 1251.81 | 8206.32 | Paid | Low
EXP-02231 | PRJ-003 | PRJ-003-ACT-09 | 2025-02-06 | Material | MAT-004 | Aggregate | VEN-001 | 12.3 | Ton | 19084.52 | 17772.75 | 3199.09 | 20971.84 | Paid | High
EXP-02232 | PRJ-003 | PRJ-003-ACT-10 | 2025-02-06 | Material | MAT-009 | Paint | VEN-010 | 5.29 | Litre | 942.37 | 989.47 | 178.1 | 1167.57 | Paid | Medium
EXP-02233 | PRJ-003 | PRJ-003-ACT-03 | 2025-02-06 | Material | MAT-001 | Cement | VEN-005 | 9.04 | Bag | 4817.08 | 4462.72 | 803.29 | 5266.01 | Paid | Low
EXP-02234 | PRJ-003 | PRJ-003-ACT-08 | 2025-02-06 | Contractor | CON-002 | Electrical Contract | VEN-001 | 1 | Contract | 390269.37 | 423619.83 | 76251.57 | 499871.4 | Partially Paid | Low
EXP-02235 | PRJ-003 | PRJ-003-ACT-01 | 2025-02-06 | Material | MAT-002 | Steel | VEN-005 | 20.27 | Ton | 1311632.83 | 1307605.56 | 235369 | 1542974.56 | Partially Paid | Medium
EXP-02236 | PRJ-003 | PRJ-003-ACT-09 | 2025-02-11 | Contractor | CON-003 | Plumbing Contract | VEN-005 | 1 | Contract | 301617.22 | 297703.58 | 53586.64 | 351290.22 | Paid | Low
EXP-02237 | PRJ-003 | PRJ-003-ACT-08 | 2025-02-11 | Material | MAT-008 | Tiles | VEN-005 | 3.22 | Sq Ft | 229.49 | 225.51 | 40.59 | 266.1 | Paid | Low
EXP-02238 | PRJ-003 | PRJ-003-ACT-02 | 2025-02-11 | Material | MAT-010 | Glass | VEN-001 | 15.86 | Sq Ft | 2135.46 | 2193.52 | 394.83 | 2588.35 | Paid | Medium
EXP-02239 | PRJ-003 | PRJ-003-ACT-02 | 2025-02-11 | Material | MAT-005 | Bricks | VEN-008 | 9.34 | Piece | 85.62 | 89.41 | 16.09 | 105.5 | Paid | Medium
EXP-02240 | PRJ-003 | PRJ-003-ACT-07 | 2025-02-11 | Material | MAT-001 | Cement | VEN-010 | 9.47 | Bag | 5409.15 | 5592.3 | 1006.61 | 6598.91 | Paid | Medium
EXP-02241 | PRJ-003 | PRJ-003-ACT-06 | 2025-02-11 | Material | MAT-010 | Glass | VEN-005 | 5.55 | Sq Ft | 788.6 | 809.93 | 145.79 | 955.72 | Paid | Medium
EXP-02242 | PRJ-003 | PRJ-003-ACT-10 | 2025-02-11 | Labour | LAB-005 | Plumber | VEN-005 | 23 | Worker | 32735.75 | 35330.39 | 6359.47 | 41689.86 | Partially Paid | Low
EXP-02243 | PRJ-003 | PRJ-003-ACT-10 | 2025-02-16 | Equipment | EQ-001 | Crane | VEN-001 | 6 | Day | 102750.04 | 99110.64 | 17839.92 | 116950.56 | Paid | Medium
EXP-02244 | PRJ-003 | PRJ-003-ACT-09 | 2025-02-16 | Contractor | CON-002 | Electrical Contract | VEN-008 | 1 | Contract | 440618.16 | 414272.85 | 74569.11 | 488841.96 | Paid | Medium
EXP-02245 | PRJ-003 | PRJ-003-ACT-02 | 2025-02-16 | Material | MAT-010 | Glass | VEN-005 | 10.34 | Sq Ft | 1335.13 | 1434.47 | 258.2 | 1692.67 | Paid | Low
EXP-02246 | PRJ-003 | PRJ-003-ACT-05 | 2025-02-16 | Material | MAT-005 | Bricks | VEN-001 | 16.82 | Piece | 150.67 | 154.06 | 27.73 | 181.79 | Paid | Low
EXP-02247 | PRJ-003 | PRJ-003-ACT-10 | 2025-02-16 | Contractor | CON-001 | Civil Structure Contract | VEN-001 | 1 | Contract | 314344.06 | 298098.84 | 53657.79 | 351756.63 | Paid | Low
EXP-02248 | PRJ-003 | PRJ-003-ACT-06 | 2025-02-16 | Contractor | CON-002 | Electrical Contract | VEN-010 | 1 | Contract | 202726.17 | 197721.52 | 35589.87 | 233311.39 | Paid | Low
EXP-02249 | PRJ-003 | PRJ-003-ACT-09 | 2025-02-16 | Material | MAT-009 | Paint | VEN-010 | 3.46 | Litre | 772.56 | 716.79 | 129.02 | 845.81 | Paid | Medium
EXP-02250 | PRJ-003 | PRJ-003-ACT-01 | 2025-02-16 | Material | MAT-009 | Paint | VEN-008 | 26.06 | Litre | 5193.73 | 5258.31 | 946.5 | 6204.81 | Paid | High
EXP-02251 | PRJ-003 | PRJ-003-ACT-10 | 2025-02-16 | Material | MAT-006 | Electrical Cable | VEN-010 | 4.73 | Meter | 491.97 | 456.22 | 82.12 | 538.34 | Paid | Low
EXP-02252 | PRJ-003 | PRJ-003-ACT-04 | 2025-02-21 | Other | OTH-001 | Transport | VEN-008 | 1 | Lot | 73330.26 | 70549.96 | 12698.99 | 83248.95 | Paid | Low
EXP-02253 | PRJ-003 | PRJ-003-ACT-02 | 2025-02-21 | Labour | LAB-003 | Carpenter | VEN-008 | 15 | Worker | 10499.49 | 11315.88 | 2036.86 | 13352.74 | Partially Paid | Low
EXP-02254 | PRJ-003 | PRJ-003-ACT-05 | 2025-02-21 | Labour | LAB-002 | Helper | VEN-008 | 5 | Worker | 7613.75 | 8164.37 | 1469.59 | 9633.96 | Paid | Low
EXP-02255 | PRJ-003 | PRJ-003-ACT-07 | 2025-02-21 | Other | OTH-001 | Permit | VEN-001 | 1 | Lot | 50143.67 | 47591.79 | 8566.52 | 56158.31 | Paid | Medium
EXP-02256 | PRJ-003 | PRJ-003-ACT-04 | 2025-02-21 | Material | MAT-002 | Steel | VEN-005 | 11.01 | Ton | 732184.98 | 690406.37 | 124273.15 | 814679.52 | Paid | Medium
EXP-02257 | PRJ-003 | PRJ-003-ACT-01 | 2025-02-21 | Equipment | EQ-003 | Concrete Mixer | VEN-005 | 5 | Day | 21003.03 | 20769.61 | 3738.53 | 24508.14 | Paid | Medium
EXP-02258 | PRJ-003 | PRJ-003-ACT-03 | 2025-02-21 | Material | MAT-010 | Glass | VEN-005 | 7.56 | Sq Ft | 1152.56 | 1200.02 | 216 | 1416.02 | Paid | Medium
EXP-02259 | PRJ-003 | PRJ-003-ACT-04 | 2025-02-21 | Other | OTH-001 | Permit | VEN-010 | 1 | Lot | 60220.32 | 57691.11 | 10384.4 | 68075.51 | Paid | Low
EXP-02260 | PRJ-003 | PRJ-003-ACT-06 | 2025-02-21 | Contractor | CON-004 | Finishing Contract | VEN-008 | 1 | Contract | 310908.84 | 287933.02 | 51827.94 | 339760.96 | Pending | Medium
EXP-02261 | PRJ-003 | PRJ-003-ACT-10 | 2025-02-26 | Labour | LAB-006 | Painter | VEN-010 | 10 | Worker | 16902.03 | 17340.45 | 3121.28 | 20461.73 | Paid | Medium
EXP-02262 | PRJ-003 | PRJ-003-ACT-06 | 2025-02-26 | Labour | LAB-002 | Helper | VEN-001 | 18 | Worker | 30861.73 | 32183.68 | 5793.06 | 37976.74 | Partially Paid | Low
EXP-02263 | PRJ-003 | PRJ-003-ACT-03 | 2025-02-26 | Labour | LAB-005 | Plumber | VEN-010 | 28 | Worker | 44777.88 | 46557.28 | 8380.31 | 54937.59 | Paid | Low
EXP-02264 | PRJ-003 | PRJ-003-ACT-07 | 2025-02-26 | Contractor | CON-001 | Civil Structure Contract | VEN-005 | 1 | Contract | 377514.06 | 353168.75 | 63570.38 | 416739.13 | Paid | Low
EXP-02265 | PRJ-003 | PRJ-003-ACT-01 | 2025-02-26 | Labour | LAB-005 | Plumber | VEN-001 | 18 | Worker | 13798.58 | 13256.49 | 2386.17 | 15642.66 | Paid | Low
EXP-02266 | PRJ-003 | PRJ-003-ACT-08 | 2025-02-26 | Labour | LAB-006 | Painter | VEN-010 | 7 | Worker | 11237.21 | 11009.34 | 1981.68 | 12991.02 | Paid | Medium
EXP-02267 | PRJ-003 | PRJ-003-ACT-01 | 2025-02-26 | Material | MAT-009 | Paint | VEN-008 | 5.78 | Litre | 1210.89 | 1166.37 | 209.95 | 1376.32 | Paid | Medium
EXP-02268 | PRJ-003 | PRJ-003-ACT-05 | 2025-02-26 | Material | MAT-001 | Cement | VEN-008 | 6.81 | Bag | 3368.94 | 3439.85 | 619.17 | 4059.02 | Paid | Low
EXP-02269 | PRJ-003 | PRJ-003-ACT-03 | 2025-02-26 | Contractor | CON-004 | Finishing Contract | VEN-001 | 1 | Contract | 394693.12 | 390544 | 70297.92 | 460841.92 | Paid | Low
EXP-02270 | PRJ-003 | PRJ-003-ACT-05 | 2025-03-03 | Contractor | CON-001 | Civil Structure Contract | VEN-008 | 1 | Contract | 372548.96 | 385779.1 | 69440.24 | 455219.34 | Paid | High
EXP-02271 | PRJ-003 | PRJ-003-ACT-06 | 2025-03-03 | Equipment | EQ-001 | Crane | VEN-008 | 3 | Day | 54465.06 | 52428.19 | 9437.07 | 61865.26 | Paid | Medium
EXP-02272 | PRJ-003 | PRJ-003-ACT-03 | 2025-03-03 | Labour | LAB-005 | Plumber | VEN-005 | 23 | Worker | 21086.52 | 22482.75 | 4046.89 | 26529.64 | Paid | Low
EXP-02273 | PRJ-003 | PRJ-003-ACT-07 | 2025-03-03 | Material | MAT-006 | Electrical Cable | VEN-005 | 27.94 | Meter | 2464.08 | 2666.74 | 480.01 | 3146.75 | Paid | Medium
EXP-02274 | PRJ-003 | PRJ-003-ACT-10 | 2025-03-03 | Material | MAT-010 | Glass | VEN-010 | 5.24 | Sq Ft | 818.85 | 871.38 | 156.85 | 1028.23 | Paid | Medium
EXP-02275 | PRJ-003 | PRJ-003-ACT-10 | 2025-03-03 | Labour | LAB-005 | Plumber | VEN-005 | 4 | Worker | 5969.55 | 5688.4 | 1023.91 | 6712.31 | Partially Paid | Medium
EXP-02276 | PRJ-003 | PRJ-003-ACT-05 | 2025-03-03 | Other | OTH-001 | Miscellaneous | VEN-008 | 1 | Lot | 41192.09 | 40369.6 | 7266.53 | 47636.13 | Partially Paid | Low
EXP-02277 | PRJ-003 | PRJ-003-ACT-04 | 2025-03-03 | Contractor | CON-002 | Electrical Contract | VEN-001 | 1 | Contract | 186184.41 | 177757.77 | 31996.4 | 209754.17 | Paid | High
EXP-02278 | PRJ-003 | PRJ-003-ACT-05 | 2025-03-03 | Other | OTH-001 | Safety | VEN-010 | 1 | Lot | 36263.45 | 39221.64 | 7059.9 | 46281.54 | Partially Paid | Low
EXP-02279 | PRJ-003 | PRJ-003-ACT-02 | 2025-03-08 | Labour | LAB-005 | Plumber | VEN-008 | 21 | Worker | 29672.85 | 27487.79 | 4947.8 | 32435.59 | Partially Paid | Low
EXP-02280 | PRJ-003 | PRJ-003-ACT-04 | 2025-03-08 | Material | MAT-009 | Paint | VEN-010 | 19.18 | Litre | 4666.17 | 4325.56 | 778.6 | 5104.16 | Paid | Low
EXP-02281 | PRJ-003 | PRJ-003-ACT-08 | 2025-03-08 | Material | MAT-009 | Paint | VEN-010 | 6.57 | Litre | 1351.34 | 1341.1 | 241.4 | 1582.5 | Pending | Low
EXP-02282 | PRJ-003 | PRJ-003-ACT-03 | 2025-03-08 | Material | MAT-003 | Sand | VEN-001 | 9.98 | Ton | 16187.38 | 17458.9 | 3142.6 | 20601.5 | Pending | High
EXP-02283 | PRJ-003 | PRJ-003-ACT-03 | 2025-03-08 | Material | MAT-010 | Glass | VEN-005 | 2.17 | Sq Ft | 316.42 | 342.68 | 61.68 | 404.36 | Paid | Medium
EXP-02284 | PRJ-003 | PRJ-003-ACT-01 | 2025-03-08 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 146760.18 | 145977.56 | 26275.96 | 172253.52 | Paid | Low
EXP-02285 | PRJ-003 | PRJ-003-ACT-08 | 2025-03-13 | Material | MAT-008 | Tiles | VEN-001 | 15.2 | Sq Ft | 1243.83 | 1164.84 | 209.67 | 1374.51 | Paid | Medium
EXP-02286 | PRJ-003 | PRJ-003-ACT-06 | 2025-03-13 | Contractor | CON-004 | Finishing Contract | VEN-008 | 1 | Contract | 231844.45 | 217793.9 | 39202.9 | 256996.8 | Paid | Low
EXP-02287 | PRJ-003 | PRJ-003-ACT-09 | 2025-03-13 | Contractor | CON-002 | Electrical Contract | VEN-005 | 1 | Contract | 407172.38 | 433502.97 | 78030.53 | 511533.5 | Paid | High
EXP-02288 | PRJ-003 | PRJ-003-ACT-07 | 2025-03-13 | Material | MAT-005 | Bricks | VEN-010 | 9.36 | Piece | 70.85 | 74.29 | 13.37 | 87.66 | Paid | Medium
EXP-02289 | PRJ-003 | PRJ-003-ACT-08 | 2025-03-13 | Material | MAT-008 | Tiles | VEN-008 | 5.18 | Sq Ft | 356.84 | 368.01 | 66.24 | 434.25 | Paid | Low
EXP-02290 | PRJ-003 | PRJ-003-ACT-10 | 2025-03-13 | Labour | LAB-002 | Helper | VEN-005 | 32 | Worker | 39376.16 | 41854.67 | 7533.84 | 49388.51 | Partially Paid | Medium
EXP-02291 | PRJ-003 | PRJ-003-ACT-04 | 2025-03-13 | Equipment | EQ-004 | Scaffolding | VEN-008 | 6 | Day | 16510.01 | 16137.1 | 2904.68 | 19041.78 | Paid | Medium
EXP-02292 | PRJ-003 | PRJ-003-ACT-01 | 2025-03-18 | Material | MAT-007 | PVC Pipe | VEN-008 | 17.21 | Meter | 2086.72 | 2110.99 | 379.98 | 2490.97 | Paid | Medium
EXP-02293 | PRJ-003 | PRJ-003-ACT-04 | 2025-03-18 | Labour | LAB-004 | Electrician | VEN-005 | 28 | Worker | 39681.55 | 40856.53 | 7354.18 | 48210.71 | Partially Paid | Low
EXP-02294 | PRJ-003 | PRJ-003-ACT-07 | 2025-03-18 | Material | MAT-004 | Aggregate | VEN-005 | 2.08 | Ton | 3306.48 | 3156.59 | 568.19 | 3724.78 | Partially Paid | Low
EXP-02295 | PRJ-003 | PRJ-003-ACT-10 | 2025-03-18 | Labour | LAB-003 | Carpenter | VEN-001 | 22 | Worker | 28395.61 | 30522.74 | 5494.09 | 36016.83 | Paid | Low
EXP-02296 | PRJ-003 | PRJ-003-ACT-09 | 2025-03-18 | Material | MAT-001 | Cement | VEN-010 | 4.53 | Bag | 2404.09 | 2533.35 | 456 | 2989.35 | Paid | Low
EXP-02297 | PRJ-003 | PRJ-003-ACT-09 | 2025-03-18 | Equipment | EQ-004 | Scaffolding | VEN-001 | 7 | Day | 15424.83 | 16284.25 | 2931.16 | 19215.41 | Paid | Low
EXP-02298 | PRJ-003 | PRJ-003-ACT-09 | 2025-03-18 | Material | MAT-003 | Sand | VEN-008 | 9.26 | Ton | 18154.41 | 17807.22 | 3205.3 | 21012.52 | Paid | Medium
EXP-02299 | PRJ-003 | PRJ-003-ACT-08 | 2025-03-18 | Equipment | EQ-004 | Scaffolding | VEN-005 | 5 | Day | 11360.4 | 11260.88 | 2026.96 | 13287.84 | Pending | Low
EXP-02300 | PRJ-003 | PRJ-003-ACT-06 | 2025-03-18 | Other | OTH-001 | Permit | VEN-001 | 1 | Lot | 45902.86 | 48388.38 | 8709.91 | 57098.29 | Paid | High
EXP-02301 | PRJ-003 | PRJ-003-ACT-04 | 2025-03-23 | Labour | LAB-006 | Painter | VEN-010 | 20 | Worker | 21716.08 | 20146.02 | 3626.28 | 23772.3 | Paid | Medium
EXP-02302 | PRJ-003 | PRJ-003-ACT-02 | 2025-03-23 | Material | MAT-003 | Sand | VEN-010 | 6.88 | Ton | 12423.05 | 11540.01 | 2077.2 | 13617.21 | Paid | High
EXP-02303 | PRJ-003 | PRJ-003-ACT-06 | 2025-03-23 | Contractor | CON-003 | Plumbing Contract | VEN-005 | 1 | Contract | 342003.41 | 341578.36 | 61484.1 | 403062.46 | Paid | Medium
EXP-02304 | PRJ-003 | PRJ-003-ACT-04 | 2025-03-23 | Material | MAT-006 | Electrical Cable | VEN-010 | 21.29 | Meter | 1820.63 | 1805.51 | 324.99 | 2130.5 | Paid | Medium
EXP-02305 | PRJ-003 | PRJ-003-ACT-05 | 2025-03-23 | Material | MAT-010 | Glass | VEN-008 | 8.66 | Sq Ft | 1539.39 | 1457.92 | 262.43 | 1720.35 | Paid | Low
EXP-02306 | PRJ-003 | PRJ-003-ACT-05 | 2025-03-23 | Contractor | CON-002 | Electrical Contract | VEN-001 | 1 | Contract | 239084.76 | 255149.1 | 45926.84 | 301075.94 | Partially Paid | Medium
EXP-02307 | PRJ-003 | PRJ-003-ACT-08 | 2025-03-23 | Material | MAT-007 | PVC Pipe | VEN-008 | 4.89 | Meter | 694.55 | 655.81 | 118.05 | 773.86 | Pending | Medium
EXP-02308 | PRJ-003 | PRJ-003-ACT-05 | 2025-03-23 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 217637.36 | 208714.89 | 37568.68 | 246283.57 | Pending | Medium
EXP-02309 | PRJ-003 | PRJ-003-ACT-09 | 2025-03-28 | Contractor | CON-003 | Plumbing Contract | VEN-005 | 1 | Contract | 118655.85 | 123285.58 | 22191.4 | 145476.98 | Partially Paid | High
EXP-02310 | PRJ-003 | PRJ-003-ACT-02 | 2025-03-28 | Labour | LAB-005 | Plumber | VEN-001 | 31 | Worker | 40567.61 | 37930.49 | 6827.49 | 44757.98 | Paid | Low
EXP-02311 | PRJ-003 | PRJ-003-ACT-04 | 2025-03-28 | Contractor | CON-003 | Plumbing Contract | VEN-001 | 1 | Contract | 201301.18 | 214660.03 | 38638.81 | 253298.84 | Pending | Medium
EXP-02312 | PRJ-003 | PRJ-003-ACT-04 | 2025-03-28 | Material | MAT-009 | Paint | VEN-001 | 8.3 | Litre | 1629.38 | 1760.2 | 316.84 | 2077.04 | Pending | Low
EXP-02313 | PRJ-003 | PRJ-003-ACT-08 | 2025-03-28 | Material | MAT-003 | Sand | VEN-008 | 11.41 | Ton | 24133.14 | 22990.66 | 4138.32 | 27128.98 | Paid | Low
EXP-02314 | PRJ-003 | PRJ-003-ACT-10 | 2025-03-28 | Contractor | CON-001 | Civil Structure Contract | VEN-008 | 1 | Contract | 247205.54 | 264777.71 | 47659.99 | 312437.7 | Paid | Low
EXP-02315 | PRJ-003 | PRJ-003-ACT-06 | 2025-03-28 | Material | MAT-007 | PVC Pipe | VEN-010 | 35.2 | Meter | 4920.46 | 4750.07 | 855.01 | 5605.08 | Partially Paid | Medium
EXP-02316 | PRJ-003 | PRJ-003-ACT-02 | 2025-03-28 | Other | OTH-001 | Site Office | VEN-001 | 1 | Lot | 41661.89 | 43800.74 | 7884.13 | 51684.87 | Paid | Medium
EXP-02317 | PRJ-003 | PRJ-003-ACT-03 | 2025-03-28 | Labour | LAB-006 | Painter | VEN-001 | 4 | Worker | 4345.86 | 4604.74 | 828.85 | 5433.59 | Paid | Low
EXP-02318 | PRJ-003 | PRJ-003-ACT-06 | 2025-04-02 | Material | MAT-004 | Aggregate | VEN-010 | 8.93 | Ton | 13970.94 | 13882.29 | 2498.81 | 16381.1 | Paid | Low
EXP-02319 | PRJ-003 | PRJ-003-ACT-08 | 2025-04-02 | Material | MAT-005 | Bricks | VEN-005 | 23.38 | Piece | 195.16 | 206.16 | 37.11 | 243.27 | Paid | Low
EXP-02320 | PRJ-003 | PRJ-003-ACT-03 | 2025-04-02 | Equipment | EQ-002 | Excavator | VEN-001 | 5 | Day | 75938.51 | 73917.8 | 13305.2 | 87223 | Paid | Medium
EXP-02321 | PRJ-003 | PRJ-003-ACT-04 | 2025-04-02 | Contractor | CON-001 | Civil Structure Contract | VEN-005 | 1 | Contract | 468999.92 | 436417.18 | 78555.09 | 514972.27 | Paid | Medium
EXP-02322 | PRJ-003 | PRJ-003-ACT-01 | 2025-04-02 | Material | MAT-004 | Aggregate | VEN-001 | 14.59 | Ton | 22513.56 | 21423.16 | 3856.17 | 25279.33 | Paid | Medium
EXP-02323 | PRJ-003 | PRJ-003-ACT-02 | 2025-04-02 | Material | MAT-006 | Electrical Cable | VEN-001 | 34.69 | Meter | 2518.67 | 2558.93 | 460.61 | 3019.54 | Pending | Medium
EXP-02324 | PRJ-003 | PRJ-003-ACT-03 | 2025-04-02 | Labour | LAB-004 | Electrician | VEN-001 | 31 | Worker | 33667.77 | 35801.89 | 6444.34 | 42246.23 | Paid | Low
EXP-02325 | PRJ-003 | PRJ-003-ACT-08 | 2025-04-02 | Equipment | EQ-003 | Concrete Mixer | VEN-008 | 6 | Day | 27408.71 | 27714.79 | 4988.66 | 32703.45 | Paid | High
EXP-02326 | PRJ-003 | PRJ-003-ACT-03 | 2025-04-07 | Contractor | CON-002 | Electrical Contract | VEN-010 | 1 | Contract | 314606.45 | 322082.72 | 57974.89 | 380057.61 | Paid | Medium
EXP-02327 | PRJ-003 | PRJ-003-ACT-04 | 2025-04-07 | Material | MAT-001 | Cement | VEN-008 | 5.36 | Bag | 2342.83 | 2522.9 | 454.12 | 2977.02 | Paid | Medium
EXP-02328 | PRJ-003 | PRJ-003-ACT-06 | 2025-04-07 | Material | MAT-006 | Electrical Cable | VEN-001 | 17.93 | Meter | 1274.07 | 1306.37 | 235.15 | 1541.52 | Paid | Medium
EXP-02329 | PRJ-003 | PRJ-003-ACT-05 | 2025-04-07 | Material | MAT-005 | Bricks | VEN-010 | 8.67 | Piece | 87.17 | 83.51 | 15.03 | 98.54 | Paid | Low
EXP-02330 | PRJ-003 | PRJ-003-ACT-04 | 2025-04-07 | Material | MAT-007 | PVC Pipe | VEN-005 | 3.41 | Meter | 416.19 | 432.53 | 77.86 | 510.39 | Paid | Low
EXP-02331 | PRJ-003 | PRJ-003-ACT-09 | 2025-04-07 | Contractor | CON-003 | Plumbing Contract | VEN-005 | 1 | Contract | 77411.37 | 82748.19 | 14894.67 | 97642.86 | Paid | Medium
EXP-02332 | PRJ-003 | PRJ-003-ACT-09 | 2025-04-07 | Material | MAT-004 | Aggregate | VEN-008 | 16.39 | Ton | 23617.21 | 22942.43 | 4129.64 | 27072.07 | Partially Paid | Low
EXP-02333 | PRJ-003 | PRJ-003-ACT-07 | 2025-04-12 | Equipment | EQ-001 | Crane | VEN-005 | 1 | Day | 16811.07 | 17730.37 | 3191.47 | 20921.84 | Paid | Low
EXP-02334 | PRJ-003 | PRJ-003-ACT-04 | 2025-04-12 | Labour | LAB-002 | Helper | VEN-010 | 18 | Worker | 27872.69 | 29498.33 | 5309.7 | 34808.03 | Paid | Low
EXP-02335 | PRJ-003 | PRJ-003-ACT-03 | 2025-04-12 | Contractor | CON-001 | Civil Structure Contract | VEN-008 | 1 | Contract | 320673.54 | 334348.92 | 60182.81 | 394531.73 | Paid | High
EXP-02336 | PRJ-003 | PRJ-003-ACT-05 | 2025-04-12 | Material | MAT-002 | Steel | VEN-005 | 13.53 | Ton | 936348.29 | 928625.96 | 167152.67 | 1095778.63 | Paid | High
EXP-02337 | PRJ-003 | PRJ-003-ACT-01 | 2025-04-12 | Contractor | CON-001 | Civil Structure Contract | VEN-010 | 1 | Contract | 239006.84 | 244008.11 | 43921.46 | 287929.57 | Paid | Medium
EXP-02338 | PRJ-003 | PRJ-003-ACT-01 | 2025-04-12 | Equipment | EQ-004 | Scaffolding | VEN-008 | 7 | Day | 16906.39 | 16267.24 | 2928.1 | 19195.34 | Paid | Low
EXP-02339 | PRJ-003 | PRJ-003-ACT-09 | 2025-04-17 | Material | MAT-002 | Steel | VEN-005 | 34.17 | Ton | 2033724.98 | 2105347.24 | 378962.5 | 2484309.74 | Paid | Medium
EXP-02340 | PRJ-003 | PRJ-003-ACT-08 | 2025-04-17 | Labour | LAB-001 | Mason | VEN-010 | 23 | Worker | 33477.44 | 32147.24 | 5786.5 | 37933.74 | Paid | Medium
EXP-02341 | PRJ-003 | PRJ-003-ACT-01 | 2025-04-17 | Material | MAT-008 | Tiles | VEN-005 | 9.24 | Sq Ft | 663.14 | 652.9 | 117.52 | 770.42 | Paid | Low
EXP-02342 | PRJ-003 | PRJ-003-ACT-03 | 2025-04-17 | Equipment | EQ-001 | Crane | VEN-001 | 6 | Day | 104630.02 | 106532.12 | 19175.78 | 125707.9 | Pending | Medium
EXP-02343 | PRJ-003 | PRJ-003-ACT-02 | 2025-04-17 | Material | MAT-006 | Electrical Cable | VEN-008 | 16.85 | Meter | 1526.76 | 1565.95 | 281.87 | 1847.82 | Pending | Low
EXP-02344 | PRJ-003 | PRJ-003-ACT-09 | 2025-04-17 | Material | MAT-006 | Electrical Cable | VEN-001 | 19.57 | Meter | 1489.4 | 1546.91 | 278.44 | 1825.35 | Partially Paid | Medium
EXP-02345 | PRJ-003 | PRJ-003-ACT-03 | 2025-04-17 | Contractor | CON-002 | Electrical Contract | VEN-005 | 1 | Contract | 339945.95 | 317239.48 | 57103.11 | 374342.59 | Paid | Low
EXP-02346 | PRJ-003 | PRJ-003-ACT-05 | 2025-04-17 | Labour | LAB-004 | Electrician | VEN-010 | 20 | Worker | 14982.25 | 15419.33 | 2775.48 | 18194.81 | Paid | High
EXP-02347 | PRJ-003 | PRJ-003-ACT-09 | 2025-04-22 | Equipment | EQ-003 | Concrete Mixer | VEN-005 | 1 | Day | 4791.19 | 4689.15 | 844.05 | 5533.2 | Pending | Low
EXP-02348 | PRJ-003 | PRJ-003-ACT-10 | 2025-04-22 | Other | OTH-001 | Permit | VEN-005 | 1 | Lot | 55979.87 | 54677.87 | 9842.02 | 64519.89 | Paid | Low
EXP-02349 | PRJ-003 | PRJ-003-ACT-10 | 2025-04-22 | Other | OTH-001 | Miscellaneous | VEN-005 | 1 | Lot | 5508.84 | 5782.04 | 1040.77 | 6822.81 | Paid | Low
EXP-02350 | PRJ-003 | PRJ-003-ACT-02 | 2025-04-22 | Labour | LAB-001 | Mason | VEN-005 | 24 | Worker | 31364.02 | 30409.53 | 5473.72 | 35883.25 | Paid | Low
EXP-02351 | PRJ-003 | PRJ-003-ACT-04 | 2025-04-22 | Material | MAT-004 | Aggregate | VEN-008 | 11.53 | Ton | 20100.72 | 19817.12 | 3567.08 | 23384.2 | Paid | Low
EXP-02352 | PRJ-003 | PRJ-003-ACT-04 | 2025-04-22 | Contractor | CON-003 | Plumbing Contract | VEN-010 | 1 | Contract | 306251.3 | 306762.18 | 55217.19 | 361979.37 | Pending | High
EXP-02353 | PRJ-003 | PRJ-003-ACT-01 | 2025-04-27 | Labour | LAB-001 | Mason | VEN-001 | 33 | Worker | 21353.35 | 22540.67 | 4057.32 | 26597.99 | Paid | Medium
EXP-02354 | PRJ-003 | PRJ-003-ACT-08 | 2025-04-27 | Equipment | EQ-004 | Scaffolding | VEN-001 | 4 | Day | 9280.7 | 9440.64 | 1699.32 | 11139.96 | Paid | Low
EXP-02355 | PRJ-003 | PRJ-003-ACT-05 | 2025-04-27 | Material | MAT-002 | Steel | VEN-001 | 25.05 | Ton | 1599550.57 | 1690516.51 | 304292.97 | 1994809.48 | Paid | Low
EXP-02356 | PRJ-003 | PRJ-003-ACT-09 | 2025-04-27 | Material | MAT-001 | Cement | VEN-010 | 27.64 | Bag | 13273.2 | 14051.39 | 2529.25 | 16580.64 | Pending | Low
EXP-02357 | PRJ-003 | PRJ-003-ACT-03 | 2025-04-27 | Equipment | EQ-003 | Concrete Mixer | VEN-008 | 5 | Day | 23050.75 | 21675.62 | 3901.61 | 25577.23 | Paid | Low
EXP-02358 | PRJ-003 | PRJ-003-ACT-08 | 2025-04-27 | Labour | LAB-006 | Painter | VEN-008 | 24 | Worker | 19799.86 | 20709.89 | 3727.78 | 24437.67 | Paid | Low
EXP-02359 | PRJ-003 | PRJ-003-ACT-04 | 2025-04-27 | Labour | LAB-004 | Electrician | VEN-010 | 23 | Worker | 29446.76 | 31271.08 | 5628.79 | 36899.87 | Paid | Medium
EXP-02360 | PRJ-003 | PRJ-003-ACT-09 | 2025-04-27 | Labour | LAB-001 | Mason | VEN-010 | 5 | Worker | 4658.47 | 4645.49 | 836.19 | 5481.68 | Partially Paid | Low
EXP-02361 | PRJ-003 | PRJ-003-ACT-07 | 2025-04-27 | Labour | LAB-001 | Mason | VEN-005 | 9 | Worker | 9818.21 | 9620.81 | 1731.75 | 11352.56 | Paid | Low
EXP-02362 | PRJ-003 | PRJ-003-ACT-05 | 2025-05-02 | Other | OTH-001 | Site Office | VEN-005 | 1 | Lot | 45025.92 | 45300.92 | 8154.17 | 53455.09 | Paid | Low
EXP-02363 | PRJ-003 | PRJ-003-ACT-05 | 2025-05-02 | Contractor | CON-001 | Civil Structure Contract | VEN-005 | 1 | Contract | 130640.92 | 130466.68 | 23484 | 153950.68 | Paid | Low
EXP-02364 | PRJ-003 | PRJ-003-ACT-08 | 2025-05-02 | Contractor | CON-002 | Electrical Contract | VEN-005 | 1 | Contract | 349144.41 | 324838.09 | 58470.86 | 383308.95 | Paid | Low
EXP-02365 | PRJ-003 | PRJ-003-ACT-07 | 2025-05-02 | Contractor | CON-004 | Finishing Contract | VEN-001 | 1 | Contract | 323752.7 | 310352.52 | 55863.45 | 366215.97 | Paid | Low
EXP-02366 | PRJ-003 | PRJ-003-ACT-04 | 2025-05-02 | Material | MAT-005 | Bricks | VEN-001 | 7.46 | Piece | 70.63 | 66.37 | 11.95 | 78.32 | Partially Paid | Medium
EXP-02367 | PRJ-003 | PRJ-003-ACT-06 | 2025-05-02 | Material | MAT-008 | Tiles | VEN-005 | 5.34 | Sq Ft | 339.56 | 348.95 | 62.81 | 411.76 | Paid | High
EXP-02368 | PRJ-003 | PRJ-003-ACT-03 | 2025-05-02 | Material | MAT-005 | Bricks | VEN-008 | 3.69 | Piece | 30.22 | 30.13 | 5.42 | 35.55 | Paid | Low
EXP-02369 | PRJ-003 | PRJ-003-ACT-03 | 2025-05-02 | Material | MAT-005 | Bricks | VEN-008 | 9.71 | Piece | 83.44 | 78.49 | 14.13 | 92.62 | Paid | Medium
EXP-02370 | PRJ-003 | PRJ-003-ACT-01 | 2025-05-07 | Labour | LAB-002 | Helper | VEN-010 | 31 | Worker | 44067.39 | 44327.09 | 7978.88 | 52305.97 | Paid | Medium
EXP-02371 | PRJ-003 | PRJ-003-ACT-03 | 2025-05-07 | Material | MAT-009 | Paint | VEN-008 | 36.02 | Litre | 7555.74 | 8087.67 | 1455.78 | 9543.45 | Paid | High
EXP-02372 | PRJ-003 | PRJ-003-ACT-02 | 2025-05-07 | Labour | LAB-001 | Mason | VEN-005 | 34 | Worker | 33704.35 | 31652.75 | 5697.49 | 37350.24 | Paid | Medium
EXP-02373 | PRJ-003 | PRJ-003-ACT-09 | 2025-05-07 | Contractor | CON-004 | Finishing Contract | VEN-010 | 1 | Contract | 421648.38 | 405454.77 | 72981.86 | 478436.63 | Paid | Medium
EXP-02374 | PRJ-003 | PRJ-003-ACT-08 | 2025-05-07 | Labour | LAB-005 | Plumber | VEN-001 | 17 | Worker | 14220.67 | 13726.7 | 2470.81 | 16197.51 | Paid | Medium
EXP-02375 | PRJ-003 | PRJ-003-ACT-09 | 2025-05-07 | Equipment | EQ-002 | Excavator | VEN-001 | 5 | Day | 72429.64 | 74880.07 | 13478.41 | 88358.48 | Paid | Low
EXP-02376 | PRJ-003 | PRJ-003-ACT-08 | 2025-05-12 | Material | MAT-003 | Sand | VEN-010 | 6.08 | Ton | 11691.94 | 10834.49 | 1950.21 | 12784.7 | Paid | Medium
EXP-02377 | PRJ-003 | PRJ-003-ACT-08 | 2025-05-12 | Labour | LAB-001 | Mason | VEN-008 | 32 | Worker | 21901.55 | 21225.27 | 3820.55 | 25045.82 | Paid | Low
EXP-02378 | PRJ-003 | PRJ-003-ACT-04 | 2025-05-12 | Labour | LAB-001 | Mason | VEN-005 | 18 | Worker | 21852.87 | 22011.65 | 3962.1 | 25973.75 | Paid | Low
EXP-02379 | PRJ-003 | PRJ-003-ACT-03 | 2025-05-12 | Labour | LAB-003 | Carpenter | VEN-008 | 5 | Worker | 6850.95 | 7104.66 | 1278.84 | 8383.5 | Paid | Low
EXP-02380 | PRJ-003 | PRJ-003-ACT-07 | 2025-05-12 | Equipment | EQ-002 | Excavator | VEN-010 | 6 | Day | 80667.18 | 79295.67 | 14273.22 | 93568.89 | Paid | Low
EXP-02381 | PRJ-003 | PRJ-003-ACT-03 | 2025-05-12 | Labour | LAB-001 | Mason | VEN-001 | 12 | Worker | 17751.65 | 18796.01 | 3383.28 | 22179.29 | Paid | Low
EXP-02382 | PRJ-003 | PRJ-003-ACT-10 | 2025-05-12 | Contractor | CON-003 | Plumbing Contract | VEN-005 | 1 | Contract | 287296.04 | 281556.12 | 50680.1 | 332236.22 | Paid | Medium
EXP-02383 | PRJ-003 | PRJ-003-ACT-10 | 2025-05-12 | Contractor | CON-001 | Civil Structure Contract | VEN-010 | 1 | Contract | 97896.86 | 99752.41 | 17955.43 | 117707.84 | Paid | High
EXP-02384 | PRJ-003 | PRJ-003-ACT-02 | 2025-05-17 | Material | MAT-007 | PVC Pipe | VEN-008 | 7.92 | Meter | 1097.85 | 1040.27 | 187.25 | 1227.52 | Paid | Medium
EXP-02385 | PRJ-003 | PRJ-003-ACT-05 | 2025-05-17 | Equipment | EQ-002 | Excavator | VEN-008 | 3 | Day | 46708.76 | 44849.05 | 8072.83 | 52921.88 | Paid | High
EXP-02386 | PRJ-003 | PRJ-003-ACT-10 | 2025-05-17 | Material | MAT-004 | Aggregate | VEN-005 | 2.67 | Ton | 3872.07 | 4092.31 | 736.62 | 4828.93 | Paid | Medium
EXP-02387 | PRJ-003 | PRJ-003-ACT-01 | 2025-05-17 | Contractor | CON-003 | Plumbing Contract | VEN-010 | 1 | Contract | 284423.05 | 264687.44 | 47643.74 | 312331.18 | Pending | Medium
EXP-02388 | PRJ-003 | PRJ-003-ACT-01 | 2025-05-17 | Contractor | CON-002 | Electrical Contract | VEN-001 | 1 | Contract | 399481.43 | 413827.19 | 74488.89 | 488316.08 | Pending | Medium
EXP-02389 | PRJ-003 | PRJ-003-ACT-07 | 2025-05-17 | Other | OTH-001 | Permit | VEN-010 | 1 | Lot | 64688.6 | 60594.82 | 10907.07 | 71501.89 | Paid | Low
EXP-02390 | PRJ-003 | PRJ-003-ACT-07 | 2025-05-17 | Material | MAT-001 | Cement | VEN-005 | 19.05 | Bag | 8679.87 | 9431.34 | 1697.64 | 11128.98 | Paid | Low
EXP-02391 | PRJ-003 | PRJ-003-ACT-06 | 2025-05-22 | Material | MAT-005 | Bricks | VEN-005 | 1.95 | Piece | 18.26 | 18.97 | 3.41 | 22.38 | Partially Paid | Low
EXP-02392 | PRJ-003 | PRJ-003-ACT-10 | 2025-05-22 | Contractor | CON-002 | Electrical Contract | VEN-008 | 1 | Contract | 459560.77 | 437769.75 | 78798.55 | 516568.3 | Paid | Medium
EXP-02393 | PRJ-003 | PRJ-003-ACT-10 | 2025-05-22 | Labour | LAB-005 | Plumber | VEN-001 | 10 | Worker | 15098.81 | 15235.32 | 2742.36 | 17977.68 | Paid | Medium
EXP-02394 | PRJ-003 | PRJ-003-ACT-01 | 2025-05-22 | Labour | LAB-006 | Painter | VEN-005 | 32 | Worker | 27827.6 | 26754.63 | 4815.83 | 31570.46 | Paid | Low
EXP-02395 | PRJ-003 | PRJ-003-ACT-02 | 2025-05-22 | Contractor | CON-002 | Electrical Contract | VEN-008 | 1 | Contract | 423070.2 | 423065.98 | 76151.88 | 499217.86 | Partially Paid | Low
EXP-02396 | PRJ-003 | PRJ-003-ACT-05 | 2025-05-22 | Material | MAT-009 | Paint | VEN-008 | 12.6 | Litre | 2728.43 | 2621.49 | 471.87 | 3093.36 | Partially Paid | Medium
EXP-02397 | PRJ-003 | PRJ-003-ACT-03 | 2025-05-27 | Material | MAT-005 | Bricks | VEN-008 | 6.83 | Piece | 50.64 | 54.49 | 9.81 | 64.3 | Pending | Medium
EXP-02398 | PRJ-003 | PRJ-003-ACT-06 | 2025-05-27 | Material | MAT-002 | Steel | VEN-001 | 39.24 | Ton | 2474211.64 | 2631353.46 | 473643.62 | 3104997.08 | Partially Paid | Medium
EXP-02399 | PRJ-003 | PRJ-003-ACT-01 | 2025-05-27 | Equipment | EQ-002 | Excavator | VEN-001 | 6 | Day | 85854.59 | 80093.08 | 14416.75 | 94509.83 | Paid | Medium
EXP-02400 | PRJ-003 | PRJ-003-ACT-01 | 2025-05-27 | Material | MAT-007 | PVC Pipe | VEN-001 | 14.29 | Meter | 2077.51 | 1947.64 | 350.58 | 2298.22 | Paid | Medium
EXP-02401 | PRJ-003 | PRJ-003-ACT-04 | 2025-05-27 | Labour | LAB-002 | Helper | VEN-001 | 10 | Worker | 8114.28 | 8335.89 | 1500.46 | 9836.35 | Paid | Low
EXP-02402 | PRJ-003 | PRJ-003-ACT-08 | 2025-05-27 | Labour | LAB-001 | Mason | VEN-008 | 15 | Worker | 26526.21 | 26812.01 | 4826.16 | 31638.17 | Paid | Medium
EXP-02403 | PRJ-003 | PRJ-003-ACT-10 | 2025-05-27 | Equipment | EQ-004 | Scaffolding | VEN-001 | 2 | Day | 5515.99 | 5191.93 | 934.55 | 6126.48 | Partially Paid | High
EXP-02404 | PRJ-003 | PRJ-003-ACT-10 | 2025-05-27 | Labour | LAB-006 | Painter | VEN-005 | 27 | Worker | 45545.85 | 44627.56 | 8032.96 | 52660.52 | Paid | Low
EXP-02405 | PRJ-003 | PRJ-003-ACT-02 | 2025-05-27 | Material | MAT-005 | Bricks | VEN-005 | 14.39 | Piece | 140.81 | 132.4 | 23.83 | 156.23 | Partially Paid | Low
EXP-02406 | PRJ-003 | PRJ-003-ACT-09 | 2025-06-01 | Material | MAT-010 | Glass | VEN-005 | 1 | Sq Ft | 148.11 | 144.38 | 25.99 | 170.37 | Paid | Low
EXP-02407 | PRJ-003 | PRJ-003-ACT-01 | 2025-06-01 | Material | MAT-009 | Paint | VEN-005 | 11.64 | Litre | 2745.86 | 2730.4 | 491.47 | 3221.87 | Paid | Medium
EXP-02408 | PRJ-003 | PRJ-003-ACT-01 | 2025-06-01 | Labour | LAB-005 | Plumber | VEN-001 | 17 | Worker | 10730.83 | 11364.31 | 2045.58 | 13409.89 | Paid | Medium
EXP-02409 | PRJ-003 | PRJ-003-ACT-09 | 2025-06-01 | Material | MAT-001 | Cement | VEN-008 | 11.65 | Bag | 6780.12 | 6294.43 | 1133 | 7427.43 | Paid | High
EXP-02410 | PRJ-003 | PRJ-003-ACT-10 | 2025-06-01 | Material | MAT-004 | Aggregate | VEN-001 | 12.7 | Ton | 19224.1 | 18392.09 | 3310.58 | 21702.67 | Paid | High
EXP-02411 | PRJ-003 | PRJ-003-ACT-04 | 2025-06-01 | Material | MAT-005 | Bricks | VEN-010 | 5.55 | Piece | 46.46 | 44.7 | 8.05 | 52.75 | Paid | Low
EXP-02412 | PRJ-003 | PRJ-003-ACT-08 | 2025-06-01 | Contractor | CON-003 | Plumbing Contract | VEN-001 | 1 | Contract | 277529.85 | 281916.35 | 50744.94 | 332661.29 | Paid | Medium
EXP-02413 | PRJ-003 | PRJ-003-ACT-09 | 2025-06-01 | Labour | LAB-003 | Carpenter | VEN-001 | 5 | Worker | 8656.88 | 8946.71 | 1610.41 | 10557.12 | Paid | Low
EXP-02414 | PRJ-003 | PRJ-003-ACT-02 | 2025-06-01 | Material | MAT-007 | PVC Pipe | VEN-005 | 9.85 | Meter | 1346.5 | 1301.4 | 234.25 | 1535.65 | Paid | Medium
EXP-02415 | PRJ-003 | PRJ-003-ACT-10 | 2025-06-06 | Material | MAT-010 | Glass | VEN-005 | 7.9 | Sq Ft | 1239.17 | 1280 | 230.4 | 1510.4 | Paid | Medium
EXP-02416 | PRJ-003 | PRJ-003-ACT-07 | 2025-06-06 | Labour | LAB-006 | Painter | VEN-008 | 15 | Worker | 19048.66 | 18225.54 | 3280.6 | 21506.14 | Paid | Low
EXP-02417 | PRJ-003 | PRJ-003-ACT-04 | 2025-06-06 | Material | MAT-010 | Glass | VEN-001 | 1 | Sq Ft | 146.2 | 147.84 | 26.61 | 174.45 | Paid | Low
EXP-02418 | PRJ-003 | PRJ-003-ACT-05 | 2025-06-06 | Equipment | EQ-003 | Concrete Mixer | VEN-005 | 2 | Day | 8543.43 | 9118.6 | 1641.35 | 10759.95 | Paid | Low
EXP-02419 | PRJ-003 | PRJ-003-ACT-07 | 2025-06-06 | Material | MAT-009 | Paint | VEN-005 | 23.88 | Litre | 4628.58 | 5006.13 | 901.1 | 5907.23 | Paid | Low
EXP-02420 | PRJ-003 | PRJ-003-ACT-02 | 2025-06-06 | Contractor | CON-003 | Plumbing Contract | VEN-010 | 1 | Contract | 387502.49 | 364221.46 | 65559.86 | 429781.32 | Paid | Medium
EXP-02421 | PRJ-003 | PRJ-003-ACT-06 | 2025-06-11 | Labour | LAB-001 | Mason | VEN-005 | 7 | Worker | 8411.08 | 7855.36 | 1413.96 | 9269.32 | Paid | High
EXP-02422 | PRJ-003 | PRJ-003-ACT-06 | 2025-06-11 | Material | MAT-007 | PVC Pipe | VEN-010 | 4.98 | Meter | 547.37 | 550.72 | 99.13 | 649.85 | Paid | Medium
EXP-02423 | PRJ-003 | PRJ-003-ACT-04 | 2025-06-11 | Labour | LAB-001 | Mason | VEN-005 | 18 | Worker | 20791.93 | 22407.11 | 4033.28 | 26440.39 | Partially Paid | Low
EXP-02424 | PRJ-003 | PRJ-003-ACT-05 | 2025-06-11 | Contractor | CON-004 | Finishing Contract | VEN-010 | 1 | Contract | 184548.92 | 192954.19 | 34731.75 | 227685.94 | Paid | Low
EXP-02425 | PRJ-003 | PRJ-003-ACT-04 | 2025-06-11 | Contractor | CON-001 | Civil Structure Contract | VEN-010 | 1 | Contract | 252441.59 | 263061.41 | 47351.05 | 310412.46 | Paid | Medium
EXP-02426 | PRJ-003 | PRJ-003-ACT-06 | 2025-06-11 | Material | MAT-008 | Tiles | VEN-008 | 9.02 | Sq Ft | 685.97 | 710.89 | 127.96 | 838.85 | Paid | Low
EXP-02427 | PRJ-003 | PRJ-003-ACT-04 | 2025-06-11 | Material | MAT-009 | Paint | VEN-001 | 17.17 | Litre | 3610.75 | 3778.81 | 680.19 | 4459 | Pending | Low
EXP-02428 | PRJ-003 | PRJ-003-ACT-02 | 2025-06-11 | Labour | LAB-005 | Plumber | VEN-010 | 5 | Worker | 8155.42 | 7909.71 | 1423.75 | 9333.46 | Partially Paid | Medium
EXP-02429 | PRJ-003 | PRJ-003-ACT-08 | 2025-06-16 | Material | MAT-001 | Cement | VEN-008 | 9.81 | Bag | 5198.28 | 5016.73 | 903.01 | 5919.74 | Paid | Low
EXP-02430 | PRJ-003 | PRJ-003-ACT-01 | 2025-06-16 | Material | MAT-010 | Glass | VEN-001 | 7.88 | Sq Ft | 1269.2 | 1315.25 | 236.75 | 1552 | Pending | Low
EXP-02431 | PRJ-003 | PRJ-003-ACT-02 | 2025-06-16 | Labour | LAB-003 | Carpenter | VEN-001 | 19 | Worker | 32373.91 | 31937.16 | 5748.69 | 37685.85 | Pending | Low
EXP-02432 | PRJ-003 | PRJ-003-ACT-04 | 2025-06-16 | Equipment | EQ-004 | Scaffolding | VEN-001 | 5 | Day | 10651.9 | 11573.96 | 2083.31 | 13657.27 | Pending | Medium
EXP-02433 | PRJ-003 | PRJ-003-ACT-08 | 2025-06-16 | Contractor | CON-001 | Civil Structure Contract | VEN-005 | 1 | Contract | 232671.2 | 225245.63 | 40544.21 | 265789.84 | Paid | High
EXP-02434 | PRJ-003 | PRJ-003-ACT-05 | 2025-06-16 | Material | MAT-003 | Sand | VEN-005 | 9.32 | Ton | 15825.69 | 16801.49 | 3024.27 | 19825.76 | Paid | Low
EXP-02435 | PRJ-003 | PRJ-003-ACT-07 | 2025-06-16 | Material | MAT-005 | Bricks | VEN-005 | 3.31 | Piece | 27.27 | 25.36 | 4.56 | 29.92 | Pending | Low
EXP-02436 | PRJ-003 | PRJ-003-ACT-01 | 2025-06-16 | Other | OTH-001 | Safety | VEN-008 | 1 | Lot | 14749.55 | 13828.86 | 2489.19 | 16318.05 | Paid | Medium
EXP-02437 | PRJ-003 | PRJ-003-ACT-08 | 2025-06-16 | Contractor | CON-002 | Electrical Contract | VEN-010 | 1 | Contract | 449574.41 | 438623.16 | 78952.17 | 517575.33 | Paid | Low
EXP-02438 | PRJ-003 | PRJ-003-ACT-07 | 2025-06-16 | Equipment | EQ-004 | Scaffolding | VEN-008 | 2 | Day | 4844.87 | 5182.57 | 932.86 | 6115.43 | Partially Paid | Low
EXP-02439 | PRJ-003 | PRJ-003-ACT-03 | 2025-06-21 | Material | MAT-003 | Sand | VEN-001 | 13.79 | Ton | 28584.71 | 27978.22 | 5036.08 | 33014.3 | Paid | Medium
EXP-02440 | PRJ-003 | PRJ-003-ACT-01 | 2025-06-21 | Contractor | CON-001 | Civil Structure Contract | VEN-008 | 1 | Contract | 107088.03 | 100690.05 | 18124.21 | 118814.26 | Paid | Low
EXP-02441 | PRJ-003 | PRJ-003-ACT-04 | 2025-06-21 | Material | MAT-008 | Tiles | VEN-010 | 6.26 | Sq Ft | 454.33 | 484.72 | 87.25 | 571.97 | Paid | High
EXP-02442 | PRJ-003 | PRJ-003-ACT-09 | 2025-06-21 | Material | MAT-004 | Aggregate | VEN-010 | 2.35 | Ton | 3116.67 | 3370.74 | 606.73 | 3977.47 | Pending | Medium
EXP-02443 | PRJ-003 | PRJ-003-ACT-08 | 2025-06-21 | Labour | LAB-003 | Carpenter | VEN-001 | 22 | Worker | 27312.18 | 28134.2 | 5064.16 | 33198.36 | Paid | Medium
EXP-02444 | PRJ-003 | PRJ-003-ACT-06 | 2025-06-21 | Labour | LAB-004 | Electrician | VEN-010 | 22 | Worker | 36028.29 | 34255.36 | 6165.96 | 40421.32 | Paid | Medium
EXP-02445 | PRJ-003 | PRJ-003-ACT-01 | 2025-06-21 | Equipment | EQ-004 | Scaffolding | VEN-001 | 2 | Day | 4859.67 | 4887.74 | 879.79 | 5767.53 | Paid | Medium
EXP-02446 | PRJ-003 | PRJ-003-ACT-09 | 2025-06-26 | Material | MAT-003 | Sand | VEN-010 | 6.99 | Ton | 12870.11 | 12666.99 | 2280.06 | 14947.05 | Paid | Low
EXP-02447 | PRJ-003 | PRJ-003-ACT-01 | 2025-06-26 | Labour | LAB-006 | Painter | VEN-001 | 31 | Worker | 23414.7 | 24639.85 | 4435.17 | 29075.02 | Paid | Medium
EXP-02448 | PRJ-003 | PRJ-003-ACT-05 | 2025-06-26 | Material | MAT-010 | Glass | VEN-008 | 7.1 | Sq Ft | 1243.91 | 1292.26 | 232.61 | 1524.87 | Paid | Low
EXP-02449 | PRJ-003 | PRJ-003-ACT-08 | 2025-06-26 | Material | MAT-009 | Paint | VEN-005 | 6.02 | Litre | 1258 | 1247.27 | 224.51 | 1471.78 | Paid | Medium
EXP-02450 | PRJ-003 | PRJ-003-ACT-04 | 2025-06-26 | Contractor | CON-003 | Plumbing Contract | VEN-010 | 1 | Contract | 337217.03 | 314579.4 | 56624.29 | 371203.69 | Paid | Medium
EXP-02451 | PRJ-003 | PRJ-003-ACT-06 | 2025-06-26 | Equipment | EQ-001 | Crane | VEN-008 | 3 | Day | 52796.57 | 52609.34 | 9469.68 | 62079.02 | Paid | Medium
EXP-02452 | PRJ-003 | PRJ-003-ACT-10 | 2025-06-26 | Labour | LAB-001 | Mason | VEN-008 | 25 | Worker | 28339.19 | 27856.04 | 5014.09 | 32870.13 | Paid | Medium
EXP-02453 | PRJ-003 | PRJ-003-ACT-06 | 2025-06-26 | Material | MAT-001 | Cement | VEN-001 | 21.9 | Bag | 13132.48 | 13046.27 | 2348.33 | 15394.6 | Paid | Medium
EXP-02454 | PRJ-003 | PRJ-003-ACT-03 | 2025-06-26 | Other | OTH-001 | Miscellaneous | VEN-008 | 1 | Lot | 43232.79 | 45641.07 | 8215.39 | 53856.46 | Paid | Low
EXP-02455 | PRJ-003 | PRJ-003-ACT-06 | 2025-06-26 | Contractor | CON-003 | Plumbing Contract | VEN-008 | 1 | Contract | 337463.1 | 365410.72 | 65773.93 | 431184.65 | Paid | Low
EXP-02456 | PRJ-003 | PRJ-003-ACT-06 | 2025-07-01 | Other | OTH-001 | Miscellaneous | VEN-005 | 1 | Lot | 40644.84 | 38714.96 | 6968.69 | 45683.65 | Paid | Low
EXP-02457 | PRJ-003 | PRJ-003-ACT-09 | 2025-07-01 | Material | MAT-002 | Steel | VEN-005 | 18.88 | Ton | 1053723.45 | 1137463.78 | 204743.48 | 1342207.26 | Paid | Medium
EXP-02458 | PRJ-003 | PRJ-003-ACT-05 | 2025-07-01 | Contractor | CON-002 | Electrical Contract | VEN-010 | 1 | Contract | 263425.76 | 263650.67 | 47457.12 | 311107.79 | Paid | Medium
EXP-02459 | PRJ-003 | PRJ-003-ACT-02 | 2025-07-01 | Material | MAT-004 | Aggregate | VEN-005 | 31.62 | Ton | 47365.51 | 47172.33 | 8491.02 | 55663.35 | Paid | High
EXP-02460 | PRJ-003 | PRJ-003-ACT-01 | 2025-07-01 | Contractor | CON-002 | Electrical Contract | VEN-008 | 1 | Contract | 294074.47 | 318211.39 | 57278.05 | 375489.44 | Partially Paid | High
EXP-02461 | PRJ-003 | PRJ-003-ACT-05 | 2025-07-01 | Equipment | EQ-001 | Crane | VEN-008 | 5 | Day | 96458.3 | 92027.9 | 16565.02 | 108592.92 | Paid | Low
EXP-02462 | PRJ-003 | PRJ-003-ACT-10 | 2025-07-01 | Labour | LAB-001 | Mason | VEN-005 | 16 | Worker | 10478.34 | 11098.29 | 1997.69 | 13095.98 | Paid | Low
EXP-02463 | PRJ-003 | PRJ-003-ACT-08 | 2025-07-01 | Other | OTH-001 | Site Office | VEN-008 | 1 | Lot | 8120.64 | 8295.31 | 1493.16 | 9788.47 | Paid | Low
EXP-02464 | PRJ-003 | PRJ-003-ACT-09 | 2025-07-01 | Material | MAT-006 | Electrical Cable | VEN-008 | 12.84 | Meter | 902.01 | 942.05 | 169.57 | 1111.62 | Paid | Low
EXP-02465 | PRJ-003 | PRJ-003-ACT-02 | 2025-07-06 | Labour | LAB-004 | Electrician | VEN-001 | 14 | Worker | 22038.42 | 23299.55 | 4193.92 | 27493.47 | Paid | Medium
EXP-02466 | PRJ-003 | PRJ-003-ACT-04 | 2025-07-06 | Material | MAT-007 | PVC Pipe | VEN-008 | 11.97 | Meter | 1663.03 | 1540.63 | 277.31 | 1817.94 | Paid | Medium
EXP-02467 | PRJ-003 | PRJ-003-ACT-07 | 2025-07-06 | Other | OTH-001 | Permit | VEN-001 | 1 | Lot | 47216.55 | 48542.53 | 8737.66 | 57280.19 | Partially Paid | Medium
EXP-02468 | PRJ-003 | PRJ-003-ACT-02 | 2025-07-06 | Equipment | EQ-003 | Concrete Mixer | VEN-008 | 7 | Day | 33254.66 | 32983.38 | 5937.01 | 38920.39 | Paid | Low
EXP-02469 | PRJ-003 | PRJ-003-ACT-08 | 2025-07-06 | Contractor | CON-001 | Civil Structure Contract | VEN-005 | 1 | Contract | 248193.73 | 239425.63 | 43096.61 | 282522.24 | Pending | Medium
EXP-02470 | PRJ-003 | PRJ-003-ACT-10 | 2025-07-06 | Labour | LAB-006 | Painter | VEN-001 | 31 | Worker | 24583.46 | 26465.22 | 4763.74 | 31228.96 | Partially Paid | Medium
EXP-02471 | PRJ-003 | PRJ-003-ACT-07 | 2025-07-06 | Material | MAT-002 | Steel | VEN-008 | 14.22 | Ton | 886180.7 | 918142.75 | 165265.7 | 1083408.45 | Partially Paid | Low
EXP-02472 | PRJ-003 | PRJ-003-ACT-08 | 2025-07-06 | Labour | LAB-001 | Mason | VEN-001 | 12 | Worker | 17787.29 | 17139.39 | 3085.09 | 20224.48 | Paid | Low
EXP-02473 | PRJ-003 | PRJ-003-ACT-08 | 2025-07-06 | Contractor | CON-002 | Electrical Contract | VEN-001 | 1 | Contract | 290382.68 | 291115.81 | 52400.85 | 343516.66 | Partially Paid | Medium
EXP-02474 | PRJ-003 | PRJ-003-ACT-07 | 2025-07-06 | Contractor | CON-001 | Civil Structure Contract | VEN-005 | 1 | Contract | 303490.42 | 318811.32 | 57386.04 | 376197.36 | Paid | Medium
EXP-02475 | PRJ-003 | PRJ-003-ACT-01 | 2025-07-11 | Material | MAT-005 | Bricks | VEN-010 | 5.14 | Piece | 46.27 | 43.36 | 7.8 | 51.16 | Partially Paid | Low
EXP-02476 | PRJ-003 | PRJ-003-ACT-07 | 2025-07-11 | Material | MAT-007 | PVC Pipe | VEN-010 | 15.7 | Meter | 2078.25 | 2014.24 | 362.56 | 2376.8 | Paid | Low
EXP-02477 | PRJ-003 | PRJ-003-ACT-05 | 2025-07-11 | Other | OTH-001 | Safety | VEN-001 | 1 | Lot | 8236.84 | 7929.1 | 1427.24 | 9356.34 | Paid | Medium
EXP-02478 | PRJ-003 | PRJ-003-ACT-02 | 2025-07-11 | Equipment | EQ-002 | Excavator | VEN-010 | 1 | Day | 13741.23 | 14226.91 | 2560.84 | 16787.75 | Paid | Medium
EXP-02479 | PRJ-003 | PRJ-003-ACT-04 | 2025-07-11 | Material | MAT-002 | Steel | VEN-008 | 12.26 | Ton | 734914.93 | 740908.97 | 133363.61 | 874272.58 | Partially Paid | Medium
EXP-02480 | PRJ-003 | PRJ-003-ACT-08 | 2025-07-11 | Material | MAT-008 | Tiles | VEN-005 | 1 | Sq Ft | 70.85 | 76.64 | 13.8 | 90.44 | Paid | Medium
EXP-02481 | PRJ-003 | PRJ-003-ACT-07 | 2025-07-11 | Material | MAT-010 | Glass | VEN-005 | 3.54 | Sq Ft | 557.83 | 559.74 | 100.75 | 660.49 | Paid | Medium
EXP-02482 | PRJ-003 | PRJ-003-ACT-06 | 2025-07-11 | Labour | LAB-004 | Electrician | VEN-005 | 32 | Worker | 22803.06 | 22767.54 | 4098.16 | 26865.7 | Paid | Low
EXP-02483 | PRJ-003 | PRJ-003-ACT-06 | 2025-07-11 | Labour | LAB-005 | Plumber | VEN-008 | 12 | Worker | 10650.09 | 10349.76 | 1862.96 | 12212.72 | Partially Paid | Low
EXP-02484 | PRJ-003 | PRJ-003-ACT-04 | 2025-07-11 | Contractor | CON-002 | Electrical Contract | VEN-001 | 1 | Contract | 413933.29 | 395898.41 | 71261.71 | 467160.12 | Partially Paid | Low
EXP-02485 | PRJ-003 | PRJ-003-ACT-09 | 2025-07-16 | Equipment | EQ-001 | Crane | VEN-010 | 1 | Day | 17223.37 | 17378.91 | 3128.2 | 20507.11 | Paid | Medium
EXP-02486 | PRJ-003 | PRJ-003-ACT-05 | 2025-07-16 | Labour | LAB-002 | Helper | VEN-008 | 32 | Worker | 53480.45 | 53361.73 | 9605.11 | 62966.84 | Paid | Low
EXP-02487 | PRJ-003 | PRJ-003-ACT-04 | 2025-07-16 | Material | MAT-008 | Tiles | VEN-005 | 15.54 | Sq Ft | 1120.33 | 1068.58 | 192.34 | 1260.92 | Partially Paid | Low
EXP-02488 | PRJ-003 | PRJ-003-ACT-07 | 2025-07-16 | Material | MAT-010 | Glass | VEN-005 | 1.91 | Sq Ft | 298.66 | 311.53 | 56.08 | 367.61 | Paid | Low
EXP-02489 | PRJ-003 | PRJ-003-ACT-10 | 2025-07-16 | Material | MAT-008 | Tiles | VEN-008 | 3.8 | Sq Ft | 319.01 | 308.34 | 55.5 | 363.84 | Paid | Medium
EXP-02490 | PRJ-003 | PRJ-003-ACT-05 | 2025-07-16 | Material | MAT-003 | Sand | VEN-001 | 2.78 | Ton | 4735.46 | 4400.66 | 792.12 | 5192.78 | Paid | Low
EXP-02491 | PRJ-003 | PRJ-003-ACT-09 | 2025-07-16 | Material | MAT-008 | Tiles | VEN-001 | 2.63 | Sq Ft | 226.45 | 210.78 | 37.94 | 248.72 | Paid | Low
EXP-02492 | PRJ-003 | PRJ-003-ACT-02 | 2025-07-16 | Equipment | EQ-004 | Scaffolding | VEN-001 | 4 | Day | 9130.84 | 9464.65 | 1703.64 | 11168.29 | Pending | Low
EXP-02493 | PRJ-003 | PRJ-003-ACT-02 | 2025-07-16 | Labour | LAB-001 | Mason | VEN-008 | 29 | Worker | 44656.38 | 46020.17 | 8283.63 | 54303.8 | Paid | Low
EXP-02494 | PRJ-003 | PRJ-003-ACT-03 | 2025-07-21 | Labour | LAB-004 | Electrician | VEN-005 | 14 | Worker | 16441.26 | 16102.47 | 2898.44 | 19000.91 | Paid | Low
EXP-02495 | PRJ-003 | PRJ-003-ACT-08 | 2025-07-21 | Material | MAT-007 | PVC Pipe | VEN-005 | 5.21 | Meter | 583.39 | 589.59 | 106.13 | 695.72 | Paid | Low
EXP-02496 | PRJ-003 | PRJ-003-ACT-04 | 2025-07-21 | Material | MAT-005 | Bricks | VEN-005 | 6.9 | Piece | 50.6 | 52.97 | 9.53 | 62.5 | Paid | Medium
EXP-02497 | PRJ-003 | PRJ-003-ACT-03 | 2025-07-21 | Equipment | EQ-004 | Scaffolding | VEN-010 | 7 | Day | 19040.43 | 18332.82 | 3299.91 | 21632.73 | Paid | Low
EXP-02498 | PRJ-003 | PRJ-003-ACT-04 | 2025-07-21 | Contractor | CON-002 | Electrical Contract | VEN-010 | 1 | Contract | 455516.67 | 445198.89 | 80135.8 | 525334.69 | Paid | Low
EXP-02499 | PRJ-003 | PRJ-003-ACT-03 | 2025-07-21 | Material | MAT-005 | Bricks | VEN-008 | 4.53 | Piece | 39.97 | 37.02 | 6.66 | 43.68 | Paid | Medium
EXP-02500 | PRJ-003 | PRJ-003-ACT-07 | 2025-07-21 | Labour | LAB-002 | Helper | VEN-010 | 14 | Worker | 17246.2 | 18710.92 | 3367.97 | 22078.89 | Partially Paid | Low
EXP-02501 | PRJ-003 | PRJ-003-ACT-06 | 2025-07-26 | Labour | LAB-003 | Carpenter | VEN-005 | 14 | Worker | 24016.54 | 24424.12 | 4396.34 | 28820.46 | Paid | Medium
EXP-02502 | PRJ-003 | PRJ-003-ACT-09 | 2025-07-26 | Contractor | CON-003 | Plumbing Contract | VEN-010 | 1 | Contract | 400857.37 | 409488.72 | 73707.97 | 483196.69 | Paid | Low
EXP-02503 | PRJ-003 | PRJ-003-ACT-02 | 2025-07-26 | Labour | LAB-005 | Plumber | VEN-001 | 7 | Worker | 11279.85 | 11361.97 | 2045.15 | 13407.12 | Paid | Low
EXP-02504 | PRJ-003 | PRJ-003-ACT-02 | 2025-07-26 | Labour | LAB-001 | Mason | VEN-005 | 15 | Worker | 22789.49 | 24558.28 | 4420.49 | 28978.77 | Paid | Low
EXP-02505 | PRJ-003 | PRJ-003-ACT-08 | 2025-07-26 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 418590.93 | 413824.21 | 74488.36 | 488312.57 | Paid | Medium
EXP-02506 | PRJ-003 | PRJ-003-ACT-05 | 2025-07-26 | Material | MAT-008 | Tiles | VEN-005 | 10.23 | Sq Ft | 746.75 | 775.96 | 139.67 | 915.63 | Partially Paid | Medium
EXP-02507 | PRJ-003 | PRJ-003-ACT-07 | 2025-07-26 | Material | MAT-008 | Tiles | VEN-008 | 16.23 | Sq Ft | 1209.71 | 1174.13 | 211.34 | 1385.47 | Paid | Low
EXP-02508 | PRJ-003 | PRJ-003-ACT-06 | 2025-07-26 | Material | MAT-006 | Electrical Cable | VEN-005 | 7.32 | Meter | 633.1 | 668.08 | 120.25 | 788.33 | Paid | Low
EXP-02509 | PRJ-003 | PRJ-003-ACT-04 | 2025-07-26 | Contractor | CON-004 | Finishing Contract | VEN-001 | 1 | Contract | 258233.74 | 246380.76 | 44348.54 | 290729.3 | Paid | Low
EXP-02510 | PRJ-003 | PRJ-003-ACT-08 | 2025-07-26 | Labour | LAB-005 | Plumber | VEN-008 | 31 | Worker | 53565.35 | 53010.23 | 9541.84 | 62552.07 | Paid | Medium
EXP-02511 | PRJ-003 | PRJ-003-ACT-05 | 2025-07-31 | Labour | LAB-001 | Mason | VEN-010 | 14 | Worker | 14386.86 | 14922.22 | 2686 | 17608.22 | Pending | Medium
EXP-02512 | PRJ-003 | PRJ-003-ACT-08 | 2025-07-31 | Material | MAT-005 | Bricks | VEN-005 | 7.17 | Piece | 70.16 | 65.94 | 11.87 | 77.81 | Paid | Medium
EXP-02513 | PRJ-003 | PRJ-003-ACT-03 | 2025-07-31 | Labour | LAB-002 | Helper | VEN-008 | 10 | Worker | 13254.69 | 13542.02 | 2437.56 | 15979.58 | Paid | Low
EXP-02514 | PRJ-003 | PRJ-003-ACT-07 | 2025-07-31 | Equipment | EQ-002 | Excavator | VEN-010 | 5 | Day | 74154.27 | 69852.53 | 12573.46 | 82425.99 | Paid | Low
EXP-02515 | PRJ-003 | PRJ-003-ACT-02 | 2025-07-31 | Labour | LAB-003 | Carpenter | VEN-005 | 9 | Worker | 13161.82 | 12824.85 | 2308.47 | 15133.32 | Paid | Low
EXP-02516 | PRJ-003 | PRJ-003-ACT-06 | 2025-07-31 | Labour | LAB-006 | Painter | VEN-005 | 5 | Worker | 3600.44 | 3356.84 | 604.23 | 3961.07 | Partially Paid | Low
EXP-02517 | PRJ-003 | PRJ-003-ACT-06 | 2025-07-31 | Labour | LAB-002 | Helper | VEN-001 | 25 | Worker | 28945.07 | 29366.99 | 5286.06 | 34653.05 | Partially Paid | Low
EXP-02518 | PRJ-003 | PRJ-003-ACT-01 | 2025-07-31 | Material | MAT-006 | Electrical Cable | VEN-010 | 17.77 | Meter | 1847.24 | 1724.32 | 310.38 | 2034.7 | Paid | High
EXP-02519 | PRJ-003 | PRJ-003-ACT-07 | 2025-08-05 | Equipment | EQ-002 | Excavator | VEN-008 | 2 | Day | 28880.16 | 29035.26 | 5226.35 | 34261.61 | Paid | Medium
EXP-02520 | PRJ-003 | PRJ-003-ACT-09 | 2025-08-05 | Other | OTH-001 | Site Office | VEN-005 | 1 | Lot | 50884.53 | 50000.34 | 9000.06 | 59000.4 | Paid | Low
EXP-02521 | PRJ-003 | PRJ-003-ACT-04 | 2025-08-05 | Labour | LAB-004 | Electrician | VEN-001 | 16 | Worker | 18197.1 | 18322.29 | 3298.01 | 21620.3 | Paid | Medium
EXP-02522 | PRJ-003 | PRJ-003-ACT-05 | 2025-08-05 | Labour | LAB-004 | Electrician | VEN-010 | 9 | Worker | 10688.44 | 10100.12 | 1818.02 | 11918.14 | Paid | High
EXP-02523 | PRJ-003 | PRJ-003-ACT-08 | 2025-08-05 | Material | MAT-007 | PVC Pipe | VEN-010 | 1 | Meter | 118.7 | 119.91 | 21.58 | 141.49 | Paid | Low
EXP-02524 | PRJ-003 | PRJ-003-ACT-01 | 2025-08-05 | Labour | LAB-005 | Plumber | VEN-010 | 12 | Worker | 12831.29 | 13011.28 | 2342.03 | 15353.31 | Paid | Low
EXP-02525 | PRJ-003 | PRJ-003-ACT-08 | 2025-08-05 | Labour | LAB-004 | Electrician | VEN-010 | 5 | Worker | 8698.93 | 8417.27 | 1515.11 | 9932.38 | Pending | Medium
EXP-02526 | PRJ-003 | PRJ-003-ACT-02 | 2025-08-05 | Other | OTH-001 | Miscellaneous | VEN-001 | 1 | Lot | 77723.66 | 78761.99 | 14177.16 | 92939.15 | Paid | Low
EXP-02527 | PRJ-003 | PRJ-003-ACT-10 | 2025-08-10 | Material | MAT-002 | Steel | VEN-001 | 8.06 | Ton | 607210.47 | 570947.27 | 102770.51 | 673717.78 | Paid | Low
EXP-02528 | PRJ-003 | PRJ-003-ACT-07 | 2025-08-10 | Material | MAT-008 | Tiles | VEN-005 | 7.41 | Sq Ft | 571.89 | 543.43 | 97.82 | 641.25 | Paid | Medium
EXP-02529 | PRJ-003 | PRJ-003-ACT-10 | 2025-08-10 | Material | MAT-003 | Sand | VEN-005 | 14.26 | Ton | 22970.49 | 22533.79 | 4056.08 | 26589.87 | Paid | Low
EXP-02530 | PRJ-003 | PRJ-003-ACT-01 | 2025-08-10 | Labour | LAB-004 | Electrician | VEN-010 | 11 | Worker | 18779.75 | 18450.79 | 3321.14 | 21771.93 | Paid | Low
EXP-02531 | PRJ-003 | PRJ-003-ACT-02 | 2025-08-10 | Labour | LAB-003 | Carpenter | VEN-010 | 26 | Worker | 42705.2 | 41068.96 | 7392.41 | 48461.37 | Paid | Medium
EXP-02532 | PRJ-003 | PRJ-003-ACT-09 | 2025-08-10 | Material | MAT-001 | Cement | VEN-010 | 60.05 | Bag | 30115.25 | 28862.04 | 5195.17 | 34057.21 | Paid | Low
EXP-02533 | PRJ-003 | PRJ-003-ACT-07 | 2025-08-10 | Labour | LAB-005 | Plumber | VEN-010 | 27 | Worker | 51547.92 | 48467.98 | 8724.24 | 57192.22 | Paid | Low
EXP-02534 | PRJ-003 | PRJ-003-ACT-06 | 2025-08-10 | Material | MAT-002 | Steel | VEN-008 | 6.9 | Ton | 429712.84 | 409682.06 | 73742.77 | 483424.83 | Paid | Low
EXP-02535 | PRJ-003 | PRJ-003-ACT-06 | 2025-08-15 | Contractor | CON-004 | Finishing Contract | VEN-001 | 1 | Contract | 345197.26 | 322659.16 | 58078.65 | 380737.81 | Paid | Low
EXP-02536 | PRJ-003 | PRJ-003-ACT-09 | 2025-08-15 | Material | MAT-004 | Aggregate | VEN-008 | 5.1 | Ton | 8315.31 | 7937.24 | 1428.7 | 9365.94 | Paid | Low
EXP-02537 | PRJ-003 | PRJ-003-ACT-02 | 2025-08-15 | Contractor | CON-001 | Civil Structure Contract | VEN-010 | 1 | Contract | 93651.91 | 101620.95 | 18291.77 | 119912.72 | Paid | Low
EXP-02538 | PRJ-003 | PRJ-003-ACT-07 | 2025-08-15 | Material | MAT-003 | Sand | VEN-008 | 2.76 | Ton | 4315.04 | 4436.15 | 798.51 | 5234.66 | Paid | Medium
EXP-02539 | PRJ-003 | PRJ-003-ACT-04 | 2025-08-15 | Labour | LAB-003 | Carpenter | VEN-005 | 13 | Worker | 15515.69 | 14575.72 | 2623.63 | 17199.35 | Partially Paid | Medium
EXP-02540 | PRJ-003 | PRJ-003-ACT-05 | 2025-08-15 | Equipment | EQ-003 | Concrete Mixer | VEN-001 | 4 | Day | 19002.48 | 19227 | 3460.86 | 22687.86 | Paid | Medium
EXP-02541 | PRJ-003 | PRJ-003-ACT-01 | 2025-08-15 | Labour | LAB-002 | Helper | VEN-008 | 7 | Worker | 7491.52 | 7499.39 | 1349.89 | 8849.28 | Paid | High
EXP-02542 | PRJ-003 | PRJ-003-ACT-09 | 2025-08-15 | Contractor | CON-002 | Electrical Contract | VEN-005 | 1 | Contract | 302858.87 | 301425.29 | 54256.55 | 355681.84 | Pending | Medium
EXP-02543 | PRJ-003 | PRJ-003-ACT-03 | 2025-08-15 | Labour | LAB-005 | Plumber | VEN-008 | 34 | Worker | 23385.74 | 22694.97 | 4085.09 | 26780.06 | Paid | Low
EXP-02544 | PRJ-003 | PRJ-003-ACT-05 | 2025-08-20 | Material | MAT-005 | Bricks | VEN-010 | 4.1 | Piece | 30.62 | 32.54 | 5.86 | 38.4 | Paid | Low
EXP-02545 | PRJ-003 | PRJ-003-ACT-03 | 2025-08-20 | Labour | LAB-006 | Painter | VEN-008 | 6 | Worker | 9978.15 | 10674.54 | 1921.42 | 12595.96 | Paid | Low
EXP-02546 | PRJ-003 | PRJ-003-ACT-02 | 2025-08-20 | Material | MAT-004 | Aggregate | VEN-001 | 5.41 | Ton | 7870.61 | 7429.08 | 1337.23 | 8766.31 | Partially Paid | Low
EXP-02547 | PRJ-003 | PRJ-003-ACT-07 | 2025-08-20 | Material | MAT-002 | Steel | VEN-005 | 10.03 | Ton | 679450.5 | 706337.21 | 127140.7 | 833477.91 | Partially Paid | High
EXP-02548 | PRJ-003 | PRJ-003-ACT-07 | 2025-08-20 | Material | MAT-001 | Cement | VEN-008 | 5.52 | Bag | 2451.53 | 2543.03 | 457.75 | 3000.78 | Paid | High
EXP-02549 | PRJ-003 | PRJ-003-ACT-06 | 2025-08-20 | Equipment | EQ-002 | Excavator | VEN-005 | 2 | Day | 28883.39 | 26778.41 | 4820.11 | 31598.52 | Paid | Low
EXP-02550 | PRJ-003 | PRJ-003-ACT-04 | 2025-08-25 | Material | MAT-004 | Aggregate | VEN-001 | 1.07 | Ton | 1732.61 | 1615.56 | 290.8 | 1906.36 | Paid | Medium
EXP-02551 | PRJ-003 | PRJ-003-ACT-01 | 2025-08-25 | Material | MAT-009 | Paint | VEN-001 | 3.17 | Litre | 730.87 | 741.03 | 133.39 | 874.42 | Paid | Low
EXP-02552 | PRJ-003 | PRJ-003-ACT-06 | 2025-08-25 | Material | MAT-006 | Electrical Cable | VEN-008 | 2.55 | Meter | 205.83 | 192.86 | 34.71 | 227.57 | Paid | Low
EXP-02553 | PRJ-003 | PRJ-003-ACT-05 | 2025-08-25 | Contractor | CON-003 | Plumbing Contract | VEN-010 | 1 | Contract | 249035.46 | 233066.45 | 41951.96 | 275018.41 | Partially Paid | Low
EXP-02554 | PRJ-003 | PRJ-003-ACT-10 | 2025-08-25 | Material | MAT-009 | Paint | VEN-001 | 11.99 | Litre | 2632.89 | 2493.38 | 448.81 | 2942.19 | Paid | Low
EXP-02555 | PRJ-003 | PRJ-003-ACT-04 | 2025-08-25 | Contractor | CON-003 | Plumbing Contract | VEN-010 | 1 | Contract | 228329.42 | 234229.45 | 42161.3 | 276390.75 | Paid | Medium
EXP-02556 | PRJ-003 | PRJ-003-ACT-07 | 2025-08-25 | Material | MAT-001 | Cement | VEN-008 | 8.45 | Bag | 4092.79 | 4319.28 | 777.47 | 5096.75 | Paid | Low
EXP-02557 | PRJ-003 | PRJ-003-ACT-06 | 2025-08-25 | Material | MAT-009 | Paint | VEN-010 | 7.75 | Litre | 1872.67 | 1743.98 | 313.92 | 2057.9 | Paid | Medium
EXP-02558 | PRJ-003 | PRJ-003-ACT-02 | 2025-08-25 | Material | MAT-003 | Sand | VEN-005 | 5.45 | Ton | 9353.64 | 8933.41 | 1608.01 | 10541.42 | Partially Paid | Low
EXP-02559 | PRJ-003 | PRJ-003-ACT-07 | 2025-08-30 | Material | MAT-002 | Steel | VEN-001 | 7.95 | Ton | 480174.35 | 467243.72 | 84103.87 | 551347.59 | Paid | Low
EXP-02560 | PRJ-003 | PRJ-003-ACT-10 | 2025-08-30 | Material | MAT-009 | Paint | VEN-010 | 15.49 | Litre | 3159.4 | 3262.54 | 587.26 | 3849.8 | Paid | Low
EXP-02561 | PRJ-003 | PRJ-003-ACT-03 | 2025-08-30 | Contractor | CON-004 | Finishing Contract | VEN-010 | 1 | Contract | 380637.61 | 410505.44 | 73890.98 | 484396.42 | Paid | Medium
EXP-02562 | PRJ-003 | PRJ-003-ACT-01 | 2025-08-30 | Equipment | EQ-003 | Concrete Mixer | VEN-005 | 2 | Day | 8310.33 | 8641.17 | 1555.41 | 10196.58 | Partially Paid | Low
EXP-02563 | PRJ-003 | PRJ-003-ACT-04 | 2025-08-30 | Equipment | EQ-004 | Scaffolding | VEN-008 | 2 | Day | 5761.31 | 5494.76 | 989.06 | 6483.82 | Paid | Medium
EXP-02564 | PRJ-003 | PRJ-003-ACT-04 | 2025-08-30 | Contractor | CON-004 | Finishing Contract | VEN-001 | 1 | Contract | 322624.17 | 325857.4 | 58654.33 | 384511.73 | Paid | Medium
EXP-02565 | PRJ-003 | PRJ-003-ACT-08 | 2025-08-30 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 189163.8 | 185029.09 | 33305.24 | 218334.33 | Paid | Medium
EXP-02566 | PRJ-003 | PRJ-003-ACT-06 | 2025-09-04 | Material | MAT-003 | Sand | VEN-010 | 3.78 | Ton | 6583.4 | 6386.85 | 1149.63 | 7536.48 | Paid | Low
EXP-02567 | PRJ-003 | PRJ-003-ACT-09 | 2025-09-04 | Material | MAT-006 | Electrical Cable | VEN-001 | 12.5 | Meter | 1125.06 | 1155.97 | 208.07 | 1364.04 | Paid | Low
EXP-02568 | PRJ-003 | PRJ-003-ACT-07 | 2025-09-04 | Material | MAT-010 | Glass | VEN-001 | 9.68 | Sq Ft | 1599.87 | 1548.6 | 278.75 | 1827.35 | Paid | Medium
EXP-02569 | PRJ-003 | PRJ-003-ACT-07 | 2025-09-04 | Material | MAT-003 | Sand | VEN-005 | 35.69 | Ton | 69281.43 | 72861.63 | 13115.09 | 85976.72 | Partially Paid | Low
EXP-02570 | PRJ-003 | PRJ-003-ACT-09 | 2025-09-04 | Material | MAT-006 | Electrical Cable | VEN-005 | 2.98 | Meter | 283.26 | 266.85 | 48.03 | 314.88 | Paid | Medium
EXP-02571 | PRJ-003 | PRJ-003-ACT-05 | 2025-09-04 | Contractor | CON-004 | Finishing Contract | VEN-008 | 1 | Contract | 270713.57 | 262243.18 | 47203.77 | 309446.95 | Paid | Medium
EXP-02572 | PRJ-003 | PRJ-003-ACT-07 | 2025-09-04 | Material | MAT-008 | Tiles | VEN-008 | 9.02 | Sq Ft | 701.07 | 658.14 | 118.47 | 776.61 | Paid | Medium
EXP-02573 | PRJ-003 | PRJ-003-ACT-01 | 2025-09-04 | Material | MAT-007 | PVC Pipe | VEN-008 | 14.78 | Meter | 2153.84 | 2008.84 | 361.59 | 2370.43 | Partially Paid | Low
EXP-02574 | PRJ-003 | PRJ-003-ACT-09 | 2025-09-09 | Material | MAT-009 | Paint | VEN-001 | 12.41 | Litre | 3031.45 | 2984.38 | 537.19 | 3521.57 | Partially Paid | High
EXP-02575 | PRJ-003 | PRJ-003-ACT-03 | 2025-09-09 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 108282.13 | 105995.65 | 19079.22 | 125074.87 | Paid | Low
EXP-02576 | PRJ-003 | PRJ-003-ACT-09 | 2025-09-09 | Contractor | CON-004 | Finishing Contract | VEN-001 | 1 | Contract | 91863.41 | 95958.1 | 17272.46 | 113230.56 | Paid | Low
EXP-02577 | PRJ-003 | PRJ-003-ACT-06 | 2025-09-09 | Material | MAT-005 | Bricks | VEN-008 | 9.15 | Piece | 90.15 | 87.18 | 15.69 | 102.87 | Partially Paid | Medium
EXP-02578 | PRJ-003 | PRJ-003-ACT-01 | 2025-09-09 | Material | MAT-005 | Bricks | VEN-001 | 6.97 | Piece | 68.03 | 68.51 | 12.33 | 80.84 | Partially Paid | High
EXP-02579 | PRJ-003 | PRJ-003-ACT-10 | 2025-09-09 | Material | MAT-002 | Steel | VEN-001 | 2.49 | Ton | 160629.63 | 158509.39 | 28531.69 | 187041.08 | Paid | Low
EXP-02580 | PRJ-003 | PRJ-003-ACT-02 | 2025-09-09 | Contractor | CON-002 | Electrical Contract | VEN-010 | 1 | Contract | 347550.53 | 326055.38 | 58689.97 | 384745.35 | Pending | Low
EXP-02581 | PRJ-003 | PRJ-003-ACT-10 | 2025-09-09 | Material | MAT-008 | Tiles | VEN-001 | 10.94 | Sq Ft | 882.82 | 878.59 | 158.15 | 1036.74 | Paid | Low
EXP-02582 | PRJ-003 | PRJ-003-ACT-02 | 2025-09-09 | Material | MAT-008 | Tiles | VEN-008 | 7.31 | Sq Ft | 506.34 | 483.36 | 87 | 570.36 | Pending | Low
EXP-02583 | PRJ-003 | PRJ-003-ACT-03 | 2025-09-09 | Material | MAT-007 | PVC Pipe | VEN-005 | 6.67 | Meter | 892.12 | 868.36 | 156.3 | 1024.66 | Paid | Low
EXP-02584 | PRJ-003 | PRJ-003-ACT-07 | 2025-09-14 | Material | MAT-003 | Sand | VEN-005 | 15.12 | Ton | 27337.52 | 25954.08 | 4671.73 | 30625.81 | Paid | Medium
EXP-02585 | PRJ-003 | PRJ-003-ACT-04 | 2025-09-14 | Labour | LAB-003 | Carpenter | VEN-005 | 24 | Worker | 23507.81 | 22219.63 | 3999.53 | 26219.16 | Paid | Medium
EXP-02586 | PRJ-003 | PRJ-003-ACT-08 | 2025-09-14 | Equipment | EQ-004 | Scaffolding | VEN-010 | 1 | Day | 2298.01 | 2285.02 | 411.3 | 2696.32 | Pending | Medium
EXP-02587 | PRJ-003 | PRJ-003-ACT-10 | 2025-09-14 | Material | MAT-003 | Sand | VEN-008 | 19.64 | Ton | 40147.5 | 39366.35 | 7085.94 | 46452.29 | Partially Paid | Low
EXP-02588 | PRJ-003 | PRJ-003-ACT-06 | 2025-09-14 | Material | MAT-007 | PVC Pipe | VEN-005 | 5.22 | Meter | 690.33 | 678.86 | 122.19 | 801.05 | Paid | Low
EXP-02589 | PRJ-003 | PRJ-003-ACT-05 | 2025-09-14 | Material | MAT-008 | Tiles | VEN-005 | 7.52 | Sq Ft | 533.29 | 516.88 | 93.04 | 609.92 | Partially Paid | Medium
EXP-02590 | PRJ-003 | PRJ-003-ACT-03 | 2025-09-14 | Material | MAT-005 | Bricks | VEN-005 | 13.32 | Piece | 117.55 | 115.61 | 20.81 | 136.42 | Paid | Medium
EXP-02591 | PRJ-003 | PRJ-003-ACT-08 | 2025-09-14 | Contractor | CON-002 | Electrical Contract | VEN-008 | 1 | Contract | 287067.3 | 295109.41 | 53119.69 | 348229.1 | Paid | Low
EXP-02592 | PRJ-003 | PRJ-003-ACT-10 | 2025-09-19 | Contractor | CON-002 | Electrical Contract | VEN-010 | 1 | Contract | 356677.86 | 370079.7 | 66614.35 | 436694.05 | Paid | Low
EXP-02593 | PRJ-003 | PRJ-003-ACT-05 | 2025-09-19 | Contractor | CON-002 | Electrical Contract | VEN-008 | 1 | Contract | 301195.95 | 314961.16 | 56693.01 | 371654.17 | Paid | Medium
EXP-02594 | PRJ-003 | PRJ-003-ACT-05 | 2025-09-19 | Contractor | CON-002 | Electrical Contract | VEN-001 | 1 | Contract | 419536.6 | 398061.98 | 71651.16 | 469713.14 | Paid | Medium
EXP-02595 | PRJ-003 | PRJ-003-ACT-07 | 2025-09-19 | Material | MAT-009 | Paint | VEN-010 | 12.99 | Litre | 2916.7 | 2760.11 | 496.82 | 3256.93 | Paid | Medium
EXP-02596 | PRJ-003 | PRJ-003-ACT-04 | 2025-09-19 | Material | MAT-008 | Tiles | VEN-001 | 4.96 | Sq Ft | 424.43 | 416.36 | 74.94 | 491.3 | Paid | High
EXP-02597 | PRJ-003 | PRJ-003-ACT-04 | 2025-09-19 | Labour | LAB-002 | Helper | VEN-001 | 21 | Worker | 19048.67 | 19747.13 | 3554.48 | 23301.61 | Pending | Low
EXP-02598 | PRJ-003 | PRJ-003-ACT-01 | 2025-09-19 | Material | MAT-001 | Cement | VEN-005 | 9.26 | Bag | 4725.57 | 4816.33 | 866.94 | 5683.27 | Partially Paid | Low
EXP-02599 | PRJ-003 | PRJ-003-ACT-04 | 2025-09-19 | Material | MAT-009 | Paint | VEN-010 | 10.15 | Litre | 1942.75 | 1997.69 | 359.58 | 2357.27 | Paid | Medium
EXP-02600 | PRJ-003 | PRJ-003-ACT-02 | 2025-09-19 | Equipment | EQ-001 | Crane | VEN-005 | 5 | Day | 87585.56 | 94646.49 | 17036.37 | 111682.86 | Paid | High
EXP-02601 | PRJ-003 | PRJ-003-ACT-06 | 2025-09-24 | Contractor | CON-001 | Civil Structure Contract | VEN-010 | 1 | Contract | 104507.55 | 98616.72 | 17751.01 | 116367.73 | Paid | Low
EXP-02602 | PRJ-003 | PRJ-003-ACT-03 | 2025-09-24 | Material | MAT-003 | Sand | VEN-005 | 10.27 | Ton | 16362.66 | 17004.71 | 3060.85 | 20065.56 | Partially Paid | Low
EXP-02603 | PRJ-003 | PRJ-003-ACT-04 | 2025-09-24 | Labour | LAB-006 | Painter | VEN-005 | 11 | Worker | 10684.1 | 10994.18 | 1978.95 | 12973.13 | Pending | Low
EXP-02604 | PRJ-003 | PRJ-003-ACT-10 | 2025-09-24 | Contractor | CON-002 | Electrical Contract | VEN-005 | 1 | Contract | 188072.37 | 200032.39 | 36005.83 | 236038.22 | Paid | Medium
EXP-02605 | PRJ-003 | PRJ-003-ACT-05 | 2025-09-24 | Material | MAT-010 | Glass | VEN-005 | 5.21 | Sq Ft | 824 | 816.58 | 146.98 | 963.56 | Paid | Medium
EXP-02606 | PRJ-003 | PRJ-003-ACT-06 | 2025-09-24 | Material | MAT-002 | Steel | VEN-008 | 8.06 | Ton | 407509.86 | 439772.14 | 79158.99 | 518931.13 | Paid | Low
EXP-02607 | PRJ-003 | PRJ-003-ACT-01 | 2025-09-24 | Equipment | EQ-003 | Concrete Mixer | VEN-008 | 5 | Day | 23692.06 | 22850.06 | 4113.01 | 26963.07 | Paid | Low
EXP-02608 | PRJ-003 | PRJ-003-ACT-04 | 2025-09-29 | Labour | LAB-003 | Carpenter | VEN-010 | 8 | Worker | 10072.49 | 9670.26 | 1740.65 | 11410.91 | Paid | High
EXP-02609 | PRJ-003 | PRJ-003-ACT-10 | 2025-09-29 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 424634.93 | 419506.57 | 75511.18 | 495017.75 | Paid | Low
EXP-02610 | PRJ-003 | PRJ-003-ACT-04 | 2025-09-29 | Material | MAT-004 | Aggregate | VEN-010 | 12.94 | Ton | 19456.51 | 18592.39 | 3346.63 | 21939.02 | Paid | Low
EXP-02611 | PRJ-003 | PRJ-003-ACT-05 | 2025-09-29 | Labour | LAB-002 | Helper | VEN-008 | 15 | Worker | 18785.48 | 17422.86 | 3136.11 | 20558.97 | Paid | Medium
EXP-02612 | PRJ-003 | PRJ-003-ACT-03 | 2025-09-29 | Labour | LAB-001 | Mason | VEN-010 | 16 | Worker | 25965.64 | 26104.98 | 4698.9 | 30803.88 | Partially Paid | Low
EXP-02613 | PRJ-003 | PRJ-003-ACT-06 | 2025-09-29 | Equipment | EQ-003 | Concrete Mixer | VEN-010 | 1 | Day | 4549.25 | 4563.92 | 821.51 | 5385.43 | Paid | Low
EXP-02614 | PRJ-003 | PRJ-003-ACT-03 | 2025-09-29 | Labour | LAB-002 | Helper | VEN-008 | 14 | Worker | 20969.07 | 21975.41 | 3955.57 | 25930.98 | Paid | Low
EXP-02615 | PRJ-003 | PRJ-003-ACT-01 | 2025-09-29 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 358553.09 | 387249.73 | 69704.95 | 456954.68 | Paid | High
EXP-02616 | PRJ-003 | PRJ-003-ACT-09 | 2025-09-29 | Contractor | CON-003 | Plumbing Contract | VEN-001 | 1 | Contract | 273817.97 | 278902.11 | 50202.38 | 329104.49 | Paid | Low
EXP-02617 | PRJ-003 | PRJ-003-ACT-05 | 2025-10-04 | Labour | LAB-005 | Plumber | VEN-001 | 23 | Worker | 33593.68 | 32388.54 | 5829.94 | 38218.48 | Paid | Medium
EXP-02618 | PRJ-003 | PRJ-003-ACT-01 | 2025-10-04 | Equipment | EQ-002 | Excavator | VEN-010 | 6 | Day | 87371.36 | 91195.19 | 16415.13 | 107610.32 | Partially Paid | Medium
EXP-02619 | PRJ-003 | PRJ-003-ACT-03 | 2025-10-04 | Labour | LAB-002 | Helper | VEN-008 | 14 | Worker | 15445.2 | 14636.69 | 2634.6 | 17271.29 | Paid | Medium
EXP-02620 | PRJ-003 | PRJ-003-ACT-06 | 2025-10-04 | Labour | LAB-004 | Electrician | VEN-010 | 31 | Worker | 33527.22 | 32229.75 | 5801.35 | 38031.1 | Paid | Low
EXP-02621 | PRJ-003 | PRJ-003-ACT-02 | 2025-10-04 | Other | OTH-001 | Miscellaneous | VEN-010 | 1 | Lot | 67171.84 | 64259.27 | 11566.67 | 75825.94 | Paid | Medium
EXP-02622 | PRJ-003 | PRJ-003-ACT-04 | 2025-10-04 | Labour | LAB-002 | Helper | VEN-005 | 12 | Worker | 13527.7 | 14540.88 | 2617.36 | 17158.24 | Paid | Low
EXP-02623 | PRJ-003 | PRJ-003-ACT-07 | 2025-10-04 | Equipment | EQ-002 | Excavator | VEN-005 | 5 | Day | 63261.11 | 65885.94 | 11859.47 | 77745.41 | Paid | Medium
EXP-02624 | PRJ-003 | PRJ-003-ACT-09 | 2025-10-09 | Equipment | EQ-002 | Excavator | VEN-010 | 7 | Day | 114015.6 | 106057.05 | 19090.27 | 125147.32 | Paid | Low
EXP-02625 | PRJ-003 | PRJ-003-ACT-09 | 2025-10-09 | Contractor | CON-003 | Plumbing Contract | VEN-008 | 1 | Contract | 368141.04 | 390022.13 | 70203.98 | 460226.11 | Paid | High
EXP-02626 | PRJ-003 | PRJ-003-ACT-02 | 2025-10-09 | Labour | LAB-006 | Painter | VEN-010 | 32 | Worker | 30954.95 | 31690.76 | 5704.34 | 37395.1 | Paid | Low
EXP-02627 | PRJ-003 | PRJ-003-ACT-01 | 2025-10-09 | Material | MAT-008 | Tiles | VEN-008 | 5.96 | Sq Ft | 470.42 | 509.32 | 91.68 | 601 | Paid | Medium
EXP-02628 | PRJ-003 | PRJ-003-ACT-08 | 2025-10-09 | Contractor | CON-003 | Plumbing Contract | VEN-008 | 1 | Contract | 358167.21 | 347931.9 | 62627.74 | 410559.64 | Paid | Medium
EXP-02629 | PRJ-003 | PRJ-003-ACT-05 | 2025-10-09 | Other | OTH-001 | Site Office | VEN-005 | 1 | Lot | 36327.88 | 35291.27 | 6352.43 | 41643.7 | Paid | Low
EXP-02630 | PRJ-003 | PRJ-003-ACT-04 | 2025-10-09 | Material | MAT-008 | Tiles | VEN-005 | 10.32 | Sq Ft | 857.14 | 842.26 | 151.61 | 993.87 | Paid | Medium
EXP-02631 | PRJ-003 | PRJ-003-ACT-04 | 2025-10-09 | Material | MAT-004 | Aggregate | VEN-008 | 4.94 | Ton | 6424.85 | 6327.46 | 1138.94 | 7466.4 | Pending | Medium
EXP-02632 | PRJ-003 | PRJ-003-ACT-06 | 2025-10-09 | Contractor | CON-001 | Civil Structure Contract | VEN-005 | 1 | Contract | 266415.84 | 247418.42 | 44535.32 | 291953.74 | Paid | Medium
EXP-02633 | PRJ-003 | PRJ-003-ACT-08 | 2025-10-14 | Material | MAT-010 | Glass | VEN-010 | 13.17 | Sq Ft | 2117.51 | 2273.83 | 409.29 | 2683.12 | Paid | Medium
EXP-02634 | PRJ-003 | PRJ-003-ACT-04 | 2025-10-14 | Material | MAT-002 | Steel | VEN-008 | 5.84 | Ton | 322166.03 | 327171.69 | 58890.9 | 386062.59 | Paid | High
EXP-02635 | PRJ-003 | PRJ-003-ACT-01 | 2025-10-14 | Other | OTH-001 | Permit | VEN-010 | 1 | Lot | 55906.59 | 52360.7 | 9424.93 | 61785.63 | Paid | Low
EXP-02636 | PRJ-003 | PRJ-003-ACT-03 | 2025-10-14 | Material | MAT-006 | Electrical Cable | VEN-001 | 10.92 | Meter | 1043.76 | 1020 | 183.6 | 1203.6 | Paid | Low
EXP-02637 | PRJ-003 | PRJ-003-ACT-01 | 2025-10-14 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 116158.4 | 120122.5 | 21622.05 | 141744.55 | Pending | Low
EXP-02638 | PRJ-003 | PRJ-003-ACT-10 | 2025-10-14 | Labour | LAB-001 | Mason | VEN-005 | 31 | Worker | 44085.5 | 44879.59 | 8078.33 | 52957.92 | Paid | High
EXP-02639 | PRJ-003 | PRJ-003-ACT-05 | 2025-10-19 | Contractor | CON-001 | Civil Structure Contract | VEN-001 | 1 | Contract | 241772.94 | 241645.32 | 43496.16 | 285141.48 | Paid | Low
EXP-02640 | PRJ-003 | PRJ-003-ACT-10 | 2025-10-19 | Material | MAT-004 | Aggregate | VEN-001 | 7.36 | Ton | 9789.73 | 10546.36 | 1898.34 | 12444.7 | Paid | Low
EXP-02641 | PRJ-003 | PRJ-003-ACT-07 | 2025-10-19 | Contractor | CON-003 | Plumbing Contract | VEN-001 | 1 | Contract | 206060.01 | 198748.43 | 35774.72 | 234523.15 | Paid | Low
EXP-02642 | PRJ-003 | PRJ-003-ACT-04 | 2025-10-19 | Contractor | CON-002 | Electrical Contract | VEN-001 | 1 | Contract | 362299.76 | 345120.08 | 62121.61 | 407241.69 | Paid | Low
EXP-02643 | PRJ-003 | PRJ-003-ACT-07 | 2025-10-19 | Material | MAT-009 | Paint | VEN-008 | 5.48 | Litre | 980.86 | 1043.84 | 187.89 | 1231.73 | Paid | Low
EXP-02644 | PRJ-003 | PRJ-003-ACT-07 | 2025-10-19 | Labour | LAB-001 | Mason | VEN-008 | 4 | Worker | 5143.18 | 5004.37 | 900.79 | 5905.16 | Paid | Medium
EXP-02645 | PRJ-003 | PRJ-003-ACT-10 | 2025-10-19 | Equipment | EQ-003 | Concrete Mixer | VEN-010 | 7 | Day | 29870.77 | 32106.11 | 5779.1 | 37885.21 | Paid | Low
EXP-02646 | PRJ-003 | PRJ-003-ACT-09 | 2025-10-19 | Material | MAT-008 | Tiles | VEN-010 | 6.01 | Sq Ft | 440.22 | 456.66 | 82.2 | 538.86 | Paid | Low
EXP-02647 | PRJ-003 | PRJ-003-ACT-04 | 2025-10-24 | Labour | LAB-004 | Electrician | VEN-005 | 11 | Worker | 17053.56 | 16427.01 | 2956.86 | 19383.87 | Pending | Medium
EXP-02648 | PRJ-003 | PRJ-003-ACT-04 | 2025-10-24 | Contractor | CON-001 | Civil Structure Contract | VEN-005 | 1 | Contract | 348650.04 | 323744.19 | 58273.95 | 382018.14 | Paid | Medium
EXP-02649 | PRJ-003 | PRJ-003-ACT-05 | 2025-10-24 | Material | MAT-008 | Tiles | VEN-005 | 1.42 | Sq Ft | 103.31 | 109.71 | 19.75 | 129.46 | Paid | High
EXP-02650 | PRJ-003 | PRJ-003-ACT-09 | 2025-10-24 | Material | MAT-003 | Sand | VEN-005 | 2.66 | Ton | 4707.78 | 4695.52 | 845.19 | 5540.71 | Paid | Medium
EXP-02651 | PRJ-003 | PRJ-003-ACT-07 | 2025-10-24 | Material | MAT-007 | PVC Pipe | VEN-001 | 11.68 | Meter | 1214.03 | 1191.93 | 214.55 | 1406.48 | Pending | Low
EXP-02652 | PRJ-003 | PRJ-003-ACT-03 | 2025-10-24 | Labour | LAB-006 | Painter | VEN-001 | 31 | Worker | 36262.91 | 36087.99 | 6495.84 | 42583.83 | Paid | Low
EXP-02653 | PRJ-003 | PRJ-003-ACT-10 | 2025-10-24 | Contractor | CON-004 | Finishing Contract | VEN-008 | 1 | Contract | 249902.62 | 251952.97 | 45351.53 | 297304.5 | Paid | Low
EXP-02654 | PRJ-003 | PRJ-003-ACT-07 | 2025-10-24 | Labour | LAB-002 | Helper | VEN-001 | 17 | Worker | 11763.77 | 11346.5 | 2042.37 | 13388.87 | Paid | Medium
EXP-02655 | PRJ-003 | PRJ-003-ACT-07 | 2025-10-24 | Contractor | CON-001 | Civil Structure Contract | VEN-005 | 1 | Contract | 182278.09 | 191911.52 | 34544.07 | 226455.59 | Paid | Low
EXP-02656 | PRJ-003 | PRJ-003-ACT-09 | 2025-10-24 | Contractor | CON-001 | Civil Structure Contract | VEN-008 | 1 | Contract | 353817.7 | 353487.86 | 63627.81 | 417115.67 | Paid | Medium
EXP-02657 | PRJ-003 | PRJ-003-ACT-09 | 2025-10-29 | Material | MAT-009 | Paint | VEN-010 | 5.18 | Litre | 1121.37 | 1077.9 | 194.02 | 1271.92 | Paid | Low
EXP-02658 | PRJ-003 | PRJ-003-ACT-10 | 2025-10-29 | Contractor | CON-003 | Plumbing Contract | VEN-001 | 1 | Contract | 121129.64 | 129340.82 | 23281.35 | 152622.17 | Paid | Low
EXP-02659 | PRJ-003 | PRJ-003-ACT-01 | 2025-10-29 | Contractor | CON-001 | Civil Structure Contract | VEN-010 | 1 | Contract | 73466.65 | 78195.52 | 14075.19 | 92270.71 | Paid | Low
EXP-02660 | PRJ-003 | PRJ-003-ACT-02 | 2025-10-29 | Contractor | CON-002 | Electrical Contract | VEN-008 | 1 | Contract | 292792.7 | 279596.91 | 50327.44 | 329924.35 | Paid | Low
EXP-02661 | PRJ-003 | PRJ-003-ACT-06 | 2025-10-29 | Contractor | CON-003 | Plumbing Contract | VEN-008 | 1 | Contract | 99147.66 | 94864.42 | 17075.6 | 111940.02 | Paid | Low
EXP-02662 | PRJ-003 | PRJ-003-ACT-06 | 2025-10-29 | Equipment | EQ-002 | Excavator | VEN-010 | 3 | Day | 42106.29 | 40889.31 | 7360.08 | 48249.39 | Paid | Low
EXP-02663 | PRJ-003 | PRJ-003-ACT-08 | 2025-11-03 | Equipment | EQ-001 | Crane | VEN-005 | 1 | Day | 19928.07 | 19468.32 | 3504.3 | 22972.62 | Paid | Medium
EXP-02664 | PRJ-003 | PRJ-003-ACT-04 | 2025-11-03 | Labour | LAB-006 | Painter | VEN-010 | 5 | Worker | 7191.5 | 7215.71 | 1298.83 | 8514.54 | Paid | Low
EXP-02665 | PRJ-003 | PRJ-003-ACT-04 | 2025-11-03 | Material | MAT-001 | Cement | VEN-005 | 7.65 | Bag | 3865.99 | 3679.58 | 662.32 | 4341.9 | Paid | High
EXP-02666 | PRJ-003 | PRJ-003-ACT-09 | 2025-11-03 | Contractor | CON-004 | Finishing Contract | VEN-008 | 1 | Contract | 474819.52 | 447531.26 | 80555.63 | 528086.89 | Paid | High
EXP-02667 | PRJ-003 | PRJ-003-ACT-01 | 2025-11-03 | Equipment | EQ-003 | Concrete Mixer | VEN-008 | 2 | Day | 8484.9 | 8702.09 | 1566.38 | 10268.47 | Paid | Medium
EXP-02668 | PRJ-003 | PRJ-003-ACT-05 | 2025-11-03 | Material | MAT-009 | Paint | VEN-008 | 22.36 | Litre | 5608.06 | 5264.98 | 947.7 | 6212.68 | Paid | Low
EXP-02669 | PRJ-003 | PRJ-003-ACT-04 | 2025-11-03 | Contractor | CON-001 | Civil Structure Contract | VEN-010 | 1 | Contract | 235973.48 | 229243.87 | 41263.9 | 270507.77 | Paid | High
EXP-02670 | PRJ-003 | PRJ-003-ACT-09 | 2025-11-03 | Labour | LAB-001 | Mason | VEN-008 | 31 | Worker | 43111.76 | 44698.66 | 8045.76 | 52744.42 | Paid | Low
EXP-02671 | PRJ-003 | PRJ-003-ACT-01 | 2025-11-08 | Equipment | EQ-003 | Concrete Mixer | VEN-010 | 6 | Day | 29360 | 28557.16 | 5140.29 | 33697.45 | Paid | Low
EXP-02672 | PRJ-003 | PRJ-003-ACT-02 | 2025-11-08 | Labour | LAB-003 | Carpenter | VEN-010 | 30 | Worker | 44035.41 | 45007.84 | 8101.41 | 53109.25 | Paid | Medium
EXP-02673 | PRJ-003 | PRJ-003-ACT-06 | 2025-11-08 | Labour | LAB-006 | Painter | VEN-010 | 4 | Worker | 6167.98 | 6657.73 | 1198.39 | 7856.12 | Partially Paid | Low
EXP-02674 | PRJ-003 | PRJ-003-ACT-06 | 2025-11-08 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 75077.68 | 80617.41 | 14511.13 | 95128.54 | Paid | Low
EXP-02675 | PRJ-003 | PRJ-003-ACT-06 | 2025-11-08 | Material | MAT-010 | Glass | VEN-008 | 27.64 | Sq Ft | 4056.01 | 4053.62 | 729.65 | 4783.27 | Partially Paid | Low
EXP-02676 | PRJ-003 | PRJ-003-ACT-07 | 2025-11-08 | Labour | LAB-001 | Mason | VEN-010 | 29 | Worker | 49292.14 | 48377.73 | 8707.99 | 57085.72 | Paid | Medium
EXP-02677 | PRJ-003 | PRJ-003-ACT-05 | 2025-11-13 | Equipment | EQ-003 | Concrete Mixer | VEN-008 | 5 | Day | 20313.04 | 20325.2 | 3658.54 | 23983.74 | Paid | Medium
EXP-02678 | PRJ-003 | PRJ-003-ACT-04 | 2025-11-13 | Equipment | EQ-002 | Excavator | VEN-008 | 5 | Day | 78588.28 | 76190.81 | 13714.35 | 89905.16 | Paid | Low
EXP-02679 | PRJ-003 | PRJ-003-ACT-04 | 2025-11-13 | Contractor | CON-003 | Plumbing Contract | VEN-005 | 1 | Contract | 240995.56 | 248893.07 | 44800.75 | 293693.82 | Paid | High
EXP-02680 | PRJ-003 | PRJ-003-ACT-02 | 2025-11-13 | Contractor | CON-003 | Plumbing Contract | VEN-005 | 1 | Contract | 317510.1 | 343981.11 | 61916.6 | 405897.71 | Paid | Low
EXP-02681 | PRJ-003 | PRJ-003-ACT-07 | 2025-11-13 | Material | MAT-005 | Bricks | VEN-008 | 9.55 | Piece | 102.93 | 98.66 | 17.76 | 116.42 | Paid | Low
EXP-02682 | PRJ-003 | PRJ-003-ACT-06 | 2025-11-13 | Labour | LAB-005 | Plumber | VEN-005 | 17 | Worker | 17968.39 | 16698.42 | 3005.72 | 19704.14 | Pending | Medium
EXP-02683 | PRJ-003 | PRJ-003-ACT-02 | 2025-11-13 | Labour | LAB-004 | Electrician | VEN-010 | 5 | Worker | 7765.7 | 7249.83 | 1304.97 | 8554.8 | Paid | Low
EXP-02684 | PRJ-003 | PRJ-003-ACT-04 | 2025-11-13 | Contractor | CON-002 | Electrical Contract | VEN-010 | 1 | Contract | 237470.76 | 223146.91 | 40166.44 | 263313.35 | Pending | High
EXP-02685 | PRJ-003 | PRJ-003-ACT-09 | 2025-11-18 | Material | MAT-003 | Sand | VEN-008 | 13.53 | Ton | 24014.36 | 22537.09 | 4056.68 | 26593.77 | Paid | Low
EXP-02686 | PRJ-003 | PRJ-003-ACT-10 | 2025-11-18 | Material | MAT-006 | Electrical Cable | VEN-008 | 11.37 | Meter | 994.44 | 1055.03 | 189.91 | 1244.94 | Paid | High
EXP-02687 | PRJ-003 | PRJ-003-ACT-04 | 2025-11-18 | Material | MAT-008 | Tiles | VEN-005 | 7.91 | Sq Ft | 589.64 | 615.33 | 110.76 | 726.09 | Paid | Medium
EXP-02688 | PRJ-003 | PRJ-003-ACT-04 | 2025-11-18 | Labour | LAB-005 | Plumber | VEN-010 | 19 | Worker | 14770.49 | 15046.17 | 2708.31 | 17754.48 | Paid | Medium
EXP-02689 | PRJ-003 | PRJ-003-ACT-10 | 2025-11-18 | Contractor | CON-003 | Plumbing Contract | VEN-008 | 1 | Contract | 361936.88 | 379436.39 | 68298.55 | 447734.94 | Partially Paid | Low
EXP-02690 | PRJ-003 | PRJ-003-ACT-08 | 2025-11-18 | Contractor | CON-003 | Plumbing Contract | VEN-001 | 1 | Contract | 86147.35 | 91156.58 | 16408.18 | 107564.76 | Paid | Low
EXP-02691 | PRJ-003 | PRJ-003-ACT-01 | 2025-11-18 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 191312 | 187509.9 | 33751.78 | 221261.68 | Paid | Low
EXP-02692 | PRJ-003 | PRJ-003-ACT-06 | 2025-11-18 | Contractor | CON-001 | Civil Structure Contract | VEN-005 | 1 | Contract | 94564.44 | 88958.51 | 16012.53 | 104971.04 | Partially Paid | Low
EXP-02693 | PRJ-003 | PRJ-003-ACT-09 | 2025-11-18 | Material | MAT-005 | Bricks | VEN-008 | 17.15 | Piece | 130.29 | 141.26 | 25.43 | 166.69 | Paid | Low
EXP-02694 | PRJ-003 | PRJ-003-ACT-01 | 2025-11-23 | Material | MAT-008 | Tiles | VEN-005 | 6.32 | Sq Ft | 485.37 | 527.49 | 94.95 | 622.44 | Pending | Low
EXP-02695 | PRJ-003 | PRJ-003-ACT-05 | 2025-11-23 | Material | MAT-008 | Tiles | VEN-010 | 9.25 | Sq Ft | 640.94 | 635.06 | 114.31 | 749.37 | Paid | Medium
EXP-02696 | PRJ-003 | PRJ-003-ACT-06 | 2025-11-23 | Labour | LAB-004 | Electrician | VEN-010 | 30 | Worker | 26354.11 | 27394.13 | 4930.94 | 32325.07 | Paid | High
EXP-02697 | PRJ-003 | PRJ-003-ACT-09 | 2025-11-23 | Equipment | EQ-001 | Crane | VEN-005 | 6 | Day | 108316.54 | 110947 | 19970.46 | 130917.46 | Paid | Medium
EXP-02698 | PRJ-003 | PRJ-003-ACT-08 | 2025-11-23 | Material | MAT-008 | Tiles | VEN-010 | 6.58 | Sq Ft | 451.66 | 440.14 | 79.23 | 519.37 | Paid | Medium
EXP-02699 | PRJ-003 | PRJ-003-ACT-09 | 2025-11-23 | Material | MAT-009 | Paint | VEN-001 | 22.4 | Litre | 5412.45 | 5323.85 | 958.29 | 6282.14 | Paid | Medium
EXP-02700 | PRJ-003 | PRJ-003-ACT-05 | 2025-11-28 | Other | OTH-001 | Miscellaneous | VEN-008 | 1 | Lot | 52636.83 | 55342.11 | 9961.58 | 65303.69 | Paid | Low
EXP-02701 | PRJ-003 | PRJ-003-ACT-07 | 2025-11-28 | Contractor | CON-003 | Plumbing Contract | VEN-008 | 1 | Contract | 287591.75 | 301619.3 | 54291.47 | 355910.77 | Paid | Low
EXP-02702 | PRJ-003 | PRJ-003-ACT-08 | 2025-11-28 | Labour | LAB-002 | Helper | VEN-005 | 29 | Worker | 42675.26 | 39739.31 | 7153.08 | 46892.39 | Paid | Medium
EXP-02703 | PRJ-003 | PRJ-003-ACT-05 | 2025-11-28 | Labour | LAB-006 | Painter | VEN-005 | 12 | Worker | 9910.25 | 10747.08 | 1934.47 | 12681.55 | Pending | Medium
EXP-02704 | PRJ-003 | PRJ-003-ACT-05 | 2025-11-28 | Material | MAT-006 | Electrical Cable | VEN-010 | 13.35 | Meter | 1160.79 | 1177.53 | 211.96 | 1389.49 | Paid | Low
EXP-02705 | PRJ-003 | PRJ-003-ACT-10 | 2025-11-28 | Contractor | CON-003 | Plumbing Contract | VEN-008 | 1 | Contract | 211441.76 | 201959.18 | 36352.65 | 238311.83 | Paid | Medium
EXP-02706 | PRJ-003 | PRJ-003-ACT-03 | 2025-11-28 | Contractor | CON-001 | Civil Structure Contract | VEN-005 | 1 | Contract | 195496.26 | 200987.49 | 36177.75 | 237165.24 | Paid | Medium
EXP-02707 | PRJ-003 | PRJ-003-ACT-08 | 2025-11-28 | Material | MAT-006 | Electrical Cable | VEN-010 | 9.29 | Meter | 804.65 | 777.79 | 140 | 917.79 | Paid | Low
EXP-02708 | PRJ-003 | PRJ-003-ACT-05 | 2025-11-28 | Material | MAT-007 | PVC Pipe | VEN-008 | 3.19 | Meter | 325.56 | 329.39 | 59.29 | 388.68 | Partially Paid | Medium
EXP-02709 | PRJ-003 | PRJ-003-ACT-08 | 2025-11-28 | Material | MAT-009 | Paint | VEN-001 | 10.19 | Litre | 1943.8 | 1906.45 | 343.16 | 2249.61 | Paid | Low
EXP-02710 | PRJ-003 | PRJ-003-ACT-02 | 2025-12-03 | Material | MAT-001 | Cement | VEN-005 | 7.31 | Bag | 4359.58 | 4308.16 | 775.47 | 5083.63 | Paid | Low
EXP-02711 | PRJ-003 | PRJ-003-ACT-04 | 2025-12-03 | Other | OTH-001 | Transport | VEN-010 | 1 | Lot | 56971.59 | 57783.58 | 10401.04 | 68184.62 | Paid | Low
EXP-02712 | PRJ-003 | PRJ-003-ACT-09 | 2025-12-03 | Contractor | CON-003 | Plumbing Contract | VEN-008 | 1 | Contract | 181515.93 | 170409.3 | 30673.67 | 201082.97 | Paid | Low
EXP-02713 | PRJ-003 | PRJ-003-ACT-08 | 2025-12-03 | Other | OTH-001 | Miscellaneous | VEN-001 | 1 | Lot | 40887.03 | 40487.38 | 7287.73 | 47775.11 | Paid | Low
EXP-02714 | PRJ-003 | PRJ-003-ACT-07 | 2025-12-03 | Contractor | CON-004 | Finishing Contract | VEN-010 | 1 | Contract | 99319.98 | 107551.72 | 19359.31 | 126911.03 | Paid | Medium
EXP-02715 | PRJ-003 | PRJ-003-ACT-03 | 2025-12-03 | Labour | LAB-001 | Mason | VEN-001 | 22 | Worker | 33135.25 | 31999.79 | 5759.96 | 37759.75 | Paid | Low
EXP-02716 | PRJ-003 | PRJ-003-ACT-08 | 2025-12-03 | Material | MAT-004 | Aggregate | VEN-005 | 7.82 | Ton | 10732.78 | 11256.15 | 2026.11 | 13282.26 | Pending | Low
EXP-02717 | PRJ-003 | PRJ-003-ACT-10 | 2025-12-08 | Material | MAT-008 | Tiles | VEN-010 | 13.74 | Sq Ft | 1042.3 | 1085.63 | 195.41 | 1281.04 | Pending | Low
EXP-02718 | PRJ-003 | PRJ-003-ACT-09 | 2025-12-08 | Material | MAT-009 | Paint | VEN-001 | 3.91 | Litre | 742.89 | 712.51 | 128.25 | 840.76 | Partially Paid | Medium
EXP-02719 | PRJ-003 | PRJ-003-ACT-02 | 2025-12-08 | Labour | LAB-006 | Painter | VEN-001 | 7 | Worker | 8176.78 | 7760.51 | 1396.89 | 9157.4 | Paid | Low
EXP-02720 | PRJ-003 | PRJ-003-ACT-10 | 2025-12-08 | Material | MAT-007 | PVC Pipe | VEN-001 | 4.62 | Meter | 502.69 | 525.85 | 94.65 | 620.5 | Paid | Low
EXP-02721 | PRJ-003 | PRJ-003-ACT-06 | 2025-12-08 | Contractor | CON-003 | Plumbing Contract | VEN-010 | 1 | Contract | 123436.62 | 122691.45 | 22084.46 | 144775.91 | Paid | Low
EXP-02722 | PRJ-003 | PRJ-003-ACT-09 | 2025-12-08 | Material | MAT-006 | Electrical Cable | VEN-005 | 14.37 | Meter | 1336.55 | 1359.55 | 244.72 | 1604.27 | Paid | Low
EXP-02723 | PRJ-003 | PRJ-003-ACT-04 | 2025-12-08 | Equipment | EQ-002 | Excavator | VEN-001 | 4 | Day | 53182.31 | 55983.09 | 10076.96 | 66060.05 | Paid | Medium
EXP-02724 | PRJ-003 | PRJ-003-ACT-05 | 2025-12-13 | Material | MAT-006 | Electrical Cable | VEN-001 | 7.87 | Meter | 655.8 | 688 | 123.84 | 811.84 | Paid | Low
EXP-02725 | PRJ-003 | PRJ-003-ACT-03 | 2025-12-13 | Equipment | EQ-001 | Crane | VEN-001 | 5 | Day | 101215.82 | 97417.23 | 17535.1 | 114952.33 | Paid | Low
EXP-02726 | PRJ-003 | PRJ-003-ACT-03 | 2025-12-13 | Material | MAT-001 | Cement | VEN-008 | 6.31 | Bag | 3376.66 | 3365.74 | 605.83 | 3971.57 | Paid | Medium
EXP-02727 | PRJ-003 | PRJ-003-ACT-07 | 2025-12-13 | Equipment | EQ-001 | Crane | VEN-008 | 2 | Day | 32423.18 | 34470.15 | 6204.63 | 40674.78 | Paid | Low
EXP-02728 | PRJ-003 | PRJ-003-ACT-04 | 2025-12-13 | Material | MAT-010 | Glass | VEN-010 | 4.34 | Sq Ft | 827.95 | 787.7 | 141.79 | 929.49 | Paid | Medium
EXP-02729 | PRJ-003 | PRJ-003-ACT-10 | 2025-12-13 | Other | OTH-001 | Safety | VEN-005 | 1 | Lot | 60723.38 | 57980.79 | 10436.54 | 68417.33 | Paid | Low
EXP-02730 | PRJ-003 | PRJ-003-ACT-04 | 2025-12-13 | Labour | LAB-003 | Carpenter | VEN-005 | 17 | Worker | 30422.5 | 30023.02 | 5404.14 | 35427.16 | Paid | Medium
EXP-02731 | PRJ-003 | PRJ-003-ACT-09 | 2025-12-13 | Contractor | CON-003 | Plumbing Contract | VEN-001 | 1 | Contract | 408281.36 | 414629.86 | 74633.37 | 489263.23 | Paid | Low
EXP-02732 | PRJ-003 | PRJ-003-ACT-05 | 2025-12-13 | Equipment | EQ-001 | Crane | VEN-005 | 7 | Day | 120700.76 | 130689.11 | 23524.04 | 154213.15 | Paid | Low
EXP-02733 | PRJ-003 | PRJ-003-ACT-07 | 2025-12-13 | Material | MAT-004 | Aggregate | VEN-001 | 2.55 | Ton | 4195.58 | 3985.47 | 717.38 | 4702.85 | Pending | Medium
EXP-02734 | PRJ-003 | PRJ-003-ACT-06 | 2025-12-18 | Material | MAT-005 | Bricks | VEN-010 | 15.61 | Piece | 123.34 | 128.35 | 23.1 | 151.45 | Paid | Medium
EXP-02735 | PRJ-003 | PRJ-003-ACT-07 | 2025-12-18 | Material | MAT-010 | Glass | VEN-005 | 2.14 | Sq Ft | 315.42 | 326.37 | 58.75 | 385.12 | Paid | Low
EXP-02736 | PRJ-003 | PRJ-003-ACT-10 | 2025-12-18 | Labour | LAB-001 | Mason | VEN-005 | 13 | Worker | 12911.23 | 12852.13 | 2313.38 | 15165.51 | Partially Paid | Low
EXP-02737 | PRJ-003 | PRJ-003-ACT-03 | 2025-12-18 | Material | MAT-005 | Bricks | VEN-005 | 14.76 | Piece | 134.45 | 131.36 | 23.64 | 155 | Paid | Low
EXP-02738 | PRJ-003 | PRJ-003-ACT-06 | 2025-12-18 | Contractor | CON-003 | Plumbing Contract | VEN-005 | 1 | Contract | 309791.69 | 292869.11 | 52716.44 | 345585.55 | Paid | Low
EXP-02739 | PRJ-003 | PRJ-003-ACT-09 | 2025-12-18 | Labour | LAB-006 | Painter | VEN-008 | 22 | Worker | 30689.84 | 33110.52 | 5959.89 | 39070.41 | Partially Paid | Medium
EXP-02740 | PRJ-003 | PRJ-003-ACT-03 | 2025-12-18 | Contractor | CON-002 | Electrical Contract | VEN-010 | 1 | Contract | 84863.27 | 80387.76 | 14469.8 | 94857.56 | Paid | Low
EXP-02741 | PRJ-003 | PRJ-003-ACT-05 | 2025-12-23 | Material | MAT-005 | Bricks | VEN-010 | 13.47 | Piece | 127.45 | 135.5 | 24.39 | 159.89 | Paid | Low
EXP-02742 | PRJ-003 | PRJ-003-ACT-06 | 2025-12-23 | Labour | LAB-001 | Mason | VEN-005 | 7 | Worker | 10192.76 | 10400.33 | 1872.06 | 12272.39 | Paid | Low
EXP-02743 | PRJ-003 | PRJ-003-ACT-07 | 2025-12-23 | Contractor | CON-003 | Plumbing Contract | VEN-001 | 1 | Contract | 150113.98 | 150473.85 | 27085.29 | 177559.14 | Paid | Low
EXP-02744 | PRJ-003 | PRJ-003-ACT-09 | 2025-12-23 | Contractor | CON-003 | Plumbing Contract | VEN-008 | 1 | Contract | 244257.98 | 228867.61 | 41196.17 | 270063.78 | Partially Paid | Low
EXP-02745 | PRJ-003 | PRJ-003-ACT-07 | 2025-12-23 | Material | MAT-004 | Aggregate | VEN-008 | 9.53 | Ton | 12814.85 | 13483.43 | 2427.02 | 15910.45 | Paid | Low
EXP-02746 | PRJ-003 | PRJ-003-ACT-01 | 2025-12-23 | Equipment | EQ-001 | Crane | VEN-005 | 6 | Day | 110403.29 | 103689.62 | 18664.13 | 122353.75 | Paid | Medium
EXP-02747 | PRJ-003 | PRJ-003-ACT-02 | 2025-12-23 | Material | MAT-003 | Sand | VEN-001 | 5.72 | Ton | 9449.16 | 9137.21 | 1644.7 | 10781.91 | Paid | Low
EXP-02748 | PRJ-003 | PRJ-003-ACT-01 | 2025-12-28 | Equipment | EQ-003 | Concrete Mixer | VEN-005 | 5 | Day | 24206.88 | 23217.84 | 4179.21 | 27397.05 | Paid | Low
EXP-02749 | PRJ-003 | PRJ-003-ACT-05 | 2025-12-28 | Contractor | CON-003 | Plumbing Contract | VEN-010 | 1 | Contract | 160946.06 | 154846.46 | 27872.36 | 182718.82 | Paid | Medium
EXP-02750 | PRJ-003 | PRJ-003-ACT-02 | 2025-12-28 | Contractor | CON-003 | Plumbing Contract | VEN-010 | 1 | Contract | 257330.18 | 265034.18 | 47706.15 | 312740.33 | Paid | Low
EXP-02751 | PRJ-003 | PRJ-003-ACT-01 | 2025-12-28 | Material | MAT-001 | Cement | VEN-010 | 5.06 | Bag | 2368.46 | 2346.18 | 422.31 | 2768.49 | Paid | High
EXP-02752 | PRJ-003 | PRJ-003-ACT-05 | 2025-12-28 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 330812.68 | 352823.49 | 63508.23 | 416331.72 | Paid | Medium
EXP-02753 | PRJ-003 | PRJ-003-ACT-01 | 2025-12-28 | Equipment | EQ-004 | Scaffolding | VEN-010 | 3 | Day | 7462.64 | 8084.89 | 1455.28 | 9540.17 | Paid | Low
EXP-02754 | PRJ-003 | PRJ-003-ACT-01 | 2025-12-28 | Material | MAT-001 | Cement | VEN-001 | 8.93 | Bag | 4334.54 | 4597.5 | 827.55 | 5425.05 | Paid | Low
EXP-02755 | PRJ-003 | PRJ-003-ACT-10 | 2025-12-28 | Contractor | CON-003 | Plumbing Contract | VEN-008 | 1 | Contract | 136246.13 | 139088.92 | 25036.01 | 164124.93 | Paid | Low
EXP-02756 | PRJ-003 | PRJ-003-ACT-08 | 2026-01-02 | Material | MAT-005 | Bricks | VEN-008 | 4.23 | Piece | 36.04 | 33.51 | 6.03 | 39.54 | Paid | Medium
EXP-02757 | PRJ-003 | PRJ-003-ACT-10 | 2026-01-02 | Material | MAT-010 | Glass | VEN-005 | 6.46 | Sq Ft | 879.92 | 928.01 | 167.04 | 1095.05 | Partially Paid | Low
EXP-02758 | PRJ-003 | PRJ-003-ACT-05 | 2026-01-02 | Contractor | CON-003 | Plumbing Contract | VEN-005 | 1 | Contract | 317419.73 | 294414.07 | 52994.53 | 347408.6 | Paid | Low
EXP-02759 | PRJ-003 | PRJ-003-ACT-08 | 2026-01-02 | Labour | LAB-004 | Electrician | VEN-001 | 27 | Worker | 45292.67 | 43832 | 7889.76 | 51721.76 | Partially Paid | Low
EXP-02760 | PRJ-003 | PRJ-003-ACT-09 | 2026-01-02 | Equipment | EQ-004 | Scaffolding | VEN-001 | 5 | Day | 14168.51 | 13175.21 | 2371.54 | 15546.75 | Pending | Low
EXP-02761 | PRJ-003 | PRJ-003-ACT-01 | 2026-01-02 | Contractor | CON-004 | Finishing Contract | VEN-001 | 1 | Contract | 201014.65 | 187616.68 | 33771 | 221387.68 | Paid | Medium
EXP-02762 | PRJ-003 | PRJ-003-ACT-07 | 2026-01-07 | Material | MAT-001 | Cement | VEN-008 | 23.39 | Bag | 12771.06 | 12069.47 | 2172.5 | 14241.97 | Paid | Low
EXP-02763 | PRJ-003 | PRJ-003-ACT-01 | 2026-01-07 | Equipment | EQ-003 | Concrete Mixer | VEN-008 | 7 | Day | 32038.14 | 32190.61 | 5794.31 | 37984.92 | Paid | Medium
EXP-02764 | PRJ-003 | PRJ-003-ACT-09 | 2026-01-07 | Material | MAT-009 | Paint | VEN-001 | 20.15 | Litre | 4058.04 | 3877.11 | 697.88 | 4574.99 | Paid | Medium
EXP-02765 | PRJ-003 | PRJ-003-ACT-10 | 2026-01-07 | Labour | LAB-006 | Painter | VEN-010 | 20 | Worker | 26950.34 | 26293.02 | 4732.74 | 31025.76 | Paid | Medium
EXP-02766 | PRJ-003 | PRJ-003-ACT-04 | 2026-01-07 | Labour | LAB-003 | Carpenter | VEN-005 | 5 | Worker | 7521.68 | 7294.05 | 1312.93 | 8606.98 | Paid | Low
EXP-02767 | PRJ-003 | PRJ-003-ACT-02 | 2026-01-07 | Labour | LAB-002 | Helper | VEN-005 | 19 | Worker | 18873.05 | 19187.26 | 3453.71 | 22640.97 | Paid | High
EXP-02768 | PRJ-003 | PRJ-003-ACT-01 | 2026-01-07 | Material | MAT-003 | Sand | VEN-001 | 8.17 | Ton | 13046.43 | 14067.24 | 2532.1 | 16599.34 | Paid | Low
EXP-02769 | PRJ-003 | PRJ-003-ACT-06 | 2026-01-07 | Material | MAT-010 | Glass | VEN-001 | 3.54 | Sq Ft | 527.88 | 501.31 | 90.24 | 591.55 | Paid | Low
EXP-02770 | PRJ-003 | PRJ-003-ACT-08 | 2026-01-12 | Contractor | CON-003 | Plumbing Contract | VEN-005 | 1 | Contract | 237413.13 | 234267.63 | 42168.17 | 276435.8 | Paid | Medium
EXP-02771 | PRJ-003 | PRJ-003-ACT-03 | 2026-01-12 | Other | OTH-001 | Transport | VEN-001 | 1 | Lot | 68079.99 | 71036.54 | 12786.58 | 83823.12 | Pending | Medium
EXP-02772 | PRJ-003 | PRJ-003-ACT-08 | 2026-01-12 | Material | MAT-005 | Bricks | VEN-008 | 19.35 | Piece | 161.85 | 164.71 | 29.65 | 194.36 | Paid | Medium
EXP-02773 | PRJ-003 | PRJ-003-ACT-02 | 2026-01-12 | Labour | LAB-006 | Painter | VEN-008 | 5 | Worker | 6923.38 | 6832.11 | 1229.78 | 8061.89 | Paid | Medium
EXP-02774 | PRJ-003 | PRJ-003-ACT-02 | 2026-01-12 | Equipment | EQ-003 | Concrete Mixer | VEN-010 | 1 | Day | 4457.95 | 4759.09 | 856.64 | 5615.73 | Paid | Low
EXP-02775 | PRJ-003 | PRJ-003-ACT-10 | 2026-01-12 | Labour | LAB-002 | Helper | VEN-008 | 4 | Worker | 7230.75 | 6766.87 | 1218.04 | 7984.91 | Paid | Medium
EXP-02776 | PRJ-003 | PRJ-003-ACT-02 | 2026-01-12 | Labour | LAB-004 | Electrician | VEN-010 | 23 | Worker | 21085.25 | 22024.88 | 3964.48 | 25989.36 | Paid | Low
EXP-02777 | PRJ-003 | PRJ-003-ACT-09 | 2026-01-17 | Equipment | EQ-001 | Crane | VEN-005 | 1 | Day | 17079.04 | 18037.29 | 3246.71 | 21284 | Paid | Low
EXP-02778 | PRJ-003 | PRJ-003-ACT-01 | 2026-01-17 | Equipment | EQ-001 | Crane | VEN-010 | 6 | Day | 112118.21 | 114991.33 | 20698.44 | 135689.77 | Paid | Low
EXP-02779 | PRJ-003 | PRJ-003-ACT-03 | 2026-01-17 | Contractor | CON-002 | Electrical Contract | VEN-010 | 1 | Contract | 216769.4 | 204937.41 | 36888.73 | 241826.14 | Paid | High
EXP-02780 | PRJ-003 | PRJ-003-ACT-04 | 2026-01-17 | Contractor | CON-001 | Civil Structure Contract | VEN-001 | 1 | Contract | 414026.59 | 397411.12 | 71534 | 468945.12 | Paid | Low
EXP-02781 | PRJ-003 | PRJ-003-ACT-02 | 2026-01-17 | Labour | LAB-001 | Mason | VEN-008 | 17 | Worker | 16312.83 | 16401.54 | 2952.28 | 19353.82 | Pending | Medium
EXP-02782 | PRJ-003 | PRJ-003-ACT-09 | 2026-01-17 | Material | MAT-004 | Aggregate | VEN-001 | 2.04 | Ton | 2880.5 | 2761.86 | 497.13 | 3258.99 | Paid | Low
EXP-02783 | PRJ-003 | PRJ-003-ACT-04 | 2026-01-17 | Equipment | EQ-001 | Crane | VEN-010 | 4 | Day | 69000.26 | 65454.61 | 11781.83 | 77236.44 | Pending | Low
EXP-02784 | PRJ-003 | PRJ-003-ACT-04 | 2026-01-17 | Other | OTH-001 | Miscellaneous | VEN-008 | 1 | Lot | 47525.29 | 47757.02 | 8596.26 | 56353.28 | Paid | Low
EXP-02785 | PRJ-003 | PRJ-003-ACT-06 | 2026-01-17 | Material | MAT-005 | Bricks | VEN-001 | 13.4 | Piece | 131.56 | 133.5 | 24.03 | 157.53 | Paid | Medium
EXP-02786 | PRJ-003 | PRJ-003-ACT-04 | 2026-01-17 | Contractor | CON-001 | Civil Structure Contract | VEN-008 | 1 | Contract | 94011.22 | 93124.55 | 16762.42 | 109886.97 | Paid | Low
EXP-02787 | PRJ-003 | PRJ-003-ACT-01 | 2026-01-22 | Material | MAT-005 | Bricks | VEN-001 | 7.9 | Piece | 79.41 | 80.81 | 14.55 | 95.36 | Paid | Low
EXP-02788 | PRJ-003 | PRJ-003-ACT-02 | 2026-01-22 | Labour | LAB-006 | Painter | VEN-010 | 4 | Worker | 6069.32 | 6163.69 | 1109.46 | 7273.15 | Paid | Low
EXP-02789 | PRJ-003 | PRJ-003-ACT-05 | 2026-01-22 | Other | OTH-001 | Site Office | VEN-008 | 1 | Lot | 48572.28 | 52538.14 | 9456.87 | 61995.01 | Paid | Medium
EXP-02790 | PRJ-003 | PRJ-003-ACT-06 | 2026-01-22 | Contractor | CON-001 | Civil Structure Contract | VEN-001 | 1 | Contract | 221933.47 | 208013.91 | 37442.5 | 245456.41 | Pending | High
EXP-02791 | PRJ-003 | PRJ-003-ACT-04 | 2026-01-22 | Equipment | EQ-001 | Crane | VEN-001 | 6 | Day | 112447.94 | 108842.23 | 19591.6 | 128433.83 | Paid | Medium
EXP-02792 | PRJ-003 | PRJ-003-ACT-01 | 2026-01-22 | Material | MAT-003 | Sand | VEN-008 | 5.88 | Ton | 8792.36 | 9526.05 | 1714.69 | 11240.74 | Paid | Medium
EXP-02793 | PRJ-003 | PRJ-003-ACT-05 | 2026-01-22 | Labour | LAB-005 | Plumber | VEN-008 | 31 | Worker | 46053.78 | 47288.66 | 8511.96 | 55800.62 | Paid | Medium
EXP-02794 | PRJ-003 | PRJ-003-ACT-01 | 2026-01-27 | Material | MAT-010 | Glass | VEN-008 | 8.15 | Sq Ft | 1361.03 | 1346.21 | 242.32 | 1588.53 | Paid | Medium
EXP-02795 | PRJ-003 | PRJ-003-ACT-02 | 2026-01-27 | Other | OTH-001 | Permit | VEN-010 | 1 | Lot | 57631.68 | 54598.31 | 9827.7 | 64426.01 | Paid | Low
EXP-02796 | PRJ-003 | PRJ-003-ACT-07 | 2026-01-27 | Labour | LAB-001 | Mason | VEN-008 | 31 | Worker | 44948.96 | 46853.83 | 8433.69 | 55287.52 | Paid | Low
EXP-02797 | PRJ-003 | PRJ-003-ACT-03 | 2026-01-27 | Material | MAT-007 | PVC Pipe | VEN-008 | 8.7 | Meter | 1229.62 | 1192.77 | 214.7 | 1407.47 | Paid | Low
EXP-02798 | PRJ-003 | PRJ-003-ACT-05 | 2026-01-27 | Labour | LAB-005 | Plumber | VEN-005 | 15 | Worker | 17190.13 | 17771.28 | 3198.83 | 20970.11 | Paid | Medium
EXP-02799 | PRJ-003 | PRJ-003-ACT-05 | 2026-01-27 | Labour | LAB-004 | Electrician | VEN-008 | 33 | Worker | 24800.56 | 25664.62 | 4619.63 | 30284.25 | Partially Paid | Medium
EXP-02800 | PRJ-003 | PRJ-003-ACT-03 | 2026-01-27 | Contractor | CON-003 | Plumbing Contract | VEN-010 | 1 | Contract | 347501.5 | 346696.06 | 62405.29 | 409101.35 | Paid | Medium
EXP-02801 | PRJ-003 | PRJ-003-ACT-07 | 2026-02-01 | Labour | LAB-006 | Painter | VEN-001 | 27 | Worker | 48376.82 | 48305.49 | 8694.99 | 57000.48 | Paid | Low
EXP-02802 | PRJ-003 | PRJ-003-ACT-08 | 2026-02-01 | Material | MAT-005 | Bricks | VEN-005 | 15.04 | Piece | 134.38 | 128.92 | 23.21 | 152.13 | Paid | High
EXP-02803 | PRJ-003 | PRJ-003-ACT-04 | 2026-02-01 | Labour | LAB-001 | Mason | VEN-008 | 9 | Worker | 12830.82 | 13884.47 | 2499.2 | 16383.67 | Paid | Low
EXP-02804 | PRJ-003 | PRJ-003-ACT-09 | 2026-02-01 | Material | MAT-003 | Sand | VEN-010 | 13.57 | Ton | 25701.9 | 27086.53 | 4875.58 | 31962.11 | Pending | Low
EXP-02805 | PRJ-003 | PRJ-003-ACT-08 | 2026-02-01 | Other | OTH-001 | Site Office | VEN-001 | 1 | Lot | 58568.23 | 62193.21 | 11194.78 | 73387.99 | Partially Paid | High
EXP-02806 | PRJ-003 | PRJ-003-ACT-09 | 2026-02-01 | Material | MAT-004 | Aggregate | VEN-001 | 12.73 | Ton | 19371.82 | 18784.22 | 3381.16 | 22165.38 | Paid | Low
EXP-02807 | PRJ-003 | PRJ-003-ACT-04 | 2026-02-01 | Material | MAT-001 | Cement | VEN-008 | 6.88 | Bag | 4087.18 | 4039.43 | 727.1 | 4766.53 | Paid | Low
EXP-02808 | PRJ-003 | PRJ-003-ACT-01 | 2026-02-01 | Material | MAT-002 | Steel | VEN-001 | 9.72 | Ton | 559079.96 | 592147.8 | 106586.6 | 698734.4 | Paid | Low
EXP-02809 | PRJ-003 | PRJ-003-ACT-01 | 2026-02-01 | Material | MAT-003 | Sand | VEN-001 | 10.25 | Ton | 16981.12 | 15953.1 | 2871.56 | 18824.66 | Paid | Low
EXP-02810 | PRJ-003 | PRJ-003-ACT-03 | 2026-02-06 | Material | MAT-006 | Electrical Cable | VEN-010 | 8.68 | Meter | 672.43 | 646.89 | 116.44 | 763.33 | Partially Paid | Low
EXP-02811 | PRJ-003 | PRJ-003-ACT-01 | 2026-02-06 | Contractor | CON-003 | Plumbing Contract | VEN-010 | 1 | Contract | 320602.29 | 327419.24 | 58935.46 | 386354.7 | Paid | Low
EXP-02812 | PRJ-003 | PRJ-003-ACT-09 | 2026-02-06 | Material | MAT-008 | Tiles | VEN-010 | 2.99 | Sq Ft | 192.14 | 194.69 | 35.04 | 229.73 | Paid | Medium
EXP-02813 | PRJ-003 | PRJ-003-ACT-02 | 2026-02-06 | Material | MAT-006 | Electrical Cable | VEN-005 | 21.57 | Meter | 1957.71 | 2100.48 | 378.09 | 2478.57 | Paid | Low
EXP-02814 | PRJ-003 | PRJ-003-ACT-03 | 2026-02-06 | Labour | LAB-006 | Painter | VEN-008 | 31 | Worker | 43602.23 | 42720.28 | 7689.65 | 50409.93 | Paid | Low
EXP-02815 | PRJ-003 | PRJ-003-ACT-10 | 2026-02-06 | Equipment | EQ-003 | Concrete Mixer | VEN-001 | 2 | Day | 9829.38 | 9256.25 | 1666.12 | 10922.37 | Paid | Low
EXP-02816 | PRJ-003 | PRJ-003-ACT-03 | 2026-02-06 | Other | OTH-001 | Site Office | VEN-010 | 1 | Lot | 24342.85 | 24289.99 | 4372.2 | 28662.19 | Paid | Low
EXP-02817 | PRJ-003 | PRJ-003-ACT-01 | 2026-02-06 | Material | MAT-003 | Sand | VEN-008 | 19.97 | Ton | 36993.67 | 37703.72 | 6786.67 | 44490.39 | Paid | Low
EXP-02818 | PRJ-003 | PRJ-003-ACT-10 | 2026-02-11 | Contractor | CON-002 | Electrical Contract | VEN-010 | 1 | Contract | 368998.89 | 353237.51 | 63582.75 | 416820.26 | Paid | Medium
EXP-02819 | PRJ-003 | PRJ-003-ACT-09 | 2026-02-11 | Material | MAT-004 | Aggregate | VEN-001 | 9.05 | Ton | 15350.89 | 15453.62 | 2781.65 | 18235.27 | Paid | Low
EXP-02820 | PRJ-003 | PRJ-003-ACT-09 | 2026-02-11 | Material | MAT-005 | Bricks | VEN-010 | 1 | Piece | 9.62 | 9.18 | 1.65 | 10.83 | Paid | High
EXP-02821 | PRJ-003 | PRJ-003-ACT-09 | 2026-02-11 | Material | MAT-007 | PVC Pipe | VEN-008 | 12.45 | Meter | 1563.17 | 1584 | 285.12 | 1869.12 | Paid | Low
EXP-02822 | PRJ-003 | PRJ-003-ACT-09 | 2026-02-11 | Material | MAT-004 | Aggregate | VEN-001 | 27.8 | Ton | 44089.8 | 42847.04 | 7712.47 | 50559.51 | Pending | High
EXP-02823 | PRJ-003 | PRJ-003-ACT-01 | 2026-02-11 | Equipment | EQ-001 | Crane | VEN-008 | 2 | Day | 39335.08 | 36545.62 | 6578.21 | 43123.83 | Pending | Low
EXP-02824 | PRJ-003 | PRJ-003-ACT-08 | 2026-02-11 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 144571.15 | 136062.05 | 24491.17 | 160553.22 | Paid | Medium
EXP-02825 | PRJ-003 | PRJ-003-ACT-07 | 2026-02-11 | Material | MAT-006 | Electrical Cable | VEN-005 | 5.42 | Meter | 512.76 | 518.81 | 93.39 | 612.2 | Paid | Low
EXP-02826 | PRJ-003 | PRJ-003-ACT-05 | 2026-02-16 | Material | MAT-002 | Steel | VEN-010 | 4.55 | Ton | 315470.02 | 317675.09 | 57181.52 | 374856.61 | Paid | Low
EXP-02827 | PRJ-003 | PRJ-003-ACT-09 | 2026-02-16 | Equipment | EQ-004 | Scaffolding | VEN-008 | 6 | Day | 16310.67 | 15237.42 | 2742.74 | 17980.16 | Paid | Low
EXP-02828 | PRJ-003 | PRJ-003-ACT-03 | 2026-02-16 | Material | MAT-010 | Glass | VEN-001 | 15.82 | Sq Ft | 2631.44 | 2620 | 471.6 | 3091.6 | Paid | Low
EXP-02829 | PRJ-003 | PRJ-003-ACT-01 | 2026-02-16 | Labour | LAB-001 | Mason | VEN-008 | 33 | Worker | 40328.02 | 40872.62 | 7357.07 | 48229.69 | Paid | Low
EXP-02830 | PRJ-003 | PRJ-003-ACT-04 | 2026-02-16 | Material | MAT-010 | Glass | VEN-008 | 7.16 | Sq Ft | 1197.92 | 1177.05 | 211.87 | 1388.92 | Paid | Low
EXP-02831 | PRJ-003 | PRJ-003-ACT-07 | 2026-02-16 | Material | MAT-009 | Paint | VEN-001 | 8.77 | Litre | 1993.42 | 1959.3 | 352.67 | 2311.97 | Pending | Low
EXP-02832 | PRJ-003 | PRJ-003-ACT-01 | 2026-02-21 | Contractor | CON-002 | Electrical Contract | VEN-005 | 1 | Contract | 208387.26 | 194027 | 34924.86 | 228951.86 | Partially Paid | Medium
EXP-02833 | PRJ-003 | PRJ-003-ACT-01 | 2026-02-21 | Material | MAT-005 | Bricks | VEN-001 | 57.09 | Piece | 444.61 | 440.44 | 79.28 | 519.72 | Paid | Low
EXP-02834 | PRJ-003 | PRJ-003-ACT-08 | 2026-02-21 | Labour | LAB-005 | Plumber | VEN-008 | 26 | Worker | 22328.44 | 20844.47 | 3752 | 24596.47 | Paid | Low
EXP-02835 | PRJ-003 | PRJ-003-ACT-02 | 2026-02-21 | Material | MAT-002 | Steel | VEN-008 | 12.74 | Ton | 890520.91 | 889261.48 | 160067.07 | 1049328.55 | Paid | Low
EXP-02836 | PRJ-003 | PRJ-003-ACT-09 | 2026-02-21 | Contractor | CON-003 | Plumbing Contract | VEN-008 | 1 | Contract | 316103.78 | 338978.6 | 61016.15 | 399994.75 | Paid | Low
EXP-02837 | PRJ-003 | PRJ-003-ACT-07 | 2026-02-21 | Labour | LAB-005 | Plumber | VEN-001 | 24 | Worker | 27088.39 | 26926.44 | 4846.76 | 31773.2 | Paid | Low
EXP-02838 | PRJ-003 | PRJ-003-ACT-07 | 2026-02-21 | Material | MAT-010 | Glass | VEN-001 | 4.04 | Sq Ft | 673.39 | 684.81 | 123.27 | 808.08 | Paid | Low
EXP-02839 | PRJ-003 | PRJ-003-ACT-03 | 2026-02-26 | Material | MAT-010 | Glass | VEN-005 | 3.89 | Sq Ft | 609.72 | 629.08 | 113.23 | 742.31 | Paid | Low
EXP-02840 | PRJ-003 | PRJ-003-ACT-10 | 2026-02-26 | Material | MAT-002 | Steel | VEN-008 | 7.23 | Ton | 395939.13 | 426842.95 | 76831.73 | 503674.68 | Partially Paid | Low
EXP-02841 | PRJ-003 | PRJ-003-ACT-06 | 2026-02-26 | Contractor | CON-001 | Civil Structure Contract | VEN-008 | 1 | Contract | 405211.37 | 391991.92 | 70558.55 | 462550.47 | Partially Paid | Low
EXP-02842 | PRJ-003 | PRJ-003-ACT-10 | 2026-02-26 | Contractor | CON-004 | Finishing Contract | VEN-001 | 1 | Contract | 321196.98 | 334711.5 | 60248.07 | 394959.57 | Paid | Low
EXP-02843 | PRJ-003 | PRJ-003-ACT-09 | 2026-02-26 | Material | MAT-009 | Paint | VEN-005 | 6.33 | Litre | 1281.52 | 1293.45 | 232.82 | 1526.27 | Partially Paid | Medium
EXP-02844 | PRJ-003 | PRJ-003-ACT-06 | 2026-02-26 | Material | MAT-010 | Glass | VEN-010 | 3.3 | Sq Ft | 514.48 | 553.01 | 99.54 | 652.55 | Paid | Low
EXP-02845 | PRJ-003 | PRJ-003-ACT-05 | 2026-02-26 | Labour | LAB-004 | Electrician | VEN-005 | 8 | Worker | 6718.58 | 6467.76 | 1164.2 | 7631.96 | Partially Paid | High
EXP-02846 | PRJ-003 | PRJ-003-ACT-07 | 2026-02-26 | Material | MAT-002 | Steel | VEN-010 | 14.58 | Ton | 808362.3 | 836578.29 | 150584.09 | 987162.38 | Paid | Low
EXP-02847 | PRJ-003 | PRJ-003-ACT-06 | 2026-02-26 | Contractor | CON-004 | Finishing Contract | VEN-001 | 1 | Contract | 255438.4 | 272094.78 | 48977.06 | 321071.84 | Paid | Low
EXP-02848 | PRJ-003 | PRJ-003-ACT-08 | 2026-03-03 | Material | MAT-004 | Aggregate | VEN-008 | 32.21 | Ton | 46110.8 | 44021.51 | 7923.87 | 51945.38 | Paid | Medium
EXP-02849 | PRJ-003 | PRJ-003-ACT-01 | 2026-03-03 | Labour | LAB-002 | Helper | VEN-005 | 33 | Worker | 36439.36 | 34192.43 | 6154.64 | 40347.07 | Paid | Low
EXP-02850 | PRJ-003 | PRJ-003-ACT-01 | 2026-03-03 | Labour | LAB-003 | Carpenter | VEN-001 | 32 | Worker | 22805.21 | 22394.87 | 4031.08 | 26425.95 | Paid | Low
EXP-02851 | PRJ-003 | PRJ-003-ACT-02 | 2026-03-03 | Material | MAT-007 | PVC Pipe | VEN-010 | 11 | Meter | 1478.66 | 1458.27 | 262.49 | 1720.76 | Paid | Low
EXP-02852 | PRJ-003 | PRJ-003-ACT-09 | 2026-03-03 | Equipment | EQ-001 | Crane | VEN-008 | 1 | Day | 16696.05 | 17763.22 | 3197.38 | 20960.6 | Pending | Low
EXP-02853 | PRJ-003 | PRJ-003-ACT-09 | 2026-03-03 | Labour | LAB-001 | Mason | VEN-001 | 17 | Worker | 16033.65 | 15995.23 | 2879.14 | 18874.37 | Pending | Medium
EXP-02854 | PRJ-003 | PRJ-003-ACT-03 | 2026-03-03 | Equipment | EQ-001 | Crane | VEN-005 | 2 | Day | 38980.4 | 38562.49 | 6941.25 | 45503.74 | Partially Paid | Low
EXP-02855 | PRJ-003 | PRJ-003-ACT-04 | 2026-03-03 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 390805.77 | 390920.33 | 70365.66 | 461285.99 | Paid | Low
EXP-02856 | PRJ-003 | PRJ-003-ACT-03 | 2026-03-03 | Material | MAT-007 | PVC Pipe | VEN-010 | 6.71 | Meter | 797.29 | 840.54 | 151.3 | 991.84 | Pending | Low
EXP-02857 | PRJ-003 | PRJ-003-ACT-06 | 2026-03-03 | Material | MAT-004 | Aggregate | VEN-008 | 3.32 | Ton | 5341.14 | 5433.15 | 977.97 | 6411.12 | Paid | Medium
EXP-02858 | PRJ-003 | PRJ-003-ACT-05 | 2026-03-08 | Labour | LAB-001 | Mason | VEN-010 | 10 | Worker | 6476.21 | 6564.84 | 1181.67 | 7746.51 | Paid | Medium
EXP-02859 | PRJ-003 | PRJ-003-ACT-01 | 2026-03-08 | Material | MAT-003 | Sand | VEN-005 | 14.56 | Ton | 27610.77 | 27280.79 | 4910.54 | 32191.33 | Paid | Medium
EXP-02860 | PRJ-003 | PRJ-003-ACT-06 | 2026-03-08 | Labour | LAB-003 | Carpenter | VEN-001 | 28 | Worker | 23477.83 | 23808.2 | 4285.48 | 28093.68 | Paid | High
EXP-02861 | PRJ-003 | PRJ-003-ACT-01 | 2026-03-08 | Other | OTH-001 | Safety | VEN-010 | 1 | Lot | 78041.33 | 73585.63 | 13245.41 | 86831.04 | Paid | Low
EXP-02862 | PRJ-003 | PRJ-003-ACT-09 | 2026-03-08 | Labour | LAB-006 | Painter | VEN-008 | 31 | Worker | 24943.52 | 25184.83 | 4533.27 | 29718.1 | Paid | Medium
EXP-02863 | PRJ-003 | PRJ-003-ACT-10 | 2026-03-08 | Material | MAT-001 | Cement | VEN-001 | 10.76 | Bag | 4886.68 | 4935.53 | 888.4 | 5823.93 | Paid | High
EXP-02864 | PRJ-003 | PRJ-003-ACT-01 | 2026-03-13 | Labour | LAB-006 | Painter | VEN-005 | 26 | Worker | 36865.9 | 37067.66 | 6672.18 | 43739.84 | Paid | Low
EXP-02865 | PRJ-003 | PRJ-003-ACT-01 | 2026-03-13 | Contractor | CON-001 | Civil Structure Contract | VEN-005 | 1 | Contract | 174828.63 | 180953.79 | 32571.68 | 213525.47 | Paid | Low
EXP-02866 | PRJ-003 | PRJ-003-ACT-04 | 2026-03-13 | Material | MAT-003 | Sand | VEN-001 | 12.18 | Ton | 25951.33 | 24394.05 | 4390.93 | 28784.98 | Paid | Low
EXP-02867 | PRJ-003 | PRJ-003-ACT-07 | 2026-03-13 | Material | MAT-005 | Bricks | VEN-005 | 13.68 | Piece | 121.6 | 113.62 | 20.45 | 134.07 | Paid | Low
EXP-02868 | PRJ-003 | PRJ-003-ACT-03 | 2026-03-13 | Labour | LAB-006 | Painter | VEN-005 | 6 | Worker | 7161.42 | 6740.46 | 1213.28 | 7953.74 | Paid | High
EXP-02869 | PRJ-003 | PRJ-003-ACT-03 | 2026-03-13 | Labour | LAB-001 | Mason | VEN-005 | 11 | Worker | 18453.49 | 18734.41 | 3372.19 | 22106.6 | Paid | Low
EXP-02870 | PRJ-003 | PRJ-003-ACT-04 | 2026-03-13 | Equipment | EQ-002 | Excavator | VEN-010 | 1 | Day | 13147.73 | 12640.57 | 2275.3 | 14915.87 | Paid | High
EXP-02871 | PRJ-003 | PRJ-003-ACT-03 | 2026-03-18 | Other | OTH-001 | Permit | VEN-005 | 1 | Lot | 24542.94 | 26187.39 | 4713.73 | 30901.12 | Paid | Low
EXP-02872 | PRJ-003 | PRJ-003-ACT-05 | 2026-03-18 | Labour | LAB-006 | Painter | VEN-010 | 33 | Worker | 49132.13 | 47772.13 | 8598.98 | 56371.11 | Partially Paid | High
EXP-02873 | PRJ-003 | PRJ-003-ACT-10 | 2026-03-18 | Equipment | EQ-004 | Scaffolding | VEN-005 | 2 | Day | 4362.12 | 4519.42 | 813.5 | 5332.92 | Paid | High
EXP-02874 | PRJ-003 | PRJ-003-ACT-02 | 2026-03-18 | Equipment | EQ-004 | Scaffolding | VEN-010 | 1 | Day | 2733.58 | 2689.24 | 484.06 | 3173.3 | Paid | Low
EXP-02875 | PRJ-003 | PRJ-003-ACT-03 | 2026-03-18 | Equipment | EQ-004 | Scaffolding | VEN-010 | 6 | Day | 14466.53 | 14026.17 | 2524.71 | 16550.88 | Pending | Medium
EXP-02876 | PRJ-003 | PRJ-003-ACT-10 | 2026-03-18 | Material | MAT-006 | Electrical Cable | VEN-008 | 4.06 | Meter | 398.12 | 381.55 | 68.68 | 450.23 | Paid | Low
EXP-02877 | PRJ-003 | PRJ-003-ACT-07 | 2026-03-18 | Contractor | CON-001 | Civil Structure Contract | VEN-008 | 1 | Contract | 269870.62 | 285928.25 | 51467.08 | 337395.33 | Paid | Medium
EXP-02878 | PRJ-003 | PRJ-003-ACT-08 | 2026-03-18 | Material | MAT-002 | Steel | VEN-001 | 22.71 | Ton | 1494316.4 | 1434303.47 | 258174.62 | 1692478.09 | Partially Paid | Medium
EXP-02879 | PRJ-003 | PRJ-003-ACT-04 | 2026-03-18 | Contractor | CON-004 | Finishing Contract | VEN-001 | 1 | Contract | 342369.99 | 326086.18 | 58695.51 | 384781.69 | Paid | Low
EXP-02880 | PRJ-003 | PRJ-003-ACT-08 | 2026-03-23 | Contractor | CON-002 | Electrical Contract | VEN-008 | 1 | Contract | 456560.07 | 447340.57 | 80521.3 | 527861.87 | Paid | Low
EXP-02881 | PRJ-003 | PRJ-003-ACT-06 | 2026-03-23 | Material | MAT-007 | PVC Pipe | VEN-010 | 3.31 | Meter | 394.21 | 372.19 | 66.99 | 439.18 | Paid | Low
EXP-02882 | PRJ-003 | PRJ-003-ACT-09 | 2026-03-23 | Equipment | EQ-001 | Crane | VEN-010 | 3 | Day | 57239.7 | 58885.4 | 10599.37 | 69484.77 | Paid | Low
EXP-02883 | PRJ-003 | PRJ-003-ACT-05 | 2026-03-23 | Material | MAT-003 | Sand | VEN-001 | 4.32 | Ton | 6996.77 | 7357.29 | 1324.31 | 8681.6 | Paid | Low
EXP-02884 | PRJ-003 | PRJ-003-ACT-08 | 2026-03-23 | Material | MAT-007 | PVC Pipe | VEN-005 | 7.29 | Meter | 809.15 | 863.37 | 155.41 | 1018.78 | Paid | Low
EXP-02885 | PRJ-003 | PRJ-003-ACT-01 | 2026-03-23 | Contractor | CON-002 | Electrical Contract | VEN-005 | 1 | Contract | 351964.76 | 343505.12 | 61830.92 | 405336.04 | Paid | Low
EXP-02886 | PRJ-003 | PRJ-003-ACT-10 | 2026-03-23 | Labour | LAB-002 | Helper | VEN-005 | 16 | Worker | 20423.58 | 20185.95 | 3633.47 | 23819.42 | Pending | High
EXP-02887 | PRJ-003 | PRJ-003-ACT-07 | 2026-03-23 | Labour | LAB-006 | Painter | VEN-005 | 12 | Worker | 12689.28 | 12073.3 | 2173.19 | 14246.49 | Paid | Low
EXP-02888 | PRJ-003 | PRJ-003-ACT-05 | 2026-03-23 | Contractor | CON-003 | Plumbing Contract | VEN-010 | 1 | Contract | 442207.04 | 447531.13 | 80555.6 | 528086.73 | Paid | Medium
EXP-02889 | PRJ-003 | PRJ-003-ACT-02 | 2026-03-23 | Other | OTH-001 | Miscellaneous | VEN-008 | 1 | Lot | 51737.41 | 52267.86 | 9408.21 | 61676.07 | Paid | Medium
EXP-02890 | PRJ-003 | PRJ-003-ACT-01 | 2026-03-28 | Contractor | CON-001 | Civil Structure Contract | VEN-008 | 1 | Contract | 444942.91 | 421429.23 | 75857.26 | 497286.49 | Paid | Medium
EXP-02891 | PRJ-003 | PRJ-003-ACT-08 | 2026-03-28 | Material | MAT-008 | Tiles | VEN-001 | 4.43 | Sq Ft | 310.1 | 325.32 | 58.56 | 383.88 | Pending | High
EXP-02892 | PRJ-003 | PRJ-003-ACT-02 | 2026-03-28 | Contractor | CON-004 | Finishing Contract | VEN-008 | 1 | Contract | 195102.77 | 196978.58 | 35456.14 | 232434.72 | Paid | Low
EXP-02893 | PRJ-003 | PRJ-003-ACT-06 | 2026-03-28 | Equipment | EQ-004 | Scaffolding | VEN-008 | 6 | Day | 16246.97 | 15551.31 | 2799.24 | 18350.55 | Paid | Low
EXP-02894 | PRJ-003 | PRJ-003-ACT-08 | 2026-03-28 | Labour | LAB-001 | Mason | VEN-010 | 13 | Worker | 10850.07 | 10092.49 | 1816.65 | 11909.14 | Paid | Low
EXP-02895 | PRJ-003 | PRJ-003-ACT-08 | 2026-03-28 | Labour | LAB-004 | Electrician | VEN-001 | 8 | Worker | 5720.87 | 5903.71 | 1062.67 | 6966.38 | Paid | Low
EXP-02896 | PRJ-003 | PRJ-003-ACT-04 | 2026-03-28 | Material | MAT-009 | Paint | VEN-010 | 27.32 | Litre | 5937.55 | 5743.55 | 1033.84 | 6777.39 | Paid | Low
EXP-02897 | PRJ-003 | PRJ-003-ACT-01 | 2026-03-28 | Labour | LAB-002 | Helper | VEN-008 | 18 | Worker | 15261.04 | 14865.14 | 2675.73 | 17540.87 | Paid | Low
EXP-02898 | PRJ-003 | PRJ-003-ACT-06 | 2026-03-28 | Contractor | CON-004 | Finishing Contract | VEN-010 | 1 | Contract | 364279.2 | 392099.58 | 70577.92 | 462677.5 | Paid | Low
EXP-02899 | PRJ-003 | PRJ-003-ACT-08 | 2026-04-02 | Equipment | EQ-003 | Concrete Mixer | VEN-008 | 2 | Day | 10313.2 | 9569.82 | 1722.57 | 11292.39 | Pending | Low
EXP-02900 | PRJ-003 | PRJ-003-ACT-07 | 2026-04-02 | Material | MAT-010 | Glass | VEN-005 | 8.24 | Sq Ft | 1277.09 | 1338.97 | 241.01 | 1579.98 | Paid | Medium
EXP-02901 | PRJ-003 | PRJ-003-ACT-10 | 2026-04-02 | Material | MAT-005 | Bricks | VEN-010 | 4.2 | Piece | 45.91 | 42.79 | 7.7 | 50.49 | Partially Paid | Low
EXP-02902 | PRJ-003 | PRJ-003-ACT-03 | 2026-04-02 | Material | MAT-002 | Steel | VEN-008 | 6.74 | Ton | 363330.32 | 380151.01 | 68427.18 | 448578.19 | Paid | Medium
EXP-02903 | PRJ-003 | PRJ-003-ACT-04 | 2026-04-02 | Material | MAT-006 | Electrical Cable | VEN-001 | 4.22 | Meter | 409.56 | 386.01 | 69.48 | 455.49 | Paid | Low
EXP-02904 | PRJ-003 | PRJ-003-ACT-01 | 2026-04-02 | Other | OTH-001 | Miscellaneous | VEN-008 | 1 | Lot | 35267.74 | 35324.46 | 6358.4 | 41682.86 | Paid | Low
EXP-02905 | PRJ-003 | PRJ-003-ACT-04 | 2026-04-02 | Equipment | EQ-001 | Crane | VEN-010 | 3 | Day | 55231.52 | 57486.84 | 10347.63 | 67834.47 | Paid | High
EXP-02906 | PRJ-003 | PRJ-003-ACT-02 | 2026-04-02 | Labour | LAB-005 | Plumber | VEN-008 | 9 | Worker | 14837.01 | 13743.66 | 2473.86 | 16217.52 | Paid | Medium
EXP-02907 | PRJ-003 | PRJ-003-ACT-07 | 2026-04-02 | Contractor | CON-002 | Electrical Contract | VEN-010 | 1 | Contract | 416701.11 | 423724.35 | 76270.38 | 499994.73 | Partially Paid | Low
EXP-02908 | PRJ-003 | PRJ-003-ACT-08 | 2026-04-07 | Equipment | EQ-003 | Concrete Mixer | VEN-005 | 3 | Day | 13800.1 | 13735.2 | 2472.34 | 16207.54 | Paid | Low
EXP-02909 | PRJ-003 | PRJ-003-ACT-07 | 2026-04-07 | Contractor | CON-003 | Plumbing Contract | VEN-010 | 1 | Contract | 442202.76 | 414810.24 | 74665.84 | 489476.08 | Paid | Low
EXP-02910 | PRJ-003 | PRJ-003-ACT-04 | 2026-04-07 | Material | MAT-006 | Electrical Cable | VEN-010 | 5.2 | Meter | 532.33 | 494.37 | 88.99 | 583.36 | Paid | Low
EXP-02911 | PRJ-003 | PRJ-003-ACT-06 | 2026-04-07 | Material | MAT-005 | Bricks | VEN-005 | 9.17 | Piece | 69.91 | 72.27 | 13.01 | 85.28 | Paid | Low
EXP-02912 | PRJ-003 | PRJ-003-ACT-06 | 2026-04-07 | Material | MAT-007 | PVC Pipe | VEN-008 | 10.16 | Meter | 1277.45 | 1274.04 | 229.33 | 1503.37 | Paid | Medium
EXP-02913 | PRJ-003 | PRJ-003-ACT-01 | 2026-04-07 | Other | OTH-001 | Transport | VEN-010 | 1 | Lot | 35411.61 | 36358.08 | 6544.45 | 42902.53 | Paid | Low
EXP-02914 | PRJ-003 | PRJ-003-ACT-06 | 2026-04-12 | Material | MAT-003 | Sand | VEN-010 | 4.84 | Ton | 9399.39 | 9884.35 | 1779.18 | 11663.53 | Partially Paid | Low
EXP-02915 | PRJ-003 | PRJ-003-ACT-08 | 2026-04-12 | Labour | LAB-001 | Mason | VEN-005 | 8 | Worker | 13584.45 | 13956.9 | 2512.24 | 16469.14 | Paid | Low
EXP-02916 | PRJ-003 | PRJ-003-ACT-08 | 2026-04-12 | Contractor | CON-001 | Civil Structure Contract | VEN-001 | 1 | Contract | 432241.45 | 429671.73 | 77340.91 | 507012.64 | Paid | Low
EXP-02917 | PRJ-003 | PRJ-003-ACT-04 | 2026-04-12 | Labour | LAB-006 | Painter | VEN-001 | 8 | Worker | 5412.43 | 5413.32 | 974.4 | 6387.72 | Paid | Low
EXP-02918 | PRJ-003 | PRJ-003-ACT-03 | 2026-04-12 | Equipment | EQ-001 | Crane | VEN-005 | 5 | Day | 97086.87 | 97519.64 | 17553.54 | 115073.18 | Paid | Low
EXP-02919 | PRJ-003 | PRJ-003-ACT-08 | 2026-04-12 | Labour | LAB-004 | Electrician | VEN-010 | 19 | Worker | 20191.88 | 19434.29 | 3498.17 | 22932.46 | Paid | Low
EXP-02920 | PRJ-003 | PRJ-003-ACT-06 | 2026-04-17 | Material | MAT-007 | PVC Pipe | VEN-010 | 13.84 | Meter | 1706.47 | 1720.99 | 309.78 | 2030.77 | Paid | Low
EXP-02921 | PRJ-003 | PRJ-003-ACT-09 | 2026-04-17 | Contractor | CON-004 | Finishing Contract | VEN-010 | 1 | Contract | 353979.3 | 331954.03 | 59751.73 | 391705.76 | Paid | Low
EXP-02922 | PRJ-003 | PRJ-003-ACT-05 | 2026-04-17 | Material | MAT-004 | Aggregate | VEN-010 | 4.15 | Ton | 5233.56 | 5596.64 | 1007.4 | 6604.04 | Paid | Low
EXP-02923 | PRJ-003 | PRJ-003-ACT-01 | 2026-04-17 | Equipment | EQ-003 | Concrete Mixer | VEN-001 | 3 | Day | 12615.82 | 13672.95 | 2461.13 | 16134.08 | Paid | Low
EXP-02924 | PRJ-003 | PRJ-003-ACT-01 | 2026-04-17 | Labour | LAB-001 | Mason | VEN-001 | 4 | Worker | 3083.28 | 3056.25 | 550.12 | 3606.37 | Paid | Low
EXP-02925 | PRJ-003 | PRJ-003-ACT-06 | 2026-04-17 | Labour | LAB-005 | Plumber | VEN-008 | 12 | Worker | 9188.04 | 9236.92 | 1662.65 | 10899.57 | Paid | Low
EXP-02926 | PRJ-003 | PRJ-003-ACT-01 | 2026-04-22 | Other | OTH-001 | Transport | VEN-010 | 1 | Lot | 12845.96 | 12254.97 | 2205.89 | 14460.86 | Paid | Low
EXP-02927 | PRJ-003 | PRJ-003-ACT-09 | 2026-04-22 | Labour | LAB-006 | Painter | VEN-005 | 33 | Worker | 44892.89 | 48542.16 | 8737.59 | 57279.75 | Paid | Medium
EXP-02928 | PRJ-003 | PRJ-003-ACT-10 | 2026-04-22 | Material | MAT-005 | Bricks | VEN-008 | 73.78 | Piece | 562.31 | 582.39 | 104.83 | 687.22 | Paid | Low
EXP-02929 | PRJ-003 | PRJ-003-ACT-10 | 2026-04-22 | Material | MAT-004 | Aggregate | VEN-010 | 15.97 | Ton | 28054.58 | 27465.51 | 4943.79 | 32409.3 | Paid | Medium
EXP-02930 | PRJ-003 | PRJ-003-ACT-08 | 2026-04-22 | Labour | LAB-004 | Electrician | VEN-005 | 15 | Worker | 22549.19 | 21752.31 | 3915.42 | 25667.73 | Paid | Low
EXP-02931 | PRJ-003 | PRJ-003-ACT-07 | 2026-04-22 | Equipment | EQ-002 | Excavator | VEN-010 | 1 | Day | 14581.61 | 15216.79 | 2739.02 | 17955.81 | Paid | Medium
EXP-02932 | PRJ-003 | PRJ-003-ACT-02 | 2026-04-27 | Material | MAT-002 | Steel | VEN-001 | 18.67 | Ton | 1052427.67 | 1027162.35 | 184889.22 | 1212051.57 | Paid | Medium
EXP-02933 | PRJ-003 | PRJ-003-ACT-03 | 2026-04-27 | Material | MAT-008 | Tiles | VEN-010 | 15.64 | Sq Ft | 1047.15 | 1039.35 | 187.08 | 1226.43 | Pending | High
EXP-02934 | PRJ-003 | PRJ-003-ACT-07 | 2026-04-27 | Labour | LAB-004 | Electrician | VEN-001 | 20 | Worker | 30872.08 | 31612.82 | 5690.31 | 37303.13 | Partially Paid | Medium
EXP-02935 | PRJ-003 | PRJ-003-ACT-05 | 2026-04-27 | Material | MAT-002 | Steel | VEN-005 | 15.02 | Ton | 1021665.42 | 1047104.63 | 188478.83 | 1235583.46 | Paid | Low
EXP-02936 | PRJ-003 | PRJ-003-ACT-06 | 2026-04-27 | Material | MAT-002 | Steel | VEN-010 | 3.92 | Ton | 284105.92 | 267061.59 | 48071.09 | 315132.68 | Paid | Low
EXP-02937 | PRJ-003 | PRJ-003-ACT-05 | 2026-04-27 | Material | MAT-009 | Paint | VEN-010 | 8.8 | Litre | 1805.35 | 1939.92 | 349.19 | 2289.11 | Partially Paid | High
EXP-02938 | PRJ-003 | PRJ-003-ACT-03 | 2026-04-27 | Labour | LAB-002 | Helper | VEN-010 | 18 | Worker | 13957.86 | 14166.37 | 2549.95 | 16716.32 | Paid | Medium
EXP-02939 | PRJ-003 | PRJ-003-ACT-09 | 2026-04-27 | Material | MAT-002 | Steel | VEN-010 | 44.12 | Ton | 3096455.49 | 3031516.13 | 545672.9 | 3577189.03 | Paid | Low
EXP-02940 | PRJ-003 | PRJ-003-ACT-08 | 2026-05-02 | Material | MAT-009 | Paint | VEN-001 | 7.48 | Litre | 1672.91 | 1742.67 | 313.68 | 2056.35 | Paid | Medium
EXP-02941 | PRJ-003 | PRJ-003-ACT-08 | 2026-05-02 | Contractor | CON-004 | Finishing Contract | VEN-001 | 1 | Contract | 419938.32 | 436780.43 | 78620.48 | 515400.91 | Partially Paid | Low
EXP-02942 | PRJ-003 | PRJ-003-ACT-01 | 2026-05-02 | Equipment | EQ-002 | Excavator | VEN-001 | 7 | Day | 103364.71 | 99895.76 | 17981.24 | 117877 | Pending | Medium
EXP-02943 | PRJ-003 | PRJ-003-ACT-08 | 2026-05-02 | Material | MAT-007 | PVC Pipe | VEN-008 | 12.17 | Meter | 1641.01 | 1561.05 | 280.99 | 1842.04 | Partially Paid | Low
EXP-02944 | PRJ-003 | PRJ-003-ACT-03 | 2026-05-02 | Material | MAT-010 | Glass | VEN-005 | 22.37 | Sq Ft | 3265.6 | 3178.22 | 572.08 | 3750.3 | Paid | Low
EXP-02945 | PRJ-003 | PRJ-003-ACT-05 | 2026-05-02 | Material | MAT-006 | Electrical Cable | VEN-001 | 6.82 | Meter | 669.31 | 643.02 | 115.74 | 758.76 | Paid | Low
EXP-02946 | PRJ-003 | PRJ-003-ACT-03 | 2026-05-02 | Material | MAT-004 | Aggregate | VEN-010 | 18.77 | Ton | 27726 | 29512.73 | 5312.29 | 34825.02 | Paid | Low
EXP-02947 | PRJ-003 | PRJ-003-ACT-04 | 2026-05-07 | Labour | LAB-001 | Mason | VEN-001 | 30 | Worker | 55904.56 | 52902.09 | 9522.38 | 62424.47 | Paid | Medium
EXP-02948 | PRJ-003 | PRJ-003-ACT-06 | 2026-05-07 | Material | MAT-003 | Sand | VEN-005 | 7.74 | Ton | 12420.13 | 12999.87 | 2339.98 | 15339.85 | Paid | Medium
EXP-02949 | PRJ-003 | PRJ-003-ACT-09 | 2026-05-07 | Equipment | EQ-001 | Crane | VEN-010 | 4 | Day | 75477.28 | 73041.23 | 13147.42 | 86188.65 | Paid | Medium
EXP-02950 | PRJ-003 | PRJ-003-ACT-05 | 2026-05-07 | Material | MAT-008 | Tiles | VEN-010 | 3.04 | Sq Ft | 257.45 | 247.64 | 44.58 | 292.22 | Paid | Low
EXP-02951 | PRJ-003 | PRJ-003-ACT-07 | 2026-05-07 | Labour | LAB-004 | Electrician | VEN-008 | 9 | Worker | 14314.72 | 14423.92 | 2596.31 | 17020.23 | Partially Paid | Medium
EXP-02952 | PRJ-003 | PRJ-003-ACT-02 | 2026-05-07 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 303477.52 | 294583.95 | 53025.11 | 347609.06 | Paid | Low
EXP-02953 | PRJ-003 | PRJ-003-ACT-04 | 2026-05-12 | Labour | LAB-003 | Carpenter | VEN-010 | 30 | Worker | 35387.64 | 33403.81 | 6012.69 | 39416.5 | Paid | Low
EXP-02954 | PRJ-003 | PRJ-003-ACT-08 | 2026-05-12 | Contractor | CON-003 | Plumbing Contract | VEN-005 | 1 | Contract | 131875.25 | 128304.89 | 23094.88 | 151399.77 | Paid | Low
EXP-02955 | PRJ-003 | PRJ-003-ACT-06 | 2026-05-12 | Contractor | CON-002 | Electrical Contract | VEN-008 | 1 | Contract | 337035.05 | 315399.88 | 56771.98 | 372171.86 | Partially Paid | Low
EXP-02956 | PRJ-003 | PRJ-003-ACT-05 | 2026-05-12 | Equipment | EQ-004 | Scaffolding | VEN-001 | 4 | Day | 9767.25 | 9564.2 | 1721.56 | 11285.76 | Paid | Medium
EXP-02957 | PRJ-003 | PRJ-003-ACT-08 | 2026-05-12 | Contractor | CON-002 | Electrical Contract | VEN-010 | 1 | Contract | 322279.73 | 349149.89 | 62846.98 | 411996.87 | Paid | High
EXP-02958 | PRJ-003 | PRJ-003-ACT-05 | 2026-05-12 | Material | MAT-008 | Tiles | VEN-010 | 3.61 | Sq Ft | 285.26 | 287.35 | 51.72 | 339.07 | Paid | Medium
EXP-02959 | PRJ-003 | PRJ-003-ACT-07 | 2026-05-12 | Material | MAT-003 | Sand | VEN-010 | 31.02 | Ton | 64197.48 | 61336.44 | 11040.56 | 72377 | Paid | Low
EXP-02960 | PRJ-003 | PRJ-003-ACT-06 | 2026-05-12 | Material | MAT-003 | Sand | VEN-001 | 3.95 | Ton | 7686.48 | 7515.33 | 1352.76 | 8868.09 | Paid | Low
EXP-02961 | PRJ-003 | PRJ-003-ACT-02 | 2026-05-17 | Equipment | EQ-003 | Concrete Mixer | VEN-001 | 5 | Day | 23181.83 | 23715.05 | 4268.71 | 27983.76 | Paid | Low
EXP-02962 | PRJ-003 | PRJ-003-ACT-03 | 2026-05-17 | Material | MAT-008 | Tiles | VEN-010 | 5.07 | Sq Ft | 336.78 | 328.73 | 59.17 | 387.9 | Paid | High
EXP-02963 | PRJ-003 | PRJ-003-ACT-07 | 2026-05-17 | Material | MAT-005 | Bricks | VEN-010 | 3.25 | Piece | 30.14 | 28.33 | 5.1 | 33.43 | Paid | Low
EXP-02964 | PRJ-003 | PRJ-003-ACT-04 | 2026-05-17 | Labour | LAB-003 | Carpenter | VEN-010 | 5 | Worker | 6260.85 | 6552.54 | 1179.46 | 7732 | Paid | High
EXP-02965 | PRJ-003 | PRJ-003-ACT-05 | 2026-05-17 | Labour | LAB-006 | Painter | VEN-008 | 25 | Worker | 38164.2 | 39037.97 | 7026.83 | 46064.8 | Paid | High
EXP-02966 | PRJ-003 | PRJ-003-ACT-05 | 2026-05-17 | Material | MAT-004 | Aggregate | VEN-001 | 19.23 | Ton | 32137.89 | 30708.51 | 5527.53 | 36236.04 | Pending | Medium
EXP-02967 | PRJ-003 | PRJ-003-ACT-09 | 2026-05-22 | Contractor | CON-003 | Plumbing Contract | VEN-010 | 1 | Contract | 131067.76 | 133202.54 | 23976.46 | 157179 | Paid | Low
EXP-02968 | PRJ-003 | PRJ-003-ACT-10 | 2026-05-22 | Other | OTH-001 | Miscellaneous | VEN-008 | 1 | Lot | 60070.04 | 60428.03 | 10877.05 | 71305.08 | Paid | Low
EXP-02969 | PRJ-003 | PRJ-003-ACT-05 | 2026-05-22 | Material | MAT-010 | Glass | VEN-005 | 5.68 | Sq Ft | 952.94 | 907.75 | 163.39 | 1071.14 | Paid | Low
EXP-02970 | PRJ-003 | PRJ-003-ACT-05 | 2026-05-22 | Labour | LAB-001 | Mason | VEN-005 | 10 | Worker | 16277.51 | 15256.9 | 2746.24 | 18003.14 | Paid | High
EXP-02971 | PRJ-003 | PRJ-003-ACT-09 | 2026-05-22 | Material | MAT-010 | Glass | VEN-005 | 5.21 | Sq Ft | 864.87 | 868.05 | 156.25 | 1024.3 | Pending | Low
EXP-02972 | PRJ-003 | PRJ-003-ACT-09 | 2026-05-22 | Equipment | EQ-002 | Excavator | VEN-008 | 1 | Day | 15107.69 | 15129.03 | 2723.23 | 17852.26 | Paid | Low
EXP-02973 | PRJ-003 | PRJ-003-ACT-09 | 2026-05-22 | Material | MAT-008 | Tiles | VEN-010 | 10.44 | Sq Ft | 767.15 | 782.93 | 140.93 | 923.86 | Paid | Low
EXP-02974 | PRJ-003 | PRJ-003-ACT-03 | 2026-05-27 | Material | MAT-009 | Paint | VEN-001 | 5.37 | Litre | 987.44 | 1033.1 | 185.96 | 1219.06 | Pending | Low
EXP-02975 | PRJ-003 | PRJ-003-ACT-09 | 2026-05-27 | Material | MAT-001 | Cement | VEN-010 | 7.37 | Bag | 3737.29 | 3934.57 | 708.22 | 4642.79 | Paid | Low
EXP-02976 | PRJ-003 | PRJ-003-ACT-04 | 2026-05-27 | Contractor | CON-002 | Electrical Contract | VEN-001 | 1 | Contract | 405162.81 | 400546.35 | 72098.34 | 472644.69 | Paid | Low
EXP-02977 | PRJ-003 | PRJ-003-ACT-05 | 2026-05-27 | Contractor | CON-004 | Finishing Contract | VEN-001 | 1 | Contract | 221531.08 | 208832.83 | 37589.91 | 246422.74 | Paid | Low
EXP-02978 | PRJ-003 | PRJ-003-ACT-05 | 2026-05-27 | Other | OTH-001 | Permit | VEN-008 | 1 | Lot | 72573.75 | 77574.81 | 13963.47 | 91538.28 | Partially Paid | Low
EXP-02979 | PRJ-003 | PRJ-003-ACT-05 | 2026-05-27 | Material | MAT-005 | Bricks | VEN-005 | 12.03 | Piece | 116.09 | 123.79 | 22.28 | 146.07 | Paid | Low
EXP-02980 | PRJ-003 | PRJ-003-ACT-03 | 2026-05-27 | Contractor | CON-004 | Finishing Contract | VEN-008 | 1 | Contract | 296357.8 | 285244.67 | 51344.04 | 336588.71 | Paid | High
EXP-02981 | PRJ-003 | PRJ-003-ACT-06 | 2026-05-27 | Labour | LAB-002 | Helper | VEN-010 | 31 | Worker | 23161.69 | 24861.37 | 4475.05 | 29336.42 | Paid | Medium
EXP-02982 | PRJ-003 | PRJ-003-ACT-01 | 2026-05-27 | Labour | LAB-001 | Mason | VEN-008 | 15 | Worker | 16635.06 | 15481.08 | 2786.59 | 18267.67 | Paid | High
EXP-02983 | PRJ-003 | PRJ-003-ACT-04 | 2026-06-01 | Labour | LAB-001 | Mason | VEN-005 | 6 | Worker | 7546.76 | 8046.61 | 1448.39 | 9495 | Paid | Low
EXP-02984 | PRJ-003 | PRJ-003-ACT-03 | 2026-06-01 | Material | MAT-010 | Glass | VEN-010 | 4.67 | Sq Ft | 610.69 | 635.79 | 114.44 | 750.23 | Paid | Low
EXP-02985 | PRJ-003 | PRJ-003-ACT-03 | 2026-06-01 | Material | MAT-003 | Sand | VEN-010 | 7.65 | Ton | 16191.95 | 15322.1 | 2757.98 | 18080.08 | Partially Paid | Medium
EXP-02986 | PRJ-003 | PRJ-003-ACT-04 | 2026-06-01 | Material | MAT-006 | Electrical Cable | VEN-008 | 26.22 | Meter | 1848.3 | 1961.17 | 353.01 | 2314.18 | Paid | High
EXP-02987 | PRJ-003 | PRJ-003-ACT-06 | 2026-06-01 | Equipment | EQ-002 | Excavator | VEN-010 | 4 | Day | 60266.44 | 60363.83 | 10865.49 | 71229.32 | Paid | Low
EXP-02988 | PRJ-003 | PRJ-003-ACT-06 | 2026-06-01 | Labour | LAB-001 | Mason | VEN-010 | 6 | Worker | 10126.66 | 9581.11 | 1724.6 | 11305.71 | Paid | Medium
EXP-02989 | PRJ-003 | PRJ-003-ACT-01 | 2026-06-01 | Contractor | CON-001 | Civil Structure Contract | VEN-005 | 1 | Contract | 286326.82 | 266329.95 | 47939.39 | 314269.34 | Pending | Low
EXP-02990 | PRJ-003 | PRJ-003-ACT-10 | 2026-06-01 | Contractor | CON-001 | Civil Structure Contract | VEN-005 | 1 | Contract | 266864 | 269455.29 | 48501.95 | 317957.24 | Paid | Medium
EXP-02991 | PRJ-003 | PRJ-003-ACT-07 | 2026-06-01 | Contractor | CON-001 | Civil Structure Contract | VEN-008 | 1 | Contract | 200479.05 | 209418.54 | 37695.34 | 247113.88 | Paid | Medium
EXP-02992 | PRJ-003 | PRJ-003-ACT-09 | 2026-06-06 | Labour | LAB-003 | Carpenter | VEN-005 | 9 | Worker | 7722.93 | 7737.98 | 1392.84 | 9130.82 | Paid | Low
EXP-02993 | PRJ-003 | PRJ-003-ACT-09 | 2026-06-06 | Material | MAT-007 | PVC Pipe | VEN-010 | 2.9 | Meter | 274.51 | 297.3 | 53.51 | 350.81 | Paid | Low
EXP-02994 | PRJ-003 | PRJ-003-ACT-08 | 2026-06-06 | Other | OTH-001 | Safety | VEN-005 | 1 | Lot | 16736.16 | 16629.48 | 2993.31 | 19622.79 | Paid | Medium
EXP-02995 | PRJ-003 | PRJ-003-ACT-04 | 2026-06-06 | Labour | LAB-005 | Plumber | VEN-008 | 31 | Worker | 56827.93 | 55524.04 | 9994.33 | 65518.37 | Paid | Medium
EXP-02996 | PRJ-003 | PRJ-003-ACT-01 | 2026-06-06 | Other | OTH-001 | Transport | VEN-001 | 1 | Lot | 81837.59 | 76130.01 | 13703.4 | 89833.41 | Pending | Low
EXP-02997 | PRJ-003 | PRJ-003-ACT-04 | 2026-06-06 | Contractor | CON-001 | Civil Structure Contract | VEN-008 | 1 | Contract | 286748.92 | 275818.09 | 49647.26 | 325465.35 | Partially Paid | Medium
EXP-02998 | PRJ-003 | PRJ-003-ACT-10 | 2026-06-06 | Material | MAT-001 | Cement | VEN-001 | 12.04 | Bag | 6022.28 | 6293.36 | 1132.8 | 7426.16 | Paid | Medium
EXP-02999 | PRJ-003 | PRJ-003-ACT-10 | 2026-06-11 | Labour | LAB-005 | Plumber | VEN-005 | 4 | Worker | 5605.13 | 6021.96 | 1083.95 | 7105.91 | Paid | Medium
EXP-03000 | PRJ-003 | PRJ-003-ACT-09 | 2026-06-11 | Material | MAT-003 | Sand | VEN-008 | 8.94 | Ton | 15995.43 | 17240.16 | 3103.23 | 20343.39 | Paid | Low
EXP-03001 | PRJ-003 | PRJ-003-ACT-09 | 2026-06-11 | Contractor | CON-004 | Finishing Contract | VEN-008 | 1 | Contract | 255555.18 | 272682.97 | 49082.93 | 321765.9 | Paid | High
EXP-03002 | PRJ-003 | PRJ-003-ACT-10 | 2026-06-11 | Labour | LAB-002 | Helper | VEN-008 | 26 | Worker | 27089.98 | 26676.6 | 4801.79 | 31478.39 | Partially Paid | Low
EXP-03003 | PRJ-003 | PRJ-003-ACT-09 | 2026-06-11 | Equipment | EQ-004 | Scaffolding | VEN-010 | 2 | Day | 5184.55 | 5273.83 | 949.29 | 6223.12 | Paid | Low
EXP-03004 | PRJ-003 | PRJ-003-ACT-09 | 2026-06-11 | Contractor | CON-002 | Electrical Contract | VEN-008 | 1 | Contract | 362364.47 | 381785.59 | 68721.41 | 450507 | Paid | High
EXP-03005 | PRJ-003 | PRJ-003-ACT-10 | 2026-06-11 | Material | MAT-008 | Tiles | VEN-010 | 10.55 | Sq Ft | 773.96 | 755.55 | 136 | 891.55 | Partially Paid | Low
EXP-03006 | PRJ-003 | PRJ-003-ACT-10 | 2026-06-11 | Equipment | EQ-003 | Concrete Mixer | VEN-005 | 4 | Day | 18043.93 | 19518.14 | 3513.27 | 23031.41 | Paid | Low
EXP-03007 | PRJ-003 | PRJ-003-ACT-07 | 2026-06-16 | Material | MAT-008 | Tiles | VEN-010 | 8.2 | Sq Ft | 651.42 | 608.16 | 109.47 | 717.63 | Paid | Medium
EXP-03008 | PRJ-003 | PRJ-003-ACT-06 | 2026-06-16 | Other | OTH-001 | Permit | VEN-001 | 1 | Lot | 40128.78 | 38378.16 | 6908.07 | 45286.23 | Paid | Medium
EXP-03009 | PRJ-003 | PRJ-003-ACT-01 | 2026-06-16 | Labour | LAB-005 | Plumber | VEN-010 | 10 | Worker | 9614.19 | 9706.62 | 1747.19 | 11453.81 | Paid | Medium
EXP-03010 | PRJ-003 | PRJ-003-ACT-04 | 2026-06-16 | Equipment | EQ-004 | Scaffolding | VEN-005 | 1 | Day | 2656.67 | 2465.47 | 443.78 | 2909.25 | Paid | Medium
EXP-03011 | PRJ-003 | PRJ-003-ACT-05 | 2026-06-16 | Labour | LAB-004 | Electrician | VEN-005 | 28 | Worker | 46432.86 | 43442.82 | 7819.71 | 51262.53 | Paid | Medium
EXP-03012 | PRJ-003 | PRJ-003-ACT-06 | 2026-06-16 | Material | MAT-010 | Glass | VEN-005 | 20.27 | Sq Ft | 3464.89 | 3431.16 | 617.61 | 4048.77 | Paid | Low
EXP-03013 | PRJ-003 | PRJ-003-ACT-05 | 2026-06-21 | Contractor | CON-004 | Finishing Contract | VEN-008 | 1 | Contract | 140114.73 | 139926.3 | 25186.73 | 165113.03 | Paid | Low
EXP-03014 | PRJ-003 | PRJ-003-ACT-03 | 2026-06-21 | Labour | LAB-002 | Helper | VEN-001 | 7 | Worker | 9186.72 | 9150.79 | 1647.14 | 10797.93 | Paid | Low
EXP-03015 | PRJ-003 | PRJ-003-ACT-04 | 2026-06-21 | Equipment | EQ-002 | Excavator | VEN-010 | 6 | Day | 93506.61 | 87516.02 | 15752.88 | 103268.9 | Partially Paid | Low
EXP-03016 | PRJ-003 | PRJ-003-ACT-09 | 2026-06-21 | Contractor | CON-004 | Finishing Contract | VEN-008 | 1 | Contract | 157313.78 | 164282.69 | 29570.88 | 193853.57 | Pending | Low
EXP-03017 | PRJ-003 | PRJ-003-ACT-08 | 2026-06-21 | Labour | LAB-006 | Painter | VEN-005 | 12 | Worker | 20516.83 | 20907.84 | 3763.41 | 24671.25 | Paid | Low
EXP-03018 | PRJ-003 | PRJ-003-ACT-04 | 2026-06-21 | Equipment | EQ-003 | Concrete Mixer | VEN-005 | 1 | Day | 4176.08 | 4111.54 | 740.08 | 4851.62 | Pending | Low
EXP-03019 | PRJ-003 | PRJ-003-ACT-10 | 2026-06-26 | Material | MAT-007 | PVC Pipe | VEN-010 | 4.76 | Meter | 503.01 | 536.48 | 96.57 | 633.05 | Paid | Low
EXP-03020 | PRJ-003 | PRJ-003-ACT-06 | 2026-06-26 | Contractor | CON-002 | Electrical Contract | VEN-008 | 1 | Contract | 279625.12 | 287638.47 | 51774.92 | 339413.39 | Paid | Low
EXP-03021 | PRJ-003 | PRJ-003-ACT-08 | 2026-06-26 | Labour | LAB-003 | Carpenter | VEN-010 | 24 | Worker | 28965.79 | 28264.31 | 5087.58 | 33351.89 | Partially Paid | Low
EXP-03022 | PRJ-003 | PRJ-003-ACT-08 | 2026-06-26 | Material | MAT-001 | Cement | VEN-001 | 5.54 | Bag | 2709.16 | 2896.4 | 521.35 | 3417.75 | Pending | Medium
EXP-03023 | PRJ-003 | PRJ-003-ACT-02 | 2026-06-26 | Labour | LAB-005 | Plumber | VEN-010 | 17 | Worker | 22162.35 | 20733.15 | 3731.97 | 24465.12 | Partially Paid | Low
EXP-03024 | PRJ-003 | PRJ-003-ACT-10 | 2026-06-26 | Labour | LAB-006 | Painter | VEN-010 | 6 | Worker | 4351.46 | 4347.67 | 782.58 | 5130.25 | Paid | Low
EXP-03025 | PRJ-004 | PRJ-004-ACT-09 | 2025-02-15 | Labour | LAB-004 | Electrician | VEN-004 | 29 | Worker | 50911.7 | 47529.07 | 8555.23 | 56084.3 | Paid | Medium
EXP-03026 | PRJ-004 | PRJ-004-ACT-05 | 2025-02-15 | Labour | LAB-003 | Carpenter | VEN-009 | 7 | Worker | 10209.92 | 10323.5 | 1858.23 | 12181.73 | Paid | Medium
EXP-03027 | PRJ-004 | PRJ-004-ACT-07 | 2025-02-15 | Labour | LAB-006 | Painter | VEN-011 | 8 | Worker | 7042.67 | 7086.78 | 1275.62 | 8362.4 | Paid | Medium
EXP-03028 | PRJ-004 | PRJ-004-ACT-06 | 2025-02-15 | Contractor | CON-002 | Electrical Contract | VEN-003 | 1 | Contract | 419144.54 | 425400.16 | 76572.03 | 501972.19 | Paid | Low
EXP-03029 | PRJ-004 | PRJ-004-ACT-05 | 2025-02-15 | Labour | LAB-003 | Carpenter | VEN-004 | 15 | Worker | 10803.05 | 10588.37 | 1905.91 | 12494.28 | Pending | High
EXP-03030 | PRJ-004 | PRJ-004-ACT-07 | 2025-02-15 | Labour | LAB-002 | Helper | VEN-004 | 22 | Worker | 37267.63 | 35399.96 | 6371.99 | 41771.95 | Pending | Medium
EXP-03031 | PRJ-004 | PRJ-004-ACT-01 | 2025-02-15 | Contractor | CON-004 | Finishing Contract | VEN-003 | 1 | Contract | 346774.17 | 368864.08 | 66395.53 | 435259.61 | Paid | High
EXP-03032 | PRJ-004 | PRJ-004-ACT-02 | 2025-02-15 | Material | MAT-006 | Electrical Cable | VEN-009 | 12.69 | Meter | 1130.77 | 1147.23 | 206.5 | 1353.73 | Paid | Medium
EXP-03033 | PRJ-004 | PRJ-004-ACT-01 | 2025-02-15 | Material | MAT-004 | Aggregate | VEN-003 | 10.57 | Ton | 17532.27 | 17714.64 | 3188.64 | 20903.28 | Partially Paid | Medium
EXP-03034 | PRJ-004 | PRJ-004-ACT-06 | 2025-02-15 | Material | MAT-010 | Glass | VEN-009 | 8.39 | Sq Ft | 1501.36 | 1456.01 | 262.08 | 1718.09 | Pending | Low
EXP-03035 | PRJ-004 | PRJ-004-ACT-04 | 2025-02-20 | Material | MAT-008 | Tiles | VEN-004 | 45.98 | Sq Ft | 3624.32 | 3582.64 | 644.88 | 4227.52 | Paid | Medium
EXP-03036 | PRJ-004 | PRJ-004-ACT-05 | 2025-02-20 | Material | MAT-003 | Sand | VEN-004 | 5.37 | Ton | 10088.48 | 10299.53 | 1853.92 | 12153.45 | Paid | Low
EXP-03037 | PRJ-004 | PRJ-004-ACT-03 | 2025-02-20 | Other | OTH-001 | Safety | VEN-004 | 1 | Lot | 65672.54 | 63268.57 | 11388.34 | 74656.91 | Partially Paid | Low
EXP-03038 | PRJ-004 | PRJ-004-ACT-06 | 2025-02-20 | Contractor | CON-002 | Electrical Contract | VEN-009 | 1 | Contract | 192719.95 | 180399.43 | 32471.9 | 212871.33 | Pending | Low
EXP-03039 | PRJ-004 | PRJ-004-ACT-03 | 2025-02-20 | Other | OTH-001 | Miscellaneous | VEN-009 | 1 | Lot | 41338.42 | 38312.66 | 6896.28 | 45208.94 | Paid | Medium
EXP-03040 | PRJ-004 | PRJ-004-ACT-03 | 2025-02-20 | Equipment | EQ-003 | Concrete Mixer | VEN-009 | 4 | Day | 16470.87 | 17006.95 | 3061.25 | 20068.2 | Paid | Medium
EXP-03041 | PRJ-004 | PRJ-004-ACT-05 | 2025-02-20 | Material | MAT-005 | Bricks | VEN-009 | 8.77 | Piece | 75.63 | 74.83 | 13.47 | 88.3 | Paid | Low
EXP-03042 | PRJ-004 | PRJ-004-ACT-03 | 2025-02-20 | Material | MAT-007 | PVC Pipe | VEN-009 | 10.73 | Meter | 1281.74 | 1271.62 | 228.89 | 1500.51 | Paid | Low
EXP-03043 | PRJ-004 | PRJ-004-ACT-04 | 2025-02-20 | Contractor | CON-001 | Civil Structure Contract | VEN-003 | 1 | Contract | 383597.36 | 383065.69 | 68951.82 | 452017.51 | Paid | Low
EXP-03044 | PRJ-004 | PRJ-004-ACT-05 | 2025-02-25 | Contractor | CON-002 | Electrical Contract | VEN-011 | 1 | Contract | 430016.21 | 424127.93 | 76343.03 | 500470.96 | Partially Paid | Low
EXP-03045 | PRJ-004 | PRJ-004-ACT-05 | 2025-02-25 | Contractor | CON-004 | Finishing Contract | VEN-009 | 1 | Contract | 340933.53 | 340745.4 | 61334.17 | 402079.57 | Paid | Low
EXP-03046 | PRJ-004 | PRJ-004-ACT-10 | 2025-02-25 | Labour | LAB-002 | Helper | VEN-011 | 9 | Worker | 7942.05 | 8287.91 | 1491.82 | 9779.73 | Paid | Medium
EXP-03047 | PRJ-004 | PRJ-004-ACT-03 | 2025-02-25 | Material | MAT-010 | Glass | VEN-003 | 19.84 | Sq Ft | 3064.86 | 3012.16 | 542.19 | 3554.35 | Paid | Medium
EXP-03048 | PRJ-004 | PRJ-004-ACT-10 | 2025-02-25 | Material | MAT-003 | Sand | VEN-009 | 36.25 | Ton | 63367.67 | 60135.32 | 10824.36 | 70959.68 | Paid | Low
EXP-03049 | PRJ-004 | PRJ-004-ACT-03 | 2025-02-25 | Other | OTH-001 | Miscellaneous | VEN-009 | 1 | Lot | 66471.65 | 64075.64 | 11533.62 | 75609.26 | Paid | Low
EXP-03050 | PRJ-004 | PRJ-004-ACT-08 | 2025-02-25 | Material | MAT-002 | Steel | VEN-003 | 13.89 | Ton | 921472.68 | 858423.64 | 154516.26 | 1012939.9 | Pending | Medium
EXP-03051 | PRJ-004 | PRJ-004-ACT-01 | 2025-02-25 | Other | OTH-001 | Permit | VEN-011 | 1 | Lot | 10833.05 | 10962.77 | 1973.3 | 12936.07 | Paid | Low
EXP-03052 | PRJ-004 | PRJ-004-ACT-10 | 2025-03-02 | Labour | LAB-003 | Carpenter | VEN-003 | 17 | Worker | 15109.4 | 15379.3 | 2768.27 | 18147.57 | Paid | Low
EXP-03053 | PRJ-004 | PRJ-004-ACT-07 | 2025-03-02 | Contractor | CON-003 | Plumbing Contract | VEN-003 | 1 | Contract | 349313.53 | 360763.18 | 64937.37 | 425700.55 | Paid | Low
EXP-03054 | PRJ-004 | PRJ-004-ACT-05 | 2025-03-02 | Contractor | CON-003 | Plumbing Contract | VEN-009 | 1 | Contract | 423749.66 | 406400.98 | 73152.18 | 479553.16 | Paid | Medium
EXP-03055 | PRJ-004 | PRJ-004-ACT-03 | 2025-03-02 | Contractor | CON-004 | Finishing Contract | VEN-011 | 1 | Contract | 190718.86 | 194640.84 | 35035.35 | 229676.19 | Paid | Medium
EXP-03056 | PRJ-004 | PRJ-004-ACT-06 | 2025-03-02 | Labour | LAB-005 | Plumber | VEN-003 | 26 | Worker | 26933.64 | 26157.72 | 4708.39 | 30866.11 | Partially Paid | Low
EXP-03057 | PRJ-004 | PRJ-004-ACT-03 | 2025-03-02 | Contractor | CON-003 | Plumbing Contract | VEN-004 | 1 | Contract | 93694.2 | 98503.6 | 17730.65 | 116234.25 | Paid | Low
EXP-03058 | PRJ-004 | PRJ-004-ACT-07 | 2025-03-02 | Labour | LAB-002 | Helper | VEN-004 | 21 | Worker | 15062.83 | 15309.74 | 2755.75 | 18065.49 | Paid | Low
EXP-03059 | PRJ-004 | PRJ-004-ACT-10 | 2025-03-07 | Contractor | CON-003 | Plumbing Contract | VEN-003 | 1 | Contract | 135817.5 | 142342.04 | 25621.57 | 167963.61 | Paid | Medium
EXP-03060 | PRJ-004 | PRJ-004-ACT-02 | 2025-03-07 | Equipment | EQ-003 | Concrete Mixer | VEN-009 | 4 | Day | 16696.4 | 16418.92 | 2955.41 | 19374.33 | Partially Paid | Low
EXP-03061 | PRJ-004 | PRJ-004-ACT-03 | 2025-03-07 | Labour | LAB-005 | Plumber | VEN-011 | 34 | Worker | 31060.84 | 33662.29 | 6059.21 | 39721.5 | Paid | Low
EXP-03062 | PRJ-004 | PRJ-004-ACT-07 | 2025-03-07 | Material | MAT-001 | Cement | VEN-004 | 28.49 | Bag | 15146.21 | 14301.67 | 2574.3 | 16875.97 | Paid | Medium
EXP-03063 | PRJ-004 | PRJ-004-ACT-09 | 2025-03-07 | Material | MAT-005 | Bricks | VEN-011 | 18.94 | Piece | 172.4 | 164.12 | 29.54 | 193.66 | Paid | Medium
EXP-03064 | PRJ-004 | PRJ-004-ACT-09 | 2025-03-07 | Material | MAT-001 | Cement | VEN-004 | 30.58 | Bag | 17545.55 | 16274.68 | 2929.44 | 19204.12 | Paid | High
EXP-03065 | PRJ-004 | PRJ-004-ACT-08 | 2025-03-07 | Material | MAT-003 | Sand | VEN-003 | 20.71 | Ton | 33804.5 | 32642.5 | 5875.65 | 38518.15 | Paid | Low
EXP-03066 | PRJ-004 | PRJ-004-ACT-10 | 2025-03-12 | Material | MAT-008 | Tiles | VEN-011 | 5.21 | Sq Ft | 399.36 | 395.99 | 71.28 | 467.27 | Paid | Medium
EXP-03067 | PRJ-004 | PRJ-004-ACT-09 | 2025-03-12 | Equipment | EQ-004 | Scaffolding | VEN-003 | 7 | Day | 17187.19 | 17368.91 | 3126.4 | 20495.31 | Paid | Medium
EXP-03068 | PRJ-004 | PRJ-004-ACT-10 | 2025-03-12 | Contractor | CON-002 | Electrical Contract | VEN-003 | 1 | Contract | 171190.85 | 184610.54 | 33229.9 | 217840.44 | Paid | Low
EXP-03069 | PRJ-004 | PRJ-004-ACT-07 | 2025-03-12 | Material | MAT-006 | Electrical Cable | VEN-011 | 5.96 | Meter | 447.29 | 480.2 | 86.44 | 566.64 | Paid | Low
EXP-03070 | PRJ-004 | PRJ-004-ACT-05 | 2025-03-12 | Equipment | EQ-003 | Concrete Mixer | VEN-011 | 6 | Day | 27722.08 | 27846.2 | 5012.32 | 32858.52 | Paid | Low
EXP-03071 | PRJ-004 | PRJ-004-ACT-10 | 2025-03-12 | Material | MAT-008 | Tiles | VEN-009 | 9.52 | Sq Ft | 727.05 | 714.44 | 128.6 | 843.04 | Paid | Medium
EXP-03072 | PRJ-004 | PRJ-004-ACT-09 | 2025-03-12 | Labour | LAB-004 | Electrician | VEN-004 | 29 | Worker | 31791.3 | 33337.07 | 6000.67 | 39337.74 | Partially Paid | Low
EXP-03073 | PRJ-004 | PRJ-004-ACT-04 | 2025-03-12 | Material | MAT-008 | Tiles | VEN-004 | 2.08 | Sq Ft | 172.47 | 171.86 | 30.93 | 202.79 | Paid | Medium
EXP-03074 | PRJ-004 | PRJ-004-ACT-08 | 2025-03-17 | Material | MAT-006 | Electrical Cable | VEN-009 | 2.06 | Meter | 170.52 | 160.05 | 28.81 | 188.86 | Partially Paid | Low
EXP-03075 | PRJ-004 | PRJ-004-ACT-01 | 2025-03-17 | Material | MAT-002 | Steel | VEN-011 | 5.29 | Ton | 287670.04 | 282714.35 | 50888.58 | 333602.93 | Paid | Medium
EXP-03076 | PRJ-004 | PRJ-004-ACT-07 | 2025-03-17 | Material | MAT-006 | Electrical Cable | VEN-003 | 8.11 | Meter | 635.54 | 664.09 | 119.54 | 783.63 | Paid | Medium
EXP-03077 | PRJ-004 | PRJ-004-ACT-08 | 2025-03-17 | Labour | LAB-002 | Helper | VEN-004 | 26 | Worker | 41449.81 | 42586.88 | 7665.64 | 50252.52 | Paid | Low
EXP-03078 | PRJ-004 | PRJ-004-ACT-04 | 2025-03-17 | Equipment | EQ-002 | Excavator | VEN-011 | 7 | Day | 98737.14 | 101680.75 | 18302.53 | 119983.28 | Paid | Medium
EXP-03079 | PRJ-004 | PRJ-004-ACT-04 | 2025-03-17 | Material | MAT-006 | Electrical Cable | VEN-009 | 16.77 | Meter | 1351.61 | 1391.16 | 250.41 | 1641.57 | Paid | Medium
EXP-03080 | PRJ-004 | PRJ-004-ACT-09 | 2025-03-17 | Material | MAT-005 | Bricks | VEN-011 | 4.28 | Piece | 32.24 | 34.28 | 6.17 | 40.45 | Paid | Medium
EXP-03081 | PRJ-004 | PRJ-004-ACT-03 | 2025-03-17 | Material | MAT-010 | Glass | VEN-011 | 30.8 | Sq Ft | 5786.89 | 5602.86 | 1008.51 | 6611.37 | Paid | Low
EXP-03082 | PRJ-004 | PRJ-004-ACT-06 | 2025-03-17 | Contractor | CON-003 | Plumbing Contract | VEN-003 | 1 | Contract | 269009.19 | 274488.36 | 49407.9 | 323896.26 | Paid | Low
EXP-03083 | PRJ-004 | PRJ-004-ACT-02 | 2025-03-17 | Labour | LAB-005 | Plumber | VEN-004 | 19 | Worker | 15378.87 | 15857.8 | 2854.4 | 18712.2 | Paid | Low
EXP-03084 | PRJ-004 | PRJ-004-ACT-05 | 2025-03-22 | Material | MAT-001 | Cement | VEN-003 | 2.98 | Bag | 1565.1 | 1691.8 | 304.52 | 1996.32 | Paid | Medium
EXP-03085 | PRJ-004 | PRJ-004-ACT-10 | 2025-03-22 | Material | MAT-008 | Tiles | VEN-009 | 4.85 | Sq Ft | 315.78 | 324.1 | 58.34 | 382.44 | Pending | Low
EXP-03086 | PRJ-004 | PRJ-004-ACT-10 | 2025-03-22 | Other | OTH-001 | Site Office | VEN-004 | 1 | Lot | 65385.57 | 63858.19 | 11494.47 | 75352.66 | Paid | High
EXP-03087 | PRJ-004 | PRJ-004-ACT-06 | 2025-03-22 | Material | MAT-009 | Paint | VEN-011 | 11.02 | Litre | 1913.45 | 2043.68 | 367.86 | 2411.54 | Paid | Low
EXP-03088 | PRJ-004 | PRJ-004-ACT-04 | 2025-03-22 | Equipment | EQ-003 | Concrete Mixer | VEN-009 | 5 | Day | 20424.43 | 20830.35 | 3749.46 | 24579.81 | Partially Paid | Medium
EXP-03089 | PRJ-004 | PRJ-004-ACT-07 | 2025-03-22 | Labour | LAB-006 | Painter | VEN-003 | 33 | Worker | 41761.26 | 45028.22 | 8105.08 | 53133.3 | Paid | Low
EXP-03090 | PRJ-004 | PRJ-004-ACT-10 | 2025-03-22 | Contractor | CON-004 | Finishing Contract | VEN-004 | 1 | Contract | 77289.73 | 75639.39 | 13615.09 | 89254.48 | Paid | Low
EXP-03091 | PRJ-004 | PRJ-004-ACT-03 | 2025-03-22 | Labour | LAB-006 | Painter | VEN-011 | 18 | Worker | 15564.29 | 16319.27 | 2937.47 | 19256.74 | Paid | High
EXP-03092 | PRJ-004 | PRJ-004-ACT-03 | 2025-03-22 | Labour | LAB-006 | Painter | VEN-003 | 8 | Worker | 11118.34 | 10948.55 | 1970.74 | 12919.29 | Paid | Medium
EXP-03093 | PRJ-004 | PRJ-004-ACT-06 | 2025-03-22 | Labour | LAB-005 | Plumber | VEN-003 | 21 | Worker | 34788.69 | 36089.48 | 6496.11 | 42585.59 | Paid | Low
EXP-03094 | PRJ-004 | PRJ-004-ACT-10 | 2025-03-27 | Material | MAT-004 | Aggregate | VEN-009 | 8.64 | Ton | 13907.29 | 13320.73 | 2397.73 | 15718.46 | Paid | Medium
EXP-03095 | PRJ-004 | PRJ-004-ACT-02 | 2025-03-27 | Contractor | CON-003 | Plumbing Contract | VEN-011 | 1 | Contract | 77151.32 | 79725.41 | 14350.57 | 94075.98 | Pending | Low
EXP-03096 | PRJ-004 | PRJ-004-ACT-10 | 2025-03-27 | Contractor | CON-004 | Finishing Contract | VEN-004 | 1 | Contract | 282353.88 | 294468.81 | 53004.39 | 347473.2 | Paid | Medium
EXP-03097 | PRJ-004 | PRJ-004-ACT-03 | 2025-03-27 | Contractor | CON-003 | Plumbing Contract | VEN-003 | 1 | Contract | 272408.23 | 259893.24 | 46780.78 | 306674.02 | Paid | Medium
EXP-03098 | PRJ-004 | PRJ-004-ACT-09 | 2025-03-27 | Contractor | CON-002 | Electrical Contract | VEN-003 | 1 | Contract | 83099.2 | 82525.16 | 14854.53 | 97379.69 | Paid | Medium
EXP-03099 | PRJ-004 | PRJ-004-ACT-03 | 2025-03-27 | Contractor | CON-001 | Civil Structure Contract | VEN-011 | 1 | Contract | 343874.36 | 347135.99 | 62484.48 | 409620.47 | Partially Paid | Medium
EXP-03100 | PRJ-004 | PRJ-004-ACT-04 | 2025-03-27 | Other | OTH-001 | Transport | VEN-009 | 1 | Lot | 42360.25 | 39429.74 | 7097.35 | 46527.09 | Partially Paid | Low
EXP-03101 | PRJ-004 | PRJ-004-ACT-07 | 2025-03-27 | Contractor | CON-003 | Plumbing Contract | VEN-011 | 1 | Contract | 415430.49 | 447777.05 | 80599.87 | 528376.92 | Paid | Medium
EXP-03102 | PRJ-004 | PRJ-004-ACT-10 | 2025-04-01 | Labour | LAB-002 | Helper | VEN-003 | 26 | Worker | 25988.4 | 27483.83 | 4947.09 | 32430.92 | Paid | Medium
EXP-03103 | PRJ-004 | PRJ-004-ACT-03 | 2025-04-01 | Labour | LAB-005 | Plumber | VEN-011 | 34 | Worker | 50125.5 | 47329.9 | 8519.38 | 55849.28 | Pending | Medium
EXP-03104 | PRJ-004 | PRJ-004-ACT-03 | 2025-04-01 | Other | OTH-001 | Safety | VEN-004 | 1 | Lot | 10600.11 | 10524.58 | 1894.42 | 12419 | Paid | Medium
EXP-03105 | PRJ-004 | PRJ-004-ACT-10 | 2025-04-01 | Equipment | EQ-001 | Crane | VEN-011 | 7 | Day | 130021.75 | 127845.72 | 23012.23 | 150857.95 | Paid | Medium
EXP-03106 | PRJ-004 | PRJ-004-ACT-03 | 2025-04-01 | Contractor | CON-002 | Electrical Contract | VEN-003 | 1 | Contract | 397212.55 | 397919.69 | 71625.54 | 469545.23 | Paid | Medium
EXP-03107 | PRJ-004 | PRJ-004-ACT-04 | 2025-04-01 | Equipment | EQ-003 | Concrete Mixer | VEN-004 | 2 | Day | 8324.07 | 8459.73 | 1522.75 | 9982.48 | Paid | Low
EXP-03108 | PRJ-004 | PRJ-004-ACT-06 | 2025-04-01 | Material | MAT-010 | Glass | VEN-003 | 11.39 | Sq Ft | 1888.47 | 1902.03 | 342.37 | 2244.4 | Paid | Low
EXP-03109 | PRJ-004 | PRJ-004-ACT-02 | 2025-04-06 | Labour | LAB-002 | Helper | VEN-011 | 11 | Worker | 10328.48 | 9666.44 | 1739.96 | 11406.4 | Paid | Medium
EXP-03110 | PRJ-004 | PRJ-004-ACT-10 | 2025-04-06 | Material | MAT-005 | Bricks | VEN-004 | 8.22 | Piece | 82.69 | 77.74 | 13.99 | 91.73 | Paid | Low
EXP-03111 | PRJ-004 | PRJ-004-ACT-07 | 2025-04-06 | Material | MAT-001 | Cement | VEN-011 | 7.09 | Bag | 4129.03 | 3944.92 | 710.09 | 4655.01 | Paid | Low
EXP-03112 | PRJ-004 | PRJ-004-ACT-02 | 2025-04-06 | Contractor | CON-004 | Finishing Contract | VEN-004 | 1 | Contract | 240768.22 | 255128.09 | 45923.06 | 301051.15 | Paid | Medium
EXP-03113 | PRJ-004 | PRJ-004-ACT-03 | 2025-04-06 | Labour | LAB-003 | Carpenter | VEN-003 | 32 | Worker | 23675.07 | 23359.85 | 4204.77 | 27564.62 | Paid | Low
EXP-03114 | PRJ-004 | PRJ-004-ACT-07 | 2025-04-06 | Material | MAT-002 | Steel | VEN-003 | 8.48 | Ton | 474391.66 | 455266.69 | 81948 | 537214.69 | Paid | Low
EXP-03115 | PRJ-004 | PRJ-004-ACT-04 | 2025-04-06 | Labour | LAB-006 | Painter | VEN-004 | 18 | Worker | 27894.47 | 30008.42 | 5401.52 | 35409.94 | Paid | Low
EXP-03116 | PRJ-004 | PRJ-004-ACT-05 | 2025-04-06 | Labour | LAB-005 | Plumber | VEN-009 | 34 | Worker | 26052.73 | 25807.29 | 4645.31 | 30452.6 | Paid | Low
EXP-03117 | PRJ-004 | PRJ-004-ACT-01 | 2025-04-11 | Material | MAT-001 | Cement | VEN-003 | 14.76 | Bag | 7023.49 | 7176.33 | 1291.74 | 8468.07 | Paid | Medium
EXP-03118 | PRJ-004 | PRJ-004-ACT-02 | 2025-04-11 | Contractor | CON-001 | Civil Structure Contract | VEN-003 | 1 | Contract | 364434.11 | 337948.24 | 60830.68 | 398778.92 | Pending | Low
EXP-03119 | PRJ-004 | PRJ-004-ACT-04 | 2025-04-11 | Contractor | CON-002 | Electrical Contract | VEN-003 | 1 | Contract | 104058.41 | 113062.81 | 20351.31 | 133414.12 | Paid | High
EXP-03120 | PRJ-004 | PRJ-004-ACT-10 | 2025-04-11 | Material | MAT-002 | Steel | VEN-011 | 6.64 | Ton | 369940.62 | 388862.79 | 69995.3 | 458858.09 | Paid | Medium
EXP-03121 | PRJ-004 | PRJ-004-ACT-05 | 2025-04-11 | Labour | LAB-002 | Helper | VEN-011 | 23 | Worker | 32392.36 | 31699.56 | 5705.92 | 37405.48 | Paid | Low
EXP-03122 | PRJ-004 | PRJ-004-ACT-04 | 2025-04-11 | Contractor | CON-004 | Finishing Contract | VEN-004 | 1 | Contract | 116210.29 | 110922.71 | 19966.09 | 130888.8 | Paid | Medium
EXP-03123 | PRJ-004 | PRJ-004-ACT-06 | 2025-04-11 | Material | MAT-008 | Tiles | VEN-009 | 6.85 | Sq Ft | 607.91 | 587.49 | 105.75 | 693.24 | Paid | Medium
EXP-03124 | PRJ-004 | PRJ-004-ACT-07 | 2025-04-16 | Contractor | CON-002 | Electrical Contract | VEN-011 | 1 | Contract | 384129.52 | 372486.85 | 67047.63 | 439534.48 | Paid | Medium
EXP-03125 | PRJ-004 | PRJ-004-ACT-05 | 2025-04-16 | Material | MAT-003 | Sand | VEN-004 | 6.68 | Ton | 12982.29 | 12311.73 | 2216.11 | 14527.84 | Paid | Low
EXP-03126 | PRJ-004 | PRJ-004-ACT-05 | 2025-04-16 | Equipment | EQ-004 | Scaffolding | VEN-011 | 2 | Day | 4859.08 | 5078.45 | 914.12 | 5992.57 | Paid | Medium
EXP-03127 | PRJ-004 | PRJ-004-ACT-03 | 2025-04-16 | Material | MAT-007 | PVC Pipe | VEN-003 | 2.59 | Meter | 258.77 | 266.75 | 48.02 | 314.77 | Paid | Low
EXP-03128 | PRJ-004 | PRJ-004-ACT-07 | 2025-04-16 | Material | MAT-009 | Paint | VEN-004 | 6.96 | Litre | 1592.31 | 1551.76 | 279.32 | 1831.08 | Paid | Low
EXP-03129 | PRJ-004 | PRJ-004-ACT-01 | 2025-04-16 | Material | MAT-006 | Electrical Cable | VEN-003 | 15.45 | Meter | 1534.75 | 1432.64 | 257.88 | 1690.52 | Pending | High
EXP-03130 | PRJ-004 | PRJ-004-ACT-01 | 2025-04-16 | Material | MAT-008 | Tiles | VEN-003 | 5.91 | Sq Ft | 436.98 | 416.56 | 74.98 | 491.54 | Paid | Medium
EXP-03131 | PRJ-004 | PRJ-004-ACT-01 | 2025-04-16 | Material | MAT-003 | Sand | VEN-003 | 8.11 | Ton | 16355.9 | 16762.97 | 3017.33 | 19780.3 | Paid | Low
EXP-03132 | PRJ-004 | PRJ-004-ACT-09 | 2025-04-16 | Labour | LAB-002 | Helper | VEN-011 | 30 | Worker | 22689.89 | 22939.31 | 4129.08 | 27068.39 | Paid | High
EXP-03133 | PRJ-004 | PRJ-004-ACT-01 | 2025-04-16 | Labour | LAB-003 | Carpenter | VEN-004 | 5 | Worker | 7606.38 | 7147.23 | 1286.5 | 8433.73 | Paid | Medium
EXP-03134 | PRJ-004 | PRJ-004-ACT-05 | 2025-04-21 | Equipment | EQ-002 | Excavator | VEN-003 | 5 | Day | 71298.39 | 68103.78 | 12258.68 | 80362.46 | Paid | Low
EXP-03135 | PRJ-004 | PRJ-004-ACT-04 | 2025-04-21 | Labour | LAB-004 | Electrician | VEN-004 | 12 | Worker | 13990.86 | 13483.53 | 2427.04 | 15910.57 | Paid | High
EXP-03136 | PRJ-004 | PRJ-004-ACT-10 | 2025-04-21 | Labour | LAB-006 | Painter | VEN-011 | 8 | Worker | 13908.33 | 13484.7 | 2427.25 | 15911.95 | Pending | Low
EXP-03137 | PRJ-004 | PRJ-004-ACT-02 | 2025-04-21 | Equipment | EQ-004 | Scaffolding | VEN-011 | 1 | Day | 2270.61 | 2355.17 | 423.93 | 2779.1 | Paid | Low
EXP-03138 | PRJ-004 | PRJ-004-ACT-07 | 2025-04-21 | Equipment | EQ-004 | Scaffolding | VEN-004 | 5 | Day | 11422.41 | 12329.8 | 2219.36 | 14549.16 | Paid | Medium
EXP-03139 | PRJ-004 | PRJ-004-ACT-02 | 2025-04-21 | Labour | LAB-002 | Helper | VEN-009 | 30 | Worker | 35035.69 | 32462.35 | 5843.22 | 38305.57 | Pending | Low
EXP-03140 | PRJ-004 | PRJ-004-ACT-10 | 2025-04-21 | Contractor | CON-002 | Electrical Contract | VEN-011 | 1 | Contract | 184765.06 | 171826.11 | 30928.7 | 202754.81 | Paid | Low
EXP-03141 | PRJ-004 | PRJ-004-ACT-09 | 2025-04-21 | Material | MAT-006 | Electrical Cable | VEN-004 | 6.91 | Meter | 578.92 | 538.5 | 96.93 | 635.43 | Paid | Medium
EXP-03142 | PRJ-004 | PRJ-004-ACT-07 | 2025-04-26 | Material | MAT-007 | PVC Pipe | VEN-009 | 11.69 | Meter | 1407.22 | 1438.05 | 258.85 | 1696.9 | Paid | Low
EXP-03143 | PRJ-004 | PRJ-004-ACT-01 | 2025-04-26 | Material | MAT-003 | Sand | VEN-011 | 11.18 | Ton | 21488.63 | 20025.62 | 3604.61 | 23630.23 | Partially Paid | High
EXP-03144 | PRJ-004 | PRJ-004-ACT-09 | 2025-04-26 | Contractor | CON-001 | Civil Structure Contract | VEN-009 | 1 | Contract | 451212.41 | 421093.4 | 75796.81 | 496890.21 | Paid | Low
EXP-03145 | PRJ-004 | PRJ-004-ACT-01 | 2025-04-26 | Material | MAT-004 | Aggregate | VEN-011 | 21.45 | Ton | 32656.8 | 31837.59 | 5730.77 | 37568.36 | Paid | Low
EXP-03146 | PRJ-004 | PRJ-004-ACT-01 | 2025-04-26 | Labour | LAB-003 | Carpenter | VEN-009 | 19 | Worker | 28425.08 | 29055.45 | 5229.98 | 34285.43 | Partially Paid | Low
EXP-03147 | PRJ-004 | PRJ-004-ACT-02 | 2025-04-26 | Equipment | EQ-002 | Excavator | VEN-004 | 5 | Day | 82562.07 | 76809.91 | 13825.78 | 90635.69 | Paid | Medium
EXP-03148 | PRJ-004 | PRJ-004-ACT-08 | 2025-04-26 | Material | MAT-008 | Tiles | VEN-004 | 8.23 | Sq Ft | 571.05 | 616.21 | 110.92 | 727.13 | Paid | Low
EXP-03149 | PRJ-004 | PRJ-004-ACT-10 | 2025-04-26 | Contractor | CON-002 | Electrical Contract | VEN-011 | 1 | Contract | 390340.79 | 402657.67 | 72478.38 | 475136.05 | Paid | Medium
EXP-03150 | PRJ-004 | PRJ-004-ACT-10 | 2025-05-01 | Other | OTH-001 | Miscellaneous | VEN-009 | 1 | Lot | 42231.07 | 44841.69 | 8071.5 | 52913.19 | Paid | Medium
EXP-03151 | PRJ-004 | PRJ-004-ACT-05 | 2025-05-01 | Equipment | EQ-004 | Scaffolding | VEN-009 | 2 | Day | 4601.79 | 4689.84 | 844.17 | 5534.01 | Pending | Low
EXP-03152 | PRJ-004 | PRJ-004-ACT-10 | 2025-05-01 | Material | MAT-009 | Paint | VEN-011 | 16.47 | Litre | 3016.72 | 3253.63 | 585.65 | 3839.28 | Paid | Medium
EXP-03153 | PRJ-004 | PRJ-004-ACT-08 | 2025-05-01 | Material | MAT-005 | Bricks | VEN-011 | 4.24 | Piece | 39.45 | 41.48 | 7.47 | 48.95 | Paid | Low
EXP-03154 | PRJ-004 | PRJ-004-ACT-05 | 2025-05-01 | Contractor | CON-003 | Plumbing Contract | VEN-011 | 1 | Contract | 288352.67 | 288716.04 | 51968.89 | 340684.93 | Paid | Medium
EXP-03155 | PRJ-004 | PRJ-004-ACT-10 | 2025-05-01 | Contractor | CON-001 | Civil Structure Contract | VEN-003 | 1 | Contract | 125776.98 | 134030.88 | 24125.56 | 158156.44 | Paid | Low
EXP-03156 | PRJ-004 | PRJ-004-ACT-02 | 2025-05-01 | Material | MAT-009 | Paint | VEN-003 | 14.9 | Litre | 3355.32 | 3174.14 | 571.35 | 3745.49 | Paid | High
EXP-03157 | PRJ-004 | PRJ-004-ACT-01 | 2025-05-01 | Material | MAT-009 | Paint | VEN-004 | 6.16 | Litre | 1437.1 | 1456.09 | 262.1 | 1718.19 | Partially Paid | Medium
EXP-03158 | PRJ-004 | PRJ-004-ACT-06 | 2025-05-01 | Equipment | EQ-003 | Concrete Mixer | VEN-004 | 5 | Day | 20968.63 | 21665.35 | 3899.76 | 25565.11 | Paid | Low
EXP-03159 | PRJ-004 | PRJ-004-ACT-10 | 2025-05-01 | Material | MAT-009 | Paint | VEN-003 | 14.79 | Litre | 3140.22 | 2976.38 | 535.75 | 3512.13 | Paid | Low
EXP-03160 | PRJ-004 | PRJ-004-ACT-10 | 2025-05-06 | Other | OTH-001 | Safety | VEN-011 | 1 | Lot | 17380.92 | 18340.3 | 3301.25 | 21641.55 | Paid | Medium
EXP-03161 | PRJ-004 | PRJ-004-ACT-08 | 2025-05-06 | Material | MAT-007 | PVC Pipe | VEN-003 | 2.8 | Meter | 355.79 | 354.49 | 63.81 | 418.3 | Paid | Medium
EXP-03162 | PRJ-004 | PRJ-004-ACT-09 | 2025-05-06 | Material | MAT-005 | Bricks | VEN-004 | 38.32 | Piece | 350.46 | 331.18 | 59.61 | 390.79 | Paid | Low
EXP-03163 | PRJ-004 | PRJ-004-ACT-10 | 2025-05-06 | Labour | LAB-002 | Helper | VEN-009 | 16 | Worker | 20486.22 | 19070.54 | 3432.7 | 22503.24 | Paid | High
EXP-03164 | PRJ-004 | PRJ-004-ACT-08 | 2025-05-06 | Labour | LAB-003 | Carpenter | VEN-011 | 18 | Worker | 16249.14 | 17082.48 | 3074.85 | 20157.33 | Paid | Low
EXP-03165 | PRJ-004 | PRJ-004-ACT-05 | 2025-05-06 | Contractor | CON-004 | Finishing Contract | VEN-004 | 1 | Contract | 302673.51 | 324662.28 | 58439.21 | 383101.49 | Pending | Medium
EXP-03166 | PRJ-004 | PRJ-004-ACT-02 | 2025-05-06 | Contractor | CON-001 | Civil Structure Contract | VEN-003 | 1 | Contract | 333089.96 | 325386.66 | 58569.6 | 383956.26 | Partially Paid | Low
EXP-03167 | PRJ-004 | PRJ-004-ACT-06 | 2025-05-06 | Contractor | CON-002 | Electrical Contract | VEN-009 | 1 | Contract | 360982.68 | 362873.23 | 65317.18 | 428190.41 | Paid | Medium
EXP-03168 | PRJ-004 | PRJ-004-ACT-07 | 2025-05-11 | Equipment | EQ-001 | Crane | VEN-003 | 7 | Day | 120777.63 | 126913.44 | 22844.42 | 149757.86 | Paid | High
EXP-03169 | PRJ-004 | PRJ-004-ACT-01 | 2025-05-11 | Contractor | CON-002 | Electrical Contract | VEN-011 | 1 | Contract | 256675.96 | 278520.89 | 50133.76 | 328654.65 | Paid | Low
EXP-03170 | PRJ-004 | PRJ-004-ACT-06 | 2025-05-11 | Labour | LAB-005 | Plumber | VEN-009 | 18 | Worker | 12921.08 | 12552.37 | 2259.43 | 14811.8 | Partially Paid | High
EXP-03171 | PRJ-004 | PRJ-004-ACT-10 | 2025-05-11 | Material | MAT-002 | Steel | VEN-003 | 9.03 | Ton | 582415.85 | 561101.95 | 100998.35 | 662100.3 | Pending | Low
EXP-03172 | PRJ-004 | PRJ-004-ACT-05 | 2025-05-11 | Labour | LAB-004 | Electrician | VEN-009 | 20 | Worker | 16183.62 | 16763.32 | 3017.4 | 19780.72 | Paid | Low
EXP-03173 | PRJ-004 | PRJ-004-ACT-01 | 2025-05-11 | Other | OTH-001 | Miscellaneous | VEN-011 | 1 | Lot | 63624.5 | 62212.16 | 11198.19 | 73410.35 | Pending | Medium
EXP-03174 | PRJ-004 | PRJ-004-ACT-02 | 2025-05-11 | Material | MAT-004 | Aggregate | VEN-009 | 8.01 | Ton | 11582.76 | 10935.74 | 1968.43 | 12904.17 | Paid | Low
EXP-03175 | PRJ-004 | PRJ-004-ACT-07 | 2025-05-11 | Labour | LAB-005 | Plumber | VEN-011 | 16 | Worker | 17992.8 | 17894.75 | 3221.05 | 21115.8 | Pending | Low
EXP-03176 | PRJ-004 | PRJ-004-ACT-08 | 2025-05-16 | Equipment | EQ-002 | Excavator | VEN-003 | 2 | Day | 26517.96 | 28087.58 | 5055.76 | 33143.34 | Paid | Medium
EXP-03177 | PRJ-004 | PRJ-004-ACT-02 | 2025-05-16 | Equipment | EQ-001 | Crane | VEN-011 | 6 | Day | 120866.93 | 115856 | 20854.08 | 136710.08 | Paid | Medium
EXP-03178 | PRJ-004 | PRJ-004-ACT-04 | 2025-05-16 | Material | MAT-001 | Cement | VEN-009 | 7.28 | Bag | 3580.92 | 3746.74 | 674.41 | 4421.15 | Partially Paid | Low
EXP-03179 | PRJ-004 | PRJ-004-ACT-05 | 2025-05-16 | Contractor | CON-002 | Electrical Contract | VEN-011 | 1 | Contract | 188620.06 | 177269.85 | 31908.57 | 209178.42 | Paid | Low
EXP-03180 | PRJ-004 | PRJ-004-ACT-10 | 2025-05-16 | Labour | LAB-002 | Helper | VEN-009 | 14 | Worker | 21724.89 | 20913.41 | 3764.41 | 24677.82 | Paid | Low
EXP-03181 | PRJ-004 | PRJ-004-ACT-01 | 2025-05-16 | Material | MAT-001 | Cement | VEN-004 | 9.98 | Bag | 4819.22 | 4845.11 | 872.12 | 5717.23 | Paid | Medium
EXP-03182 | PRJ-004 | PRJ-004-ACT-03 | 2025-05-16 | Labour | LAB-005 | Plumber | VEN-011 | 9 | Worker | 11807.12 | 11491.25 | 2068.42 | 13559.67 | Paid | Medium
EXP-03183 | PRJ-004 | PRJ-004-ACT-02 | 2025-05-16 | Contractor | CON-001 | Civil Structure Contract | VEN-004 | 1 | Contract | 192557.07 | 194701.48 | 35046.27 | 229747.75 | Paid | High
EXP-03184 | PRJ-004 | PRJ-004-ACT-03 | 2025-05-16 | Labour | LAB-006 | Painter | VEN-003 | 33 | Worker | 56855.71 | 54479.93 | 9806.39 | 64286.32 | Paid | Low
EXP-03185 | PRJ-004 | PRJ-004-ACT-08 | 2025-05-16 | Equipment | EQ-003 | Concrete Mixer | VEN-003 | 2 | Day | 9360.59 | 9706.95 | 1747.25 | 11454.2 | Paid | Medium
EXP-03186 | PRJ-004 | PRJ-004-ACT-08 | 2025-05-21 | Material | MAT-005 | Bricks | VEN-004 | 5.41 | Piece | 48.86 | 46.75 | 8.41 | 55.16 | Paid | High
EXP-03187 | PRJ-004 | PRJ-004-ACT-04 | 2025-05-21 | Material | MAT-010 | Glass | VEN-003 | 10.97 | Sq Ft | 1784.05 | 1697.38 | 305.53 | 2002.91 | Paid | Medium
EXP-03188 | PRJ-004 | PRJ-004-ACT-07 | 2025-05-21 | Material | MAT-006 | Electrical Cable | VEN-004 | 5.69 | Meter | 431.05 | 461.75 | 83.11 | 544.86 | Partially Paid | Medium
EXP-03189 | PRJ-004 | PRJ-004-ACT-04 | 2025-05-21 | Contractor | CON-003 | Plumbing Contract | VEN-004 | 1 | Contract | 174378.51 | 187657.57 | 33778.36 | 221435.93 | Paid | High
EXP-03190 | PRJ-004 | PRJ-004-ACT-05 | 2025-05-21 | Material | MAT-006 | Electrical Cable | VEN-009 | 5.92 | Meter | 425.4 | 450.12 | 81.02 | 531.14 | Paid | Medium
EXP-03191 | PRJ-004 | PRJ-004-ACT-10 | 2025-05-21 | Material | MAT-009 | Paint | VEN-003 | 3.81 | Litre | 851.15 | 822.22 | 148 | 970.22 | Paid | Low
EXP-03192 | PRJ-004 | PRJ-004-ACT-06 | 2025-05-26 | Material | MAT-010 | Glass | VEN-011 | 25.21 | Sq Ft | 3843.69 | 4163.6 | 749.45 | 4913.05 | Paid | Low
EXP-03193 | PRJ-004 | PRJ-004-ACT-07 | 2025-05-26 | Labour | LAB-001 | Mason | VEN-003 | 28 | Worker | 26326.92 | 26378.4 | 4748.11 | 31126.51 | Paid | Medium
EXP-03194 | PRJ-004 | PRJ-004-ACT-05 | 2025-05-26 | Material | MAT-008 | Tiles | VEN-003 | 4.34 | Sq Ft | 344.07 | 344.4 | 61.99 | 406.39 | Paid | Medium
EXP-03195 | PRJ-004 | PRJ-004-ACT-07 | 2025-05-26 | Contractor | CON-004 | Finishing Contract | VEN-009 | 1 | Contract | 182921 | 189550.29 | 34119.05 | 223669.34 | Partially Paid | Medium
EXP-03196 | PRJ-004 | PRJ-004-ACT-08 | 2025-05-26 | Labour | LAB-001 | Mason | VEN-009 | 7 | Worker | 5538.6 | 5366.34 | 965.94 | 6332.28 | Paid | Medium
EXP-03197 | PRJ-004 | PRJ-004-ACT-09 | 2025-05-26 | Contractor | CON-002 | Electrical Contract | VEN-009 | 1 | Contract | 396486.37 | 382709.9 | 68887.78 | 451597.68 | Partially Paid | Low
EXP-03198 | PRJ-004 | PRJ-004-ACT-04 | 2025-05-26 | Material | MAT-010 | Glass | VEN-003 | 3.5 | Sq Ft | 608.03 | 640.55 | 115.3 | 755.85 | Partially Paid | Low
EXP-03199 | PRJ-004 | PRJ-004-ACT-04 | 2025-05-26 | Material | MAT-001 | Cement | VEN-009 | 10.49 | Bag | 5400.59 | 5259.61 | 946.73 | 6206.34 | Pending | Medium
EXP-03200 | PRJ-004 | PRJ-004-ACT-01 | 2025-05-31 | Contractor | CON-003 | Plumbing Contract | VEN-011 | 1 | Contract | 399885.68 | 407168.38 | 73290.31 | 480458.69 | Paid | Low
EXP-03201 | PRJ-004 | PRJ-004-ACT-10 | 2025-05-31 | Material | MAT-009 | Paint | VEN-011 | 9.75 | Litre | 2046.13 | 2049 | 368.82 | 2417.82 | Paid | Low
EXP-03202 | PRJ-004 | PRJ-004-ACT-02 | 2025-05-31 | Equipment | EQ-004 | Scaffolding | VEN-004 | 1 | Day | 2760.29 | 2663.25 | 479.38 | 3142.63 | Paid | Medium
EXP-03203 | PRJ-004 | PRJ-004-ACT-03 | 2025-05-31 | Contractor | CON-004 | Finishing Contract | VEN-003 | 1 | Contract | 261006.47 | 258035.68 | 46446.42 | 304482.1 | Paid | Low
EXP-03204 | PRJ-004 | PRJ-004-ACT-05 | 2025-05-31 | Material | MAT-008 | Tiles | VEN-009 | 5.29 | Sq Ft | 442.95 | 413.09 | 74.36 | 487.45 | Paid | Low
EXP-03205 | PRJ-004 | PRJ-004-ACT-04 | 2025-05-31 | Labour | LAB-003 | Carpenter | VEN-011 | 26 | Worker | 17617.78 | 18440.31 | 3319.26 | 21759.57 | Paid | Low
EXP-03206 | PRJ-004 | PRJ-004-ACT-10 | 2025-05-31 | Material | MAT-007 | PVC Pipe | VEN-003 | 19.74 | Meter | 2266.09 | 2405.3 | 432.95 | 2838.25 | Partially Paid | Medium
EXP-03207 | PRJ-004 | PRJ-004-ACT-08 | 2025-05-31 | Labour | LAB-002 | Helper | VEN-004 | 5 | Worker | 4522.57 | 4411.26 | 794.03 | 5205.29 | Paid | Low
EXP-03208 | PRJ-004 | PRJ-004-ACT-04 | 2025-06-05 | Labour | LAB-005 | Plumber | VEN-003 | 33 | Worker | 31531.68 | 32389.52 | 5830.11 | 38219.63 | Paid | Low
EXP-03209 | PRJ-004 | PRJ-004-ACT-05 | 2025-06-05 | Contractor | CON-003 | Plumbing Contract | VEN-009 | 1 | Contract | 154283.71 | 155506.01 | 27991.08 | 183497.09 | Paid | Medium
EXP-03210 | PRJ-004 | PRJ-004-ACT-06 | 2025-06-05 | Other | OTH-001 | Transport | VEN-009 | 1 | Lot | 9834.78 | 10407.43 | 1873.34 | 12280.77 | Paid | Low
EXP-03211 | PRJ-004 | PRJ-004-ACT-04 | 2025-06-05 | Material | MAT-010 | Glass | VEN-011 | 3.69 | Sq Ft | 613.26 | 635.69 | 114.42 | 750.11 | Partially Paid | Low
EXP-03212 | PRJ-004 | PRJ-004-ACT-02 | 2025-06-05 | Other | OTH-001 | Site Office | VEN-009 | 1 | Lot | 28400.27 | 28342.85 | 5101.71 | 33444.56 | Paid | Low
EXP-03213 | PRJ-004 | PRJ-004-ACT-10 | 2025-06-05 | Labour | LAB-004 | Electrician | VEN-011 | 33 | Worker | 41275.61 | 42791.1 | 7702.4 | 50493.5 | Paid | High
EXP-03214 | PRJ-004 | PRJ-004-ACT-10 | 2025-06-05 | Contractor | CON-004 | Finishing Contract | VEN-004 | 1 | Contract | 215257.01 | 203743.8 | 36673.88 | 240417.68 | Partially Paid | Low
EXP-03215 | PRJ-004 | PRJ-004-ACT-07 | 2025-06-05 | Labour | LAB-003 | Carpenter | VEN-011 | 19 | Worker | 28219.06 | 26278.58 | 4730.14 | 31008.72 | Pending | Medium
EXP-03216 | PRJ-004 | PRJ-004-ACT-10 | 2025-06-10 | Contractor | CON-002 | Electrical Contract | VEN-009 | 1 | Contract | 396533.22 | 397417.37 | 71535.13 | 468952.5 | Paid | Low
EXP-03217 | PRJ-004 | PRJ-004-ACT-07 | 2025-06-10 | Labour | LAB-005 | Plumber | VEN-011 | 13 | Worker | 11481.47 | 11562.35 | 2081.22 | 13643.57 | Paid | Low
EXP-03218 | PRJ-004 | PRJ-004-ACT-09 | 2025-06-10 | Contractor | CON-004 | Finishing Contract | VEN-003 | 1 | Contract | 146129.37 | 137321.59 | 24717.89 | 162039.48 | Paid | Low
EXP-03219 | PRJ-004 | PRJ-004-ACT-06 | 2025-06-10 | Labour | LAB-002 | Helper | VEN-003 | 10 | Worker | 15692.17 | 17028 | 3065.04 | 20093.04 | Paid | Low
EXP-03220 | PRJ-004 | PRJ-004-ACT-09 | 2025-06-10 | Material | MAT-009 | Paint | VEN-003 | 9.3 | Litre | 1823.01 | 1880.95 | 338.57 | 2219.52 | Partially Paid | High
EXP-03221 | PRJ-004 | PRJ-004-ACT-03 | 2025-06-10 | Contractor | CON-004 | Finishing Contract | VEN-003 | 1 | Contract | 340586.99 | 365048.72 | 65708.77 | 430757.49 | Partially Paid | Low
EXP-03222 | PRJ-004 | PRJ-004-ACT-07 | 2025-06-10 | Equipment | EQ-002 | Excavator | VEN-009 | 4 | Day | 51617.9 | 50799.86 | 9143.97 | 59943.83 | Paid | Low
EXP-03223 | PRJ-004 | PRJ-004-ACT-05 | 2025-06-10 | Contractor | CON-002 | Electrical Contract | VEN-011 | 1 | Contract | 379508.54 | 404056.52 | 72730.17 | 476786.69 | Paid | Medium
EXP-03224 | PRJ-004 | PRJ-004-ACT-09 | 2025-06-10 | Contractor | CON-001 | Civil Structure Contract | VEN-009 | 1 | Contract | 168713.57 | 157382.86 | 28328.91 | 185711.77 | Paid | Low
EXP-03225 | PRJ-004 | PRJ-004-ACT-08 | 2025-06-10 | Labour | LAB-006 | Painter | VEN-011 | 14 | Worker | 24526.98 | 24376.64 | 4387.8 | 28764.44 | Partially Paid | Medium
EXP-03226 | PRJ-004 | PRJ-004-ACT-08 | 2025-06-15 | Material | MAT-007 | PVC Pipe | VEN-003 | 2.09 | Meter | 217.35 | 233.25 | 41.98 | 275.23 | Pending | High
EXP-03227 | PRJ-004 | PRJ-004-ACT-06 | 2025-06-15 | Contractor | CON-001 | Civil Structure Contract | VEN-009 | 1 | Contract | 124167.19 | 134166 | 24149.88 | 158315.88 | Partially Paid | Medium
EXP-03228 | PRJ-004 | PRJ-004-ACT-06 | 2025-06-15 | Labour | LAB-002 | Helper | VEN-003 | 17 | Worker | 30521.53 | 28303.91 | 5094.7 | 33398.61 | Paid | Low
EXP-03229 | PRJ-004 | PRJ-004-ACT-07 | 2025-06-15 | Equipment | EQ-004 | Scaffolding | VEN-004 | 4 | Day | 10780.51 | 9982.46 | 1796.84 | 11779.3 | Paid | High
EXP-03230 | PRJ-004 | PRJ-004-ACT-04 | 2025-06-15 | Material | MAT-009 | Paint | VEN-003 | 17.01 | Litre | 3904.37 | 4082.53 | 734.86 | 4817.39 | Paid | Medium
EXP-03231 | PRJ-004 | PRJ-004-ACT-09 | 2025-06-15 | Material | MAT-003 | Sand | VEN-011 | 10.08 | Ton | 19394.1 | 18387.79 | 3309.8 | 21697.59 | Paid | Medium
EXP-03232 | PRJ-004 | PRJ-004-ACT-01 | 2025-06-15 | Material | MAT-001 | Cement | VEN-003 | 8.93 | Bag | 4538.74 | 4415.21 | 794.74 | 5209.95 | Paid | Low
EXP-03233 | PRJ-004 | PRJ-004-ACT-07 | 2025-06-15 | Material | MAT-006 | Electrical Cable | VEN-011 | 7.26 | Meter | 504.16 | 537.93 | 96.83 | 634.76 | Paid | Medium
EXP-03234 | PRJ-004 | PRJ-004-ACT-02 | 2025-06-15 | Material | MAT-006 | Electrical Cable | VEN-004 | 8.15 | Meter | 768.55 | 757.17 | 136.29 | 893.46 | Pending | Low
EXP-03235 | PRJ-004 | PRJ-004-ACT-09 | 2025-06-15 | Contractor | CON-002 | Electrical Contract | VEN-011 | 1 | Contract | 190056.47 | 197338.58 | 35520.94 | 232859.52 | Paid | Medium
EXP-03236 | PRJ-004 | PRJ-004-ACT-02 | 2025-06-20 | Contractor | CON-002 | Electrical Contract | VEN-009 | 1 | Contract | 186930.18 | 180160.33 | 32428.86 | 212589.19 | Paid | Medium
EXP-03237 | PRJ-004 | PRJ-004-ACT-10 | 2025-06-20 | Contractor | CON-001 | Civil Structure Contract | VEN-011 | 1 | Contract | 214085.41 | 228915.71 | 41204.83 | 270120.54 | Paid | Low
EXP-03238 | PRJ-004 | PRJ-004-ACT-04 | 2025-06-20 | Labour | LAB-006 | Painter | VEN-011 | 21 | Worker | 29089.86 | 27427.23 | 4936.9 | 32364.13 | Paid | Medium
EXP-03239 | PRJ-004 | PRJ-004-ACT-04 | 2025-06-20 | Material | MAT-009 | Paint | VEN-011 | 11.44 | Litre | 2431.6 | 2620.55 | 471.7 | 3092.25 | Paid | Low
EXP-03240 | PRJ-004 | PRJ-004-ACT-07 | 2025-06-20 | Material | MAT-004 | Aggregate | VEN-003 | 3.58 | Ton | 4884.99 | 4790.62 | 862.31 | 5652.93 | Paid | Low
EXP-03241 | PRJ-004 | PRJ-004-ACT-02 | 2025-06-20 | Material | MAT-005 | Bricks | VEN-011 | 10.91 | Piece | 112.13 | 109.66 | 19.74 | 129.4 | Paid | Low
EXP-03242 | PRJ-004 | PRJ-004-ACT-05 | 2025-06-20 | Contractor | CON-002 | Electrical Contract | VEN-004 | 1 | Contract | 197520.11 | 198415.98 | 35714.88 | 234130.86 | Paid | Low
EXP-03243 | PRJ-004 | PRJ-004-ACT-06 | 2025-06-20 | Material | MAT-010 | Glass | VEN-004 | 6.33 | Sq Ft | 974.59 | 932.91 | 167.92 | 1100.83 | Paid | Low
EXP-03244 | PRJ-004 | PRJ-004-ACT-10 | 2025-06-25 | Contractor | CON-004 | Finishing Contract | VEN-011 | 1 | Contract | 339926.61 | 358818.31 | 64587.3 | 423405.61 | Paid | Medium
EXP-03245 | PRJ-004 | PRJ-004-ACT-03 | 2025-06-25 | Material | MAT-007 | PVC Pipe | VEN-003 | 8.41 | Meter | 898.97 | 947.05 | 170.47 | 1117.52 | Paid | Low
EXP-03246 | PRJ-004 | PRJ-004-ACT-10 | 2025-06-25 | Material | MAT-003 | Sand | VEN-004 | 10.04 | Ton | 15393.15 | 16370.28 | 2946.65 | 19316.93 | Paid | Low
EXP-03247 | PRJ-004 | PRJ-004-ACT-09 | 2025-06-25 | Labour | LAB-003 | Carpenter | VEN-009 | 26 | Worker | 29927.89 | 30053.32 | 5409.6 | 35462.92 | Paid | Medium
EXP-03248 | PRJ-004 | PRJ-004-ACT-10 | 2025-06-25 | Material | MAT-008 | Tiles | VEN-003 | 16.24 | Sq Ft | 1102.69 | 1189.92 | 214.19 | 1404.11 | Paid | Low
EXP-03249 | PRJ-004 | PRJ-004-ACT-01 | 2025-06-25 | Contractor | CON-003 | Plumbing Contract | VEN-009 | 1 | Contract | 348312.12 | 342432.74 | 61637.89 | 404070.63 | Pending | Low
EXP-03250 | PRJ-004 | PRJ-004-ACT-03 | 2025-06-25 | Contractor | CON-004 | Finishing Contract | VEN-009 | 1 | Contract | 166493.4 | 172302.99 | 31014.54 | 203317.53 | Paid | Low
EXP-03251 | PRJ-004 | PRJ-004-ACT-06 | 2025-06-30 | Material | MAT-009 | Paint | VEN-003 | 7.73 | Litre | 1500.25 | 1465.22 | 263.74 | 1728.96 | Paid | Low
EXP-03252 | PRJ-004 | PRJ-004-ACT-08 | 2025-06-30 | Equipment | EQ-001 | Crane | VEN-003 | 7 | Day | 124152.11 | 126589.72 | 22786.15 | 149375.87 | Paid | Medium
EXP-03253 | PRJ-004 | PRJ-004-ACT-02 | 2025-06-30 | Contractor | CON-004 | Finishing Contract | VEN-004 | 1 | Contract | 400840.56 | 395804.38 | 71244.79 | 467049.17 | Paid | Low
EXP-03254 | PRJ-004 | PRJ-004-ACT-01 | 2025-06-30 | Labour | LAB-002 | Helper | VEN-011 | 28 | Worker | 46554.69 | 43960.6 | 7912.91 | 51873.51 | Paid | Low
EXP-03255 | PRJ-004 | PRJ-004-ACT-05 | 2025-06-30 | Material | MAT-006 | Electrical Cable | VEN-003 | 5.28 | Meter | 421.12 | 417.01 | 75.06 | 492.07 | Paid | Medium
EXP-03256 | PRJ-004 | PRJ-004-ACT-04 | 2025-06-30 | Labour | LAB-002 | Helper | VEN-009 | 23 | Worker | 19573.32 | 20122.48 | 3622.05 | 23744.53 | Paid | High
EXP-03257 | PRJ-004 | PRJ-004-ACT-04 | 2025-06-30 | Material | MAT-010 | Glass | VEN-009 | 13.95 | Sq Ft | 2501.5 | 2496.14 | 449.31 | 2945.45 | Paid | Low
EXP-03258 | PRJ-004 | PRJ-004-ACT-10 | 2025-06-30 | Equipment | EQ-002 | Excavator | VEN-011 | 1 | Day | 13009.16 | 14057.88 | 2530.42 | 16588.3 | Paid | Low
EXP-03259 | PRJ-004 | PRJ-004-ACT-09 | 2025-07-05 | Material | MAT-003 | Sand | VEN-004 | 8.35 | Ton | 15775.25 | 15171.65 | 2730.9 | 17902.55 | Paid | High
EXP-03260 | PRJ-004 | PRJ-004-ACT-03 | 2025-07-05 | Contractor | CON-003 | Plumbing Contract | VEN-011 | 1 | Contract | 314784.22 | 325939.16 | 58669.05 | 384608.21 | Paid | Medium
EXP-03261 | PRJ-004 | PRJ-004-ACT-08 | 2025-07-05 | Labour | LAB-005 | Plumber | VEN-004 | 22 | Worker | 41305.51 | 39068.33 | 7032.3 | 46100.63 | Paid | Low
EXP-03262 | PRJ-004 | PRJ-004-ACT-01 | 2025-07-05 | Labour | LAB-006 | Painter | VEN-003 | 32 | Worker | 59319.25 | 55618.58 | 10011.34 | 65629.92 | Paid | Medium
EXP-03263 | PRJ-004 | PRJ-004-ACT-08 | 2025-07-05 | Material | MAT-002 | Steel | VEN-011 | 3.05 | Ton | 206676.29 | 215899.63 | 38861.93 | 254761.56 | Partially Paid | Medium
EXP-03264 | PRJ-004 | PRJ-004-ACT-04 | 2025-07-05 | Material | MAT-010 | Glass | VEN-011 | 3.14 | Sq Ft | 492.44 | 488.13 | 87.86 | 575.99 | Paid | Low
EXP-03265 | PRJ-004 | PRJ-004-ACT-06 | 2025-07-05 | Contractor | CON-003 | Plumbing Contract | VEN-011 | 1 | Contract | 369410.71 | 342403.84 | 61632.69 | 404036.53 | Partially Paid | Low
EXP-03266 | PRJ-004 | PRJ-004-ACT-01 | 2025-07-10 | Labour | LAB-004 | Electrician | VEN-003 | 13 | Worker | 9966.3 | 9866.89 | 1776.04 | 11642.93 | Paid | Medium
EXP-03267 | PRJ-004 | PRJ-004-ACT-05 | 2025-07-10 | Material | MAT-002 | Steel | VEN-004 | 5.19 | Ton | 328086.55 | 351160.94 | 63208.97 | 414369.91 | Partially Paid | Low
EXP-03268 | PRJ-004 | PRJ-004-ACT-04 | 2025-07-10 | Material | MAT-002 | Steel | VEN-004 | 2.36 | Ton | 147701.19 | 154784.72 | 27861.25 | 182645.97 | Pending | Low
EXP-03269 | PRJ-004 | PRJ-004-ACT-07 | 2025-07-10 | Labour | LAB-001 | Mason | VEN-009 | 14 | Worker | 15407.98 | 16381.43 | 2948.66 | 19330.09 | Partially Paid | Low
EXP-03270 | PRJ-004 | PRJ-004-ACT-04 | 2025-07-10 | Material | MAT-009 | Paint | VEN-003 | 3.11 | Litre | 567.07 | 583.46 | 105.02 | 688.48 | Paid | Low
EXP-03271 | PRJ-004 | PRJ-004-ACT-01 | 2025-07-10 | Material | MAT-005 | Bricks | VEN-011 | 11.73 | Piece | 103.42 | 99.52 | 17.91 | 117.43 | Paid | Low
EXP-03272 | PRJ-004 | PRJ-004-ACT-07 | 2025-07-10 | Contractor | CON-004 | Finishing Contract | VEN-004 | 1 | Contract | 312604.92 | 302822.57 | 54508.06 | 357330.63 | Paid | Low
EXP-03273 | PRJ-004 | PRJ-004-ACT-07 | 2025-07-15 | Labour | LAB-002 | Helper | VEN-004 | 33 | Worker | 34753.23 | 35985.26 | 6477.35 | 42462.61 | Paid | Low
EXP-03274 | PRJ-004 | PRJ-004-ACT-07 | 2025-07-15 | Material | MAT-009 | Paint | VEN-004 | 3.56 | Litre | 756.91 | 771.34 | 138.84 | 910.18 | Paid | Medium
EXP-03275 | PRJ-004 | PRJ-004-ACT-01 | 2025-07-15 | Equipment | EQ-001 | Crane | VEN-009 | 3 | Day | 55386.79 | 54210.3 | 9757.85 | 63968.15 | Paid | Medium
EXP-03276 | PRJ-004 | PRJ-004-ACT-10 | 2025-07-15 | Labour | LAB-004 | Electrician | VEN-003 | 12 | Worker | 18731.78 | 19866.56 | 3575.98 | 23442.54 | Partially Paid | Low
EXP-03277 | PRJ-004 | PRJ-004-ACT-08 | 2025-07-15 | Material | MAT-010 | Glass | VEN-004 | 13.75 | Sq Ft | 2152.8 | 2204.33 | 396.78 | 2601.11 | Paid | Low
EXP-03278 | PRJ-004 | PRJ-004-ACT-04 | 2025-07-15 | Equipment | EQ-001 | Crane | VEN-009 | 3 | Day | 60122.74 | 57377.95 | 10328.03 | 67705.98 | Pending | Low
EXP-03279 | PRJ-004 | PRJ-004-ACT-09 | 2025-07-20 | Equipment | EQ-002 | Excavator | VEN-003 | 4 | Day | 62683.79 | 61294.15 | 11032.95 | 72327.1 | Paid | Medium
EXP-03280 | PRJ-004 | PRJ-004-ACT-02 | 2025-07-20 | Material | MAT-004 | Aggregate | VEN-009 | 2.7 | Ton | 4491.56 | 4632.82 | 833.91 | 5466.73 | Paid | Medium
EXP-03281 | PRJ-004 | PRJ-004-ACT-05 | 2025-07-20 | Material | MAT-001 | Cement | VEN-003 | 31.15 | Bag | 14299.32 | 15301.17 | 2754.21 | 18055.38 | Paid | High
EXP-03282 | PRJ-004 | PRJ-004-ACT-08 | 2025-07-20 | Contractor | CON-003 | Plumbing Contract | VEN-009 | 1 | Contract | 301080.63 | 324067.81 | 58332.21 | 382400.02 | Paid | Low
EXP-03283 | PRJ-004 | PRJ-004-ACT-01 | 2025-07-20 | Equipment | EQ-003 | Concrete Mixer | VEN-003 | 3 | Day | 13365.66 | 12468.49 | 2244.33 | 14712.82 | Partially Paid | Low
EXP-03284 | PRJ-004 | PRJ-004-ACT-02 | 2025-07-20 | Material | MAT-009 | Paint | VEN-009 | 15.41 | Litre | 2909.85 | 3000.97 | 540.17 | 3541.14 | Paid | Low
EXP-03285 | PRJ-004 | PRJ-004-ACT-05 | 2025-07-25 | Labour | LAB-004 | Electrician | VEN-004 | 15 | Worker | 13748.27 | 13144.84 | 2366.07 | 15510.91 | Paid | Low
EXP-03286 | PRJ-004 | PRJ-004-ACT-04 | 2025-07-25 | Labour | LAB-001 | Mason | VEN-003 | 4 | Worker | 5912.93 | 6007.2 | 1081.3 | 7088.5 | Paid | Medium
EXP-03287 | PRJ-004 | PRJ-004-ACT-08 | 2025-07-25 | Material | MAT-004 | Aggregate | VEN-004 | 16.29 | Ton | 23491.99 | 24231.7 | 4361.71 | 28593.41 | Paid | Low
EXP-03288 | PRJ-004 | PRJ-004-ACT-08 | 2025-07-25 | Material | MAT-005 | Bricks | VEN-011 | 4.96 | Piece | 43.39 | 46.95 | 8.45 | 55.4 | Paid | Medium
EXP-03289 | PRJ-004 | PRJ-004-ACT-02 | 2025-07-25 | Material | MAT-003 | Sand | VEN-011 | 6.29 | Ton | 11489.78 | 12289.82 | 2212.17 | 14501.99 | Partially Paid | Medium
EXP-03290 | PRJ-004 | PRJ-004-ACT-01 | 2025-07-25 | Contractor | CON-002 | Electrical Contract | VEN-004 | 1 | Contract | 323426.9 | 333478.05 | 60026.05 | 393504.1 | Paid | Low
EXP-03291 | PRJ-004 | PRJ-004-ACT-07 | 2025-07-25 | Labour | LAB-002 | Helper | VEN-004 | 16 | Worker | 22108.78 | 23327.68 | 4198.98 | 27526.66 | Paid | Low
EXP-03292 | PRJ-004 | PRJ-004-ACT-05 | 2025-07-25 | Labour | LAB-002 | Helper | VEN-011 | 10 | Worker | 12666.15 | 12102.71 | 2178.49 | 14281.2 | Partially Paid | Low
EXP-03293 | PRJ-004 | PRJ-004-ACT-05 | 2025-07-25 | Material | MAT-009 | Paint | VEN-003 | 2.63 | Litre | 478.56 | 495.41 | 89.17 | 584.58 | Paid | Low
EXP-03294 | PRJ-004 | PRJ-004-ACT-10 | 2025-07-25 | Equipment | EQ-002 | Excavator | VEN-003 | 7 | Day | 85281.91 | 91263.18 | 16427.37 | 107690.55 | Paid | High
EXP-03295 | PRJ-004 | PRJ-004-ACT-07 | 2025-07-30 | Material | MAT-003 | Sand | VEN-009 | 6.87 | Ton | 10945.56 | 10571.8 | 1902.92 | 12474.72 | Paid | Medium
EXP-03296 | PRJ-004 | PRJ-004-ACT-08 | 2025-07-30 | Labour | LAB-002 | Helper | VEN-009 | 22 | Worker | 36024.83 | 37632.96 | 6773.93 | 44406.89 | Pending | Medium
EXP-03297 | PRJ-004 | PRJ-004-ACT-10 | 2025-07-30 | Labour | LAB-003 | Carpenter | VEN-009 | 16 | Worker | 18357.23 | 17267.34 | 3108.12 | 20375.46 | Paid | Low
EXP-03298 | PRJ-004 | PRJ-004-ACT-09 | 2025-07-30 | Material | MAT-004 | Aggregate | VEN-009 | 5.99 | Ton | 7778.67 | 8126.16 | 1462.71 | 9588.87 | Paid | Low
EXP-03299 | PRJ-004 | PRJ-004-ACT-05 | 2025-07-30 | Labour | LAB-003 | Carpenter | VEN-009 | 7 | Worker | 7899.57 | 7355.33 | 1323.96 | 8679.29 | Paid | Low
EXP-03300 | PRJ-004 | PRJ-004-ACT-05 | 2025-07-30 | Labour | LAB-003 | Carpenter | VEN-011 | 4 | Worker | 6068.59 | 5862.01 | 1055.16 | 6917.17 | Paid | Low
EXP-03301 | PRJ-004 | PRJ-004-ACT-09 | 2025-07-30 | Contractor | CON-004 | Finishing Contract | VEN-011 | 1 | Contract | 146922.13 | 158839.73 | 28591.15 | 187430.88 | Paid | Low
EXP-03302 | PRJ-004 | PRJ-004-ACT-10 | 2025-07-30 | Material | MAT-010 | Glass | VEN-009 | 9.29 | Sq Ft | 1579.65 | 1471.92 | 264.95 | 1736.87 | Partially Paid | Low
EXP-03303 | PRJ-004 | PRJ-004-ACT-06 | 2025-08-04 | Labour | LAB-005 | Plumber | VEN-009 | 16 | Worker | 15543.94 | 16636.26 | 2994.53 | 19630.79 | Partially Paid | Low
EXP-03304 | PRJ-004 | PRJ-004-ACT-05 | 2025-08-04 | Material | MAT-008 | Tiles | VEN-003 | 14.1 | Sq Ft | 1090.62 | 1178.3 | 212.09 | 1390.39 | Partially Paid | Low
EXP-03305 | PRJ-004 | PRJ-004-ACT-09 | 2025-08-04 | Equipment | EQ-001 | Crane | VEN-003 | 7 | Day | 135408.92 | 128003.06 | 23040.55 | 151043.61 | Paid | Low
EXP-03306 | PRJ-004 | PRJ-004-ACT-07 | 2025-08-04 | Labour | LAB-001 | Mason | VEN-009 | 26 | Worker | 46305.27 | 43748.63 | 7874.75 | 51623.38 | Paid | Medium
EXP-03307 | PRJ-004 | PRJ-004-ACT-07 | 2025-08-04 | Labour | LAB-005 | Plumber | VEN-004 | 8 | Worker | 13247.45 | 12630.34 | 2273.46 | 14903.8 | Paid | Low
EXP-03308 | PRJ-004 | PRJ-004-ACT-08 | 2025-08-04 | Equipment | EQ-001 | Crane | VEN-004 | 4 | Day | 74665.52 | 79126.48 | 14242.77 | 93369.25 | Paid | Medium
EXP-03309 | PRJ-004 | PRJ-004-ACT-07 | 2025-08-04 | Equipment | EQ-001 | Crane | VEN-003 | 2 | Day | 36289.41 | 34358.35 | 6184.5 | 40542.85 | Paid | Medium
EXP-03310 | PRJ-004 | PRJ-004-ACT-03 | 2025-08-09 | Labour | LAB-004 | Electrician | VEN-004 | 32 | Worker | 21753.81 | 21651.41 | 3897.25 | 25548.66 | Paid | Medium
EXP-03311 | PRJ-004 | PRJ-004-ACT-03 | 2025-08-09 | Material | MAT-006 | Electrical Cable | VEN-004 | 3.59 | Meter | 370.72 | 348.73 | 62.77 | 411.5 | Paid | Low
EXP-03312 | PRJ-004 | PRJ-004-ACT-10 | 2025-08-09 | Labour | LAB-006 | Painter | VEN-011 | 20 | Worker | 23441.92 | 22009.73 | 3961.75 | 25971.48 | Partially Paid | Low
EXP-03313 | PRJ-004 | PRJ-004-ACT-02 | 2025-08-09 | Material | MAT-005 | Bricks | VEN-011 | 29.58 | Piece | 253.3 | 274.22 | 49.36 | 323.58 | Pending | Low
EXP-03314 | PRJ-004 | PRJ-004-ACT-01 | 2025-08-09 | Material | MAT-008 | Tiles | VEN-003 | 9.62 | Sq Ft | 765.84 | 779.14 | 140.25 | 919.39 | Paid | Low
EXP-03315 | PRJ-004 | PRJ-004-ACT-10 | 2025-08-09 | Material | MAT-003 | Sand | VEN-011 | 8 | Ton | 15651.75 | 15847.79 | 2852.6 | 18700.39 | Paid | High
EXP-03316 | PRJ-004 | PRJ-004-ACT-06 | 2025-08-09 | Contractor | CON-004 | Finishing Contract | VEN-011 | 1 | Contract | 276753.58 | 257113.09 | 46280.36 | 303393.45 | Partially Paid | Medium
EXP-03317 | PRJ-004 | PRJ-004-ACT-04 | 2025-08-14 | Material | MAT-002 | Steel | VEN-004 | 5.51 | Ton | 417841.85 | 386896.85 | 69641.43 | 456538.28 | Partially Paid | Medium
EXP-03318 | PRJ-004 | PRJ-004-ACT-04 | 2025-08-14 | Labour | LAB-005 | Plumber | VEN-011 | 9 | Worker | 10069.44 | 9957.55 | 1792.36 | 11749.91 | Paid | Low
EXP-03319 | PRJ-004 | PRJ-004-ACT-07 | 2025-08-14 | Material | MAT-004 | Aggregate | VEN-003 | 31.67 | Ton | 43171.05 | 40571.61 | 7302.89 | 47874.5 | Paid | Medium
EXP-03320 | PRJ-004 | PRJ-004-ACT-05 | 2025-08-14 | Material | MAT-005 | Bricks | VEN-009 | 10.61 | Piece | 94.88 | 98.16 | 17.67 | 115.83 | Paid | Low
EXP-03321 | PRJ-004 | PRJ-004-ACT-07 | 2025-08-14 | Material | MAT-005 | Bricks | VEN-003 | 9.02 | Piece | 75.78 | 74.18 | 13.35 | 87.53 | Paid | Low
EXP-03322 | PRJ-004 | PRJ-004-ACT-05 | 2025-08-14 | Labour | LAB-003 | Carpenter | VEN-011 | 32 | Worker | 43857.11 | 40618.15 | 7311.27 | 47929.42 | Paid | Low
EXP-03323 | PRJ-004 | PRJ-004-ACT-08 | 2025-08-14 | Contractor | CON-004 | Finishing Contract | VEN-009 | 1 | Contract | 405640.4 | 389470.41 | 70104.67 | 459575.08 | Paid | Medium
EXP-03324 | PRJ-004 | PRJ-004-ACT-10 | 2025-08-19 | Material | MAT-004 | Aggregate | VEN-011 | 28.42 | Ton | 38626.13 | 41041.05 | 7387.39 | 48428.44 | Paid | Medium
EXP-03325 | PRJ-004 | PRJ-004-ACT-02 | 2025-08-19 | Labour | LAB-003 | Carpenter | VEN-011 | 22 | Worker | 32902.77 | 31104.75 | 5598.85 | 36703.6 | Pending | Medium
EXP-03326 | PRJ-004 | PRJ-004-ACT-06 | 2025-08-19 | Material | MAT-003 | Sand | VEN-003 | 11.47 | Ton | 21495.04 | 23144.59 | 4166.03 | 27310.62 | Paid | Medium
EXP-03327 | PRJ-004 | PRJ-004-ACT-10 | 2025-08-19 | Labour | LAB-005 | Plumber | VEN-009 | 18 | Worker | 17580 | 18277.93 | 3290.03 | 21567.96 | Paid | Low
EXP-03328 | PRJ-004 | PRJ-004-ACT-04 | 2025-08-19 | Contractor | CON-003 | Plumbing Contract | VEN-009 | 1 | Contract | 400899.82 | 406351.4 | 73143.25 | 479494.65 | Paid | Low
EXP-03329 | PRJ-004 | PRJ-004-ACT-04 | 2025-08-19 | Contractor | CON-001 | Civil Structure Contract | VEN-004 | 1 | Contract | 232357.24 | 216790.61 | 39022.31 | 255812.92 | Paid | Medium
EXP-03330 | PRJ-004 | PRJ-004-ACT-01 | 2025-08-19 | Material | MAT-001 | Cement | VEN-011 | 13.41 | Bag | 6780.7 | 7349.07 | 1322.83 | 8671.9 | Partially Paid | Medium
EXP-03331 | PRJ-004 | PRJ-004-ACT-07 | 2025-08-19 | Material | MAT-002 | Steel | VEN-009 | 4.77 | Ton | 294484.62 | 273131.82 | 49163.73 | 322295.55 | Paid | Medium
EXP-03332 | PRJ-004 | PRJ-004-ACT-08 | 2025-08-19 | Material | MAT-004 | Aggregate | VEN-011 | 19.54 | Ton | 29907.51 | 29991.28 | 5398.43 | 35389.71 | Paid | Low
EXP-03333 | PRJ-004 | PRJ-004-ACT-03 | 2025-08-19 | Labour | LAB-002 | Helper | VEN-004 | 16 | Worker | 12397.5 | 11892.28 | 2140.61 | 14032.89 | Paid | Medium
EXP-03334 | PRJ-004 | PRJ-004-ACT-07 | 2025-08-24 | Material | MAT-002 | Steel | VEN-004 | 27.79 | Ton | 1563315.23 | 1580153.16 | 284427.57 | 1864580.73 | Pending | Low
EXP-03335 | PRJ-004 | PRJ-004-ACT-05 | 2025-08-24 | Contractor | CON-001 | Civil Structure Contract | VEN-011 | 1 | Contract | 136736.41 | 133996.15 | 24119.31 | 158115.46 | Paid | Low
EXP-03336 | PRJ-004 | PRJ-004-ACT-02 | 2025-08-24 | Material | MAT-007 | PVC Pipe | VEN-003 | 4.45 | Meter | 617.99 | 575.23 | 103.54 | 678.77 | Partially Paid | Low
EXP-03337 | PRJ-004 | PRJ-004-ACT-03 | 2025-08-24 | Material | MAT-009 | Paint | VEN-004 | 13.27 | Litre | 2778.35 | 2891.54 | 520.48 | 3412.02 | Paid | Low
EXP-03338 | PRJ-004 | PRJ-004-ACT-01 | 2025-08-24 | Labour | LAB-004 | Electrician | VEN-004 | 20 | Worker | 22340.31 | 21876.36 | 3937.74 | 25814.1 | Paid | Low
EXP-03339 | PRJ-004 | PRJ-004-ACT-04 | 2025-08-24 | Material | MAT-001 | Cement | VEN-003 | 14.12 | Bag | 7275.62 | 7192.05 | 1294.57 | 8486.62 | Paid | Low
EXP-03340 | PRJ-004 | PRJ-004-ACT-01 | 2025-08-24 | Material | MAT-005 | Bricks | VEN-011 | 42.89 | Piece | 432.23 | 403.21 | 72.58 | 475.79 | Partially Paid | Medium
EXP-03341 | PRJ-004 | PRJ-004-ACT-04 | 2025-08-24 | Other | OTH-001 | Site Office | VEN-004 | 1 | Lot | 29166.91 | 28879.54 | 5198.32 | 34077.86 | Paid | Low
EXP-03342 | PRJ-004 | PRJ-004-ACT-06 | 2025-08-29 | Other | OTH-001 | Miscellaneous | VEN-009 | 1 | Lot | 33466.65 | 34530.83 | 6215.55 | 40746.38 | Partially Paid | Medium
EXP-03343 | PRJ-004 | PRJ-004-ACT-05 | 2025-08-29 | Material | MAT-006 | Electrical Cable | VEN-011 | 6.04 | Meter | 594.21 | 573.78 | 103.28 | 677.06 | Paid | Low
EXP-03344 | PRJ-004 | PRJ-004-ACT-07 | 2025-08-29 | Contractor | CON-002 | Electrical Contract | VEN-003 | 1 | Contract | 269097.54 | 266725.81 | 48010.65 | 314736.46 | Paid | Low
EXP-03345 | PRJ-004 | PRJ-004-ACT-09 | 2025-08-29 | Equipment | EQ-001 | Crane | VEN-003 | 3 | Day | 51536.87 | 54905.66 | 9883.02 | 64788.68 | Paid | Low
EXP-03346 | PRJ-004 | PRJ-004-ACT-07 | 2025-08-29 | Equipment | EQ-004 | Scaffolding | VEN-009 | 2 | Day | 5268.64 | 5112.8 | 920.3 | 6033.1 | Paid | Low
EXP-03347 | PRJ-004 | PRJ-004-ACT-07 | 2025-08-29 | Other | OTH-001 | Safety | VEN-003 | 1 | Lot | 70426.74 | 71776.92 | 12919.85 | 84696.77 | Paid | Medium
EXP-03348 | PRJ-004 | PRJ-004-ACT-03 | 2025-08-29 | Contractor | CON-001 | Civil Structure Contract | VEN-004 | 1 | Contract | 186917.24 | 182596.85 | 32867.43 | 215464.28 | Paid | Medium
EXP-03349 | PRJ-004 | PRJ-004-ACT-05 | 2025-08-29 | Material | MAT-001 | Cement | VEN-003 | 16.15 | Bag | 9221.24 | 9078.33 | 1634.1 | 10712.43 | Paid | Low
EXP-03350 | PRJ-004 | PRJ-004-ACT-01 | 2025-09-03 | Material | MAT-007 | PVC Pipe | VEN-003 | 10.12 | Meter | 1077.76 | 1093.38 | 196.81 | 1290.19 | Paid | Low
EXP-03351 | PRJ-004 | PRJ-004-ACT-01 | 2025-09-03 | Equipment | EQ-003 | Concrete Mixer | VEN-009 | 2 | Day | 10065.15 | 9408.46 | 1693.52 | 11101.98 | Paid | Low
EXP-03352 | PRJ-004 | PRJ-004-ACT-08 | 2025-09-03 | Material | MAT-009 | Paint | VEN-004 | 3.43 | Litre | 766.84 | 752.51 | 135.45 | 887.96 | Paid | Low
EXP-03353 | PRJ-004 | PRJ-004-ACT-07 | 2025-09-03 | Contractor | CON-004 | Finishing Contract | VEN-009 | 1 | Contract | 376562.18 | 404570.57 | 72822.7 | 477393.27 | Paid | Low
EXP-03354 | PRJ-004 | PRJ-004-ACT-02 | 2025-09-03 | Contractor | CON-003 | Plumbing Contract | VEN-011 | 1 | Contract | 408002.83 | 422119.2 | 75981.46 | 498100.66 | Paid | Low
EXP-03355 | PRJ-004 | PRJ-004-ACT-10 | 2025-09-03 | Material | MAT-008 | Tiles | VEN-004 | 8.93 | Sq Ft | 724.16 | 685.79 | 123.44 | 809.23 | Pending | Medium
EXP-03356 | PRJ-004 | PRJ-004-ACT-06 | 2025-09-08 | Material | MAT-007 | PVC Pipe | VEN-009 | 23.23 | Meter | 2776.09 | 2987.98 | 537.84 | 3525.82 | Paid | Low
EXP-03357 | PRJ-004 | PRJ-004-ACT-10 | 2025-09-08 | Labour | LAB-003 | Carpenter | VEN-003 | 34 | Worker | 51849.5 | 50078.38 | 9014.11 | 59092.49 | Paid | Low
EXP-03358 | PRJ-004 | PRJ-004-ACT-05 | 2025-09-08 | Material | MAT-001 | Cement | VEN-011 | 31.74 | Bag | 18932.5 | 18485.12 | 3327.32 | 21812.44 | Paid | Medium
EXP-03359 | PRJ-004 | PRJ-004-ACT-10 | 2025-09-08 | Contractor | CON-003 | Plumbing Contract | VEN-004 | 1 | Contract | 319564.62 | 303895.19 | 54701.13 | 358596.32 | Paid | Medium
EXP-03360 | PRJ-004 | PRJ-004-ACT-03 | 2025-09-08 | Contractor | CON-001 | Civil Structure Contract | VEN-004 | 1 | Contract | 194103.28 | 197760.12 | 35596.82 | 233356.94 | Paid | Medium
EXP-03361 | PRJ-004 | PRJ-004-ACT-10 | 2025-09-08 | Material | MAT-010 | Glass | VEN-004 | 23.19 | Sq Ft | 3385.75 | 3345.11 | 602.12 | 3947.23 | Paid | Medium
EXP-03362 | PRJ-004 | PRJ-004-ACT-03 | 2025-09-08 | Material | MAT-001 | Cement | VEN-003 | 14.64 | Bag | 8108.54 | 7778.44 | 1400.12 | 9178.56 | Paid | Medium
EXP-03363 | PRJ-004 | PRJ-004-ACT-04 | 2025-09-13 | Other | OTH-001 | Site Office | VEN-003 | 1 | Lot | 66573.04 | 71429.54 | 12857.32 | 84286.86 | Partially Paid | Low
EXP-03364 | PRJ-004 | PRJ-004-ACT-08 | 2025-09-13 | Labour | LAB-003 | Carpenter | VEN-009 | 21 | Worker | 16114.09 | 16347.7 | 2942.59 | 19290.29 | Partially Paid | Medium
EXP-03365 | PRJ-004 | PRJ-004-ACT-02 | 2025-09-13 | Material | MAT-009 | Paint | VEN-011 | 8.72 | Litre | 1962.49 | 1902.85 | 342.51 | 2245.36 | Paid | Low
EXP-03366 | PRJ-004 | PRJ-004-ACT-07 | 2025-09-13 | Equipment | EQ-002 | Excavator | VEN-004 | 4 | Day | 54544.72 | 56549.33 | 10178.88 | 66728.21 | Paid | Low
EXP-03367 | PRJ-004 | PRJ-004-ACT-07 | 2025-09-13 | Material | MAT-007 | PVC Pipe | VEN-011 | 16.06 | Meter | 2070.24 | 2022.97 | 364.13 | 2387.1 | Paid | Low
EXP-03368 | PRJ-004 | PRJ-004-ACT-01 | 2025-09-13 | Other | OTH-001 | Miscellaneous | VEN-009 | 1 | Lot | 17770.61 | 16893.57 | 3040.84 | 19934.41 | Paid | Low
EXP-03369 | PRJ-004 | PRJ-004-ACT-02 | 2025-09-13 | Equipment | EQ-004 | Scaffolding | VEN-004 | 5 | Day | 12168.38 | 12696.49 | 2285.37 | 14981.86 | Paid | Medium
EXP-03370 | PRJ-004 | PRJ-004-ACT-09 | 2025-09-13 | Material | MAT-008 | Tiles | VEN-003 | 2.98 | Sq Ft | 207 | 210.69 | 37.92 | 248.61 | Paid | Medium
EXP-03371 | PRJ-004 | PRJ-004-ACT-04 | 2025-09-18 | Material | MAT-009 | Paint | VEN-009 | 6.15 | Litre | 1059.7 | 1144.81 | 206.07 | 1350.88 | Paid | High
EXP-03372 | PRJ-004 | PRJ-004-ACT-02 | 2025-09-18 | Material | MAT-003 | Sand | VEN-003 | 16.52 | Ton | 27900.6 | 28344.45 | 5102 | 33446.45 | Paid | Medium
EXP-03373 | PRJ-004 | PRJ-004-ACT-07 | 2025-09-18 | Contractor | CON-004 | Finishing Contract | VEN-004 | 1 | Contract | 237614.44 | 244693.41 | 44044.81 | 288738.22 | Paid | Medium
EXP-03374 | PRJ-004 | PRJ-004-ACT-05 | 2025-09-18 | Labour | LAB-002 | Helper | VEN-003 | 28 | Worker | 48844.1 | 49950.39 | 8991.07 | 58941.46 | Paid | Low
EXP-03375 | PRJ-004 | PRJ-004-ACT-02 | 2025-09-18 | Material | MAT-010 | Glass | VEN-003 | 9.12 | Sq Ft | 1544.74 | 1613.02 | 290.34 | 1903.36 | Paid | Medium
EXP-03376 | PRJ-004 | PRJ-004-ACT-08 | 2025-09-18 | Material | MAT-005 | Bricks | VEN-011 | 4.55 | Piece | 43.59 | 42.38 | 7.63 | 50.01 | Paid | Medium
EXP-03377 | PRJ-004 | PRJ-004-ACT-07 | 2025-09-18 | Equipment | EQ-002 | Excavator | VEN-011 | 3 | Day | 40962.02 | 43611.01 | 7849.98 | 51460.99 | Paid | Medium
EXP-03378 | PRJ-004 | PRJ-004-ACT-08 | 2025-09-18 | Labour | LAB-002 | Helper | VEN-004 | 27 | Worker | 34546.42 | 33177.78 | 5972 | 39149.78 | Paid | Low
EXP-03379 | PRJ-004 | PRJ-004-ACT-07 | 2025-09-18 | Contractor | CON-001 | Civil Structure Contract | VEN-009 | 1 | Contract | 118811.73 | 116223.98 | 20920.32 | 137144.3 | Paid | Low
EXP-03380 | PRJ-004 | PRJ-004-ACT-10 | 2025-09-18 | Equipment | EQ-004 | Scaffolding | VEN-009 | 2 | Day | 4729.48 | 4639.98 | 835.2 | 5475.18 | Paid | Low
EXP-03381 | PRJ-004 | PRJ-004-ACT-03 | 2025-09-23 | Equipment | EQ-001 | Crane | VEN-009 | 4 | Day | 70732.09 | 68153.68 | 12267.66 | 80421.34 | Paid | Low
EXP-03382 | PRJ-004 | PRJ-004-ACT-10 | 2025-09-23 | Material | MAT-006 | Electrical Cable | VEN-004 | 9.08 | Meter | 840.5 | 850.96 | 153.17 | 1004.13 | Paid | Medium
EXP-03383 | PRJ-004 | PRJ-004-ACT-01 | 2025-09-23 | Material | MAT-003 | Sand | VEN-011 | 8.44 | Ton | 14991.28 | 14892.8 | 2680.7 | 17573.5 | Partially Paid | Medium
EXP-03384 | PRJ-004 | PRJ-004-ACT-07 | 2025-09-23 | Equipment | EQ-001 | Crane | VEN-004 | 1 | Day | 16898.08 | 18282.06 | 3290.77 | 21572.83 | Pending | Low
EXP-03385 | PRJ-004 | PRJ-004-ACT-02 | 2025-09-23 | Material | MAT-006 | Electrical Cable | VEN-009 | 1 | Meter | 91.38 | 92.48 | 16.65 | 109.13 | Paid | Low
EXP-03386 | PRJ-004 | PRJ-004-ACT-08 | 2025-09-23 | Material | MAT-008 | Tiles | VEN-003 | 7.76 | Sq Ft | 603.42 | 560.92 | 100.97 | 661.89 | Paid | Low
EXP-03387 | PRJ-004 | PRJ-004-ACT-03 | 2025-09-23 | Material | MAT-001 | Cement | VEN-011 | 24.43 | Bag | 12559.58 | 11744.19 | 2113.95 | 13858.14 | Paid | Medium
EXP-03388 | PRJ-004 | PRJ-004-ACT-08 | 2025-09-23 | Material | MAT-009 | Paint | VEN-003 | 22.62 | Litre | 5819.06 | 5403.38 | 972.61 | 6375.99 | Paid | Low
EXP-03389 | PRJ-004 | PRJ-004-ACT-09 | 2025-09-23 | Material | MAT-007 | PVC Pipe | VEN-003 | 4.29 | Meter | 545 | 581.81 | 104.73 | 686.54 | Paid | Medium
EXP-03390 | PRJ-004 | PRJ-004-ACT-05 | 2025-09-23 | Material | MAT-004 | Aggregate | VEN-003 | 42.95 | Ton | 57076.99 | 56905.38 | 10242.97 | 67148.35 | Paid | Low
EXP-03391 | PRJ-004 | PRJ-004-ACT-04 | 2025-09-28 | Material | MAT-008 | Tiles | VEN-004 | 9.67 | Sq Ft | 665.25 | 688.34 | 123.9 | 812.24 | Paid | Low
EXP-03392 | PRJ-004 | PRJ-004-ACT-04 | 2025-09-28 | Material | MAT-010 | Glass | VEN-011 | 4.91 | Sq Ft | 874.86 | 819.48 | 147.51 | 966.99 | Paid | Medium
EXP-03393 | PRJ-004 | PRJ-004-ACT-05 | 2025-09-28 | Other | OTH-001 | Transport | VEN-004 | 1 | Lot | 19295.71 | 19977.51 | 3595.95 | 23573.46 | Paid | Low
EXP-03394 | PRJ-004 | PRJ-004-ACT-02 | 2025-09-28 | Material | MAT-009 | Paint | VEN-011 | 15.77 | Litre | 3961.84 | 3754.41 | 675.79 | 4430.2 | Paid | Low
EXP-03395 | PRJ-004 | PRJ-004-ACT-07 | 2025-09-28 | Contractor | CON-001 | Civil Structure Contract | VEN-003 | 1 | Contract | 129117.61 | 122897.27 | 22121.51 | 145018.78 | Pending | Low
EXP-03396 | PRJ-004 | PRJ-004-ACT-01 | 2025-09-28 | Equipment | EQ-001 | Crane | VEN-011 | 1 | Day | 17872.45 | 17395.19 | 3131.13 | 20526.32 | Paid | Medium
EXP-03397 | PRJ-004 | PRJ-004-ACT-04 | 2025-10-03 | Equipment | EQ-002 | Excavator | VEN-004 | 7 | Day | 105013.24 | 102621.91 | 18471.94 | 121093.85 | Pending | High
EXP-03398 | PRJ-004 | PRJ-004-ACT-01 | 2025-10-03 | Material | MAT-006 | Electrical Cable | VEN-003 | 6.91 | Meter | 527.92 | 520.86 | 93.75 | 614.61 | Partially Paid | High
EXP-03399 | PRJ-004 | PRJ-004-ACT-07 | 2025-10-03 | Material | MAT-008 | Tiles | VEN-009 | 9.57 | Sq Ft | 623.59 | 673.92 | 121.31 | 795.23 | Pending | Low
EXP-03400 | PRJ-004 | PRJ-004-ACT-02 | 2025-10-03 | Labour | LAB-004 | Electrician | VEN-003 | 29 | Worker | 30674.35 | 29925.74 | 5386.63 | 35312.37 | Paid | Medium
EXP-03401 | PRJ-004 | PRJ-004-ACT-02 | 2025-10-03 | Contractor | CON-002 | Electrical Contract | VEN-004 | 1 | Contract | 269108.62 | 281290.02 | 50632.2 | 331922.22 | Paid | Medium
EXP-03402 | PRJ-004 | PRJ-004-ACT-10 | 2025-10-03 | Equipment | EQ-004 | Scaffolding | VEN-011 | 3 | Day | 6307.44 | 6785.01 | 1221.3 | 8006.31 | Paid | Low
EXP-03403 | PRJ-004 | PRJ-004-ACT-07 | 2025-10-03 | Contractor | CON-001 | Civil Structure Contract | VEN-011 | 1 | Contract | 422802.81 | 415857.41 | 74854.33 | 490711.74 | Partially Paid | Low
EXP-03404 | PRJ-004 | PRJ-004-ACT-10 | 2025-10-03 | Labour | LAB-003 | Carpenter | VEN-004 | 11 | Worker | 17772.99 | 18170.96 | 3270.77 | 21441.73 | Paid | Low
EXP-03405 | PRJ-004 | PRJ-004-ACT-08 | 2025-10-03 | Labour | LAB-003 | Carpenter | VEN-009 | 25 | Worker | 40043.94 | 42956.97 | 7732.25 | 50689.22 | Paid | Low
EXP-03406 | PRJ-004 | PRJ-004-ACT-10 | 2025-10-08 | Labour | LAB-004 | Electrician | VEN-004 | 8 | Worker | 12199.56 | 12149.1 | 2186.84 | 14335.94 | Paid | Medium
EXP-03407 | PRJ-004 | PRJ-004-ACT-04 | 2025-10-08 | Equipment | EQ-004 | Scaffolding | VEN-004 | 7 | Day | 17135.83 | 16122.04 | 2901.97 | 19024.01 | Paid | Medium
EXP-03408 | PRJ-004 | PRJ-004-ACT-02 | 2025-10-08 | Equipment | EQ-003 | Concrete Mixer | VEN-011 | 4 | Day | 17740.94 | 17970.87 | 3234.76 | 21205.63 | Partially Paid | Low
EXP-03409 | PRJ-004 | PRJ-004-ACT-01 | 2025-10-08 | Contractor | CON-002 | Electrical Contract | VEN-011 | 1 | Contract | 356587.73 | 366473.21 | 65965.18 | 432438.39 | Paid | Medium
EXP-03410 | PRJ-004 | PRJ-004-ACT-04 | 2025-10-08 | Labour | LAB-004 | Electrician | VEN-011 | 7 | Worker | 4824.52 | 5155.1 | 927.92 | 6083.02 | Paid | Low
EXP-03411 | PRJ-004 | PRJ-004-ACT-09 | 2025-10-08 | Contractor | CON-004 | Finishing Contract | VEN-011 | 1 | Contract | 318194.07 | 342690.86 | 61684.35 | 404375.21 | Paid | Medium
EXP-03412 | PRJ-004 | PRJ-004-ACT-04 | 2025-10-08 | Contractor | CON-004 | Finishing Contract | VEN-004 | 1 | Contract | 323442.07 | 336477.83 | 60566.01 | 397043.84 | Paid | Low
EXP-03413 | PRJ-004 | PRJ-004-ACT-05 | 2025-10-13 | Material | MAT-003 | Sand | VEN-011 | 11.82 | Ton | 23899.88 | 22321.48 | 4017.87 | 26339.35 | Pending | Medium
EXP-03414 | PRJ-004 | PRJ-004-ACT-01 | 2025-10-13 | Material | MAT-009 | Paint | VEN-003 | 4.31 | Litre | 919.84 | 904.88 | 162.88 | 1067.76 | Pending | Medium
EXP-03415 | PRJ-004 | PRJ-004-ACT-01 | 2025-10-13 | Material | MAT-002 | Steel | VEN-003 | 9.79 | Ton | 554442.8 | 534613.36 | 96230.4 | 630843.76 | Paid | Medium
EXP-03416 | PRJ-004 | PRJ-004-ACT-08 | 2025-10-13 | Contractor | CON-004 | Finishing Contract | VEN-009 | 1 | Contract | 374890.97 | 353037.64 | 63546.78 | 416584.42 | Paid | High
EXP-03417 | PRJ-004 | PRJ-004-ACT-04 | 2025-10-13 | Material | MAT-001 | Cement | VEN-011 | 14.06 | Bag | 7440.71 | 7163.78 | 1289.48 | 8453.26 | Pending | Low
EXP-03418 | PRJ-004 | PRJ-004-ACT-02 | 2025-10-13 | Material | MAT-009 | Paint | VEN-011 | 7.41 | Litre | 1655.62 | 1687.77 | 303.8 | 1991.57 | Paid | Medium
EXP-03419 | PRJ-004 | PRJ-004-ACT-04 | 2025-10-13 | Material | MAT-006 | Electrical Cable | VEN-011 | 9.76 | Meter | 901.69 | 916.43 | 164.96 | 1081.39 | Pending | Low
EXP-03420 | PRJ-004 | PRJ-004-ACT-07 | 2025-10-18 | Contractor | CON-003 | Plumbing Contract | VEN-011 | 1 | Contract | 139130.62 | 138800.17 | 24984.03 | 163784.2 | Paid | Medium
EXP-03421 | PRJ-004 | PRJ-004-ACT-06 | 2025-10-18 | Material | MAT-006 | Electrical Cable | VEN-009 | 8.47 | Meter | 626.74 | 666.57 | 119.98 | 786.55 | Paid | Low
EXP-03422 | PRJ-004 | PRJ-004-ACT-10 | 2025-10-18 | Material | MAT-007 | PVC Pipe | VEN-003 | 5.53 | Meter | 787.18 | 739.16 | 133.05 | 872.21 | Paid | Low
EXP-03423 | PRJ-004 | PRJ-004-ACT-03 | 2025-10-18 | Contractor | CON-004 | Finishing Contract | VEN-009 | 1 | Contract | 161365.11 | 155030.41 | 27905.47 | 182935.88 | Paid | Low
EXP-03424 | PRJ-004 | PRJ-004-ACT-03 | 2025-10-18 | Labour | LAB-001 | Mason | VEN-004 | 12 | Worker | 16168.4 | 16434.76 | 2958.26 | 19393.02 | Paid | Medium
EXP-03425 | PRJ-004 | PRJ-004-ACT-04 | 2025-10-18 | Material | MAT-008 | Tiles | VEN-003 | 11.99 | Sq Ft | 916.88 | 921.9 | 165.94 | 1087.84 | Paid | Medium
EXP-03426 | PRJ-004 | PRJ-004-ACT-04 | 2025-10-23 | Equipment | EQ-004 | Scaffolding | VEN-003 | 6 | Day | 13902.16 | 13570.13 | 2442.62 | 16012.75 | Pending | Low
EXP-03427 | PRJ-004 | PRJ-004-ACT-08 | 2025-10-23 | Labour | LAB-001 | Mason | VEN-011 | 28 | Worker | 35416.38 | 36426.07 | 6556.69 | 42982.76 | Paid | Medium
EXP-03428 | PRJ-004 | PRJ-004-ACT-07 | 2025-10-23 | Material | MAT-002 | Steel | VEN-011 | 9.6 | Ton | 544822.21 | 568254.18 | 102285.75 | 670539.93 | Paid | Low
EXP-03429 | PRJ-004 | PRJ-004-ACT-05 | 2025-10-23 | Labour | LAB-006 | Painter | VEN-011 | 10 | Worker | 10933.56 | 10816.06 | 1946.89 | 12762.95 | Paid | Medium
EXP-03430 | PRJ-004 | PRJ-004-ACT-07 | 2025-10-23 | Contractor | CON-003 | Plumbing Contract | VEN-011 | 1 | Contract | 364371.73 | 385050.62 | 69309.11 | 454359.73 | Paid | High
EXP-03431 | PRJ-004 | PRJ-004-ACT-08 | 2025-10-23 | Material | MAT-005 | Bricks | VEN-009 | 10.34 | Piece | 84.59 | 83.53 | 15.04 | 98.57 | Paid | Medium
EXP-03432 | PRJ-004 | PRJ-004-ACT-03 | 2025-10-23 | Material | MAT-007 | PVC Pipe | VEN-003 | 13.34 | Meter | 1575.3 | 1492.28 | 268.61 | 1760.89 | Paid | Medium
EXP-03433 | PRJ-004 | PRJ-004-ACT-09 | 2025-10-23 | Contractor | CON-004 | Finishing Contract | VEN-003 | 1 | Contract | 305399.2 | 323110.07 | 58159.81 | 381269.88 | Paid | Medium
EXP-03434 | PRJ-004 | PRJ-004-ACT-08 | 2025-10-28 | Material | MAT-006 | Electrical Cable | VEN-011 | 3.81 | Meter | 306.75 | 322.92 | 58.13 | 381.05 | Paid | Medium
EXP-03435 | PRJ-004 | PRJ-004-ACT-02 | 2025-10-28 | Contractor | CON-002 | Electrical Contract | VEN-004 | 1 | Contract | 249855.5 | 235744.96 | 42434.09 | 278179.05 | Pending | Low
EXP-03436 | PRJ-004 | PRJ-004-ACT-05 | 2025-10-28 | Labour | LAB-006 | Painter | VEN-011 | 13 | Worker | 16330.52 | 17142.02 | 3085.56 | 20227.58 | Paid | Low
EXP-03437 | PRJ-004 | PRJ-004-ACT-10 | 2025-10-28 | Contractor | CON-002 | Electrical Contract | VEN-011 | 1 | Contract | 145554.16 | 147495.91 | 26549.26 | 174045.17 | Paid | Low
EXP-03438 | PRJ-004 | PRJ-004-ACT-03 | 2025-10-28 | Labour | LAB-005 | Plumber | VEN-009 | 25 | Worker | 19841.63 | 20329.93 | 3659.39 | 23989.32 | Partially Paid | Low
EXP-03439 | PRJ-004 | PRJ-004-ACT-06 | 2025-10-28 | Contractor | CON-001 | Civil Structure Contract | VEN-003 | 1 | Contract | 285512.98 | 267304.61 | 48114.83 | 315419.44 | Paid | High
EXP-03440 | PRJ-004 | PRJ-004-ACT-09 | 2025-10-28 | Contractor | CON-002 | Electrical Contract | VEN-004 | 1 | Contract | 380830.06 | 364457.87 | 65602.42 | 430060.29 | Paid | Low
EXP-03441 | PRJ-004 | PRJ-004-ACT-10 | 2025-10-28 | Contractor | CON-004 | Finishing Contract | VEN-003 | 1 | Contract | 434493.65 | 409264.89 | 73667.68 | 482932.57 | Paid | Low
EXP-03442 | PRJ-004 | PRJ-004-ACT-09 | 2025-10-28 | Material | MAT-010 | Glass | VEN-011 | 4.24 | Sq Ft | 628.93 | 637.38 | 114.73 | 752.11 | Paid | Low
EXP-03443 | PRJ-004 | PRJ-004-ACT-06 | 2025-11-02 | Contractor | CON-001 | Civil Structure Contract | VEN-009 | 1 | Contract | 121527.7 | 121651.26 | 21897.23 | 143548.49 | Paid | Low
EXP-03444 | PRJ-004 | PRJ-004-ACT-04 | 2025-11-02 | Equipment | EQ-003 | Concrete Mixer | VEN-004 | 5 | Day | 21804.67 | 23389.22 | 4210.06 | 27599.28 | Paid | Medium
EXP-03445 | PRJ-004 | PRJ-004-ACT-01 | 2025-11-02 | Material | MAT-009 | Paint | VEN-011 | 11.12 | Litre | 2057.31 | 2050.88 | 369.16 | 2420.04 | Paid | Low
EXP-03446 | PRJ-004 | PRJ-004-ACT-09 | 2025-11-02 | Material | MAT-004 | Aggregate | VEN-009 | 7.2 | Ton | 9436.48 | 9237.33 | 1662.72 | 10900.05 | Paid | Low
EXP-03447 | PRJ-004 | PRJ-004-ACT-04 | 2025-11-02 | Labour | LAB-003 | Carpenter | VEN-004 | 10 | Worker | 12599.16 | 11824.2 | 2128.36 | 13952.56 | Paid | Medium
EXP-03448 | PRJ-004 | PRJ-004-ACT-07 | 2025-11-02 | Material | MAT-009 | Paint | VEN-003 | 5.58 | Litre | 1118.62 | 1076.04 | 193.69 | 1269.73 | Paid | Low
EXP-03449 | PRJ-004 | PRJ-004-ACT-07 | 2025-11-02 | Labour | LAB-006 | Painter | VEN-003 | 19 | Worker | 19393.86 | 19731.82 | 3551.73 | 23283.55 | Partially Paid | Medium
EXP-03450 | PRJ-004 | PRJ-004-ACT-01 | 2025-11-07 | Labour | LAB-005 | Plumber | VEN-003 | 22 | Worker | 29694.03 | 28396.48 | 5111.37 | 33507.85 | Paid | Low
EXP-03451 | PRJ-004 | PRJ-004-ACT-02 | 2025-11-07 | Contractor | CON-004 | Finishing Contract | VEN-004 | 1 | Contract | 150437.54 | 140955.56 | 25372 | 166327.56 | Paid | Medium
EXP-03452 | PRJ-004 | PRJ-004-ACT-09 | 2025-11-07 | Material | MAT-007 | PVC Pipe | VEN-003 | 22.08 | Meter | 2543.93 | 2462.61 | 443.27 | 2905.88 | Partially Paid | Low
EXP-03453 | PRJ-004 | PRJ-004-ACT-08 | 2025-11-07 | Labour | LAB-005 | Plumber | VEN-009 | 28 | Worker | 42445.67 | 40903.71 | 7362.67 | 48266.38 | Partially Paid | Low
EXP-03454 | PRJ-004 | PRJ-004-ACT-01 | 2025-11-07 | Contractor | CON-004 | Finishing Contract | VEN-003 | 1 | Contract | 339489.88 | 330899.35 | 59561.88 | 390461.23 | Paid | Medium
EXP-03455 | PRJ-004 | PRJ-004-ACT-08 | 2025-11-07 | Equipment | EQ-003 | Concrete Mixer | VEN-003 | 5 | Day | 20889.36 | 20251.08 | 3645.19 | 23896.27 | Paid | Low
EXP-03456 | PRJ-004 | PRJ-004-ACT-10 | 2025-11-07 | Material | MAT-009 | Paint | VEN-003 | 6.5 | Litre | 1352.25 | 1257.6 | 226.37 | 1483.97 | Paid | Low
EXP-03457 | PRJ-004 | PRJ-004-ACT-02 | 2025-11-07 | Material | MAT-004 | Aggregate | VEN-004 | 35.92 | Ton | 64596.96 | 60886.12 | 10959.5 | 71845.62 | Paid | Low
EXP-03458 | PRJ-004 | PRJ-004-ACT-05 | 2025-11-12 | Contractor | CON-003 | Plumbing Contract | VEN-011 | 1 | Contract | 345735.33 | 337422.73 | 60736.09 | 398158.82 | Paid | Medium
EXP-03459 | PRJ-004 | PRJ-004-ACT-06 | 2025-11-12 | Other | OTH-001 | Safety | VEN-003 | 1 | Lot | 36271.01 | 33884.87 | 6099.28 | 39984.15 | Paid | High
EXP-03460 | PRJ-004 | PRJ-004-ACT-05 | 2025-11-12 | Labour | LAB-006 | Painter | VEN-003 | 19 | Worker | 31989.4 | 31185.46 | 5613.38 | 36798.84 | Paid | Medium
EXP-03461 | PRJ-004 | PRJ-004-ACT-05 | 2025-11-12 | Equipment | EQ-002 | Excavator | VEN-011 | 3 | Day | 45937.03 | 42815.26 | 7706.75 | 50522.01 | Paid | Low
EXP-03462 | PRJ-004 | PRJ-004-ACT-03 | 2025-11-12 | Labour | LAB-003 | Carpenter | VEN-003 | 9 | Worker | 8986.45 | 9224.64 | 1660.44 | 10885.08 | Paid | Low
EXP-03463 | PRJ-004 | PRJ-004-ACT-08 | 2025-11-12 | Material | MAT-005 | Bricks | VEN-004 | 5.87 | Piece | 53.52 | 52.62 | 9.47 | 62.09 | Partially Paid | Low
EXP-03464 | PRJ-004 | PRJ-004-ACT-02 | 2025-11-12 | Equipment | EQ-002 | Excavator | VEN-003 | 3 | Day | 48704.44 | 45610.36 | 8209.86 | 53820.22 | Paid | High
EXP-03465 | PRJ-004 | PRJ-004-ACT-01 | 2025-11-12 | Other | OTH-001 | Permit | VEN-009 | 1 | Lot | 44087.6 | 41241.87 | 7423.54 | 48665.41 | Paid | Medium
EXP-03466 | PRJ-004 | PRJ-004-ACT-03 | 2025-11-12 | Material | MAT-008 | Tiles | VEN-003 | 4.45 | Sq Ft | 322.22 | 302.54 | 54.46 | 357 | Paid | Medium
EXP-03467 | PRJ-004 | PRJ-004-ACT-07 | 2025-11-12 | Material | MAT-009 | Paint | VEN-009 | 14.33 | Litre | 3632.19 | 3385.1 | 609.32 | 3994.42 | Paid | Low
EXP-03468 | PRJ-004 | PRJ-004-ACT-08 | 2025-11-17 | Contractor | CON-003 | Plumbing Contract | VEN-004 | 1 | Contract | 94275.38 | 88837.06 | 15990.67 | 104827.73 | Partially Paid | Low
EXP-03469 | PRJ-004 | PRJ-004-ACT-03 | 2025-11-17 | Contractor | CON-001 | Civil Structure Contract | VEN-003 | 1 | Contract | 244774.96 | 248493.14 | 44728.77 | 293221.91 | Paid | Medium
EXP-03470 | PRJ-004 | PRJ-004-ACT-07 | 2025-11-17 | Material | MAT-005 | Bricks | VEN-011 | 19.92 | Piece | 185.12 | 185.4 | 33.37 | 218.77 | Paid | Medium
EXP-03471 | PRJ-004 | PRJ-004-ACT-09 | 2025-11-17 | Contractor | CON-004 | Finishing Contract | VEN-009 | 1 | Contract | 179469.14 | 177967.28 | 32034.11 | 210001.39 | Paid | Low
EXP-03472 | PRJ-004 | PRJ-004-ACT-08 | 2025-11-17 | Material | MAT-004 | Aggregate | VEN-011 | 6.03 | Ton | 10475.55 | 9808.59 | 1765.55 | 11574.14 | Paid | Low
EXP-03473 | PRJ-004 | PRJ-004-ACT-06 | 2025-11-17 | Labour | LAB-002 | Helper | VEN-011 | 17 | Worker | 24647.85 | 25550.61 | 4599.11 | 30149.72 | Paid | Low
EXP-03474 | PRJ-004 | PRJ-004-ACT-02 | 2025-11-17 | Other | OTH-001 | Site Office | VEN-004 | 1 | Lot | 67165.43 | 67553.03 | 12159.55 | 79712.58 | Paid | Low
EXP-03475 | PRJ-004 | PRJ-004-ACT-04 | 2025-11-17 | Material | MAT-002 | Steel | VEN-003 | 7.59 | Ton | 502867.11 | 525412.25 | 94574.21 | 619986.46 | Paid | Low
EXP-03476 | PRJ-004 | PRJ-004-ACT-10 | 2025-11-17 | Contractor | CON-004 | Finishing Contract | VEN-009 | 1 | Contract | 476288.96 | 441312.81 | 79436.31 | 520749.12 | Paid | High
EXP-03477 | PRJ-004 | PRJ-004-ACT-01 | 2025-11-22 | Equipment | EQ-004 | Scaffolding | VEN-004 | 4 | Day | 10104.64 | 9818.42 | 1767.32 | 11585.74 | Paid | Low
EXP-03478 | PRJ-004 | PRJ-004-ACT-06 | 2025-11-22 | Labour | LAB-004 | Electrician | VEN-004 | 6 | Worker | 8535.86 | 8841.77 | 1591.52 | 10433.29 | Paid | Low
EXP-03479 | PRJ-004 | PRJ-004-ACT-01 | 2025-11-22 | Labour | LAB-001 | Mason | VEN-011 | 16 | Worker | 15234.56 | 14261.75 | 2567.11 | 16828.86 | Paid | Medium
EXP-03480 | PRJ-004 | PRJ-004-ACT-04 | 2025-11-22 | Labour | LAB-002 | Helper | VEN-004 | 5 | Worker | 3914.69 | 3943.26 | 709.79 | 4653.05 | Paid | Low
EXP-03481 | PRJ-004 | PRJ-004-ACT-07 | 2025-11-22 | Labour | LAB-001 | Mason | VEN-004 | 17 | Worker | 22371.02 | 21925.74 | 3946.63 | 25872.37 | Paid | Low
EXP-03482 | PRJ-004 | PRJ-004-ACT-01 | 2025-11-22 | Labour | LAB-001 | Mason | VEN-004 | 30 | Worker | 40578.63 | 38239.64 | 6883.14 | 45122.78 | Pending | Low
EXP-03483 | PRJ-004 | PRJ-004-ACT-09 | 2025-11-22 | Material | MAT-003 | Sand | VEN-011 | 20.17 | Ton | 35616.53 | 38453.68 | 6921.66 | 45375.34 | Paid | Low
EXP-03484 | PRJ-004 | PRJ-004-ACT-06 | 2025-11-22 | Other | OTH-001 | Miscellaneous | VEN-011 | 1 | Lot | 18597.81 | 19752.66 | 3555.48 | 23308.14 | Paid | Low
EXP-03485 | PRJ-004 | PRJ-004-ACT-01 | 2025-11-22 | Material | MAT-007 | PVC Pipe | VEN-011 | 14.44 | Meter | 2016.9 | 1991.9 | 358.54 | 2350.44 | Paid | Medium
EXP-03486 | PRJ-004 | PRJ-004-ACT-09 | 2025-11-27 | Contractor | CON-004 | Finishing Contract | VEN-004 | 1 | Contract | 414879.02 | 418135.04 | 75264.31 | 493399.35 | Partially Paid | Low
EXP-03487 | PRJ-004 | PRJ-004-ACT-03 | 2025-11-27 | Material | MAT-008 | Tiles | VEN-011 | 13.13 | Sq Ft | 907.78 | 957.21 | 172.3 | 1129.51 | Paid | Low
EXP-03488 | PRJ-004 | PRJ-004-ACT-10 | 2025-11-27 | Material | MAT-007 | PVC Pipe | VEN-009 | 3.29 | Meter | 364.28 | 395.18 | 71.13 | 466.31 | Paid | High
EXP-03489 | PRJ-004 | PRJ-004-ACT-05 | 2025-11-27 | Material | MAT-005 | Bricks | VEN-004 | 6.66 | Piece | 61.99 | 61.16 | 11.01 | 72.17 | Paid | Medium
EXP-03490 | PRJ-004 | PRJ-004-ACT-01 | 2025-11-27 | Labour | LAB-006 | Painter | VEN-003 | 23 | Worker | 40896.73 | 41203.45 | 7416.62 | 48620.07 | Paid | Medium
EXP-03491 | PRJ-004 | PRJ-004-ACT-08 | 2025-11-27 | Contractor | CON-004 | Finishing Contract | VEN-004 | 1 | Contract | 183347.01 | 196759.82 | 35416.77 | 232176.59 | Paid | High
EXP-03492 | PRJ-004 | PRJ-004-ACT-01 | 2025-12-02 | Equipment | EQ-003 | Concrete Mixer | VEN-011 | 2 | Day | 9688.81 | 9774.24 | 1759.36 | 11533.6 | Paid | Medium
EXP-03493 | PRJ-004 | PRJ-004-ACT-08 | 2025-12-02 | Material | MAT-008 | Tiles | VEN-011 | 3.28 | Sq Ft | 222.47 | 209.11 | 37.64 | 246.75 | Paid | High
EXP-03494 | PRJ-004 | PRJ-004-ACT-06 | 2025-12-02 | Material | MAT-006 | Electrical Cable | VEN-009 | 6.94 | Meter | 641 | 618.56 | 111.34 | 729.9 | Paid | Medium
EXP-03495 | PRJ-004 | PRJ-004-ACT-06 | 2025-12-02 | Contractor | CON-001 | Civil Structure Contract | VEN-004 | 1 | Contract | 394020.64 | 415251.16 | 74745.21 | 489996.37 | Paid | Medium
EXP-03496 | PRJ-004 | PRJ-004-ACT-01 | 2025-12-02 | Material | MAT-010 | Glass | VEN-009 | 1.02 | Sq Ft | 178.2 | 175.35 | 31.56 | 206.91 | Paid | Low
EXP-03497 | PRJ-004 | PRJ-004-ACT-07 | 2025-12-02 | Labour | LAB-002 | Helper | VEN-009 | 29 | Worker | 26757.1 | 25998.37 | 4679.71 | 30678.08 | Pending | Low
EXP-03498 | PRJ-004 | PRJ-004-ACT-03 | 2025-12-07 | Labour | LAB-002 | Helper | VEN-004 | 17 | Worker | 29881.36 | 28589.77 | 5146.16 | 33735.93 | Paid | High
EXP-03499 | PRJ-004 | PRJ-004-ACT-09 | 2025-12-07 | Other | OTH-001 | Site Office | VEN-011 | 1 | Lot | 8513.45 | 7946.15 | 1430.31 | 9376.46 | Paid | Medium
EXP-03500 | PRJ-004 | PRJ-004-ACT-03 | 2025-12-07 | Contractor | CON-002 | Electrical Contract | VEN-003 | 1 | Contract | 126244.23 | 130282.04 | 23450.77 | 153732.81 | Paid | Low
EXP-03501 | PRJ-004 | PRJ-004-ACT-04 | 2025-12-07 | Labour | LAB-004 | Electrician | VEN-011 | 26 | Worker | 44706.1 | 41474.88 | 7465.48 | 48940.36 | Paid | Low
EXP-03502 | PRJ-004 | PRJ-004-ACT-06 | 2025-12-07 | Contractor | CON-001 | Civil Structure Contract | VEN-004 | 1 | Contract | 465716.53 | 435211.01 | 78337.98 | 513548.99 | Partially Paid | High
EXP-03503 | PRJ-004 | PRJ-004-ACT-05 | 2025-12-07 | Contractor | CON-002 | Electrical Contract | VEN-011 | 1 | Contract | 182779.52 | 178244.3 | 32083.97 | 210328.27 | Paid | Low
EXP-03504 | PRJ-004 | PRJ-004-ACT-02 | 2025-12-07 | Material | MAT-004 | Aggregate | VEN-004 | 10.49 | Ton | 18741.83 | 18011.32 | 3242.04 | 21253.36 | Pending | Low
EXP-03505 | PRJ-004 | PRJ-004-ACT-04 | 2025-12-07 | Other | OTH-001 | Safety | VEN-003 | 1 | Lot | 18037.97 | 16758.3 | 3016.49 | 19774.79 | Paid | Low
EXP-03506 | PRJ-004 | PRJ-004-ACT-04 | 2025-12-07 | Contractor | CON-001 | Civil Structure Contract | VEN-004 | 1 | Contract | 133625.85 | 128994.37 | 23218.99 | 152213.36 | Paid | Low
EXP-03507 | PRJ-004 | PRJ-004-ACT-09 | 2025-12-07 | Contractor | CON-004 | Finishing Contract | VEN-004 | 1 | Contract | 275007.67 | 257641.61 | 46375.49 | 304017.1 | Paid | Medium
EXP-03508 | PRJ-004 | PRJ-004-ACT-10 | 2025-12-12 | Contractor | CON-003 | Plumbing Contract | VEN-009 | 1 | Contract | 166738.15 | 170630.17 | 30713.43 | 201343.6 | Paid | Low
EXP-03509 | PRJ-004 | PRJ-004-ACT-08 | 2025-12-12 | Other | OTH-001 | Miscellaneous | VEN-011 | 1 | Lot | 63349.64 | 61147.5 | 11006.55 | 72154.05 | Paid | Medium
EXP-03510 | PRJ-004 | PRJ-004-ACT-03 | 2025-12-12 | Labour | LAB-002 | Helper | VEN-009 | 17 | Worker | 14327.92 | 13631.06 | 2453.59 | 16084.65 | Paid | Medium
EXP-03511 | PRJ-004 | PRJ-004-ACT-05 | 2025-12-12 | Equipment | EQ-002 | Excavator | VEN-003 | 6 | Day | 96142.37 | 90634.77 | 16314.26 | 106949.03 | Paid | Medium
EXP-03512 | PRJ-004 | PRJ-004-ACT-09 | 2025-12-12 | Contractor | CON-001 | Civil Structure Contract | VEN-009 | 1 | Contract | 118790.01 | 120293.5 | 21652.83 | 141946.33 | Paid | Low
EXP-03513 | PRJ-004 | PRJ-004-ACT-03 | 2025-12-12 | Other | OTH-001 | Transport | VEN-011 | 1 | Lot | 52523.83 | 53217.44 | 9579.14 | 62796.58 | Paid | High
EXP-03514 | PRJ-004 | PRJ-004-ACT-03 | 2025-12-12 | Material | MAT-004 | Aggregate | VEN-011 | 8.54 | Ton | 15010 | 14242.57 | 2563.66 | 16806.23 | Pending | Low
EXP-03515 | PRJ-004 | PRJ-004-ACT-05 | 2025-12-12 | Material | MAT-008 | Tiles | VEN-004 | 16.68 | Sq Ft | 1274.33 | 1260.98 | 226.98 | 1487.96 | Paid | Low
EXP-03516 | PRJ-004 | PRJ-004-ACT-03 | 2025-12-17 | Material | MAT-008 | Tiles | VEN-003 | 7.81 | Sq Ft | 673.91 | 628.14 | 113.07 | 741.21 | Paid | Medium
EXP-03517 | PRJ-004 | PRJ-004-ACT-03 | 2025-12-17 | Material | MAT-001 | Cement | VEN-003 | 1.63 | Bag | 913.41 | 965.94 | 173.87 | 1139.81 | Paid | Low
EXP-03518 | PRJ-004 | PRJ-004-ACT-01 | 2025-12-17 | Labour | LAB-002 | Helper | VEN-004 | 25 | Worker | 39579.45 | 40408.37 | 7273.51 | 47681.88 | Paid | Medium
EXP-03519 | PRJ-004 | PRJ-004-ACT-01 | 2025-12-17 | Equipment | EQ-002 | Excavator | VEN-011 | 2 | Day | 23573.37 | 25298.73 | 4553.77 | 29852.5 | Paid | Medium
EXP-03520 | PRJ-004 | PRJ-004-ACT-10 | 2025-12-17 | Material | MAT-004 | Aggregate | VEN-004 | 11.9 | Ton | 19331.79 | 17953.75 | 3231.67 | 21185.42 | Paid | Medium
EXP-03521 | PRJ-004 | PRJ-004-ACT-02 | 2025-12-17 | Material | MAT-002 | Steel | VEN-009 | 28.52 | Ton | 1618361.61 | 1552998.95 | 279539.81 | 1832538.76 | Paid | Medium
EXP-03522 | PRJ-004 | PRJ-004-ACT-07 | 2025-12-17 | Other | OTH-001 | Safety | VEN-009 | 1 | Lot | 26999.5 | 28874.55 | 5197.42 | 34071.97 | Paid | Medium
EXP-03523 | PRJ-004 | PRJ-004-ACT-01 | 2025-12-17 | Equipment | EQ-001 | Crane | VEN-009 | 2 | Day | 38206.85 | 37158.23 | 6688.48 | 43846.71 | Paid | Medium
EXP-03524 | PRJ-004 | PRJ-004-ACT-09 | 2025-12-17 | Other | OTH-001 | Transport | VEN-009 | 1 | Lot | 57677.05 | 58479.08 | 10526.23 | 69005.31 | Paid | Medium
EXP-03525 | PRJ-004 | PRJ-004-ACT-08 | 2025-12-22 | Contractor | CON-004 | Finishing Contract | VEN-009 | 1 | Contract | 95714.21 | 99040.5 | 17827.29 | 116867.79 | Paid | Low
EXP-03526 | PRJ-004 | PRJ-004-ACT-07 | 2025-12-22 | Material | MAT-005 | Bricks | VEN-011 | 18.04 | Piece | 173.08 | 163.15 | 29.37 | 192.52 | Paid | Low
EXP-03527 | PRJ-004 | PRJ-004-ACT-04 | 2025-12-22 | Material | MAT-001 | Cement | VEN-004 | 4.22 | Bag | 1910.95 | 1961.55 | 353.08 | 2314.63 | Paid | Low
EXP-03528 | PRJ-004 | PRJ-004-ACT-03 | 2025-12-22 | Labour | LAB-001 | Mason | VEN-003 | 8 | Worker | 10721.65 | 10941.5 | 1969.47 | 12910.97 | Paid | Low
EXP-03529 | PRJ-004 | PRJ-004-ACT-07 | 2025-12-22 | Labour | LAB-003 | Carpenter | VEN-011 | 16 | Worker | 14483.49 | 15109.08 | 2719.63 | 17828.71 | Paid | Medium
EXP-03530 | PRJ-004 | PRJ-004-ACT-05 | 2025-12-22 | Material | MAT-009 | Paint | VEN-009 | 6.01 | Litre | 1270.89 | 1314.85 | 236.67 | 1551.52 | Paid | Medium
EXP-03531 | PRJ-004 | PRJ-004-ACT-02 | 2025-12-22 | Other | OTH-001 | Site Office | VEN-003 | 1 | Lot | 51418.57 | 51969.25 | 9354.47 | 61323.72 | Paid | Low
EXP-03532 | PRJ-004 | PRJ-004-ACT-03 | 2025-12-22 | Labour | LAB-004 | Electrician | VEN-003 | 22 | Worker | 32505.78 | 31771.55 | 5718.88 | 37490.43 | Paid | Medium
EXP-03533 | PRJ-004 | PRJ-004-ACT-09 | 2025-12-22 | Material | MAT-010 | Glass | VEN-009 | 6.24 | Sq Ft | 916.63 | 939.78 | 169.16 | 1108.94 | Paid | Medium
EXP-03534 | PRJ-004 | PRJ-004-ACT-01 | 2025-12-27 | Other | OTH-001 | Permit | VEN-003 | 1 | Lot | 45688.84 | 46706.17 | 8407.11 | 55113.28 | Paid | Low
EXP-03535 | PRJ-004 | PRJ-004-ACT-02 | 2025-12-27 | Contractor | CON-002 | Electrical Contract | VEN-011 | 1 | Contract | 309223.56 | 333999.9 | 60119.98 | 394119.88 | Paid | Medium
EXP-03536 | PRJ-004 | PRJ-004-ACT-02 | 2025-12-27 | Contractor | CON-001 | Civil Structure Contract | VEN-003 | 1 | Contract | 455197.23 | 431553.83 | 77679.69 | 509233.52 | Paid | Low
EXP-03537 | PRJ-004 | PRJ-004-ACT-05 | 2025-12-27 | Contractor | CON-004 | Finishing Contract | VEN-003 | 1 | Contract | 157392.49 | 158645.23 | 28556.14 | 187201.37 | Paid | Low
EXP-03538 | PRJ-004 | PRJ-004-ACT-03 | 2025-12-27 | Other | OTH-001 | Permit | VEN-003 | 1 | Lot | 44427.59 | 47734.86 | 8592.27 | 56327.13 | Paid | High
EXP-03539 | PRJ-004 | PRJ-004-ACT-09 | 2025-12-27 | Material | MAT-004 | Aggregate | VEN-004 | 9.19 | Ton | 15686.34 | 15104.13 | 2718.74 | 17822.87 | Partially Paid | Medium
EXP-03540 | PRJ-004 | PRJ-004-ACT-09 | 2025-12-27 | Other | OTH-001 | Safety | VEN-009 | 1 | Lot | 54682.63 | 52716.94 | 9489.05 | 62205.99 | Paid | Low
EXP-03541 | PRJ-004 | PRJ-004-ACT-08 | 2025-12-27 | Contractor | CON-003 | Plumbing Contract | VEN-004 | 1 | Contract | 169232.6 | 163987.14 | 29517.69 | 193504.83 | Partially Paid | Low
EXP-03542 | PRJ-004 | PRJ-004-ACT-02 | 2025-12-27 | Labour | LAB-004 | Electrician | VEN-004 | 19 | Worker | 30561.72 | 29641.32 | 5335.44 | 34976.76 | Paid | Medium
EXP-03543 | PRJ-004 | PRJ-004-ACT-01 | 2025-12-27 | Contractor | CON-004 | Finishing Contract | VEN-009 | 1 | Contract | 141963.02 | 145242.65 | 26143.68 | 171386.33 | Paid | Low
EXP-03544 | PRJ-004 | PRJ-004-ACT-07 | 2026-01-01 | Equipment | EQ-003 | Concrete Mixer | VEN-003 | 4 | Day | 17718.64 | 18785 | 3381.3 | 22166.3 | Pending | Low
EXP-03545 | PRJ-004 | PRJ-004-ACT-01 | 2026-01-01 | Contractor | CON-004 | Finishing Contract | VEN-003 | 1 | Contract | 131876.59 | 122853.44 | 22113.62 | 144967.06 | Paid | Low
EXP-03546 | PRJ-004 | PRJ-004-ACT-06 | 2026-01-01 | Equipment | EQ-004 | Scaffolding | VEN-011 | 7 | Day | 17502.98 | 17071.25 | 3072.82 | 20144.07 | Paid | Low
EXP-03547 | PRJ-004 | PRJ-004-ACT-05 | 2026-01-01 | Material | MAT-005 | Bricks | VEN-011 | 5.47 | Piece | 42.47 | 42.62 | 7.67 | 50.29 | Paid | Low
EXP-03548 | PRJ-004 | PRJ-004-ACT-01 | 2026-01-01 | Material | MAT-002 | Steel | VEN-004 | 3.08 | Ton | 153978.84 | 165644.24 | 29815.96 | 195460.2 | Paid | Low
EXP-03549 | PRJ-004 | PRJ-004-ACT-03 | 2026-01-01 | Contractor | CON-001 | Civil Structure Contract | VEN-009 | 1 | Contract | 184178.6 | 189356.98 | 34084.26 | 223441.24 | Paid | Medium
EXP-03550 | PRJ-004 | PRJ-004-ACT-05 | 2026-01-01 | Contractor | CON-004 | Finishing Contract | VEN-004 | 1 | Contract | 168985.71 | 177258.39 | 31906.51 | 209164.9 | Paid | Medium
EXP-03551 | PRJ-004 | PRJ-004-ACT-08 | 2026-01-06 | Material | MAT-002 | Steel | VEN-004 | 7.18 | Ton | 422512.69 | 428126.17 | 77062.71 | 505188.88 | Paid | Low
EXP-03552 | PRJ-004 | PRJ-004-ACT-05 | 2026-01-06 | Labour | LAB-005 | Plumber | VEN-004 | 12 | Worker | 8675.3 | 8398.27 | 1511.69 | 9909.96 | Paid | Low
EXP-03553 | PRJ-004 | PRJ-004-ACT-09 | 2026-01-06 | Material | MAT-007 | PVC Pipe | VEN-003 | 3.7 | Meter | 442.79 | 455.73 | 82.03 | 537.76 | Paid | Low
EXP-03554 | PRJ-004 | PRJ-004-ACT-09 | 2026-01-06 | Contractor | CON-002 | Electrical Contract | VEN-011 | 1 | Contract | 149283.47 | 146519.16 | 26373.45 | 172892.61 | Paid | Low
EXP-03555 | PRJ-004 | PRJ-004-ACT-08 | 2026-01-06 | Contractor | CON-003 | Plumbing Contract | VEN-004 | 1 | Contract | 434393.86 | 412937.22 | 74328.7 | 487265.92 | Paid | High
EXP-03556 | PRJ-004 | PRJ-004-ACT-02 | 2026-01-06 | Equipment | EQ-004 | Scaffolding | VEN-003 | 3 | Day | 8220.77 | 7976.07 | 1435.69 | 9411.76 | Partially Paid | Low
EXP-03557 | PRJ-004 | PRJ-004-ACT-05 | 2026-01-06 | Equipment | EQ-003 | Concrete Mixer | VEN-011 | 2 | Day | 9620.72 | 9160.17 | 1648.83 | 10809 | Paid | Medium
EXP-03558 | PRJ-004 | PRJ-004-ACT-07 | 2026-01-11 | Material | MAT-010 | Glass | VEN-003 | 7.14 | Sq Ft | 1127.05 | 1157.8 | 208.4 | 1366.2 | Paid | Low
EXP-03559 | PRJ-004 | PRJ-004-ACT-09 | 2026-01-11 | Material | MAT-006 | Electrical Cable | VEN-004 | 4.81 | Meter | 367.28 | 351.2 | 63.22 | 414.42 | Paid | Medium
EXP-03560 | PRJ-004 | PRJ-004-ACT-03 | 2026-01-11 | Labour | LAB-001 | Mason | VEN-009 | 29 | Worker | 35676.24 | 33661.69 | 6059.1 | 39720.79 | Paid | Low
EXP-03561 | PRJ-004 | PRJ-004-ACT-07 | 2026-01-11 | Equipment | EQ-003 | Concrete Mixer | VEN-011 | 4 | Day | 15654.66 | 17001.22 | 3060.22 | 20061.44 | Paid | Low
EXP-03562 | PRJ-004 | PRJ-004-ACT-01 | 2026-01-11 | Material | MAT-006 | Electrical Cable | VEN-011 | 1.76 | Meter | 145.41 | 135.3 | 24.35 | 159.65 | Paid | Medium
EXP-03563 | PRJ-004 | PRJ-004-ACT-06 | 2026-01-11 | Labour | LAB-006 | Painter | VEN-011 | 10 | Worker | 10513.83 | 10506.66 | 1891.2 | 12397.86 | Paid | High
EXP-03564 | PRJ-004 | PRJ-004-ACT-09 | 2026-01-11 | Material | MAT-005 | Bricks | VEN-003 | 3.27 | Piece | 26.87 | 28.41 | 5.11 | 33.52 | Partially Paid | Medium
EXP-03565 | PRJ-004 | PRJ-004-ACT-06 | 2026-01-16 | Labour | LAB-003 | Carpenter | VEN-011 | 18 | Worker | 21010.59 | 21231.95 | 3821.75 | 25053.7 | Paid | Low
EXP-03566 | PRJ-004 | PRJ-004-ACT-06 | 2026-01-16 | Other | OTH-001 | Site Office | VEN-011 | 1 | Lot | 42889.67 | 42257.16 | 7606.29 | 49863.45 | Partially Paid | Low
EXP-03567 | PRJ-004 | PRJ-004-ACT-07 | 2026-01-16 | Material | MAT-005 | Bricks | VEN-011 | 12.15 | Piece | 124.14 | 120.28 | 21.65 | 141.93 | Paid | Medium
EXP-03568 | PRJ-004 | PRJ-004-ACT-03 | 2026-01-16 | Material | MAT-002 | Steel | VEN-009 | 18.83 | Ton | 1046520.97 | 1104995.66 | 198899.22 | 1303894.88 | Paid | Low
EXP-03569 | PRJ-004 | PRJ-004-ACT-08 | 2026-01-16 | Labour | LAB-005 | Plumber | VEN-003 | 18 | Worker | 28299.47 | 28682.87 | 5162.92 | 33845.79 | Paid | Low
EXP-03570 | PRJ-004 | PRJ-004-ACT-06 | 2026-01-16 | Material | MAT-002 | Steel | VEN-003 | 6.26 | Ton | 404832.93 | 381858.9 | 68734.6 | 450593.5 | Paid | High
EXP-03571 | PRJ-004 | PRJ-004-ACT-01 | 2026-01-16 | Contractor | CON-003 | Plumbing Contract | VEN-003 | 1 | Contract | 105314.69 | 109823.38 | 19768.21 | 129591.59 | Paid | High
EXP-03572 | PRJ-004 | PRJ-004-ACT-06 | 2026-01-16 | Contractor | CON-002 | Electrical Contract | VEN-004 | 1 | Contract | 311241.11 | 330880.66 | 59558.52 | 390439.18 | Paid | High
EXP-03573 | PRJ-004 | PRJ-004-ACT-09 | 2026-01-21 | Equipment | EQ-003 | Concrete Mixer | VEN-004 | 2 | Day | 7683.86 | 8138.62 | 1464.95 | 9603.57 | Paid | Medium
EXP-03574 | PRJ-004 | PRJ-004-ACT-08 | 2026-01-21 | Equipment | EQ-001 | Crane | VEN-009 | 1 | Day | 20402.72 | 18985.68 | 3417.42 | 22403.1 | Partially Paid | Medium
EXP-03575 | PRJ-004 | PRJ-004-ACT-08 | 2026-01-21 | Equipment | EQ-002 | Excavator | VEN-003 | 6 | Day | 93718.35 | 89380.7 | 16088.53 | 105469.23 | Paid | Low
EXP-03576 | PRJ-004 | PRJ-004-ACT-01 | 2026-01-21 | Material | MAT-006 | Electrical Cable | VEN-003 | 5.23 | Meter | 413.57 | 403.66 | 72.66 | 476.32 | Paid | Medium
EXP-03577 | PRJ-004 | PRJ-004-ACT-05 | 2026-01-21 | Material | MAT-001 | Cement | VEN-009 | 9.03 | Bag | 4264.47 | 4226.68 | 760.8 | 4987.48 | Paid | Medium
EXP-03578 | PRJ-004 | PRJ-004-ACT-07 | 2026-01-21 | Contractor | CON-004 | Finishing Contract | VEN-003 | 1 | Contract | 173481.81 | 186321.98 | 33537.96 | 219859.94 | Paid | Low
EXP-03579 | PRJ-004 | PRJ-004-ACT-08 | 2026-01-21 | Labour | LAB-002 | Helper | VEN-011 | 28 | Worker | 26947.17 | 27922.3 | 5026.01 | 32948.31 | Paid | Low
EXP-03580 | PRJ-004 | PRJ-004-ACT-04 | 2026-01-26 | Material | MAT-007 | PVC Pipe | VEN-011 | 9.22 | Meter | 1137.23 | 1160.4 | 208.87 | 1369.27 | Paid | Medium
EXP-03581 | PRJ-004 | PRJ-004-ACT-04 | 2026-01-26 | Other | OTH-001 | Site Office | VEN-011 | 1 | Lot | 63095.04 | 67383.21 | 12128.98 | 79512.19 | Paid | High
EXP-03582 | PRJ-004 | PRJ-004-ACT-02 | 2026-01-26 | Material | MAT-010 | Glass | VEN-011 | 21.16 | Sq Ft | 3665.96 | 3625.76 | 652.64 | 4278.4 | Paid | Medium
EXP-03583 | PRJ-004 | PRJ-004-ACT-03 | 2026-01-26 | Material | MAT-001 | Cement | VEN-003 | 12.5 | Bag | 7079.04 | 7183.33 | 1293 | 8476.33 | Pending | Low
EXP-03584 | PRJ-004 | PRJ-004-ACT-03 | 2026-01-26 | Material | MAT-004 | Aggregate | VEN-003 | 7.5 | Ton | 10229.1 | 10194.41 | 1834.99 | 12029.4 | Partially Paid | Low
EXP-03585 | PRJ-004 | PRJ-004-ACT-01 | 2026-01-26 | Contractor | CON-001 | Civil Structure Contract | VEN-004 | 1 | Contract | 152944.97 | 148936.24 | 26808.52 | 175744.76 | Partially Paid | Low
EXP-03586 | PRJ-004 | PRJ-004-ACT-06 | 2026-01-26 | Equipment | EQ-001 | Crane | VEN-004 | 2 | Day | 40338.87 | 39325.75 | 7078.63 | 46404.38 | Partially Paid | Medium
EXP-03587 | PRJ-004 | PRJ-004-ACT-08 | 2026-01-31 | Material | MAT-002 | Steel | VEN-003 | 2.32 | Ton | 137832.58 | 144583.23 | 26024.98 | 170608.21 | Paid | Low
EXP-03588 | PRJ-004 | PRJ-004-ACT-06 | 2026-01-31 | Labour | LAB-002 | Helper | VEN-011 | 27 | Worker | 28382.57 | 30764.39 | 5537.59 | 36301.98 | Paid | Low
EXP-03589 | PRJ-004 | PRJ-004-ACT-04 | 2026-01-31 | Material | MAT-010 | Glass | VEN-011 | 27.64 | Sq Ft | 4809.64 | 4942.59 | 889.67 | 5832.26 | Partially Paid | High
EXP-03590 | PRJ-004 | PRJ-004-ACT-06 | 2026-01-31 | Equipment | EQ-002 | Excavator | VEN-003 | 1 | Day | 12756.03 | 13452.53 | 2421.46 | 15873.99 | Paid | Medium
EXP-03591 | PRJ-004 | PRJ-004-ACT-02 | 2026-01-31 | Contractor | CON-004 | Finishing Contract | VEN-009 | 1 | Contract | 306280.21 | 296920.95 | 53445.77 | 350366.72 | Partially Paid | Medium
EXP-03592 | PRJ-004 | PRJ-004-ACT-02 | 2026-01-31 | Contractor | CON-001 | Civil Structure Contract | VEN-003 | 1 | Contract | 365678.7 | 378839.8 | 68191.16 | 447030.96 | Paid | Low
EXP-03593 | PRJ-004 | PRJ-004-ACT-02 | 2026-02-05 | Material | MAT-010 | Glass | VEN-003 | 16.64 | Sq Ft | 2262.23 | 2381.39 | 428.65 | 2810.04 | Paid | Low
EXP-03594 | PRJ-004 | PRJ-004-ACT-07 | 2026-02-05 | Contractor | CON-002 | Electrical Contract | VEN-009 | 1 | Contract | 217849.93 | 212097.32 | 38177.52 | 250274.84 | Paid | High
EXP-03595 | PRJ-004 | PRJ-004-ACT-08 | 2026-02-05 | Contractor | CON-001 | Civil Structure Contract | VEN-011 | 1 | Contract | 135768.89 | 129573.43 | 23323.22 | 152896.65 | Paid | High
EXP-03596 | PRJ-004 | PRJ-004-ACT-03 | 2026-02-05 | Labour | LAB-001 | Mason | VEN-004 | 9 | Worker | 15947.24 | 15211.62 | 2738.09 | 17949.71 | Paid | Low
EXP-03597 | PRJ-004 | PRJ-004-ACT-07 | 2026-02-05 | Material | MAT-008 | Tiles | VEN-004 | 8.45 | Sq Ft | 557.7 | 540.62 | 97.31 | 637.93 | Paid | Medium
EXP-03598 | PRJ-004 | PRJ-004-ACT-09 | 2026-02-05 | Labour | LAB-002 | Helper | VEN-004 | 10 | Worker | 6995.83 | 6766.18 | 1217.91 | 7984.09 | Paid | Medium
EXP-03599 | PRJ-004 | PRJ-004-ACT-03 | 2026-02-05 | Equipment | EQ-004 | Scaffolding | VEN-009 | 6 | Day | 15210.93 | 14298.25 | 2573.68 | 16871.93 | Paid | Medium
EXP-03600 | PRJ-004 | PRJ-004-ACT-07 | 2026-02-05 | Material | MAT-002 | Steel | VEN-004 | 28.78 | Ton | 1851015.81 | 1902434.9 | 342438.28 | 2244873.18 | Paid | Medium
EXP-03601 | PRJ-004 | PRJ-004-ACT-04 | 2026-02-10 | Labour | LAB-003 | Carpenter | VEN-004 | 23 | Worker | 28095.65 | 29382.55 | 5288.86 | 34671.41 | Partially Paid | Low
EXP-03602 | PRJ-004 | PRJ-004-ACT-01 | 2026-02-10 | Material | MAT-007 | PVC Pipe | VEN-004 | 4.52 | Meter | 641.37 | 598.01 | 107.64 | 705.65 | Paid | Medium
EXP-03603 | PRJ-004 | PRJ-004-ACT-09 | 2026-02-10 | Labour | LAB-002 | Helper | VEN-004 | 13 | Worker | 19561.66 | 19094.09 | 3436.94 | 22531.03 | Paid | Low
EXP-03604 | PRJ-004 | PRJ-004-ACT-07 | 2026-02-10 | Labour | LAB-004 | Electrician | VEN-009 | 15 | Worker | 11825.55 | 11696.84 | 2105.43 | 13802.27 | Partially Paid | Low
EXP-03605 | PRJ-004 | PRJ-004-ACT-02 | 2026-02-10 | Material | MAT-009 | Paint | VEN-004 | 17.47 | Litre | 3818.4 | 4064.22 | 731.56 | 4795.78 | Paid | Low
EXP-03606 | PRJ-004 | PRJ-004-ACT-09 | 2026-02-10 | Material | MAT-007 | PVC Pipe | VEN-003 | 1 | Meter | 114.56 | 124.35 | 22.38 | 146.73 | Paid | Medium
EXP-03607 | PRJ-004 | PRJ-004-ACT-10 | 2026-02-10 | Material | MAT-002 | Steel | VEN-004 | 4.07 | Ton | 253506.02 | 268825.86 | 48388.65 | 317214.51 | Partially Paid | Medium
EXP-03608 | PRJ-004 | PRJ-004-ACT-05 | 2026-02-10 | Material | MAT-009 | Paint | VEN-004 | 10.41 | Litre | 2267.39 | 2294.5 | 413.01 | 2707.51 | Partially Paid | Medium
EXP-03609 | PRJ-004 | PRJ-004-ACT-06 | 2026-02-15 | Material | MAT-006 | Electrical Cable | VEN-011 | 12.68 | Meter | 1055.9 | 1136.7 | 204.61 | 1341.31 | Paid | Low
EXP-03610 | PRJ-004 | PRJ-004-ACT-04 | 2026-02-15 | Equipment | EQ-001 | Crane | VEN-003 | 6 | Day | 121384.72 | 114156.82 | 20548.23 | 134705.05 | Pending | Medium
EXP-03611 | PRJ-004 | PRJ-004-ACT-09 | 2026-02-15 | Material | MAT-004 | Aggregate | VEN-011 | 7.71 | Ton | 11206.3 | 12098.04 | 2177.65 | 14275.69 | Paid | High
EXP-03612 | PRJ-004 | PRJ-004-ACT-08 | 2026-02-15 | Other | OTH-001 | Safety | VEN-004 | 1 | Lot | 74849.94 | 77222.95 | 13900.13 | 91123.08 | Paid | Low
EXP-03613 | PRJ-004 | PRJ-004-ACT-02 | 2026-02-15 | Equipment | EQ-003 | Concrete Mixer | VEN-009 | 7 | Day | 30052.46 | 29006.48 | 5221.17 | 34227.65 | Paid | Low
EXP-03614 | PRJ-004 | PRJ-004-ACT-02 | 2026-02-15 | Labour | LAB-003 | Carpenter | VEN-009 | 18 | Worker | 18352.84 | 17422.13 | 3135.98 | 20558.11 | Paid | Medium
EXP-03615 | PRJ-004 | PRJ-004-ACT-10 | 2026-02-15 | Other | OTH-001 | Permit | VEN-003 | 1 | Lot | 5896.35 | 6094.24 | 1096.96 | 7191.2 | Paid | High
EXP-03616 | PRJ-004 | PRJ-004-ACT-02 | 2026-02-20 | Material | MAT-008 | Tiles | VEN-011 | 55.81 | Sq Ft | 3521.66 | 3571.97 | 642.95 | 4214.92 | Partially Paid | High
EXP-03617 | PRJ-004 | PRJ-004-ACT-04 | 2026-02-20 | Material | MAT-001 | Cement | VEN-004 | 13.39 | Bag | 7094.57 | 6991.73 | 1258.51 | 8250.24 | Paid | Low
EXP-03618 | PRJ-004 | PRJ-004-ACT-03 | 2026-02-20 | Other | OTH-001 | Transport | VEN-011 | 1 | Lot | 29224.21 | 30777.72 | 5539.99 | 36317.71 | Paid | Low
EXP-03619 | PRJ-004 | PRJ-004-ACT-09 | 2026-02-20 | Material | MAT-010 | Glass | VEN-011 | 24.27 | Sq Ft | 3596.89 | 3902.25 | 702.4 | 4604.65 | Paid | Low
EXP-03620 | PRJ-004 | PRJ-004-ACT-06 | 2026-02-20 | Contractor | CON-003 | Plumbing Contract | VEN-004 | 1 | Contract | 143401.87 | 133061.74 | 23951.11 | 157012.85 | Paid | Low
EXP-03621 | PRJ-004 | PRJ-004-ACT-01 | 2026-02-20 | Material | MAT-010 | Glass | VEN-004 | 9.73 | Sq Ft | 1373.43 | 1389.02 | 250.02 | 1639.04 | Paid | Low
EXP-03622 | PRJ-004 | PRJ-004-ACT-01 | 2026-02-20 | Material | MAT-001 | Cement | VEN-009 | 2.96 | Bag | 1609.96 | 1587.47 | 285.74 | 1873.21 | Paid | Low
EXP-03623 | PRJ-004 | PRJ-004-ACT-01 | 2026-02-25 | Material | MAT-007 | PVC Pipe | VEN-011 | 20.57 | Meter | 2332.44 | 2167.73 | 390.19 | 2557.92 | Paid | Medium
EXP-03624 | PRJ-004 | PRJ-004-ACT-04 | 2026-02-25 | Material | MAT-003 | Sand | VEN-009 | 5.54 | Ton | 8612.33 | 8511.16 | 1532.01 | 10043.17 | Partially Paid | Low
EXP-03625 | PRJ-004 | PRJ-004-ACT-01 | 2026-02-25 | Contractor | CON-002 | Electrical Contract | VEN-004 | 1 | Contract | 260566.88 | 275819.78 | 49647.56 | 325467.34 | Paid | High
EXP-03626 | PRJ-004 | PRJ-004-ACT-05 | 2026-02-25 | Labour | LAB-005 | Plumber | VEN-004 | 25 | Worker | 24558.66 | 24259.83 | 4366.77 | 28626.6 | Paid | Low
EXP-03627 | PRJ-004 | PRJ-004-ACT-04 | 2026-02-25 | Labour | LAB-002 | Helper | VEN-011 | 24 | Worker | 35612.05 | 36490.44 | 6568.28 | 43058.72 | Paid | Low
EXP-03628 | PRJ-004 | PRJ-004-ACT-07 | 2026-02-25 | Equipment | EQ-001 | Crane | VEN-003 | 7 | Day | 122973.13 | 119503.88 | 21510.7 | 141014.58 | Paid | Medium
EXP-03629 | PRJ-004 | PRJ-004-ACT-10 | 2026-02-25 | Material | MAT-007 | PVC Pipe | VEN-004 | 5.01 | Meter | 545.89 | 518.1 | 93.26 | 611.36 | Paid | Medium
EXP-03630 | PRJ-004 | PRJ-004-ACT-05 | 2026-03-02 | Other | OTH-001 | Site Office | VEN-004 | 1 | Lot | 73108.96 | 67826.23 | 12208.72 | 80034.95 | Partially Paid | Low
EXP-03631 | PRJ-004 | PRJ-004-ACT-02 | 2026-03-02 | Labour | LAB-004 | Electrician | VEN-003 | 23 | Worker | 32499.04 | 31840.68 | 5731.32 | 37572 | Paid | Medium
EXP-03632 | PRJ-004 | PRJ-004-ACT-01 | 2026-03-02 | Equipment | EQ-001 | Crane | VEN-011 | 6 | Day | 107687.35 | 102245.55 | 18404.2 | 120649.75 | Partially Paid | Low
EXP-03633 | PRJ-004 | PRJ-004-ACT-10 | 2026-03-02 | Material | MAT-008 | Tiles | VEN-011 | 7.22 | Sq Ft | 533.28 | 496.89 | 89.44 | 586.33 | Paid | Low
EXP-03634 | PRJ-004 | PRJ-004-ACT-07 | 2026-03-02 | Equipment | EQ-001 | Crane | VEN-011 | 4 | Day | 79714.14 | 75335.53 | 13560.4 | 88895.93 | Partially Paid | Medium
EXP-03635 | PRJ-004 | PRJ-004-ACT-05 | 2026-03-02 | Material | MAT-007 | PVC Pipe | VEN-009 | 3.62 | Meter | 473.61 | 446.03 | 80.29 | 526.32 | Paid | Medium
EXP-03636 | PRJ-004 | PRJ-004-ACT-09 | 2026-03-07 | Labour | LAB-002 | Helper | VEN-004 | 15 | Worker | 19916.13 | 19895.83 | 3581.25 | 23477.08 | Paid | Low
EXP-03637 | PRJ-004 | PRJ-004-ACT-10 | 2026-03-07 | Material | MAT-009 | Paint | VEN-003 | 10.03 | Litre | 2195.94 | 2057.74 | 370.39 | 2428.13 | Paid | Low
EXP-03638 | PRJ-004 | PRJ-004-ACT-05 | 2026-03-07 | Material | MAT-009 | Paint | VEN-009 | 10.21 | Litre | 2062.45 | 2165.15 | 389.73 | 2554.88 | Partially Paid | Low
EXP-03639 | PRJ-004 | PRJ-004-ACT-09 | 2026-03-07 | Material | MAT-008 | Tiles | VEN-009 | 12.88 | Sq Ft | 871.68 | 902.84 | 162.51 | 1065.35 | Paid | Medium
EXP-03640 | PRJ-004 | PRJ-004-ACT-04 | 2026-03-07 | Contractor | CON-004 | Finishing Contract | VEN-004 | 1 | Contract | 299957.4 | 299581.37 | 53924.65 | 353506.02 | Paid | Low
EXP-03641 | PRJ-004 | PRJ-004-ACT-09 | 2026-03-07 | Labour | LAB-003 | Carpenter | VEN-009 | 14 | Worker | 17339.93 | 16195.07 | 2915.11 | 19110.18 | Paid | Low
EXP-03642 | PRJ-004 | PRJ-004-ACT-01 | 2026-03-07 | Contractor | CON-003 | Plumbing Contract | VEN-009 | 1 | Contract | 477703.47 | 442895.56 | 79721.2 | 522616.76 | Paid | Low
EXP-03643 | PRJ-004 | PRJ-004-ACT-06 | 2026-03-07 | Other | OTH-001 | Transport | VEN-011 | 1 | Lot | 54820.73 | 59265.69 | 10667.82 | 69933.51 | Paid | Low
EXP-03644 | PRJ-004 | PRJ-004-ACT-06 | 2026-03-07 | Material | MAT-010 | Glass | VEN-011 | 27.68 | Sq Ft | 5431.17 | 5062.51 | 911.25 | 5973.76 | Paid | Low
EXP-03645 | PRJ-004 | PRJ-004-ACT-10 | 2026-03-07 | Material | MAT-010 | Glass | VEN-009 | 8.59 | Sq Ft | 1354.43 | 1400.51 | 252.09 | 1652.6 | Paid | Low
EXP-03646 | PRJ-004 | PRJ-004-ACT-09 | 2026-03-12 | Contractor | CON-003 | Plumbing Contract | VEN-003 | 1 | Contract | 403030.15 | 417894.39 | 75220.99 | 493115.38 | Paid | Low
EXP-03647 | PRJ-004 | PRJ-004-ACT-05 | 2026-03-12 | Contractor | CON-002 | Electrical Contract | VEN-003 | 1 | Contract | 233226.64 | 232300.84 | 41814.15 | 274114.99 | Paid | Medium
EXP-03648 | PRJ-004 | PRJ-004-ACT-05 | 2026-03-12 | Contractor | CON-003 | Plumbing Contract | VEN-011 | 1 | Contract | 329458.59 | 316708.35 | 57007.5 | 373715.85 | Paid | Medium
EXP-03649 | PRJ-004 | PRJ-004-ACT-08 | 2026-03-12 | Material | MAT-005 | Bricks | VEN-009 | 6.3 | Piece | 64.06 | 63.32 | 11.4 | 74.72 | Pending | Low
EXP-03650 | PRJ-004 | PRJ-004-ACT-07 | 2026-03-12 | Labour | LAB-001 | Mason | VEN-004 | 26 | Worker | 44650.41 | 46714.49 | 8408.61 | 55123.1 | Paid | Low
EXP-03651 | PRJ-004 | PRJ-004-ACT-04 | 2026-03-12 | Contractor | CON-004 | Finishing Contract | VEN-011 | 1 | Contract | 419994.57 | 420563.9 | 75701.5 | 496265.4 | Paid | Low
EXP-03652 | PRJ-004 | PRJ-004-ACT-10 | 2026-03-12 | Material | MAT-009 | Paint | VEN-011 | 2.77 | Litre | 555.98 | 538.62 | 96.95 | 635.57 | Partially Paid | Medium
EXP-03653 | PRJ-004 | PRJ-004-ACT-02 | 2026-03-17 | Material | MAT-008 | Tiles | VEN-004 | 1.05 | Sq Ft | 64.25 | 67.08 | 12.07 | 79.15 | Paid | Low
EXP-03654 | PRJ-004 | PRJ-004-ACT-08 | 2026-03-17 | Material | MAT-001 | Cement | VEN-003 | 6.62 | Bag | 3799.5 | 3647.28 | 656.51 | 4303.79 | Paid | Low
EXP-03655 | PRJ-004 | PRJ-004-ACT-06 | 2026-03-17 | Labour | LAB-004 | Electrician | VEN-003 | 4 | Worker | 6053.37 | 6433.64 | 1158.06 | 7591.7 | Paid | Low
EXP-03656 | PRJ-004 | PRJ-004-ACT-04 | 2026-03-17 | Contractor | CON-004 | Finishing Contract | VEN-004 | 1 | Contract | 142299.34 | 143049.32 | 25748.88 | 168798.2 | Paid | Low
EXP-03657 | PRJ-004 | PRJ-004-ACT-04 | 2026-03-17 | Contractor | CON-001 | Civil Structure Contract | VEN-011 | 1 | Contract | 96431.68 | 98415.27 | 17714.75 | 116130.02 | Partially Paid | Medium
EXP-03658 | PRJ-004 | PRJ-004-ACT-05 | 2026-03-17 | Other | OTH-001 | Transport | VEN-004 | 1 | Lot | 58180.9 | 55721.03 | 10029.79 | 65750.82 | Paid | Low
EXP-03659 | PRJ-004 | PRJ-004-ACT-04 | 2026-03-17 | Material | MAT-006 | Electrical Cable | VEN-003 | 2.58 | Meter | 206.13 | 203.8 | 36.68 | 240.48 | Paid | Medium
EXP-03660 | PRJ-004 | PRJ-004-ACT-08 | 2026-03-17 | Contractor | CON-003 | Plumbing Contract | VEN-004 | 1 | Contract | 223790.86 | 226049.86 | 40688.97 | 266738.83 | Paid | Medium
EXP-03661 | PRJ-004 | PRJ-004-ACT-10 | 2026-03-17 | Other | OTH-001 | Transport | VEN-003 | 1 | Lot | 75288.34 | 73085.63 | 13155.41 | 86241.04 | Paid | Low
EXP-03662 | PRJ-004 | PRJ-004-ACT-06 | 2026-03-22 | Contractor | CON-001 | Civil Structure Contract | VEN-011 | 1 | Contract | 253324.32 | 258860.98 | 46594.98 | 305455.96 | Paid | Low
EXP-03663 | PRJ-004 | PRJ-004-ACT-10 | 2026-03-22 | Material | MAT-004 | Aggregate | VEN-003 | 29.14 | Ton | 41554.21 | 43747.29 | 7874.51 | 51621.8 | Paid | Low
EXP-03664 | PRJ-004 | PRJ-004-ACT-08 | 2026-03-22 | Material | MAT-007 | PVC Pipe | VEN-011 | 25.81 | Meter | 3559.13 | 3384.11 | 609.14 | 3993.25 | Paid | Low
EXP-03665 | PRJ-004 | PRJ-004-ACT-10 | 2026-03-22 | Material | MAT-002 | Steel | VEN-004 | 12.51 | Ton | 788934.82 | 789127.01 | 142042.86 | 931169.87 | Paid | Low
EXP-03666 | PRJ-004 | PRJ-004-ACT-10 | 2026-03-22 | Material | MAT-004 | Aggregate | VEN-003 | 11.81 | Ton | 19226.52 | 19497.51 | 3509.55 | 23007.06 | Paid | Low
EXP-03667 | PRJ-004 | PRJ-004-ACT-10 | 2026-03-22 | Material | MAT-005 | Bricks | VEN-003 | 9.26 | Piece | 78.66 | 82.95 | 14.93 | 97.88 | Paid | Low
EXP-03668 | PRJ-004 | PRJ-004-ACT-07 | 2026-03-22 | Contractor | CON-003 | Plumbing Contract | VEN-011 | 1 | Contract | 235076.68 | 230055.73 | 41410.03 | 271465.76 | Paid | Medium
EXP-03669 | PRJ-004 | PRJ-004-ACT-06 | 2026-03-27 | Labour | LAB-005 | Plumber | VEN-011 | 25 | Worker | 29454.45 | 27847.22 | 5012.5 | 32859.72 | Partially Paid | Low
EXP-03670 | PRJ-004 | PRJ-004-ACT-04 | 2026-03-27 | Contractor | CON-004 | Finishing Contract | VEN-011 | 1 | Contract | 244335.38 | 257753.45 | 46395.62 | 304149.07 | Paid | Medium
EXP-03671 | PRJ-004 | PRJ-004-ACT-04 | 2026-03-27 | Contractor | CON-003 | Plumbing Contract | VEN-009 | 1 | Contract | 326997.3 | 313978.71 | 56516.17 | 370494.88 | Paid | Low
EXP-03672 | PRJ-004 | PRJ-004-ACT-08 | 2026-03-27 | Material | MAT-006 | Electrical Cable | VEN-003 | 12.39 | Meter | 911.45 | 905.23 | 162.94 | 1068.17 | Paid | Low
EXP-03673 | PRJ-004 | PRJ-004-ACT-06 | 2026-03-27 | Contractor | CON-002 | Electrical Contract | VEN-011 | 1 | Contract | 142255.27 | 134977.24 | 24295.9 | 159273.14 | Paid | Medium
EXP-03674 | PRJ-004 | PRJ-004-ACT-06 | 2026-03-27 | Labour | LAB-006 | Painter | VEN-004 | 22 | Worker | 32381.24 | 34591.43 | 6226.46 | 40817.89 | Paid | Medium
EXP-03675 | PRJ-004 | PRJ-004-ACT-03 | 2026-04-01 | Material | MAT-001 | Cement | VEN-011 | 27.81 | Bag | 16057.76 | 14979.44 | 2696.3 | 17675.74 | Partially Paid | Medium
EXP-03676 | PRJ-004 | PRJ-004-ACT-09 | 2026-04-01 | Equipment | EQ-004 | Scaffolding | VEN-011 | 4 | Day | 9344.43 | 9161.53 | 1649.08 | 10810.61 | Partially Paid | Medium
EXP-03677 | PRJ-004 | PRJ-004-ACT-02 | 2026-04-01 | Material | MAT-008 | Tiles | VEN-011 | 29.41 | Sq Ft | 1954.64 | 1926.88 | 346.84 | 2273.72 | Paid | Medium
EXP-03678 | PRJ-004 | PRJ-004-ACT-07 | 2026-04-01 | Equipment | EQ-002 | Excavator | VEN-004 | 6 | Day | 83424.37 | 79289.92 | 14272.19 | 93562.11 | Paid | Medium
EXP-03679 | PRJ-004 | PRJ-004-ACT-07 | 2026-04-01 | Contractor | CON-003 | Plumbing Contract | VEN-009 | 1 | Contract | 233925.26 | 234598.07 | 42227.65 | 276825.72 | Paid | Low
EXP-03680 | PRJ-004 | PRJ-004-ACT-01 | 2026-04-01 | Contractor | CON-003 | Plumbing Contract | VEN-003 | 1 | Contract | 272857.17 | 292351.61 | 52623.29 | 344974.9 | Paid | Medium
EXP-03681 | PRJ-004 | PRJ-004-ACT-05 | 2026-04-06 | Other | OTH-001 | Site Office | VEN-011 | 1 | Lot | 18178.35 | 18067.51 | 3252.15 | 21319.66 | Paid | Low
EXP-03682 | PRJ-004 | PRJ-004-ACT-09 | 2026-04-06 | Equipment | EQ-001 | Crane | VEN-011 | 4 | Day | 75491.58 | 76182.88 | 13712.92 | 89895.8 | Paid | Low
EXP-03683 | PRJ-004 | PRJ-004-ACT-03 | 2026-04-06 | Material | MAT-010 | Glass | VEN-011 | 10.35 | Sq Ft | 1664.73 | 1683.27 | 302.99 | 1986.26 | Paid | Low
EXP-03684 | PRJ-004 | PRJ-004-ACT-02 | 2026-04-06 | Contractor | CON-003 | Plumbing Contract | VEN-011 | 1 | Contract | 87853.78 | 83402.85 | 15012.51 | 98415.36 | Paid | Low
EXP-03685 | PRJ-004 | PRJ-004-ACT-07 | 2026-04-06 | Labour | LAB-005 | Plumber | VEN-009 | 17 | Worker | 27317.43 | 26243.47 | 4723.82 | 30967.29 | Partially Paid | Low
EXP-03686 | PRJ-004 | PRJ-004-ACT-09 | 2026-04-06 | Equipment | EQ-004 | Scaffolding | VEN-009 | 2 | Day | 4821.05 | 4683.51 | 843.03 | 5526.54 | Paid | High
EXP-03687 | PRJ-004 | PRJ-004-ACT-01 | 2026-04-06 | Contractor | CON-002 | Electrical Contract | VEN-004 | 1 | Contract | 376011.41 | 377595.06 | 67967.11 | 445562.17 | Paid | Medium
EXP-03688 | PRJ-004 | PRJ-004-ACT-04 | 2026-04-06 | Material | MAT-003 | Sand | VEN-004 | 12.51 | Ton | 22359.19 | 23968.26 | 4314.29 | 28282.55 | Paid | Low
EXP-03689 | PRJ-004 | PRJ-004-ACT-07 | 2026-04-11 | Material | MAT-005 | Bricks | VEN-009 | 9.25 | Piece | 85 | 83.39 | 15.01 | 98.4 | Partially Paid | Low
EXP-03690 | PRJ-004 | PRJ-004-ACT-01 | 2026-04-11 | Material | MAT-007 | PVC Pipe | VEN-004 | 10.13 | Meter | 1233.8 | 1142.84 | 205.71 | 1348.55 | Paid | Low
EXP-03691 | PRJ-004 | PRJ-004-ACT-09 | 2026-04-11 | Labour | LAB-005 | Plumber | VEN-004 | 32 | Worker | 38272.28 | 38558.8 | 6940.58 | 45499.38 | Paid | Low
EXP-03692 | PRJ-004 | PRJ-004-ACT-08 | 2026-04-11 | Contractor | CON-004 | Finishing Contract | VEN-009 | 1 | Contract | 374909.56 | 403022.76 | 72544.1 | 475566.86 | Partially Paid | Low
EXP-03693 | PRJ-004 | PRJ-004-ACT-03 | 2026-04-11 | Labour | LAB-004 | Electrician | VEN-009 | 34 | Worker | 40342.07 | 39575.95 | 7123.67 | 46699.62 | Paid | Medium
EXP-03694 | PRJ-004 | PRJ-004-ACT-01 | 2026-04-11 | Equipment | EQ-004 | Scaffolding | VEN-011 | 2 | Day | 5545.86 | 5253.65 | 945.66 | 6199.31 | Paid | Low
EXP-03695 | PRJ-004 | PRJ-004-ACT-09 | 2026-04-16 | Material | MAT-004 | Aggregate | VEN-009 | 4.27 | Ton | 7046.18 | 7211.27 | 1298.03 | 8509.3 | Paid | Medium
EXP-03696 | PRJ-004 | PRJ-004-ACT-08 | 2026-04-16 | Equipment | EQ-001 | Crane | VEN-009 | 4 | Day | 62478.15 | 66658.22 | 11998.48 | 78656.7 | Paid | Medium
EXP-03697 | PRJ-004 | PRJ-004-ACT-06 | 2026-04-16 | Material | MAT-001 | Cement | VEN-003 | 12.16 | Bag | 6187.84 | 6124.94 | 1102.49 | 7227.43 | Partially Paid | High
EXP-03698 | PRJ-004 | PRJ-004-ACT-06 | 2026-04-16 | Other | OTH-001 | Site Office | VEN-003 | 1 | Lot | 7089.61 | 6738.95 | 1213.01 | 7951.96 | Partially Paid | Medium
EXP-03699 | PRJ-004 | PRJ-004-ACT-06 | 2026-04-16 | Material | MAT-010 | Glass | VEN-004 | 10.81 | Sq Ft | 1758.69 | 1843.16 | 331.77 | 2174.93 | Paid | High
EXP-03700 | PRJ-004 | PRJ-004-ACT-08 | 2026-04-16 | Material | MAT-007 | PVC Pipe | VEN-009 | 6.9 | Meter | 879.65 | 843.61 | 151.85 | 995.46 | Paid | Medium
EXP-03701 | PRJ-004 | PRJ-004-ACT-02 | 2026-04-16 | Contractor | CON-002 | Electrical Contract | VEN-011 | 1 | Contract | 250013.27 | 270091.71 | 48616.51 | 318708.22 | Paid | Medium
EXP-03702 | PRJ-004 | PRJ-004-ACT-09 | 2026-04-16 | Material | MAT-006 | Electrical Cable | VEN-011 | 6.41 | Meter | 567.83 | 559.1 | 100.64 | 659.74 | Paid | Low
EXP-03703 | PRJ-004 | PRJ-004-ACT-09 | 2026-04-16 | Contractor | CON-001 | Civil Structure Contract | VEN-009 | 1 | Contract | 216832.29 | 224328.87 | 40379.2 | 264708.07 | Paid | Medium
EXP-03704 | PRJ-004 | PRJ-004-ACT-09 | 2026-04-21 | Material | MAT-005 | Bricks | VEN-011 | 7.64 | Piece | 65.57 | 65.07 | 11.71 | 76.78 | Paid | Low
EXP-03705 | PRJ-004 | PRJ-004-ACT-02 | 2026-04-21 | Contractor | CON-001 | Civil Structure Contract | VEN-004 | 1 | Contract | 279509.48 | 282434.21 | 50838.16 | 333272.37 | Paid | Low
EXP-03706 | PRJ-004 | PRJ-004-ACT-08 | 2026-04-21 | Labour | LAB-006 | Painter | VEN-004 | 18 | Worker | 30486.21 | 30058.1 | 5410.46 | 35468.56 | Paid | Low
EXP-03707 | PRJ-004 | PRJ-004-ACT-05 | 2026-04-21 | Labour | LAB-001 | Mason | VEN-003 | 15 | Worker | 15153.95 | 16275.76 | 2929.64 | 19205.4 | Paid | Low
EXP-03708 | PRJ-004 | PRJ-004-ACT-09 | 2026-04-21 | Material | MAT-002 | Steel | VEN-009 | 6.7 | Ton | 362139.45 | 356227.08 | 64120.87 | 420347.95 | Paid | Medium
EXP-03709 | PRJ-004 | PRJ-004-ACT-07 | 2026-04-21 | Contractor | CON-001 | Civil Structure Contract | VEN-004 | 1 | Contract | 375210.62 | 354350.79 | 63783.14 | 418133.93 | Paid | Low
EXP-03710 | PRJ-004 | PRJ-004-ACT-09 | 2026-04-21 | Material | MAT-007 | PVC Pipe | VEN-009 | 8.44 | Meter | 1097.89 | 1118.65 | 201.36 | 1320.01 | Paid | Low
EXP-03711 | PRJ-004 | PRJ-004-ACT-02 | 2026-04-26 | Material | MAT-002 | Steel | VEN-003 | 7.23 | Ton | 438946.53 | 416397.14 | 74951.49 | 491348.63 | Paid | Low
EXP-03712 | PRJ-004 | PRJ-004-ACT-08 | 2026-04-26 | Labour | LAB-003 | Carpenter | VEN-003 | 15 | Worker | 25950.46 | 26315.08 | 4736.71 | 31051.79 | Paid | Low
EXP-03713 | PRJ-004 | PRJ-004-ACT-02 | 2026-04-26 | Contractor | CON-002 | Electrical Contract | VEN-009 | 1 | Contract | 249953.64 | 264936 | 47688.48 | 312624.48 | Paid | High
EXP-03714 | PRJ-004 | PRJ-004-ACT-09 | 2026-04-26 | Material | MAT-004 | Aggregate | VEN-004 | 4.08 | Ton | 5604.9 | 5529.41 | 995.29 | 6524.7 | Paid | Medium
EXP-03715 | PRJ-004 | PRJ-004-ACT-08 | 2026-04-26 | Equipment | EQ-003 | Concrete Mixer | VEN-003 | 1 | Day | 4455.6 | 4653.89 | 837.7 | 5491.59 | Paid | Medium
EXP-03716 | PRJ-004 | PRJ-004-ACT-06 | 2026-04-26 | Contractor | CON-004 | Finishing Contract | VEN-003 | 1 | Contract | 178592.5 | 189576.06 | 34123.69 | 223699.75 | Paid | Medium
EXP-03717 | PRJ-004 | PRJ-004-ACT-07 | 2026-04-26 | Equipment | EQ-002 | Excavator | VEN-003 | 5 | Day | 76523.67 | 71595.7 | 12887.23 | 84482.93 | Paid | Medium
EXP-03718 | PRJ-004 | PRJ-004-ACT-08 | 2026-04-26 | Contractor | CON-003 | Plumbing Contract | VEN-003 | 1 | Contract | 369186.68 | 361500.55 | 65070.1 | 426570.65 | Partially Paid | Low
EXP-03719 | PRJ-004 | PRJ-004-ACT-05 | 2026-05-01 | Material | MAT-002 | Steel | VEN-011 | 6.06 | Ton | 373752.41 | 384615.13 | 69230.72 | 453845.85 | Paid | Low
EXP-03720 | PRJ-004 | PRJ-004-ACT-09 | 2026-05-01 | Labour | LAB-002 | Helper | VEN-011 | 19 | Worker | 17724.31 | 17478.85 | 3146.19 | 20625.04 | Pending | Low
EXP-03721 | PRJ-004 | PRJ-004-ACT-04 | 2026-05-01 | Material | MAT-005 | Bricks | VEN-004 | 11.26 | Piece | 96.19 | 89.8 | 16.16 | 105.96 | Paid | Low
EXP-03722 | PRJ-004 | PRJ-004-ACT-04 | 2026-05-01 | Other | OTH-001 | Permit | VEN-009 | 1 | Lot | 42893.75 | 41819.12 | 7527.44 | 49346.56 | Paid | Low
EXP-03723 | PRJ-004 | PRJ-004-ACT-10 | 2026-05-01 | Other | OTH-001 | Safety | VEN-009 | 1 | Lot | 39524.01 | 38688.23 | 6963.88 | 45652.11 | Paid | Medium
EXP-03724 | PRJ-004 | PRJ-004-ACT-10 | 2026-05-01 | Labour | LAB-001 | Mason | VEN-004 | 32 | Worker | 47346.56 | 48729.81 | 8771.37 | 57501.18 | Paid | Medium
EXP-03725 | PRJ-004 | PRJ-004-ACT-09 | 2026-05-06 | Labour | LAB-002 | Helper | VEN-011 | 27 | Worker | 32784.18 | 31573.26 | 5683.19 | 37256.45 | Paid | High
EXP-03726 | PRJ-004 | PRJ-004-ACT-10 | 2026-05-06 | Material | MAT-007 | PVC Pipe | VEN-011 | 8.55 | Meter | 1056.15 | 1038.16 | 186.87 | 1225.03 | Paid | Low
EXP-03727 | PRJ-004 | PRJ-004-ACT-03 | 2026-05-06 | Material | MAT-009 | Paint | VEN-004 | 4.62 | Litre | 1038.73 | 1108.28 | 199.49 | 1307.77 | Paid | Low
EXP-03728 | PRJ-004 | PRJ-004-ACT-10 | 2026-05-06 | Material | MAT-008 | Tiles | VEN-003 | 36.75 | Sq Ft | 2661.21 | 2585.37 | 465.37 | 3050.74 | Partially Paid | Medium
EXP-03729 | PRJ-004 | PRJ-004-ACT-03 | 2026-05-06 | Material | MAT-008 | Tiles | VEN-009 | 18.75 | Sq Ft | 1310.23 | 1387.97 | 249.83 | 1637.8 | Paid | Low
EXP-03730 | PRJ-004 | PRJ-004-ACT-07 | 2026-05-06 | Material | MAT-001 | Cement | VEN-011 | 5.74 | Bag | 3249.91 | 3132.73 | 563.89 | 3696.62 | Paid | Medium
EXP-03731 | PRJ-004 | PRJ-004-ACT-07 | 2026-05-06 | Material | MAT-006 | Electrical Cable | VEN-004 | 4.8 | Meter | 416.34 | 401.22 | 72.22 | 473.44 | Pending | Low
EXP-03732 | PRJ-004 | PRJ-004-ACT-05 | 2026-05-06 | Labour | LAB-004 | Electrician | VEN-011 | 12 | Worker | 9422.43 | 9763.15 | 1757.37 | 11520.52 | Partially Paid | Low
EXP-03733 | PRJ-004 | PRJ-004-ACT-07 | 2026-05-06 | Material | MAT-004 | Aggregate | VEN-003 | 7.11 | Ton | 10190.72 | 10496.46 | 1889.36 | 12385.82 | Pending | Medium
EXP-03734 | PRJ-004 | PRJ-004-ACT-08 | 2026-05-11 | Material | MAT-008 | Tiles | VEN-009 | 13.87 | Sq Ft | 1107.65 | 1099.33 | 197.88 | 1297.21 | Paid | Medium
EXP-03735 | PRJ-004 | PRJ-004-ACT-04 | 2026-05-11 | Contractor | CON-002 | Electrical Contract | VEN-011 | 1 | Contract | 100133.56 | 102593.06 | 18466.75 | 121059.81 | Paid | Low
EXP-03736 | PRJ-004 | PRJ-004-ACT-08 | 2026-05-11 | Material | MAT-005 | Bricks | VEN-009 | 16.63 | Piece | 145.88 | 150.1 | 27.02 | 177.12 | Paid | Low
EXP-03737 | PRJ-004 | PRJ-004-ACT-10 | 2026-05-11 | Contractor | CON-001 | Civil Structure Contract | VEN-011 | 1 | Contract | 174183.07 | 162599.91 | 29267.98 | 191867.89 | Paid | High
EXP-03738 | PRJ-004 | PRJ-004-ACT-08 | 2026-05-11 | Material | MAT-010 | Glass | VEN-003 | 3.67 | Sq Ft | 515.68 | 511.37 | 92.05 | 603.42 | Paid | Low
EXP-03739 | PRJ-004 | PRJ-004-ACT-06 | 2026-05-11 | Contractor | CON-003 | Plumbing Contract | VEN-003 | 1 | Contract | 150382.19 | 153128.39 | 27563.11 | 180691.5 | Paid | Medium
EXP-03740 | PRJ-004 | PRJ-004-ACT-08 | 2026-05-11 | Equipment | EQ-003 | Concrete Mixer | VEN-011 | 3 | Day | 13975.64 | 14795.95 | 2663.27 | 17459.22 | Partially Paid | Low
EXP-03741 | PRJ-004 | PRJ-004-ACT-04 | 2026-05-11 | Equipment | EQ-003 | Concrete Mixer | VEN-011 | 6 | Day | 26676.46 | 26560.94 | 4780.97 | 31341.91 | Paid | Low
EXP-03742 | PRJ-004 | PRJ-004-ACT-09 | 2026-05-11 | Material | MAT-010 | Glass | VEN-004 | 10.81 | Sq Ft | 1802.98 | 1710.94 | 307.97 | 2018.91 | Paid | Low
EXP-03743 | PRJ-004 | PRJ-004-ACT-04 | 2026-05-16 | Labour | LAB-002 | Helper | VEN-003 | 13 | Worker | 20418.61 | 19825.25 | 3568.55 | 23393.8 | Paid | Low
EXP-03744 | PRJ-004 | PRJ-004-ACT-01 | 2026-05-16 | Labour | LAB-004 | Electrician | VEN-004 | 32 | Worker | 35684.66 | 37194.95 | 6695.09 | 43890.04 | Paid | Low
EXP-03745 | PRJ-004 | PRJ-004-ACT-07 | 2026-05-16 | Contractor | CON-002 | Electrical Contract | VEN-011 | 1 | Contract | 103614.7 | 97424.75 | 17536.45 | 114961.2 | Paid | Low
EXP-03746 | PRJ-004 | PRJ-004-ACT-06 | 2026-05-16 | Material | MAT-007 | PVC Pipe | VEN-004 | 9.77 | Meter | 1231.93 | 1288.03 | 231.85 | 1519.88 | Partially Paid | Low
EXP-03747 | PRJ-004 | PRJ-004-ACT-01 | 2026-05-16 | Material | MAT-008 | Tiles | VEN-003 | 41.61 | Sq Ft | 2755 | 2830.5 | 509.49 | 3339.99 | Paid | Low
EXP-03748 | PRJ-004 | PRJ-004-ACT-07 | 2026-05-16 | Contractor | CON-004 | Finishing Contract | VEN-004 | 1 | Contract | 104431.88 | 109510.39 | 19711.87 | 129222.26 | Paid | Low
EXP-03749 | PRJ-004 | PRJ-004-ACT-10 | 2026-05-16 | Labour | LAB-004 | Electrician | VEN-003 | 14 | Worker | 11992.78 | 12271.66 | 2208.9 | 14480.56 | Paid | Low
EXP-03750 | PRJ-004 | PRJ-004-ACT-03 | 2026-05-16 | Material | MAT-009 | Paint | VEN-011 | 7.22 | Litre | 1434.73 | 1504.81 | 270.87 | 1775.68 | Paid | Low
EXP-03751 | PRJ-004 | PRJ-004-ACT-09 | 2026-05-16 | Material | MAT-010 | Glass | VEN-004 | 8.16 | Sq Ft | 1211.11 | 1305.75 | 235.03 | 1540.78 | Paid | Low
EXP-03752 | PRJ-004 | PRJ-004-ACT-05 | 2026-05-21 | Labour | LAB-006 | Painter | VEN-004 | 28 | Worker | 18818.45 | 19575.54 | 3523.6 | 23099.14 | Paid | Low
EXP-03753 | PRJ-004 | PRJ-004-ACT-04 | 2026-05-21 | Labour | LAB-004 | Electrician | VEN-009 | 33 | Worker | 56049.42 | 52737.85 | 9492.81 | 62230.66 | Paid | Medium
EXP-03754 | PRJ-004 | PRJ-004-ACT-09 | 2026-05-21 | Material | MAT-001 | Cement | VEN-011 | 5.22 | Bag | 3045.88 | 3063.3 | 551.39 | 3614.69 | Paid | Low
EXP-03755 | PRJ-004 | PRJ-004-ACT-06 | 2026-05-21 | Contractor | CON-002 | Electrical Contract | VEN-009 | 1 | Contract | 163153.73 | 158060.57 | 28450.9 | 186511.47 | Partially Paid | Low
EXP-03756 | PRJ-004 | PRJ-004-ACT-06 | 2026-05-21 | Material | MAT-004 | Aggregate | VEN-004 | 33.6 | Ton | 48024.11 | 46985.06 | 8457.31 | 55442.37 | Paid | Medium
EXP-03757 | PRJ-004 | PRJ-004-ACT-07 | 2026-05-21 | Contractor | CON-004 | Finishing Contract | VEN-011 | 1 | Contract | 217509.55 | 235948.52 | 42470.73 | 278419.25 | Paid | Low
EXP-03758 | PRJ-004 | PRJ-004-ACT-02 | 2026-05-21 | Contractor | CON-001 | Civil Structure Contract | VEN-003 | 1 | Contract | 279889.61 | 271852.63 | 48933.47 | 320786.1 | Paid | High
EXP-03759 | PRJ-004 | PRJ-004-ACT-07 | 2026-05-21 | Material | MAT-006 | Electrical Cable | VEN-009 | 6.24 | Meter | 559.89 | 554.82 | 99.87 | 654.69 | Paid | Medium
EXP-03760 | PRJ-004 | PRJ-004-ACT-06 | 2026-05-21 | Contractor | CON-002 | Electrical Contract | VEN-009 | 1 | Contract | 147805.82 | 153400.94 | 27612.17 | 181013.11 | Paid | Low
EXP-03761 | PRJ-004 | PRJ-004-ACT-04 | 2026-05-26 | Material | MAT-009 | Paint | VEN-004 | 20.63 | Litre | 4087.85 | 4058.82 | 730.59 | 4789.41 | Paid | Medium
EXP-03762 | PRJ-004 | PRJ-004-ACT-05 | 2026-05-26 | Material | MAT-001 | Cement | VEN-004 | 9.03 | Bag | 5471.36 | 5276.51 | 949.77 | 6226.28 | Paid | Low
EXP-03763 | PRJ-004 | PRJ-004-ACT-07 | 2026-05-26 | Material | MAT-010 | Glass | VEN-009 | 5.3 | Sq Ft | 857.4 | 913.94 | 164.51 | 1078.45 | Pending | Medium
EXP-03764 | PRJ-004 | PRJ-004-ACT-09 | 2026-05-26 | Material | MAT-002 | Steel | VEN-003 | 6.69 | Ton | 388082.29 | 405923.21 | 73066.18 | 478989.39 | Paid | Low
EXP-03765 | PRJ-004 | PRJ-004-ACT-05 | 2026-05-26 | Material | MAT-004 | Aggregate | VEN-003 | 30 | Ton | 46940.72 | 48216.4 | 8678.95 | 56895.35 | Partially Paid | Low
EXP-03766 | PRJ-004 | PRJ-004-ACT-08 | 2026-05-26 | Material | MAT-005 | Bricks | VEN-011 | 10.92 | Piece | 103.64 | 101.25 | 18.22 | 119.47 | Paid | Medium
EXP-03767 | PRJ-004 | PRJ-004-ACT-10 | 2026-05-26 | Material | MAT-009 | Paint | VEN-011 | 5.54 | Litre | 1081.94 | 1053.66 | 189.66 | 1243.32 | Paid | Medium
EXP-03768 | PRJ-004 | PRJ-004-ACT-01 | 2026-05-26 | Labour | LAB-001 | Mason | VEN-009 | 31 | Worker | 31215.74 | 32974.33 | 5935.38 | 38909.71 | Partially Paid | Low
EXP-03769 | PRJ-004 | PRJ-004-ACT-09 | 2026-05-26 | Labour | LAB-005 | Plumber | VEN-003 | 21 | Worker | 20345.01 | 19934.29 | 3588.17 | 23522.46 | Paid | Low
EXP-03770 | PRJ-004 | PRJ-004-ACT-09 | 2026-05-31 | Contractor | CON-002 | Electrical Contract | VEN-004 | 1 | Contract | 130982.48 | 123835.48 | 22290.39 | 146125.87 | Paid | Medium
EXP-03771 | PRJ-004 | PRJ-004-ACT-05 | 2026-05-31 | Contractor | CON-004 | Finishing Contract | VEN-011 | 1 | Contract | 284140.2 | 280851.79 | 50553.32 | 331405.11 | Paid | Medium
EXP-03772 | PRJ-004 | PRJ-004-ACT-01 | 2026-05-31 | Other | OTH-001 | Transport | VEN-011 | 1 | Lot | 55772.05 | 54082.83 | 9734.91 | 63817.74 | Paid | Low
EXP-03773 | PRJ-004 | PRJ-004-ACT-05 | 2026-05-31 | Contractor | CON-001 | Civil Structure Contract | VEN-011 | 1 | Contract | 229539.14 | 229048.87 | 41228.8 | 270277.67 | Paid | Low
EXP-03774 | PRJ-004 | PRJ-004-ACT-04 | 2026-05-31 | Other | OTH-001 | Safety | VEN-003 | 1 | Lot | 42134.87 | 43632.27 | 7853.81 | 51486.08 | Pending | Low
EXP-03775 | PRJ-004 | PRJ-004-ACT-03 | 2026-05-31 | Labour | LAB-005 | Plumber | VEN-011 | 30 | Worker | 49952.62 | 48319.69 | 8697.54 | 57017.23 | Paid | Low
EXP-03776 | PRJ-004 | PRJ-004-ACT-07 | 2026-05-31 | Contractor | CON-004 | Finishing Contract | VEN-009 | 1 | Contract | 205206.92 | 200100.44 | 36018.08 | 236118.52 | Partially Paid | Low
EXP-03777 | PRJ-004 | PRJ-004-ACT-07 | 2026-05-31 | Labour | LAB-004 | Electrician | VEN-003 | 34 | Worker | 27216.26 | 27665.84 | 4979.85 | 32645.69 | Paid | Medium
EXP-03778 | PRJ-004 | PRJ-004-ACT-07 | 2026-05-31 | Contractor | CON-003 | Plumbing Contract | VEN-009 | 1 | Contract | 162457.44 | 151970.38 | 27354.67 | 179325.05 | Paid | Low
EXP-03779 | PRJ-004 | PRJ-004-ACT-08 | 2026-06-05 | Labour | LAB-002 | Helper | VEN-009 | 11 | Worker | 16408.78 | 16869.86 | 3036.57 | 19906.43 | Partially Paid | High
EXP-03780 | PRJ-004 | PRJ-004-ACT-02 | 2026-06-05 | Material | MAT-010 | Glass | VEN-011 | 10.7 | Sq Ft | 1802.9 | 1867.84 | 336.21 | 2204.05 | Paid | Low
EXP-03781 | PRJ-004 | PRJ-004-ACT-02 | 2026-06-05 | Contractor | CON-003 | Plumbing Contract | VEN-009 | 1 | Contract | 228251.67 | 221334.82 | 39840.27 | 261175.09 | Paid | Low
EXP-03782 | PRJ-004 | PRJ-004-ACT-08 | 2026-06-05 | Labour | LAB-002 | Helper | VEN-003 | 23 | Worker | 19128.98 | 18170.88 | 3270.76 | 21441.64 | Paid | Low
EXP-03783 | PRJ-004 | PRJ-004-ACT-05 | 2026-06-05 | Equipment | EQ-003 | Concrete Mixer | VEN-004 | 5 | Day | 22570.22 | 22318.69 | 4017.36 | 26336.05 | Paid | Medium
EXP-03784 | PRJ-004 | PRJ-004-ACT-08 | 2026-06-05 | Equipment | EQ-002 | Excavator | VEN-004 | 7 | Day | 93103.11 | 92406.32 | 16633.14 | 109039.46 | Paid | Low
EXP-03785 | PRJ-004 | PRJ-004-ACT-01 | 2026-06-05 | Material | MAT-008 | Tiles | VEN-003 | 5.46 | Sq Ft | 417.52 | 422.33 | 76.02 | 498.35 | Partially Paid | Medium
EXP-03786 | PRJ-004 | PRJ-004-ACT-07 | 2026-06-10 | Labour | LAB-006 | Painter | VEN-011 | 27 | Worker | 20785.78 | 20837.5 | 3750.75 | 24588.25 | Partially Paid | Medium
EXP-03787 | PRJ-004 | PRJ-004-ACT-06 | 2026-06-10 | Equipment | EQ-001 | Crane | VEN-003 | 3 | Day | 50626.96 | 53627.74 | 9652.99 | 63280.73 | Paid | Low
EXP-03788 | PRJ-004 | PRJ-004-ACT-09 | 2026-06-10 | Material | MAT-004 | Aggregate | VEN-011 | 22.43 | Ton | 30493.83 | 28744.49 | 5174.01 | 33918.5 | Pending | Medium
EXP-03789 | PRJ-004 | PRJ-004-ACT-05 | 2026-06-10 | Contractor | CON-001 | Civil Structure Contract | VEN-009 | 1 | Contract | 258362.06 | 259562.87 | 46721.32 | 306284.19 | Paid | Medium
EXP-03790 | PRJ-004 | PRJ-004-ACT-05 | 2026-06-10 | Material | MAT-008 | Tiles | VEN-003 | 13.56 | Sq Ft | 1084.26 | 1006.88 | 181.24 | 1188.12 | Paid | High
EXP-03791 | PRJ-004 | PRJ-004-ACT-07 | 2026-06-10 | Contractor | CON-004 | Finishing Contract | VEN-003 | 1 | Contract | 193459.56 | 189119.76 | 34041.56 | 223161.32 | Paid | Medium
EXP-03792 | PRJ-004 | PRJ-004-ACT-07 | 2026-06-10 | Contractor | CON-002 | Electrical Contract | VEN-009 | 1 | Contract | 344074.06 | 323532.97 | 58235.93 | 381768.9 | Paid | Medium
EXP-03793 | PRJ-004 | PRJ-004-ACT-01 | 2026-06-10 | Material | MAT-009 | Paint | VEN-004 | 10.48 | Litre | 2298.81 | 2387.83 | 429.81 | 2817.64 | Paid | Low
EXP-03794 | PRJ-004 | PRJ-004-ACT-03 | 2026-06-10 | Labour | LAB-005 | Plumber | VEN-009 | 5 | Worker | 7738.92 | 7353.74 | 1323.67 | 8677.41 | Paid | Medium
EXP-03795 | PRJ-004 | PRJ-004-ACT-07 | 2026-06-15 | Contractor | CON-002 | Electrical Contract | VEN-004 | 1 | Contract | 115641.99 | 118107.08 | 21259.27 | 139366.35 | Paid | Low
EXP-03796 | PRJ-004 | PRJ-004-ACT-03 | 2026-06-15 | Material | MAT-002 | Steel | VEN-009 | 60.91 | Ton | 776473.34 | 776050.79 | 139689.14 | 915739.93 | Pending | High
EXP-03797 | PRJ-004 | PRJ-004-ACT-07 | 2026-06-15 | Contractor | CON-002 | Electrical Contract | VEN-009 | 1 | Contract | 280319.32 | 259833.96 | 46770.11 | 306604.07 | Paid | Medium
EXP-03798 | PRJ-004 | PRJ-004-ACT-04 | 2026-06-15 | Material | MAT-005 | Bricks | VEN-003 | 4.61 | Piece | 44.15 | 47.3 | 8.51 | 55.81 | Partially Paid | Low
EXP-03799 | PRJ-004 | PRJ-004-ACT-09 | 2026-06-15 | Contractor | CON-004 | Finishing Contract | VEN-011 | 1 | Contract | 313585.25 | 309849.3 | 55772.87 | 365622.17 | Paid | Low
EXP-03800 | PRJ-004 | PRJ-004-ACT-10 | 2026-06-15 | Labour | LAB-003 | Carpenter | VEN-011 | 33 | Worker | 52450.18 | 50388.43 | 9069.92 | 59458.35 | Paid | Medium
EXP-03801 | PRJ-004 | PRJ-004-ACT-03 | 2026-06-15 | Labour | LAB-006 | Painter | VEN-004 | 29 | Worker | 50111.95 | 49775.2 | 8959.54 | 58734.74 | Paid | Medium
EXP-03802 | PRJ-004 | PRJ-004-ACT-02 | 2026-06-15 | Material | MAT-008 | Tiles | VEN-009 | 2.83 | Sq Ft | 199.13 | 197.59 | 35.57 | 233.16 | Paid | Low
EXP-03803 | PRJ-004 | PRJ-004-ACT-05 | 2026-06-15 | Material | MAT-005 | Bricks | VEN-009 | 35.06 | Piece | 300.68 | 304.53 | 54.82 | 359.35 | Paid | Low
EXP-03804 | PRJ-004 | PRJ-004-ACT-09 | 2026-06-20 | Contractor | CON-004 | Finishing Contract | VEN-011 | 1 | Contract | 230452.97 | 225440.79 | 40579.34 | 266020.13 | Partially Paid | Medium
EXP-03805 | PRJ-004 | PRJ-004-ACT-02 | 2026-06-20 | Material | MAT-004 | Aggregate | VEN-009 | 32.98 | Ton | 51365.23 | 52843.46 | 9511.82 | 62355.28 | Paid | Low
EXP-03806 | PRJ-004 | PRJ-004-ACT-08 | 2026-06-20 | Material | MAT-001 | Cement | VEN-003 | 8.16 | Bag | 3987.84 | 4329.97 | 779.39 | 5109.36 | Paid | Medium
EXP-03807 | PRJ-004 | PRJ-004-ACT-06 | 2026-06-20 | Material | MAT-010 | Glass | VEN-004 | 27.23 | Sq Ft | 4292.38 | 4198.19 | 755.67 | 4953.86 | Paid | Medium
EXP-03808 | PRJ-004 | PRJ-004-ACT-10 | 2026-06-20 | Contractor | CON-001 | Civil Structure Contract | VEN-004 | 1 | Contract | 271070.21 | 289669.3 | 52140.47 | 341809.77 | Paid | Medium
EXP-03809 | PRJ-004 | PRJ-004-ACT-08 | 2026-06-20 | Labour | LAB-001 | Mason | VEN-011 | 22 | Worker | 22006.02 | 20901.44 | 3762.26 | 24663.7 | Paid | Low
EXP-03810 | PRJ-004 | PRJ-004-ACT-08 | 2026-06-20 | Material | MAT-009 | Paint | VEN-004 | 6 | Litre | 1333.57 | 1314.93 | 236.69 | 1551.62 | Paid | Low
EXP-03811 | PRJ-004 | PRJ-004-ACT-09 | 2026-06-20 | Equipment | EQ-002 | Excavator | VEN-003 | 5 | Day | 77525.86 | 75796.22 | 13643.32 | 89439.54 | Paid | Medium
EXP-03812 | PRJ-004 | PRJ-004-ACT-06 | 2026-06-25 | Labour | LAB-006 | Painter | VEN-003 | 5 | Worker | 8570.69 | 8408.73 | 1513.57 | 9922.3 | Paid | Medium
EXP-03813 | PRJ-004 | PRJ-004-ACT-05 | 2026-06-25 | Material | MAT-002 | Steel | VEN-003 | 6.54 | Ton | 471602.84 | 464946.76 | 83690.42 | 548637.18 | Paid | High
EXP-03814 | PRJ-004 | PRJ-004-ACT-01 | 2026-06-25 | Material | MAT-004 | Aggregate | VEN-003 | 11.51 | Ton | 20678.25 | 19534.45 | 3516.2 | 23050.65 | Paid | Low
EXP-03815 | PRJ-004 | PRJ-004-ACT-09 | 2026-06-25 | Labour | LAB-005 | Plumber | VEN-009 | 15 | Worker | 12104.12 | 11981.45 | 2156.66 | 14138.11 | Paid | Medium
EXP-03816 | PRJ-004 | PRJ-004-ACT-04 | 2026-06-25 | Contractor | CON-002 | Electrical Contract | VEN-009 | 1 | Contract | 93605.88 | 92865.35 | 16715.76 | 109581.11 | Pending | Low
EXP-03817 | PRJ-004 | PRJ-004-ACT-10 | 2026-06-25 | Material | MAT-010 | Glass | VEN-004 | 21.19 | Sq Ft | 3858.86 | 3845.4 | 692.17 | 4537.57 | Paid | Medium
EXP-03818 | PRJ-004 | PRJ-004-ACT-08 | 2026-06-25 | Labour | LAB-006 | Painter | VEN-004 | 17 | Worker | 24401.62 | 23095.03 | 4157.11 | 27252.14 | Partially Paid | Low
EXP-03819 | PRJ-004 | PRJ-004-ACT-08 | 2026-06-25 | Material | MAT-008 | Tiles | VEN-004 | 10.18 | Sq Ft | 813.01 | 826.43 | 148.76 | 975.19 | Pending | Low
EXP-03820 | PRJ-004 | PRJ-004-ACT-02 | 2026-06-30 | Contractor | CON-003 | Plumbing Contract | VEN-009 | 1 | Contract | 252893.49 | 246010.99 | 44281.98 | 290292.97 | Paid | Medium
EXP-03821 | PRJ-004 | PRJ-004-ACT-04 | 2026-06-30 | Equipment | EQ-003 | Concrete Mixer | VEN-011 | 4 | Day | 15465.95 | 16594.8 | 2987.06 | 19581.86 | Paid | Low
EXP-03822 | PRJ-004 | PRJ-004-ACT-01 | 2026-06-30 | Labour | LAB-006 | Painter | VEN-003 | 31 | Worker | 47512.35 | 47275.16 | 8509.53 | 55784.69 | Paid | Medium
EXP-03823 | PRJ-004 | PRJ-004-ACT-05 | 2026-06-30 | Other | OTH-001 | Transport | VEN-011 | 1 | Lot | 8420.44 | 7992.75 | 1438.69 | 9431.44 | Paid | Low
EXP-03824 | PRJ-004 | PRJ-004-ACT-04 | 2026-06-30 | Labour | LAB-005 | Plumber | VEN-003 | 11 | Worker | 16618.49 | 16687.89 | 3003.82 | 19691.71 | Partially Paid | Medium
EXP-03825 | PRJ-004 | PRJ-004-ACT-09 | 2026-06-30 | Contractor | CON-004 | Finishing Contract | VEN-011 | 1 | Contract | 365573.6 | 351923.78 | 63346.28 | 415270.06 | Paid | Low
EXP-03826 | PRJ-004 | PRJ-004-ACT-07 | 2026-06-30 | Material | MAT-003 | Sand | VEN-009 | 15.91 | Ton | 29570.06 | 31566.69 | 5682 | 37248.69 | Pending | Low
EXP-03827 | PRJ-004 | PRJ-004-ACT-02 | 2026-06-30 | Material | MAT-007 | PVC Pipe | VEN-009 | 8.49 | Meter | 1123.61 | 1158.47 | 208.52 | 1366.99 | Paid | Medium
EXP-03828 | PRJ-004 | PRJ-004-ACT-02 | 2026-06-30 | Contractor | CON-004 | Finishing Contract | VEN-003 | 1 | Contract | 172551.26 | 179977.24 | 32395.9 | 212373.14 | Paid | Low
EXP-03829 | PRJ-004 | PRJ-004-ACT-08 | 2026-06-30 | Labour | LAB-006 | Painter | VEN-004 | 16 | Worker | 15489.19 | 15716.91 | 2829.04 | 18545.95 | Paid | Medium
EXP-03830 | PRJ-004 | PRJ-004-ACT-05 | 2026-07-05 | Material | MAT-009 | Paint | VEN-003 | 8.15 | Litre | 1438.51 | 1515.22 | 272.74 | 1787.96 | Paid | Medium
EXP-03831 | PRJ-004 | PRJ-004-ACT-04 | 2026-07-05 | Material | MAT-009 | Paint | VEN-011 | 7.66 | Litre | 1492.68 | 1606.47 | 289.16 | 1895.63 | Paid | Low
EXP-03832 | PRJ-004 | PRJ-004-ACT-09 | 2026-07-05 | Material | MAT-001 | Cement | VEN-011 | 5.97 | Bag | 3346.64 | 3551.46 | 639.26 | 4190.72 | Paid | Low
EXP-03833 | PRJ-004 | PRJ-004-ACT-02 | 2026-07-05 | Contractor | CON-004 | Finishing Contract | VEN-003 | 1 | Contract | 213676.03 | 219767.91 | 39558.22 | 259326.13 | Paid | Low
EXP-03834 | PRJ-004 | PRJ-004-ACT-04 | 2026-07-05 | Material | MAT-006 | Electrical Cable | VEN-004 | 16.42 | Meter | 1201.73 | 1287.58 | 231.76 | 1519.34 | Partially Paid | Low
EXP-03835 | PRJ-004 | PRJ-004-ACT-08 | 2026-07-05 | Material | MAT-003 | Sand | VEN-003 | 18.69 | Ton | 34317.73 | 31886.78 | 5739.62 | 37626.4 | Partially Paid | Medium
EXP-03836 | PRJ-004 | PRJ-004-ACT-01 | 2026-07-05 | Material | MAT-001 | Cement | VEN-004 | 4.73 | Bag | 2557.28 | 2441.28 | 439.43 | 2880.71 | Paid | High
EXP-03837 | PRJ-004 | PRJ-004-ACT-08 | 2026-07-05 | Labour | LAB-004 | Electrician | VEN-003 | 24 | Worker | 19205.76 | 18399.84 | 3311.97 | 21711.81 | Paid | Low
EXP-03838 | PRJ-004 | PRJ-004-ACT-10 | 2026-07-05 | Labour | LAB-004 | Electrician | VEN-011 | 13 | Worker | 10985.33 | 11175.02 | 2011.5 | 13186.52 | Pending | Low
EXP-03839 | PRJ-004 | PRJ-004-ACT-06 | 2026-07-10 | Material | MAT-004 | Aggregate | VEN-009 | 6.06 | Ton | 9006.63 | 8937.28 | 1608.71 | 10545.99 | Partially Paid | Medium
EXP-03840 | PRJ-004 | PRJ-004-ACT-05 | 2026-07-10 | Contractor | CON-001 | Civil Structure Contract | VEN-009 | 1 | Contract | 342099.18 | 363650.03 | 65457.01 | 429107.04 | Paid | Low
EXP-03841 | PRJ-004 | PRJ-004-ACT-08 | 2026-07-10 | Labour | LAB-003 | Carpenter | VEN-009 | 5 | Worker | 4741.33 | 4625.58 | 832.6 | 5458.18 | Paid | Medium
EXP-03842 | PRJ-004 | PRJ-004-ACT-08 | 2026-07-10 | Contractor | CON-002 | Electrical Contract | VEN-009 | 1 | Contract | 238228.66 | 222169.38 | 39990.49 | 262159.87 | Partially Paid | Medium
EXP-03843 | PRJ-004 | PRJ-004-ACT-03 | 2026-07-10 | Material | MAT-005 | Bricks | VEN-011 | 14.74 | Piece | 122.85 | 122.37 | 22.03 | 144.4 | Paid | Low
EXP-03844 | PRJ-004 | PRJ-004-ACT-10 | 2026-07-10 | Material | MAT-001 | Cement | VEN-009 | 20.85 | Bag | 10145.61 | 9485.04 | 1707.31 | 11192.35 | Paid | Low
EXP-03845 | PRJ-004 | PRJ-004-ACT-03 | 2026-07-10 | Material | MAT-006 | Electrical Cable | VEN-009 | 12.49 | Meter | 1047.17 | 1015.41 | 182.77 | 1198.18 | Paid | Low
EXP-03846 | PRJ-004 | PRJ-004-ACT-03 | 2026-07-10 | Labour | LAB-005 | Plumber | VEN-003 | 4 | Worker | 2737.19 | 2832.13 | 509.78 | 3341.91 | Partially Paid | Low
EXP-03847 | PRJ-004 | PRJ-004-ACT-06 | 2026-07-15 | Contractor | CON-001 | Civil Structure Contract | VEN-004 | 1 | Contract | 438530.09 | 448926.38 | 80806.75 | 529733.13 | Paid | Low
EXP-03848 | PRJ-004 | PRJ-004-ACT-09 | 2026-07-15 | Equipment | EQ-003 | Concrete Mixer | VEN-009 | 7 | Day | 32550.91 | 30793.6 | 5542.85 | 36336.45 | Paid | Low
EXP-03849 | PRJ-004 | PRJ-004-ACT-08 | 2026-07-15 | Labour | LAB-003 | Carpenter | VEN-011 | 7 | Worker | 7981.92 | 8299.74 | 1493.95 | 9793.69 | Paid | Medium
EXP-03850 | PRJ-004 | PRJ-004-ACT-01 | 2026-07-15 | Material | MAT-007 | PVC Pipe | VEN-003 | 1 | Meter | 119.01 | 128.92 | 23.21 | 152.13 | Paid | Low
EXP-03851 | PRJ-004 | PRJ-004-ACT-01 | 2026-07-15 | Labour | LAB-006 | Painter | VEN-004 | 16 | Worker | 14632.03 | 14429.2 | 2597.26 | 17026.46 | Paid | Medium
EXP-03852 | PRJ-004 | PRJ-004-ACT-04 | 2026-07-15 | Material | MAT-002 | Steel | VEN-009 | 27.63 | Ton | 1702475.39 | 1808277.78 | 325490 | 2133767.78 | Paid | Low
EXP-03853 | PRJ-004 | PRJ-004-ACT-07 | 2026-07-15 | Material | MAT-006 | Electrical Cable | VEN-004 | 16.45 | Meter | 1416.98 | 1465.94 | 263.87 | 1729.81 | Pending | Low
EXP-03854 | PRJ-004 | PRJ-004-ACT-02 | 2026-07-15 | Labour | LAB-003 | Carpenter | VEN-009 | 34 | Worker | 31799.76 | 30467.44 | 5484.14 | 35951.58 | Paid | Low
EXP-03855 | PRJ-004 | PRJ-004-ACT-07 | 2026-07-15 | Labour | LAB-006 | Painter | VEN-011 | 32 | Worker | 47498.54 | 44072.22 | 7933 | 52005.22 | Paid | High
EXP-03856 | PRJ-004 | PRJ-004-ACT-10 | 2026-07-20 | Material | MAT-010 | Glass | VEN-009 | 4.8 | Sq Ft | 749.53 | 770.8 | 138.74 | 909.54 | Paid | Medium
EXP-03857 | PRJ-004 | PRJ-004-ACT-05 | 2026-07-20 | Material | MAT-008 | Tiles | VEN-011 | 8.56 | Sq Ft | 667.9 | 667.18 | 120.09 | 787.27 | Paid | High
EXP-03858 | PRJ-004 | PRJ-004-ACT-02 | 2026-07-20 | Labour | LAB-002 | Helper | VEN-011 | 23 | Worker | 31725.81 | 30263.75 | 5447.47 | 35711.22 | Paid | Low
EXP-03859 | PRJ-004 | PRJ-004-ACT-06 | 2026-07-20 | Equipment | EQ-003 | Concrete Mixer | VEN-011 | 4 | Day | 16795.3 | 17315.14 | 3116.73 | 20431.87 | Paid | Low
EXP-03860 | PRJ-004 | PRJ-004-ACT-09 | 2026-07-20 | Material | MAT-004 | Aggregate | VEN-009 | 20.04 | Ton | 28914.94 | 29764.49 | 5357.61 | 35122.1 | Paid | Low
EXP-03861 | PRJ-004 | PRJ-004-ACT-09 | 2026-07-20 | Material | MAT-004 | Aggregate | VEN-004 | 6.61 | Ton | 11641.15 | 11176.95 | 2011.85 | 13188.8 | Paid | Low
EXP-03862 | PRJ-004 | PRJ-004-ACT-01 | 2026-07-20 | Material | MAT-008 | Tiles | VEN-011 | 15.58 | Sq Ft | 1411.72 | 1309.47 | 235.7 | 1545.17 | Partially Paid | Low
EXP-03863 | PRJ-004 | PRJ-004-ACT-02 | 2026-07-25 | Contractor | CON-003 | Plumbing Contract | VEN-011 | 1 | Contract | 417585.54 | 389992.2 | 70198.6 | 460190.8 | Paid | Low
EXP-03864 | PRJ-004 | PRJ-004-ACT-05 | 2026-07-25 | Material | MAT-003 | Sand | VEN-004 | 8.98 | Ton | 14551.51 | 13983.01 | 2516.94 | 16499.95 | Paid | Low
EXP-03865 | PRJ-004 | PRJ-004-ACT-03 | 2026-07-25 | Material | MAT-010 | Glass | VEN-009 | 13.89 | Sq Ft | 1960.99 | 1943.87 | 349.9 | 2293.77 | Paid | Low
EXP-03866 | PRJ-004 | PRJ-004-ACT-01 | 2026-07-25 | Material | MAT-010 | Glass | VEN-011 | 4.27 | Sq Ft | 634.46 | 652.24 | 117.4 | 769.64 | Paid | Low
EXP-03867 | PRJ-004 | PRJ-004-ACT-03 | 2026-07-25 | Contractor | CON-004 | Finishing Contract | VEN-011 | 1 | Contract | 306438.09 | 298422.8 | 53716.1 | 352138.9 | Partially Paid | High
EXP-03868 | PRJ-004 | PRJ-004-ACT-09 | 2026-07-25 | Contractor | CON-002 | Electrical Contract | VEN-003 | 1 | Contract | 403858.84 | 419106.71 | 75439.21 | 494545.92 | Partially Paid | High
EXP-03869 | PRJ-004 | PRJ-004-ACT-05 | 2026-07-25 | Contractor | CON-002 | Electrical Contract | VEN-009 | 1 | Contract | 142765.61 | 144068.88 | 25932.4 | 170001.28 | Paid | Low
EXP-03870 | PRJ-004 | PRJ-004-ACT-01 | 2026-07-25 | Contractor | CON-004 | Finishing Contract | VEN-004 | 1 | Contract | 103095.71 | 102709.55 | 18487.72 | 121197.27 | Paid | Low
EXP-03871 | PRJ-004 | PRJ-004-ACT-02 | 2026-07-25 | Material | MAT-005 | Bricks | VEN-011 | 13.65 | Piece | 117.58 | 122.81 | 22.11 | 144.92 | Paid | Low
EXP-03872 | PRJ-004 | PRJ-004-ACT-09 | 2026-07-30 | Other | OTH-001 | Transport | VEN-009 | 1 | Lot | 16797.86 | 16603.02 | 2988.54 | 19591.56 | Pending | Medium
EXP-03873 | PRJ-004 | PRJ-004-ACT-02 | 2026-07-30 | Contractor | CON-002 | Electrical Contract | VEN-003 | 1 | Contract | 290434.16 | 304196.59 | 54755.39 | 358951.98 | Paid | Low
EXP-03874 | PRJ-004 | PRJ-004-ACT-03 | 2026-07-30 | Material | MAT-004 | Aggregate | VEN-011 | 13.93 | Ton | 21854.2 | 21637.49 | 3894.75 | 25532.24 | Paid | Low
EXP-03875 | PRJ-004 | PRJ-004-ACT-05 | 2026-07-30 | Contractor | CON-003 | Plumbing Contract | VEN-003 | 1 | Contract | 132883.29 | 142370.62 | 25626.71 | 167997.33 | Paid | Medium
EXP-03876 | PRJ-004 | PRJ-004-ACT-04 | 2026-07-30 | Contractor | CON-002 | Electrical Contract | VEN-011 | 1 | Contract | 200637.88 | 211044.76 | 37988.06 | 249032.82 | Paid | Medium
EXP-03877 | PRJ-004 | PRJ-004-ACT-05 | 2026-07-30 | Equipment | EQ-004 | Scaffolding | VEN-003 | 2 | Day | 5548.77 | 5217.97 | 939.23 | 6157.2 | Paid | High
EXP-03878 | PRJ-004 | PRJ-004-ACT-01 | 2026-07-30 | Labour | LAB-005 | Plumber | VEN-004 | 14 | Worker | 9979.8 | 9733.96 | 1752.11 | 11486.07 | Partially Paid | Low
EXP-03879 | PRJ-004 | PRJ-004-ACT-02 | 2026-08-04 | Contractor | CON-002 | Electrical Contract | VEN-004 | 1 | Contract | 219663.16 | 229477.11 | 41305.88 | 270782.99 | Paid | Low
EXP-03880 | PRJ-004 | PRJ-004-ACT-04 | 2026-08-04 | Contractor | CON-002 | Electrical Contract | VEN-011 | 1 | Contract | 173678.94 | 167199.04 | 30095.83 | 197294.87 | Paid | Medium
EXP-03881 | PRJ-004 | PRJ-004-ACT-07 | 2026-08-04 | Material | MAT-005 | Bricks | VEN-011 | 3.46 | Piece | 34.07 | 31.55 | 5.68 | 37.23 | Partially Paid | Low
EXP-03882 | PRJ-004 | PRJ-004-ACT-07 | 2026-08-04 | Material | MAT-002 | Steel | VEN-009 | 14.31 | Ton | 833525.8 | 897922.29 | 161626.01 | 1059548.3 | Paid | Low
EXP-03883 | PRJ-004 | PRJ-004-ACT-02 | 2026-08-04 | Material | MAT-007 | PVC Pipe | VEN-009 | 7.13 | Meter | 783.21 | 766.14 | 137.91 | 904.05 | Paid | Low
EXP-03884 | PRJ-004 | PRJ-004-ACT-10 | 2026-08-04 | Equipment | EQ-003 | Concrete Mixer | VEN-011 | 3 | Day | 13958.01 | 13794.8 | 2483.06 | 16277.86 | Paid | Low
EXP-03885 | PRJ-004 | PRJ-004-ACT-05 | 2026-08-04 | Other | OTH-001 | Site Office | VEN-011 | 1 | Lot | 6358.72 | 6570.9 | 1182.76 | 7753.66 | Paid | High
EXP-03886 | PRJ-004 | PRJ-004-ACT-10 | 2026-08-04 | Labour | LAB-006 | Painter | VEN-011 | 10 | Worker | 11798.45 | 12310.08 | 2215.81 | 14525.89 | Paid | Low
EXP-03887 | PRJ-004 | PRJ-004-ACT-09 | 2026-08-09 | Material | MAT-006 | Electrical Cable | VEN-011 | 14.01 | Meter | 1196.74 | 1204.86 | 216.87 | 1421.73 | Paid | Low
EXP-03888 | PRJ-004 | PRJ-004-ACT-06 | 2026-08-09 | Equipment | EQ-001 | Crane | VEN-004 | 7 | Day | 123280.55 | 130543.49 | 23497.83 | 154041.32 | Paid | Low
EXP-03889 | PRJ-004 | PRJ-004-ACT-04 | 2026-08-09 | Material | MAT-001 | Cement | VEN-011 | 3.31 | Bag | 1652.53 | 1549.32 | 278.88 | 1828.2 | Partially Paid | High
EXP-03890 | PRJ-004 | PRJ-004-ACT-03 | 2026-08-09 | Material | MAT-009 | Paint | VEN-004 | 2.61 | Litre | 569.13 | 540.59 | 97.31 | 637.9 | Paid | Low
EXP-03891 | PRJ-004 | PRJ-004-ACT-07 | 2026-08-09 | Material | MAT-002 | Steel | VEN-003 | 3.17 | Ton | 213648.86 | 203804.92 | 36684.89 | 240489.81 | Paid | Medium
EXP-03892 | PRJ-004 | PRJ-004-ACT-01 | 2026-08-09 | Material | MAT-005 | Bricks | VEN-004 | 5.58 | Piece | 58.91 | 54.78 | 9.86 | 64.64 | Paid | High
EXP-03893 | PRJ-004 | PRJ-004-ACT-06 | 2026-08-09 | Material | MAT-010 | Glass | VEN-003 | 10.95 | Sq Ft | 1894.78 | 2005.15 | 360.93 | 2366.08 | Paid | Low
EXP-03894 | PRJ-004 | PRJ-004-ACT-09 | 2026-08-09 | Material | MAT-007 | PVC Pipe | VEN-004 | 15.61 | Meter | 2154.17 | 2050.09 | 369.02 | 2419.11 | Paid | Medium
EXP-03895 | PRJ-004 | PRJ-004-ACT-01 | 2026-08-14 | Labour | LAB-004 | Electrician | VEN-009 | 24 | Worker | 33122.26 | 31021.36 | 5583.84 | 36605.2 | Paid | Low
EXP-03896 | PRJ-004 | PRJ-004-ACT-06 | 2026-08-14 | Material | MAT-008 | Tiles | VEN-009 | 4.09 | Sq Ft | 335.69 | 321.37 | 57.85 | 379.22 | Paid | Low
EXP-03897 | PRJ-004 | PRJ-004-ACT-04 | 2026-08-14 | Other | OTH-001 | Site Office | VEN-011 | 1 | Lot | 63545.45 | 66612.82 | 11990.31 | 78603.13 | Paid | Low
EXP-03898 | PRJ-004 | PRJ-004-ACT-08 | 2026-08-14 | Material | MAT-006 | Electrical Cable | VEN-004 | 15.45 | Meter | 1102.24 | 1158.27 | 208.49 | 1366.76 | Paid | Medium
EXP-03899 | PRJ-004 | PRJ-004-ACT-06 | 2026-08-14 | Contractor | CON-002 | Electrical Contract | VEN-009 | 1 | Contract | 401992.45 | 400331.12 | 72059.6 | 472390.72 | Paid | Medium
EXP-03900 | PRJ-004 | PRJ-004-ACT-01 | 2026-08-14 | Material | MAT-002 | Steel | VEN-004 | 4.39 | Ton | 284727.03 | 298620.91 | 53751.76 | 352372.67 | Partially Paid | Medium
EXP-03901 | PRJ-004 | PRJ-004-ACT-05 | 2026-08-14 | Contractor | CON-004 | Finishing Contract | VEN-011 | 1 | Contract | 427426.9 | 404057.94 | 72730.43 | 476788.37 | Paid | Low
EXP-03902 | PRJ-004 | PRJ-004-ACT-07 | 2026-08-19 | Labour | LAB-006 | Painter | VEN-004 | 26 | Worker | 33865.79 | 36761.07 | 6616.99 | 43378.06 | Paid | Medium
EXP-03903 | PRJ-004 | PRJ-004-ACT-02 | 2026-08-19 | Material | MAT-001 | Cement | VEN-003 | 5.3 | Bag | 2873.68 | 2838.87 | 511 | 3349.87 | Paid | Low
EXP-03904 | PRJ-004 | PRJ-004-ACT-01 | 2026-08-19 | Contractor | CON-004 | Finishing Contract | VEN-011 | 1 | Contract | 205580.59 | 218954.86 | 39411.87 | 258366.73 | Paid | High
EXP-03905 | PRJ-004 | PRJ-004-ACT-03 | 2026-08-19 | Labour | LAB-001 | Mason | VEN-009 | 17 | Worker | 12960.67 | 12479.47 | 2246.3 | 14725.77 | Pending | Medium
EXP-03906 | PRJ-004 | PRJ-004-ACT-08 | 2026-08-19 | Contractor | CON-003 | Plumbing Contract | VEN-003 | 1 | Contract | 91471.2 | 97596.48 | 17567.37 | 115163.85 | Paid | Low
EXP-03907 | PRJ-004 | PRJ-004-ACT-01 | 2026-08-19 | Material | MAT-009 | Paint | VEN-003 | 15.95 | Litre | 2984.35 | 3178.61 | 572.15 | 3750.76 | Paid | Low
EXP-03908 | PRJ-004 | PRJ-004-ACT-09 | 2026-08-19 | Contractor | CON-004 | Finishing Contract | VEN-009 | 1 | Contract | 167779.64 | 155379.59 | 27968.33 | 183347.92 | Paid | Low
EXP-03909 | PRJ-004 | PRJ-004-ACT-09 | 2026-08-19 | Material | MAT-003 | Sand | VEN-004 | 7.26 | Ton | 13824.42 | 14308.44 | 2575.52 | 16883.96 | Pending | Low
EXP-03910 | PRJ-004 | PRJ-004-ACT-10 | 2026-08-24 | Contractor | CON-003 | Plumbing Contract | VEN-011 | 1 | Contract | 355011.14 | 350684.55 | 63123.22 | 413807.77 | Paid | Low
EXP-03911 | PRJ-004 | PRJ-004-ACT-08 | 2026-08-24 | Labour | LAB-002 | Helper | VEN-004 | 25 | Worker | 24355.2 | 25633.75 | 4614.07 | 30247.82 | Paid | Medium
EXP-03912 | PRJ-004 | PRJ-004-ACT-04 | 2026-08-24 | Labour | LAB-006 | Painter | VEN-003 | 12 | Worker | 14998.55 | 14330.49 | 2579.49 | 16909.98 | Pending | Low
EXP-03913 | PRJ-004 | PRJ-004-ACT-09 | 2026-08-24 | Material | MAT-003 | Sand | VEN-011 | 8.33 | Ton | 15787.04 | 15265.79 | 2747.84 | 18013.63 | Paid | Low
EXP-03914 | PRJ-004 | PRJ-004-ACT-10 | 2026-08-24 | Material | MAT-002 | Steel | VEN-004 | 23.62 | Ton | 1560696.25 | 1658431.6 | 298517.69 | 1956949.29 | Paid | Low
EXP-03915 | PRJ-004 | PRJ-004-ACT-08 | 2026-08-24 | Contractor | CON-001 | Civil Structure Contract | VEN-004 | 1 | Contract | 214758.94 | 199888.97 | 35980.01 | 235868.98 | Paid | Low
EXP-03916 | PRJ-004 | PRJ-004-ACT-07 | 2026-08-29 | Material | MAT-004 | Aggregate | VEN-009 | 18.57 | Ton | 27795 | 28828.92 | 5189.21 | 34018.13 | Paid | Low
EXP-03917 | PRJ-004 | PRJ-004-ACT-01 | 2026-08-29 | Material | MAT-003 | Sand | VEN-003 | 2.96 | Ton | 5728.81 | 5608.44 | 1009.52 | 6617.96 | Paid | Low
EXP-03918 | PRJ-004 | PRJ-004-ACT-06 | 2026-08-29 | Labour | LAB-004 | Electrician | VEN-003 | 32 | Worker | 48279.21 | 50282.55 | 9050.86 | 59333.41 | Paid | Low
EXP-03919 | PRJ-004 | PRJ-004-ACT-08 | 2026-08-29 | Contractor | CON-003 | Plumbing Contract | VEN-009 | 1 | Contract | 414875.08 | 416225.92 | 74920.67 | 491146.59 | Paid | Low
EXP-03920 | PRJ-004 | PRJ-004-ACT-04 | 2026-08-29 | Labour | LAB-006 | Painter | VEN-004 | 7 | Worker | 12392.11 | 11974.04 | 2155.33 | 14129.37 | Paid | Medium
EXP-03921 | PRJ-004 | PRJ-004-ACT-10 | 2026-08-29 | Equipment | EQ-002 | Excavator | VEN-004 | 1 | Day | 14184.21 | 13307.7 | 2395.39 | 15703.09 | Paid | High
EXP-03922 | PRJ-004 | PRJ-004-ACT-01 | 2026-08-29 | Labour | LAB-005 | Plumber | VEN-011 | 19 | Worker | 26621.73 | 28901.12 | 5202.2 | 34103.32 | Paid | Medium
EXP-03923 | PRJ-004 | PRJ-004-ACT-01 | 2026-08-29 | Contractor | CON-003 | Plumbing Contract | VEN-009 | 1 | Contract | 90493.37 | 96891.48 | 17440.47 | 114331.95 | Partially Paid | Low
EXP-03924 | PRJ-004 | PRJ-004-ACT-10 | 2026-08-29 | Material | MAT-004 | Aggregate | VEN-004 | 9.6 | Ton | 16096.61 | 15451.64 | 2781.3 | 18232.94 | Paid | Medium
EXP-03925 | PRJ-004 | PRJ-004-ACT-10 | 2026-08-29 | Material | MAT-007 | PVC Pipe | VEN-011 | 6.56 | Meter | 637.36 | 691.33 | 124.44 | 815.77 | Partially Paid | Medium
EXP-03926 | PRJ-005 | PRJ-005-ACT-01 | 2024-10-01 | Contractor | CON-001 | Civil Structure Contract | VEN-008 | 1 | Contract | 468030.68 | 437947.85 | 78830.61 | 516778.46 | Paid | Medium
EXP-03927 | PRJ-005 | PRJ-005-ACT-10 | 2024-10-01 | Equipment | EQ-004 | Scaffolding | VEN-012 | 5 | Day | 11390.75 | 11834.34 | 2130.18 | 13964.52 | Partially Paid | Medium
EXP-03928 | PRJ-005 | PRJ-005-ACT-03 | 2024-10-01 | Labour | LAB-003 | Carpenter | VEN-012 | 10 | Worker | 7057.35 | 7077.06 | 1273.87 | 8350.93 | Partially Paid | Medium
EXP-03929 | PRJ-005 | PRJ-005-ACT-06 | 2024-10-01 | Material | MAT-001 | Cement | VEN-005 | 12.93 | Bag | 6176.39 | 6572.47 | 1183.04 | 7755.51 | Partially Paid | Low
EXP-03930 | PRJ-005 | PRJ-005-ACT-03 | 2024-10-01 | Material | MAT-003 | Sand | VEN-008 | 18.7 | Ton | 27980.16 | 29061.51 | 5231.07 | 34292.58 | Paid | High
EXP-03931 | PRJ-005 | PRJ-005-ACT-10 | 2024-10-01 | Contractor | CON-001 | Civil Structure Contract | VEN-008 | 1 | Contract | 386158.43 | 406438.43 | 73158.92 | 479597.35 | Paid | Low
EXP-03932 | PRJ-005 | PRJ-005-ACT-02 | 2024-10-01 | Labour | LAB-005 | Plumber | VEN-008 | 11 | Worker | 15698.85 | 14602.01 | 2628.36 | 17230.37 | Paid | Low
EXP-03933 | PRJ-005 | PRJ-005-ACT-03 | 2024-10-06 | Contractor | CON-002 | Electrical Contract | VEN-005 | 1 | Contract | 306186.72 | 298917.82 | 53805.21 | 352723.03 | Paid | Low
EXP-03934 | PRJ-005 | PRJ-005-ACT-02 | 2024-10-06 | Material | MAT-006 | Electrical Cable | VEN-008 | 5.4 | Meter | 420.39 | 449.45 | 80.9 | 530.35 | Paid | Low
EXP-03935 | PRJ-005 | PRJ-005-ACT-03 | 2024-10-06 | Labour | LAB-002 | Helper | VEN-008 | 26 | Worker | 33937.16 | 34695.51 | 6245.19 | 40940.7 | Paid | Medium
EXP-03936 | PRJ-005 | PRJ-005-ACT-01 | 2024-10-06 | Contractor | CON-003 | Plumbing Contract | VEN-008 | 1 | Contract | 103680.26 | 103219.45 | 18579.5 | 121798.95 | Partially Paid | Low
EXP-03937 | PRJ-005 | PRJ-005-ACT-01 | 2024-10-06 | Labour | LAB-006 | Painter | VEN-005 | 18 | Worker | 12809.61 | 12019.71 | 2163.55 | 14183.26 | Paid | Low
EXP-03938 | PRJ-005 | PRJ-005-ACT-05 | 2024-10-06 | Contractor | CON-004 | Finishing Contract | VEN-012 | 1 | Contract | 204196.43 | 190881.36 | 34358.64 | 225240 | Paid | High
EXP-03939 | PRJ-005 | PRJ-005-ACT-05 | 2024-10-06 | Contractor | CON-001 | Civil Structure Contract | VEN-012 | 1 | Contract | 134466.14 | 130454.45 | 23481.8 | 153936.25 | Paid | Medium
EXP-03940 | PRJ-005 | PRJ-005-ACT-07 | 2024-10-06 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 197244.09 | 200834.03 | 36150.13 | 236984.16 | Paid | Low
EXP-03941 | PRJ-005 | PRJ-005-ACT-10 | 2024-10-06 | Contractor | CON-002 | Electrical Contract | VEN-005 | 1 | Contract | 224461.96 | 213967.39 | 38514.13 | 252481.52 | Paid | Low
EXP-03942 | PRJ-005 | PRJ-005-ACT-09 | 2024-10-06 | Contractor | CON-002 | Electrical Contract | VEN-008 | 1 | Contract | 429241.58 | 441804.31 | 79524.78 | 521329.09 | Paid | Low
EXP-03943 | PRJ-005 | PRJ-005-ACT-08 | 2024-10-11 | Labour | LAB-006 | Painter | VEN-005 | 27 | Worker | 40068.64 | 41760.95 | 7516.97 | 49277.92 | Paid | High
EXP-03944 | PRJ-005 | PRJ-005-ACT-04 | 2024-10-11 | Contractor | CON-004 | Finishing Contract | VEN-012 | 1 | Contract | 80318.06 | 80007.16 | 14401.29 | 94408.45 | Paid | Medium
EXP-03945 | PRJ-005 | PRJ-005-ACT-06 | 2024-10-11 | Material | MAT-004 | Aggregate | VEN-008 | 5.31 | Ton | 6878.88 | 6825.72 | 1228.63 | 8054.35 | Paid | Low
EXP-03946 | PRJ-005 | PRJ-005-ACT-07 | 2024-10-11 | Equipment | EQ-004 | Scaffolding | VEN-012 | 7 | Day | 17740.14 | 18304.32 | 3294.78 | 21599.1 | Paid | Medium
EXP-03947 | PRJ-005 | PRJ-005-ACT-02 | 2024-10-11 | Material | MAT-008 | Tiles | VEN-012 | 14.1 | Sq Ft | 1118.54 | 1198.69 | 215.76 | 1414.45 | Paid | Medium
EXP-03948 | PRJ-005 | PRJ-005-ACT-09 | 2024-10-11 | Material | MAT-004 | Aggregate | VEN-005 | 3.41 | Ton | 5243.56 | 5137.81 | 924.81 | 6062.62 | Paid | Low
EXP-03949 | PRJ-005 | PRJ-005-ACT-10 | 2024-10-11 | Material | MAT-002 | Steel | VEN-012 | 14.54 | Ton | 753365.4 | 792599.49 | 142667.91 | 935267.4 | Paid | Medium
EXP-03950 | PRJ-005 | PRJ-005-ACT-03 | 2024-10-11 | Contractor | CON-002 | Electrical Contract | VEN-012 | 1 | Contract | 142930.75 | 139082.64 | 25034.88 | 164117.52 | Paid | Low
EXP-03951 | PRJ-005 | PRJ-005-ACT-05 | 2024-10-11 | Labour | LAB-001 | Mason | VEN-012 | 22 | Worker | 34179.75 | 32206.41 | 5797.15 | 38003.56 | Paid | Low
EXP-03952 | PRJ-005 | PRJ-005-ACT-01 | 2024-10-11 | Contractor | CON-001 | Civil Structure Contract | VEN-012 | 1 | Contract | 384616.18 | 409571.89 | 73722.94 | 483294.83 | Paid | Medium
EXP-03953 | PRJ-005 | PRJ-005-ACT-10 | 2024-10-16 | Material | MAT-004 | Aggregate | VEN-005 | 4.24 | Ton | 7232.65 | 6805.72 | 1225.03 | 8030.75 | Paid | Medium
EXP-03954 | PRJ-005 | PRJ-005-ACT-01 | 2024-10-16 | Labour | LAB-005 | Plumber | VEN-005 | 6 | Worker | 3873.63 | 4083.54 | 735.04 | 4818.58 | Paid | High
EXP-03955 | PRJ-005 | PRJ-005-ACT-05 | 2024-10-16 | Material | MAT-009 | Paint | VEN-008 | 12.15 | Litre | 2216.25 | 2211.33 | 398.04 | 2609.37 | Paid | High
EXP-03956 | PRJ-005 | PRJ-005-ACT-07 | 2024-10-16 | Material | MAT-001 | Cement | VEN-012 | 14.55 | Bag | 8357.28 | 8066.78 | 1452.02 | 9518.8 | Paid | Low
EXP-03957 | PRJ-005 | PRJ-005-ACT-09 | 2024-10-16 | Material | MAT-010 | Glass | VEN-008 | 13.56 | Sq Ft | 1861.83 | 1906.54 | 343.18 | 2249.72 | Paid | High
EXP-03958 | PRJ-005 | PRJ-005-ACT-04 | 2024-10-16 | Material | MAT-003 | Sand | VEN-012 | 6.01 | Ton | 9694.73 | 10205.35 | 1836.96 | 12042.31 | Paid | Low
EXP-03959 | PRJ-005 | PRJ-005-ACT-02 | 2024-10-21 | Equipment | EQ-002 | Excavator | VEN-008 | 3 | Day | 40606.55 | 40121.25 | 7221.82 | 47343.07 | Paid | Low
EXP-03960 | PRJ-005 | PRJ-005-ACT-08 | 2024-10-21 | Material | MAT-003 | Sand | VEN-008 | 3.2 | Ton | 5517.67 | 5763.15 | 1037.37 | 6800.52 | Paid | Medium
EXP-03961 | PRJ-005 | PRJ-005-ACT-10 | 2024-10-21 | Labour | LAB-006 | Painter | VEN-005 | 22 | Worker | 21714.15 | 23274.44 | 4189.4 | 27463.84 | Paid | Medium
EXP-03962 | PRJ-005 | PRJ-005-ACT-01 | 2024-10-21 | Material | MAT-006 | Electrical Cable | VEN-012 | 2.59 | Meter | 197.41 | 209.76 | 37.76 | 247.52 | Paid | Low
EXP-03963 | PRJ-005 | PRJ-005-ACT-05 | 2024-10-21 | Equipment | EQ-002 | Excavator | VEN-008 | 4 | Day | 48556.27 | 50410.35 | 9073.86 | 59484.21 | Paid | Low
EXP-03964 | PRJ-005 | PRJ-005-ACT-03 | 2024-10-21 | Material | MAT-004 | Aggregate | VEN-005 | 9.71 | Ton | 17086.85 | 16139.84 | 2905.17 | 19045.01 | Paid | Low
EXP-03965 | PRJ-005 | PRJ-005-ACT-06 | 2024-10-21 | Equipment | EQ-001 | Crane | VEN-012 | 3 | Day | 55296.66 | 53743.55 | 9673.84 | 63417.39 | Partially Paid | Medium
EXP-03966 | PRJ-005 | PRJ-005-ACT-03 | 2024-10-26 | Equipment | EQ-002 | Excavator | VEN-008 | 1 | Day | 13116.57 | 14097.27 | 2537.51 | 16634.78 | Paid | Low
EXP-03967 | PRJ-005 | PRJ-005-ACT-02 | 2024-10-26 | Material | MAT-004 | Aggregate | VEN-005 | 4.59 | Ton | 6890.86 | 7360.65 | 1324.92 | 8685.57 | Partially Paid | Low
EXP-03968 | PRJ-005 | PRJ-005-ACT-10 | 2024-10-26 | Equipment | EQ-003 | Concrete Mixer | VEN-005 | 7 | Day | 29671.35 | 28725.27 | 5170.55 | 33895.82 | Paid | Low
EXP-03969 | PRJ-005 | PRJ-005-ACT-05 | 2024-10-26 | Other | OTH-001 | Site Office | VEN-012 | 1 | Lot | 46395.56 | 44474.46 | 8005.4 | 52479.86 | Paid | Medium
EXP-03970 | PRJ-005 | PRJ-005-ACT-04 | 2024-10-26 | Other | OTH-001 | Transport | VEN-005 | 1 | Lot | 63547.42 | 64833.35 | 11670 | 76503.35 | Paid | High
EXP-03971 | PRJ-005 | PRJ-005-ACT-08 | 2024-10-26 | Material | MAT-006 | Electrical Cable | VEN-012 | 9.64 | Meter | 658.74 | 708.58 | 127.54 | 836.12 | Paid | Low
EXP-03972 | PRJ-005 | PRJ-005-ACT-09 | 2024-10-31 | Labour | LAB-002 | Helper | VEN-008 | 5 | Worker | 3456.94 | 3456.7 | 622.21 | 4078.91 | Paid | Medium
EXP-03973 | PRJ-005 | PRJ-005-ACT-07 | 2024-10-31 | Material | MAT-006 | Electrical Cable | VEN-005 | 7.64 | Meter | 604.12 | 590.02 | 106.2 | 696.22 | Paid | Medium
EXP-03974 | PRJ-005 | PRJ-005-ACT-09 | 2024-10-31 | Contractor | CON-003 | Plumbing Contract | VEN-005 | 1 | Contract | 90243.76 | 96253.37 | 17325.61 | 113578.98 | Partially Paid | Low
EXP-03975 | PRJ-005 | PRJ-005-ACT-04 | 2024-10-31 | Material | MAT-004 | Aggregate | VEN-008 | 10.35 | Ton | 12823.51 | 13599.4 | 2447.89 | 16047.29 | Partially Paid | Medium
EXP-03976 | PRJ-005 | PRJ-005-ACT-10 | 2024-10-31 | Material | MAT-007 | PVC Pipe | VEN-008 | 7.34 | Meter | 757.41 | 810.07 | 145.81 | 955.88 | Paid | Low
EXP-03977 | PRJ-005 | PRJ-005-ACT-02 | 2024-10-31 | Material | MAT-006 | Electrical Cable | VEN-012 | 2.25 | Meter | 198.45 | 186.18 | 33.51 | 219.69 | Paid | Low
EXP-03978 | PRJ-005 | PRJ-005-ACT-09 | 2024-10-31 | Labour | LAB-004 | Electrician | VEN-005 | 34 | Worker | 44968.96 | 42058.6 | 7570.55 | 49629.15 | Paid | Low
EXP-03979 | PRJ-005 | PRJ-005-ACT-05 | 2024-10-31 | Contractor | CON-001 | Civil Structure Contract | VEN-005 | 1 | Contract | 295530.48 | 307962 | 55433.16 | 363395.16 | Partially Paid | Low
EXP-03980 | PRJ-005 | PRJ-005-ACT-08 | 2024-11-05 | Material | MAT-010 | Glass | VEN-012 | 5.61 | Sq Ft | 804.19 | 826.26 | 148.73 | 974.99 | Paid | Low
EXP-03981 | PRJ-005 | PRJ-005-ACT-10 | 2024-11-05 | Labour | LAB-005 | Plumber | VEN-008 | 28 | Worker | 30284.66 | 29661.19 | 5339.01 | 35000.2 | Partially Paid | Medium
EXP-03982 | PRJ-005 | PRJ-005-ACT-04 | 2024-11-05 | Contractor | CON-001 | Civil Structure Contract | VEN-008 | 1 | Contract | 400948.41 | 413411.87 | 74414.14 | 487826.01 | Partially Paid | Low
EXP-03983 | PRJ-005 | PRJ-005-ACT-10 | 2024-11-05 | Labour | LAB-006 | Painter | VEN-012 | 16 | Worker | 19986.53 | 20458.12 | 3682.46 | 24140.58 | Paid | Medium
EXP-03984 | PRJ-005 | PRJ-005-ACT-01 | 2024-11-05 | Equipment | EQ-002 | Excavator | VEN-005 | 1 | Day | 16176.26 | 15184.38 | 2733.19 | 17917.57 | Paid | Low
EXP-03985 | PRJ-005 | PRJ-005-ACT-04 | 2024-11-05 | Contractor | CON-004 | Finishing Contract | VEN-012 | 1 | Contract | 114382.14 | 116508.52 | 20971.53 | 137480.05 | Paid | Low
EXP-03986 | PRJ-005 | PRJ-005-ACT-02 | 2024-11-05 | Equipment | EQ-003 | Concrete Mixer | VEN-012 | 5 | Day | 22193.91 | 22379.95 | 4028.39 | 26408.34 | Paid | Medium
EXP-03987 | PRJ-005 | PRJ-005-ACT-04 | 2024-11-05 | Equipment | EQ-004 | Scaffolding | VEN-005 | 7 | Day | 18317.98 | 18670.12 | 3360.62 | 22030.74 | Paid | Low
EXP-03988 | PRJ-005 | PRJ-005-ACT-01 | 2024-11-05 | Material | MAT-005 | Bricks | VEN-012 | 10.34 | Piece | 109.92 | 106.27 | 19.13 | 125.4 | Paid | High
EXP-03989 | PRJ-005 | PRJ-005-ACT-10 | 2024-11-05 | Labour | LAB-006 | Painter | VEN-008 | 14 | Worker | 12527.86 | 12013.67 | 2162.46 | 14176.13 | Pending | Low
EXP-03990 | PRJ-005 | PRJ-005-ACT-07 | 2024-11-10 | Material | MAT-007 | PVC Pipe | VEN-005 | 3.27 | Meter | 370.04 | 373.86 | 67.29 | 441.15 | Paid | Low
EXP-03991 | PRJ-005 | PRJ-005-ACT-09 | 2024-11-10 | Material | MAT-010 | Glass | VEN-005 | 20.31 | Sq Ft | 2999.98 | 2965.69 | 533.82 | 3499.51 | Paid | Medium
EXP-03992 | PRJ-005 | PRJ-005-ACT-10 | 2024-11-10 | Material | MAT-002 | Steel | VEN-008 | 3.36 | Ton | 194381.96 | 185550.24 | 33399.04 | 218949.28 | Paid | Medium
EXP-03993 | PRJ-005 | PRJ-005-ACT-02 | 2024-11-10 | Material | MAT-006 | Electrical Cable | VEN-005 | 5.12 | Meter | 475.75 | 475.05 | 85.51 | 560.56 | Paid | High
EXP-03994 | PRJ-005 | PRJ-005-ACT-02 | 2024-11-10 | Contractor | CON-003 | Plumbing Contract | VEN-005 | 1 | Contract | 389589.27 | 380022.49 | 68404.05 | 448426.54 | Paid | Medium
EXP-03995 | PRJ-005 | PRJ-005-ACT-06 | 2024-11-10 | Material | MAT-002 | Steel | VEN-005 | 20.04 | Ton | 1473031.67 | 1427891.8 | 257020.52 | 1684912.32 | Paid | Low
EXP-03996 | PRJ-005 | PRJ-005-ACT-10 | 2024-11-15 | Material | MAT-002 | Steel | VEN-012 | 99.12 | Ton | 491242.23 | 519350.47 | 93483.08 | 612833.55 | Paid | Low
EXP-03997 | PRJ-005 | PRJ-005-ACT-07 | 2024-11-15 | Contractor | CON-001 | Civil Structure Contract | VEN-008 | 1 | Contract | 246266.63 | 250078.99 | 45014.22 | 295093.21 | Paid | Low
EXP-03998 | PRJ-005 | PRJ-005-ACT-06 | 2024-11-15 | Contractor | CON-003 | Plumbing Contract | VEN-012 | 1 | Contract | 166245.43 | 162434.25 | 29238.16 | 191672.41 | Partially Paid | Low
EXP-03999 | PRJ-005 | PRJ-005-ACT-05 | 2024-11-15 | Contractor | CON-001 | Civil Structure Contract | VEN-008 | 1 | Contract | 93572.99 | 90986.59 | 16377.59 | 107364.18 | Partially Paid | Medium
EXP-04000 | PRJ-005 | PRJ-005-ACT-02 | 2024-11-15 | Material | MAT-008 | Tiles | VEN-012 | 6.66 | Sq Ft | 515.24 | 531.92 | 95.75 | 627.67 | Paid | Medium
EXP-04001 | PRJ-005 | PRJ-005-ACT-10 | 2024-11-15 | Labour | LAB-005 | Plumber | VEN-005 | 15 | Worker | 27456.31 | 25922.18 | 4665.99 | 30588.17 | Paid | Low
EXP-04002 | PRJ-005 | PRJ-005-ACT-08 | 2024-11-20 | Equipment | EQ-003 | Concrete Mixer | VEN-008 | 7 | Day | 31147.82 | 32617.17 | 5871.09 | 38488.26 | Paid | Low
EXP-04003 | PRJ-005 | PRJ-005-ACT-07 | 2024-11-20 | Labour | LAB-004 | Electrician | VEN-012 | 28 | Worker | 31448.69 | 33634.58 | 6054.22 | 39688.8 | Paid | Low
EXP-04004 | PRJ-005 | PRJ-005-ACT-03 | 2024-11-20 | Contractor | CON-001 | Civil Structure Contract | VEN-005 | 1 | Contract | 306363.05 | 290415.37 | 52274.77 | 342690.14 | Paid | Low
EXP-04005 | PRJ-005 | PRJ-005-ACT-05 | 2024-11-20 | Material | MAT-001 | Cement | VEN-008 | 15.65 | Bag | 7753.68 | 7892.88 | 1420.72 | 9313.6 | Paid | Medium
EXP-04006 | PRJ-005 | PRJ-005-ACT-09 | 2024-11-20 | Equipment | EQ-004 | Scaffolding | VEN-008 | 1 | Day | 2583.15 | 2702.3 | 486.41 | 3188.71 | Paid | Low
EXP-04007 | PRJ-005 | PRJ-005-ACT-02 | 2024-11-20 | Material | MAT-004 | Aggregate | VEN-012 | 12.92 | Ton | 19539.13 | 18961.29 | 3413.03 | 22374.32 | Paid | Low
EXP-04008 | PRJ-005 | PRJ-005-ACT-07 | 2024-11-20 | Contractor | CON-002 | Electrical Contract | VEN-005 | 1 | Contract | 182731.03 | 187666.39 | 33779.95 | 221446.34 | Paid | Medium
EXP-04009 | PRJ-005 | PRJ-005-ACT-04 | 2024-11-25 | Contractor | CON-002 | Electrical Contract | VEN-005 | 1 | Contract | 419900.21 | 443268.15 | 79788.27 | 523056.42 | Paid | Medium
EXP-04010 | PRJ-005 | PRJ-005-ACT-05 | 2024-11-25 | Material | MAT-007 | PVC Pipe | VEN-012 | 5.44 | Meter | 678.18 | 686.88 | 123.64 | 810.52 | Paid | Low
EXP-04011 | PRJ-005 | PRJ-005-ACT-02 | 2024-11-25 | Contractor | CON-002 | Electrical Contract | VEN-005 | 1 | Contract | 364844.5 | 351433.95 | 63258.11 | 414692.06 | Paid | Medium
EXP-04012 | PRJ-005 | PRJ-005-ACT-06 | 2024-11-25 | Material | MAT-008 | Tiles | VEN-008 | 6.13 | Sq Ft | 397.66 | 424.93 | 76.49 | 501.42 | Paid | Low
EXP-04013 | PRJ-005 | PRJ-005-ACT-07 | 2024-11-25 | Labour | LAB-004 | Electrician | VEN-012 | 16 | Worker | 27976.22 | 28794.43 | 5183 | 33977.43 | Partially Paid | Medium
EXP-04014 | PRJ-005 | PRJ-005-ACT-10 | 2024-11-25 | Other | OTH-001 | Miscellaneous | VEN-012 | 1 | Lot | 59518.64 | 61768.74 | 11118.37 | 72887.11 | Paid | Medium
EXP-04015 | PRJ-005 | PRJ-005-ACT-07 | 2024-11-30 | Equipment | EQ-002 | Excavator | VEN-005 | 2 | Day | 25302.16 | 27375.29 | 4927.55 | 32302.84 | Partially Paid | Low
EXP-04016 | PRJ-005 | PRJ-005-ACT-08 | 2024-11-30 | Material | MAT-005 | Bricks | VEN-005 | 2.82 | Piece | 23.81 | 22.44 | 4.04 | 26.48 | Paid | Medium
EXP-04017 | PRJ-005 | PRJ-005-ACT-04 | 2024-11-30 | Material | MAT-009 | Paint | VEN-012 | 3.88 | Litre | 863.48 | 880.94 | 158.57 | 1039.51 | Paid | Medium
EXP-04018 | PRJ-005 | PRJ-005-ACT-09 | 2024-11-30 | Material | MAT-006 | Electrical Cable | VEN-005 | 10.35 | Meter | 810.65 | 779.83 | 140.37 | 920.2 | Paid | Low
EXP-04019 | PRJ-005 | PRJ-005-ACT-03 | 2024-11-30 | Material | MAT-004 | Aggregate | VEN-012 | 6.23 | Ton | 8778.27 | 8790.65 | 1582.32 | 10372.97 | Paid | Low
EXP-04020 | PRJ-005 | PRJ-005-ACT-02 | 2024-11-30 | Contractor | CON-003 | Plumbing Contract | VEN-005 | 1 | Contract | 243650.85 | 229735.84 | 41352.45 | 271088.29 | Paid | Medium
EXP-04021 | PRJ-005 | PRJ-005-ACT-01 | 2024-11-30 | Material | MAT-009 | Paint | VEN-005 | 16.59 | Litre | 3484.46 | 3272.12 | 588.98 | 3861.1 | Paid | Low
EXP-04022 | PRJ-005 | PRJ-005-ACT-07 | 2024-12-05 | Material | MAT-006 | Electrical Cable | VEN-012 | 8.65 | Meter | 712.79 | 686.82 | 123.63 | 810.45 | Paid | High
EXP-04023 | PRJ-005 | PRJ-005-ACT-01 | 2024-12-05 | Equipment | EQ-002 | Excavator | VEN-008 | 3 | Day | 41876.92 | 40320.77 | 7257.74 | 47578.51 | Paid | High
EXP-04024 | PRJ-005 | PRJ-005-ACT-07 | 2024-12-05 | Labour | LAB-006 | Painter | VEN-008 | 10 | Worker | 10839.73 | 10091.69 | 1816.5 | 11908.19 | Pending | Medium
EXP-04025 | PRJ-005 | PRJ-005-ACT-09 | 2024-12-05 | Material | MAT-006 | Electrical Cable | VEN-012 | 3.34 | Meter | 268.65 | 288.79 | 51.98 | 340.77 | Paid | Low
EXP-04026 | PRJ-005 | PRJ-005-ACT-09 | 2024-12-05 | Material | MAT-003 | Sand | VEN-005 | 16.35 | Ton | 33610.15 | 32144.03 | 5785.93 | 37929.96 | Paid | Low
EXP-04027 | PRJ-005 | PRJ-005-ACT-08 | 2024-12-05 | Other | OTH-001 | Transport | VEN-008 | 1 | Lot | 75734.63 | 76346.28 | 13742.33 | 90088.61 | Paid | Medium
EXP-04028 | PRJ-005 | PRJ-005-ACT-08 | 2024-12-05 | Other | OTH-001 | Site Office | VEN-005 | 1 | Lot | 34336.19 | 36706.16 | 6607.11 | 43313.27 | Paid | High
EXP-04029 | PRJ-005 | PRJ-005-ACT-07 | 2024-12-10 | Labour | LAB-004 | Electrician | VEN-008 | 15 | Worker | 17558.16 | 16942.03 | 3049.57 | 19991.6 | Paid | Medium
EXP-04030 | PRJ-005 | PRJ-005-ACT-01 | 2024-12-10 | Other | OTH-001 | Miscellaneous | VEN-012 | 1 | Lot | 33750.05 | 33490.85 | 6028.35 | 39519.2 | Partially Paid | Low
EXP-04031 | PRJ-005 | PRJ-005-ACT-02 | 2024-12-10 | Material | MAT-002 | Steel | VEN-005 | 18.66 | Ton | 1138953.36 | 1126297.81 | 202733.61 | 1329031.42 | Paid | Low
EXP-04032 | PRJ-005 | PRJ-005-ACT-09 | 2024-12-10 | Material | MAT-009 | Paint | VEN-008 | 4.33 | Litre | 1004.9 | 1036.67 | 186.6 | 1223.27 | Paid | Low
EXP-04033 | PRJ-005 | PRJ-005-ACT-05 | 2024-12-10 | Material | MAT-003 | Sand | VEN-008 | 1.47 | Ton | 2386.68 | 2356.64 | 424.2 | 2780.84 | Paid | Medium
EXP-04034 | PRJ-005 | PRJ-005-ACT-02 | 2024-12-10 | Material | MAT-001 | Cement | VEN-008 | 6.12 | Bag | 3743.18 | 3513.29 | 632.39 | 4145.68 | Partially Paid | Medium
EXP-04035 | PRJ-005 | PRJ-005-ACT-05 | 2024-12-15 | Material | MAT-007 | PVC Pipe | VEN-008 | 10.04 | Meter | 1260.72 | 1281.97 | 230.75 | 1512.72 | Paid | Low
EXP-04036 | PRJ-005 | PRJ-005-ACT-08 | 2024-12-15 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 87330.43 | 88426.29 | 15916.73 | 104343.02 | Paid | Medium
EXP-04037 | PRJ-005 | PRJ-005-ACT-08 | 2024-12-15 | Labour | LAB-005 | Plumber | VEN-008 | 33 | Worker | 49987.72 | 52655.65 | 9478.02 | 62133.67 | Paid | Medium
EXP-04038 | PRJ-005 | PRJ-005-ACT-05 | 2024-12-15 | Material | MAT-006 | Electrical Cable | VEN-012 | 3.38 | Meter | 319.57 | 298.15 | 53.67 | 351.82 | Paid | Medium
EXP-04039 | PRJ-005 | PRJ-005-ACT-06 | 2024-12-15 | Labour | LAB-002 | Helper | VEN-012 | 7 | Worker | 7271.32 | 7560.45 | 1360.88 | 8921.33 | Paid | Medium
EXP-04040 | PRJ-005 | PRJ-005-ACT-07 | 2024-12-15 | Labour | LAB-005 | Plumber | VEN-008 | 20 | Worker | 31571.4 | 31653.99 | 5697.72 | 37351.71 | Paid | Low
EXP-04041 | PRJ-005 | PRJ-005-ACT-04 | 2024-12-15 | Material | MAT-007 | PVC Pipe | VEN-008 | 6.95 | Meter | 793 | 803.39 | 144.61 | 948 | Partially Paid | High
EXP-04042 | PRJ-005 | PRJ-005-ACT-10 | 2024-12-15 | Material | MAT-001 | Cement | VEN-008 | 44.87 | Bag | 23146.85 | 22641.49 | 4075.47 | 26716.96 | Paid | Low
EXP-04043 | PRJ-005 | PRJ-005-ACT-03 | 2024-12-15 | Contractor | CON-004 | Finishing Contract | VEN-008 | 1 | Contract | 119283.31 | 116968.43 | 21054.32 | 138022.75 | Paid | Medium
EXP-04044 | PRJ-005 | PRJ-005-ACT-02 | 2024-12-20 | Material | MAT-004 | Aggregate | VEN-012 | 3.16 | Ton | 4535.24 | 4472.45 | 805.04 | 5277.49 | Partially Paid | Medium
EXP-04045 | PRJ-005 | PRJ-005-ACT-07 | 2024-12-20 | Labour | LAB-001 | Mason | VEN-005 | 25 | Worker | 17368.01 | 17197.52 | 3095.55 | 20293.07 | Paid | Low
EXP-04046 | PRJ-005 | PRJ-005-ACT-10 | 2024-12-20 | Labour | LAB-005 | Plumber | VEN-012 | 22 | Worker | 36693.89 | 39106.06 | 7039.09 | 46145.15 | Paid | Low
EXP-04047 | PRJ-005 | PRJ-005-ACT-08 | 2024-12-20 | Labour | LAB-005 | Plumber | VEN-012 | 29 | Worker | 48469.93 | 50773.93 | 9139.31 | 59913.24 | Pending | Low
EXP-04048 | PRJ-005 | PRJ-005-ACT-09 | 2024-12-20 | Equipment | EQ-003 | Concrete Mixer | VEN-012 | 3 | Day | 12967.04 | 14069.24 | 2532.46 | 16601.7 | Paid | High
EXP-04049 | PRJ-005 | PRJ-005-ACT-07 | 2024-12-20 | Labour | LAB-004 | Electrician | VEN-012 | 10 | Worker | 10186.4 | 10789.14 | 1942.05 | 12731.19 | Pending | Medium
EXP-04050 | PRJ-005 | PRJ-005-ACT-10 | 2024-12-20 | Material | MAT-006 | Electrical Cable | VEN-012 | 6.67 | Meter | 588.27 | 629.55 | 113.32 | 742.87 | Paid | Low
EXP-04051 | PRJ-005 | PRJ-005-ACT-09 | 2024-12-20 | Material | MAT-005 | Bricks | VEN-012 | 17.12 | Piece | 170.72 | 173.85 | 31.29 | 205.14 | Paid | Low
EXP-04052 | PRJ-005 | PRJ-005-ACT-08 | 2024-12-25 | Labour | LAB-006 | Painter | VEN-012 | 26 | Worker | 43426.58 | 40844.79 | 7352.06 | 48196.85 | Paid | Medium
EXP-04053 | PRJ-005 | PRJ-005-ACT-03 | 2024-12-25 | Other | OTH-001 | Transport | VEN-012 | 1 | Lot | 11000.89 | 11480.25 | 2066.44 | 13546.69 | Paid | Medium
EXP-04054 | PRJ-005 | PRJ-005-ACT-06 | 2024-12-25 | Material | MAT-006 | Electrical Cable | VEN-012 | 1.96 | Meter | 151.25 | 143.46 | 25.82 | 169.28 | Paid | Medium
EXP-04055 | PRJ-005 | PRJ-005-ACT-07 | 2024-12-25 | Contractor | CON-003 | Plumbing Contract | VEN-012 | 1 | Contract | 221670.4 | 215928.55 | 38867.14 | 254795.69 | Paid | Low
EXP-04056 | PRJ-005 | PRJ-005-ACT-01 | 2024-12-25 | Labour | LAB-001 | Mason | VEN-012 | 11 | Worker | 12489.55 | 13106.16 | 2359.11 | 15465.27 | Paid | Low
EXP-04057 | PRJ-005 | PRJ-005-ACT-10 | 2024-12-25 | Labour | LAB-003 | Carpenter | VEN-005 | 11 | Worker | 18400.26 | 18778.84 | 3380.19 | 22159.03 | Paid | Low
EXP-04058 | PRJ-005 | PRJ-005-ACT-03 | 2024-12-25 | Material | MAT-010 | Glass | VEN-008 | 12.51 | Sq Ft | 1939.31 | 1823.45 | 328.22 | 2151.67 | Paid | Low
EXP-04059 | PRJ-005 | PRJ-005-ACT-10 | 2024-12-30 | Labour | LAB-004 | Electrician | VEN-008 | 15 | Worker | 22353.05 | 21837.45 | 3930.74 | 25768.19 | Paid | Medium
EXP-04060 | PRJ-005 | PRJ-005-ACT-03 | 2024-12-30 | Material | MAT-008 | Tiles | VEN-008 | 5.12 | Sq Ft | 323.9 | 343.22 | 61.78 | 405 | Paid | Medium
EXP-04061 | PRJ-005 | PRJ-005-ACT-04 | 2024-12-30 | Contractor | CON-002 | Electrical Contract | VEN-008 | 1 | Contract | 70308.61 | 75093.01 | 13516.74 | 88609.75 | Paid | Medium
EXP-04062 | PRJ-005 | PRJ-005-ACT-03 | 2024-12-30 | Material | MAT-004 | Aggregate | VEN-005 | 8.97 | Ton | 12399.48 | 11528.44 | 2075.12 | 13603.56 | Pending | Low
EXP-04063 | PRJ-005 | PRJ-005-ACT-07 | 2024-12-30 | Other | OTH-001 | Site Office | VEN-005 | 1 | Lot | 52895.53 | 55875.47 | 10057.58 | 65933.05 | Paid | Low
EXP-04064 | PRJ-005 | PRJ-005-ACT-02 | 2024-12-30 | Material | MAT-005 | Bricks | VEN-005 | 21.15 | Piece | 209.41 | 218.14 | 39.27 | 257.41 | Partially Paid | Low
EXP-04065 | PRJ-005 | PRJ-005-ACT-05 | 2025-01-04 | Material | MAT-010 | Glass | VEN-008 | 33.99 | Sq Ft | 5327.81 | 5287.12 | 951.68 | 6238.8 | Paid | Low
EXP-04066 | PRJ-005 | PRJ-005-ACT-03 | 2025-01-04 | Material | MAT-009 | Paint | VEN-012 | 4.74 | Litre | 1017.57 | 1071.84 | 192.93 | 1264.77 | Paid | Low
EXP-04067 | PRJ-005 | PRJ-005-ACT-01 | 2025-01-04 | Material | MAT-001 | Cement | VEN-008 | 5.2 | Bag | 2575.99 | 2609.33 | 469.68 | 3079.01 | Paid | Low
EXP-04068 | PRJ-005 | PRJ-005-ACT-03 | 2025-01-04 | Material | MAT-005 | Bricks | VEN-012 | 16.66 | Piece | 150.6 | 143.57 | 25.84 | 169.41 | Pending | Low
EXP-04069 | PRJ-005 | PRJ-005-ACT-05 | 2025-01-04 | Contractor | CON-002 | Electrical Contract | VEN-005 | 1 | Contract | 412110.37 | 391452.96 | 70461.53 | 461914.49 | Pending | Low
EXP-04070 | PRJ-005 | PRJ-005-ACT-10 | 2025-01-04 | Material | MAT-004 | Aggregate | VEN-008 | 13.95 | Ton | 22109.96 | 20730.77 | 3731.54 | 24462.31 | Paid | Medium
EXP-04071 | PRJ-005 | PRJ-005-ACT-03 | 2025-01-04 | Material | MAT-007 | PVC Pipe | VEN-008 | 5.99 | Meter | 680.19 | 657.84 | 118.41 | 776.25 | Paid | Low
EXP-04072 | PRJ-005 | PRJ-005-ACT-01 | 2025-01-04 | Contractor | CON-004 | Finishing Contract | VEN-008 | 1 | Contract | 334583.56 | 339712.43 | 61148.24 | 400860.67 | Paid | Medium
EXP-04073 | PRJ-005 | PRJ-005-ACT-01 | 2025-01-04 | Contractor | CON-001 | Civil Structure Contract | VEN-012 | 1 | Contract | 433009.86 | 417192.23 | 75094.6 | 492286.83 | Paid | Medium
EXP-04074 | PRJ-005 | PRJ-005-ACT-04 | 2025-01-09 | Labour | LAB-004 | Electrician | VEN-005 | 22 | Worker | 35261.9 | 34220.97 | 6159.77 | 40380.74 | Partially Paid | Low
EXP-04075 | PRJ-005 | PRJ-005-ACT-10 | 2025-01-09 | Labour | LAB-004 | Electrician | VEN-005 | 8 | Worker | 9947.77 | 9585.37 | 1725.37 | 11310.74 | Paid | Medium
EXP-04076 | PRJ-005 | PRJ-005-ACT-03 | 2025-01-09 | Material | MAT-009 | Paint | VEN-008 | 6.22 | Litre | 1415.5 | 1497.73 | 269.59 | 1767.32 | Paid | Low
EXP-04077 | PRJ-005 | PRJ-005-ACT-01 | 2025-01-09 | Material | MAT-005 | Bricks | VEN-012 | 10.03 | Piece | 105.95 | 99.98 | 18 | 117.98 | Paid | Low
EXP-04078 | PRJ-005 | PRJ-005-ACT-04 | 2025-01-09 | Contractor | CON-003 | Plumbing Contract | VEN-008 | 1 | Contract | 177301.43 | 189321.7 | 34077.91 | 223399.61 | Paid | High
EXP-04079 | PRJ-005 | PRJ-005-ACT-02 | 2025-01-09 | Labour | LAB-001 | Mason | VEN-005 | 5 | Worker | 5176.4 | 4974.74 | 895.45 | 5870.19 | Paid | Low
EXP-04080 | PRJ-005 | PRJ-005-ACT-09 | 2025-01-09 | Contractor | CON-002 | Electrical Contract | VEN-008 | 1 | Contract | 423450.63 | 408959.8 | 73612.76 | 482572.56 | Paid | Low
EXP-04081 | PRJ-005 | PRJ-005-ACT-08 | 2025-01-09 | Labour | LAB-001 | Mason | VEN-008 | 8 | Worker | 7420.25 | 7968.73 | 1434.37 | 9403.1 | Pending | Low
EXP-04082 | PRJ-005 | PRJ-005-ACT-07 | 2025-01-14 | Material | MAT-001 | Cement | VEN-012 | 24.01 | Bag | 13049.39 | 12460.11 | 2242.82 | 14702.93 | Paid | Medium
EXP-04083 | PRJ-005 | PRJ-005-ACT-09 | 2025-01-14 | Equipment | EQ-002 | Excavator | VEN-008 | 3 | Day | 44573.74 | 46030.98 | 8285.58 | 54316.56 | Paid | Medium
EXP-04084 | PRJ-005 | PRJ-005-ACT-01 | 2025-01-14 | Material | MAT-010 | Glass | VEN-005 | 23.51 | Sq Ft | 3370.42 | 3285.08 | 591.31 | 3876.39 | Partially Paid | High
EXP-04085 | PRJ-005 | PRJ-005-ACT-07 | 2025-01-14 | Material | MAT-007 | PVC Pipe | VEN-005 | 7.41 | Meter | 713.8 | 774.44 | 139.4 | 913.84 | Paid | Low
EXP-04086 | PRJ-005 | PRJ-005-ACT-09 | 2025-01-14 | Material | MAT-001 | Cement | VEN-012 | 13.86 | Bag | 6956.08 | 7270 | 1308.6 | 8578.6 | Paid | Medium
EXP-04087 | PRJ-005 | PRJ-005-ACT-02 | 2025-01-14 | Material | MAT-005 | Bricks | VEN-008 | 10.29 | Piece | 84.34 | 81.7 | 14.71 | 96.41 | Paid | Low
EXP-04088 | PRJ-005 | PRJ-005-ACT-02 | 2025-01-14 | Labour | LAB-004 | Electrician | VEN-008 | 11 | Worker | 18899.38 | 18456.97 | 3322.25 | 21779.22 | Paid | Low
EXP-04089 | PRJ-005 | PRJ-005-ACT-03 | 2025-01-14 | Material | MAT-006 | Electrical Cable | VEN-008 | 11.09 | Meter | 813.29 | 801.77 | 144.32 | 946.09 | Paid | Low
EXP-04090 | PRJ-005 | PRJ-005-ACT-09 | 2025-01-14 | Equipment | EQ-004 | Scaffolding | VEN-012 | 6 | Day | 14743.35 | 15680.19 | 2822.43 | 18502.62 | Paid | Medium
EXP-04091 | PRJ-005 | PRJ-005-ACT-03 | 2025-01-14 | Contractor | CON-003 | Plumbing Contract | VEN-005 | 1 | Contract | 154915.18 | 144682.64 | 26042.88 | 170725.52 | Paid | Low
EXP-04092 | PRJ-005 | PRJ-005-ACT-06 | 2025-01-19 | Contractor | CON-003 | Plumbing Contract | VEN-012 | 1 | Contract | 85741.81 | 86479.98 | 15566.4 | 102046.38 | Paid | Low
EXP-04093 | PRJ-005 | PRJ-005-ACT-01 | 2025-01-19 | Material | MAT-001 | Cement | VEN-012 | 3.84 | Bag | 1967.72 | 2109.91 | 379.78 | 2489.69 | Paid | Medium
EXP-04094 | PRJ-005 | PRJ-005-ACT-01 | 2025-01-19 | Other | OTH-001 | Transport | VEN-008 | 1 | Lot | 10397.6 | 9795.73 | 1763.23 | 11558.96 | Paid | Medium
EXP-04095 | PRJ-005 | PRJ-005-ACT-07 | 2025-01-19 | Material | MAT-008 | Tiles | VEN-008 | 7.03 | Sq Ft | 595.49 | 584.31 | 105.18 | 689.49 | Paid | Low
EXP-04096 | PRJ-005 | PRJ-005-ACT-04 | 2025-01-19 | Other | OTH-001 | Permit | VEN-012 | 1 | Lot | 18441.15 | 18093.36 | 3256.8 | 21350.16 | Paid | Low
EXP-04097 | PRJ-005 | PRJ-005-ACT-04 | 2025-01-19 | Contractor | CON-001 | Civil Structure Contract | VEN-005 | 1 | Contract | 261569.83 | 278346.27 | 50102.33 | 328448.6 | Paid | Medium
EXP-04098 | PRJ-005 | PRJ-005-ACT-03 | 2025-01-19 | Material | MAT-010 | Glass | VEN-008 | 12.03 | Sq Ft | 1792.91 | 1693.94 | 304.91 | 1998.85 | Partially Paid | Medium
EXP-04099 | PRJ-005 | PRJ-005-ACT-04 | 2025-01-24 | Material | MAT-008 | Tiles | VEN-008 | 17.64 | Sq Ft | 1565.97 | 1473.87 | 265.3 | 1739.17 | Paid | Medium
EXP-04100 | PRJ-005 | PRJ-005-ACT-02 | 2025-01-24 | Material | MAT-004 | Aggregate | VEN-012 | 8.4 | Ton | 11247.47 | 11066.69 | 1992 | 13058.69 | Partially Paid | Medium
EXP-04101 | PRJ-005 | PRJ-005-ACT-03 | 2025-01-24 | Material | MAT-010 | Glass | VEN-012 | 3.67 | Sq Ft | 572.66 | 561.31 | 101.04 | 662.35 | Paid | Medium
EXP-04102 | PRJ-005 | PRJ-005-ACT-10 | 2025-01-24 | Contractor | CON-003 | Plumbing Contract | VEN-005 | 1 | Contract | 182812.51 | 192219.68 | 34599.54 | 226819.22 | Paid | High
EXP-04103 | PRJ-005 | PRJ-005-ACT-10 | 2025-01-24 | Labour | LAB-002 | Helper | VEN-008 | 14 | Worker | 10562.11 | 11010.36 | 1981.86 | 12992.22 | Paid | Low
EXP-04104 | PRJ-005 | PRJ-005-ACT-04 | 2025-01-24 | Material | MAT-004 | Aggregate | VEN-005 | 10.81 | Ton | 15900.94 | 17226.9 | 3100.84 | 20327.74 | Paid | Low
EXP-04105 | PRJ-005 | PRJ-005-ACT-03 | 2025-01-24 | Other | OTH-001 | Safety | VEN-008 | 1 | Lot | 48744.21 | 47724.67 | 8590.44 | 56315.11 | Partially Paid | High
EXP-04106 | PRJ-005 | PRJ-005-ACT-10 | 2025-01-24 | Material | MAT-004 | Aggregate | VEN-012 | 6.21 | Ton | 9526.72 | 9232.79 | 1661.9 | 10894.69 | Paid | Low
EXP-04107 | PRJ-005 | PRJ-005-ACT-03 | 2025-01-24 | Contractor | CON-004 | Finishing Contract | VEN-008 | 1 | Contract | 305904.69 | 310080.35 | 55814.46 | 365894.81 | Paid | Low
EXP-04108 | PRJ-005 | PRJ-005-ACT-10 | 2025-01-29 | Equipment | EQ-001 | Crane | VEN-012 | 7 | Day | 128589.58 | 126450.3 | 22761.05 | 149211.35 | Paid | Low
EXP-04109 | PRJ-005 | PRJ-005-ACT-07 | 2025-01-29 | Other | OTH-001 | Permit | VEN-008 | 1 | Lot | 62134.17 | 59631.32 | 10733.64 | 70364.96 | Partially Paid | Low
EXP-04110 | PRJ-005 | PRJ-005-ACT-07 | 2025-01-29 | Equipment | EQ-001 | Crane | VEN-005 | 4 | Day | 62806.4 | 67817.46 | 12207.14 | 80024.6 | Paid | Medium
EXP-04111 | PRJ-005 | PRJ-005-ACT-10 | 2025-01-29 | Material | MAT-008 | Tiles | VEN-012 | 4.3 | Sq Ft | 280.46 | 279.61 | 50.33 | 329.94 | Partially Paid | Low
EXP-04112 | PRJ-005 | PRJ-005-ACT-08 | 2025-01-29 | Material | MAT-003 | Sand | VEN-008 | 13.11 | Ton | 20595.11 | 22348.26 | 4022.69 | 26370.95 | Paid | Low
EXP-04113 | PRJ-005 | PRJ-005-ACT-04 | 2025-01-29 | Contractor | CON-001 | Civil Structure Contract | VEN-012 | 1 | Contract | 154243.57 | 156181.98 | 28112.76 | 184294.74 | Paid | Low
EXP-04114 | PRJ-005 | PRJ-005-ACT-10 | 2025-01-29 | Contractor | CON-002 | Electrical Contract | VEN-005 | 1 | Contract | 210310.52 | 206880.83 | 37238.55 | 244119.38 | Paid | Medium
EXP-04115 | PRJ-005 | PRJ-005-ACT-01 | 2025-01-29 | Material | MAT-008 | Tiles | VEN-008 | 10.69 | Sq Ft | 838.89 | 834.68 | 150.24 | 984.92 | Paid | Low
EXP-04116 | PRJ-005 | PRJ-005-ACT-04 | 2025-01-29 | Labour | LAB-001 | Mason | VEN-012 | 21 | Worker | 29363.58 | 29243.72 | 5263.87 | 34507.59 | Paid | Low
EXP-04117 | PRJ-005 | PRJ-005-ACT-04 | 2025-02-03 | Material | MAT-005 | Bricks | VEN-005 | 12.79 | Piece | 122.7 | 119.78 | 21.56 | 141.34 | Paid | High
EXP-04118 | PRJ-005 | PRJ-005-ACT-10 | 2025-02-03 | Contractor | CON-003 | Plumbing Contract | VEN-008 | 1 | Contract | 83960.13 | 87385.88 | 15729.46 | 103115.34 | Paid | Low
EXP-04119 | PRJ-005 | PRJ-005-ACT-04 | 2025-02-03 | Material | MAT-002 | Steel | VEN-005 | 17.48 | Ton | 1131688.56 | 1130356.18 | 203464.11 | 1333820.29 | Paid | Low
EXP-04120 | PRJ-005 | PRJ-005-ACT-06 | 2025-02-03 | Material | MAT-008 | Tiles | VEN-008 | 13.87 | Sq Ft | 958.61 | 996.94 | 179.45 | 1176.39 | Paid | Medium
EXP-04121 | PRJ-005 | PRJ-005-ACT-03 | 2025-02-03 | Material | MAT-001 | Cement | VEN-005 | 5.73 | Bag | 3372.24 | 3201.94 | 576.35 | 3778.29 | Paid | High
EXP-04122 | PRJ-005 | PRJ-005-ACT-07 | 2025-02-03 | Material | MAT-001 | Cement | VEN-005 | 17.07 | Bag | 7739.81 | 7857.29 | 1414.31 | 9271.6 | Paid | Low
EXP-04123 | PRJ-005 | PRJ-005-ACT-08 | 2025-02-08 | Other | OTH-001 | Permit | VEN-012 | 1 | Lot | 53375.31 | 53736.74 | 9672.61 | 63409.35 | Paid | Low
EXP-04124 | PRJ-005 | PRJ-005-ACT-06 | 2025-02-08 | Labour | LAB-002 | Helper | VEN-008 | 31 | Worker | 30383.71 | 29175.85 | 5251.65 | 34427.5 | Paid | Medium
EXP-04125 | PRJ-005 | PRJ-005-ACT-05 | 2025-02-08 | Material | MAT-007 | PVC Pipe | VEN-005 | 114.64 | Meter | 15011.11 | 14875.42 | 2677.58 | 17553 | Paid | Low
EXP-04126 | PRJ-005 | PRJ-005-ACT-10 | 2025-02-08 | Material | MAT-004 | Aggregate | VEN-008 | 9.91 | Ton | 13744.65 | 13380.05 | 2408.41 | 15788.46 | Paid | Low
EXP-04127 | PRJ-005 | PRJ-005-ACT-04 | 2025-02-08 | Contractor | CON-001 | Civil Structure Contract | VEN-005 | 1 | Contract | 249247.55 | 235534.68 | 42396.24 | 277930.92 | Paid | Medium
EXP-04128 | PRJ-005 | PRJ-005-ACT-03 | 2025-02-08 | Material | MAT-009 | Paint | VEN-008 | 17.81 | Litre | 4152.85 | 4211.95 | 758.15 | 4970.1 | Partially Paid | Low
EXP-04129 | PRJ-005 | PRJ-005-ACT-08 | 2025-02-08 | Material | MAT-005 | Bricks | VEN-005 | 5.78 | Piece | 61.57 | 57.34 | 10.32 | 67.66 | Pending | Low
EXP-04130 | PRJ-005 | PRJ-005-ACT-09 | 2025-02-08 | Contractor | CON-003 | Plumbing Contract | VEN-008 | 1 | Contract | 249155.49 | 245845.82 | 44252.25 | 290098.07 | Partially Paid | Low
EXP-04131 | PRJ-005 | PRJ-005-ACT-07 | 2025-02-08 | Equipment | EQ-002 | Excavator | VEN-012 | 7 | Day | 108907.89 | 104462.03 | 18803.17 | 123265.2 | Paid | Low
EXP-04132 | PRJ-005 | PRJ-005-ACT-07 | 2025-02-08 | Material | MAT-001 | Cement | VEN-012 | 3.57 | Bag | 1797.64 | 1825.54 | 328.6 | 2154.14 | Paid | Medium
EXP-04133 | PRJ-005 | PRJ-005-ACT-08 | 2025-02-13 | Other | OTH-001 | Permit | VEN-005 | 1 | Lot | 20921.97 | 20569.62 | 3702.53 | 24272.15 | Paid | Medium
EXP-04134 | PRJ-005 | PRJ-005-ACT-04 | 2025-02-13 | Labour | LAB-006 | Painter | VEN-005 | 33 | Worker | 49568.9 | 48162.59 | 8669.27 | 56831.86 | Paid | Low
EXP-04135 | PRJ-005 | PRJ-005-ACT-03 | 2025-02-13 | Material | MAT-008 | Tiles | VEN-012 | 14.85 | Sq Ft | 1172.25 | 1151.43 | 207.26 | 1358.69 | Paid | Low
EXP-04136 | PRJ-005 | PRJ-005-ACT-05 | 2025-02-13 | Contractor | CON-004 | Finishing Contract | VEN-012 | 1 | Contract | 209911.58 | 205359.98 | 36964.8 | 242324.78 | Paid | Low
EXP-04137 | PRJ-005 | PRJ-005-ACT-09 | 2025-02-13 | Material | MAT-007 | PVC Pipe | VEN-005 | 5.59 | Meter | 677.29 | 695.14 | 125.13 | 820.27 | Paid | Low
EXP-04138 | PRJ-005 | PRJ-005-ACT-10 | 2025-02-13 | Material | MAT-010 | Glass | VEN-012 | 7.69 | Sq Ft | 1063.34 | 1086.9 | 195.64 | 1282.54 | Paid | Low
EXP-04139 | PRJ-005 | PRJ-005-ACT-02 | 2025-02-13 | Other | OTH-001 | Safety | VEN-005 | 1 | Lot | 5975.73 | 5777.12 | 1039.88 | 6817 | Paid | High
EXP-04140 | PRJ-005 | PRJ-005-ACT-04 | 2025-02-13 | Equipment | EQ-001 | Crane | VEN-008 | 6 | Day | 107814.86 | 112423.76 | 20236.28 | 132660.04 | Paid | Medium
EXP-04141 | PRJ-005 | PRJ-005-ACT-07 | 2025-02-13 | Labour | LAB-002 | Helper | VEN-008 | 24 | Worker | 21526.68 | 23356.91 | 4204.24 | 27561.15 | Partially Paid | Medium
EXP-04142 | PRJ-005 | PRJ-005-ACT-09 | 2025-02-18 | Material | MAT-003 | Sand | VEN-005 | 2.09 | Ton | 3396.37 | 3330.48 | 599.49 | 3929.97 | Paid | Medium
EXP-04143 | PRJ-005 | PRJ-005-ACT-01 | 2025-02-18 | Other | OTH-001 | Site Office | VEN-008 | 1 | Lot | 39020.53 | 39048.96 | 7028.81 | 46077.77 | Paid | Medium
EXP-04144 | PRJ-005 | PRJ-005-ACT-01 | 2025-02-18 | Material | MAT-010 | Glass | VEN-012 | 2.94 | Sq Ft | 503.18 | 527.53 | 94.96 | 622.49 | Partially Paid | Low
EXP-04145 | PRJ-005 | PRJ-005-ACT-01 | 2025-02-18 | Material | MAT-005 | Bricks | VEN-012 | 17.29 | Piece | 184.47 | 171.87 | 30.94 | 202.81 | Partially Paid | Medium
EXP-04146 | PRJ-005 | PRJ-005-ACT-02 | 2025-02-18 | Labour | LAB-004 | Electrician | VEN-008 | 16 | Worker | 15187.69 | 15584.16 | 2805.15 | 18389.31 | Paid | Low
EXP-04147 | PRJ-005 | PRJ-005-ACT-04 | 2025-02-18 | Material | MAT-004 | Aggregate | VEN-008 | 9.71 | Ton | 15976.88 | 15014.46 | 2702.6 | 17717.06 | Paid | Low
EXP-04148 | PRJ-005 | PRJ-005-ACT-02 | 2025-02-18 | Labour | LAB-005 | Plumber | VEN-008 | 6 | Worker | 8926 | 8809.5 | 1585.71 | 10395.21 | Paid | Medium
EXP-04149 | PRJ-005 | PRJ-005-ACT-04 | 2025-02-18 | Equipment | EQ-004 | Scaffolding | VEN-012 | 3 | Day | 7101.49 | 7108.45 | 1279.52 | 8387.97 | Paid | Low
EXP-04150 | PRJ-005 | PRJ-005-ACT-02 | 2025-02-18 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 167702.82 | 180240.2 | 32443.24 | 212683.44 | Paid | Low
EXP-04151 | PRJ-005 | PRJ-005-ACT-01 | 2025-02-18 | Labour | LAB-004 | Electrician | VEN-012 | 33 | Worker | 55509.54 | 54196.18 | 9755.31 | 63951.49 | Partially Paid | High
EXP-04152 | PRJ-005 | PRJ-005-ACT-02 | 2025-02-23 | Equipment | EQ-002 | Excavator | VEN-005 | 3 | Day | 42240.12 | 39469.48 | 7104.51 | 46573.99 | Paid | High
EXP-04153 | PRJ-005 | PRJ-005-ACT-07 | 2025-02-23 | Material | MAT-002 | Steel | VEN-008 | 6.15 | Ton | 312272.74 | 327042.57 | 58867.66 | 385910.23 | Paid | Medium
EXP-04154 | PRJ-005 | PRJ-005-ACT-08 | 2025-02-23 | Material | MAT-001 | Cement | VEN-012 | 13.91 | Bag | 8416.93 | 8283.24 | 1490.98 | 9774.22 | Paid | Medium
EXP-04155 | PRJ-005 | PRJ-005-ACT-05 | 2025-02-23 | Contractor | CON-001 | Civil Structure Contract | VEN-012 | 1 | Contract | 418415.64 | 415882.68 | 74858.88 | 490741.56 | Pending | Low
EXP-04156 | PRJ-005 | PRJ-005-ACT-08 | 2025-02-23 | Material | MAT-006 | Electrical Cable | VEN-008 | 6 | Meter | 537.5 | 572.83 | 103.11 | 675.94 | Paid | Medium
EXP-04157 | PRJ-005 | PRJ-005-ACT-03 | 2025-02-23 | Material | MAT-004 | Aggregate | VEN-005 | 3.52 | Ton | 5822.2 | 5521.2 | 993.82 | 6515.02 | Paid | Medium
EXP-04158 | PRJ-005 | PRJ-005-ACT-03 | 2025-02-28 | Labour | LAB-002 | Helper | VEN-008 | 27 | Worker | 24899.41 | 25642.7 | 4615.69 | 30258.39 | Paid | Low
EXP-04159 | PRJ-005 | PRJ-005-ACT-08 | 2025-02-28 | Labour | LAB-004 | Electrician | VEN-008 | 32 | Worker | 32657.03 | 34118.2 | 6141.28 | 40259.48 | Partially Paid | Low
EXP-04160 | PRJ-005 | PRJ-005-ACT-03 | 2025-02-28 | Material | MAT-006 | Electrical Cable | VEN-012 | 5.51 | Meter | 446.29 | 421.64 | 75.9 | 497.54 | Paid | Low
EXP-04161 | PRJ-005 | PRJ-005-ACT-05 | 2025-02-28 | Material | MAT-010 | Glass | VEN-008 | 2.07 | Sq Ft | 332.01 | 338.97 | 61.01 | 399.98 | Paid | Medium
EXP-04162 | PRJ-005 | PRJ-005-ACT-05 | 2025-02-28 | Material | MAT-005 | Bricks | VEN-012 | 33.08 | Piece | 272.39 | 290.12 | 52.22 | 342.34 | Paid | Medium
EXP-04163 | PRJ-005 | PRJ-005-ACT-05 | 2025-02-28 | Contractor | CON-003 | Plumbing Contract | VEN-012 | 1 | Contract | 237354.77 | 229656.79 | 41338.22 | 270995.01 | Paid | Low
EXP-04164 | PRJ-005 | PRJ-005-ACT-05 | 2025-02-28 | Contractor | CON-002 | Electrical Contract | VEN-005 | 1 | Contract | 377614.91 | 408810.88 | 73585.96 | 482396.84 | Paid | Medium
EXP-04165 | PRJ-005 | PRJ-005-ACT-01 | 2025-02-28 | Other | OTH-001 | Miscellaneous | VEN-005 | 1 | Lot | 72179.21 | 71844.49 | 12932.01 | 84776.5 | Paid | Low
EXP-04166 | PRJ-005 | PRJ-005-ACT-10 | 2025-02-28 | Equipment | EQ-004 | Scaffolding | VEN-008 | 3 | Day | 6894.61 | 7478.58 | 1346.14 | 8824.72 | Paid | Medium
EXP-04167 | PRJ-005 | PRJ-005-ACT-10 | 2025-03-05 | Material | MAT-006 | Electrical Cable | VEN-008 | 6.25 | Meter | 574.89 | 572.65 | 103.08 | 675.73 | Paid | Low
EXP-04168 | PRJ-005 | PRJ-005-ACT-04 | 2025-03-05 | Material | MAT-006 | Electrical Cable | VEN-005 | 17.16 | Meter | 1596.25 | 1524.79 | 274.46 | 1799.25 | Paid | Low
EXP-04169 | PRJ-005 | PRJ-005-ACT-04 | 2025-03-05 | Material | MAT-008 | Tiles | VEN-008 | 26.39 | Sq Ft | 1778.34 | 1693.29 | 304.79 | 1998.08 | Paid | Low
EXP-04170 | PRJ-005 | PRJ-005-ACT-04 | 2025-03-05 | Material | MAT-008 | Tiles | VEN-005 | 16.03 | Sq Ft | 1241.23 | 1334.78 | 240.26 | 1575.04 | Paid | High
EXP-04171 | PRJ-005 | PRJ-005-ACT-08 | 2025-03-05 | Material | MAT-002 | Steel | VEN-008 | 7.61 | Ton | 530006.4 | 510106.98 | 91819.26 | 601926.24 | Partially Paid | Medium
EXP-04172 | PRJ-005 | PRJ-005-ACT-03 | 2025-03-05 | Labour | LAB-006 | Painter | VEN-008 | 34 | Worker | 42322.04 | 42103.03 | 7578.55 | 49681.58 | Paid | Medium
EXP-04173 | PRJ-005 | PRJ-005-ACT-09 | 2025-03-05 | Material | MAT-010 | Glass | VEN-008 | 1.66 | Sq Ft | 273.83 | 282.01 | 50.76 | 332.77 | Paid | High
EXP-04174 | PRJ-005 | PRJ-005-ACT-10 | 2025-03-05 | Labour | LAB-002 | Helper | VEN-012 | 32 | Worker | 50102.46 | 47425.39 | 8536.57 | 55961.96 | Paid | Low
EXP-04175 | PRJ-005 | PRJ-005-ACT-08 | 2025-03-05 | Equipment | EQ-003 | Concrete Mixer | VEN-008 | 7 | Day | 31473.8 | 31565.5 | 5681.79 | 37247.29 | Paid | Medium
EXP-04176 | PRJ-005 | PRJ-005-ACT-04 | 2025-03-10 | Labour | LAB-001 | Mason | VEN-008 | 21 | Worker | 32088.56 | 32971.18 | 5934.81 | 38905.99 | Paid | Medium
EXP-04177 | PRJ-005 | PRJ-005-ACT-10 | 2025-03-10 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 117926.73 | 109826.36 | 19768.74 | 129595.1 | Paid | Low
EXP-04178 | PRJ-005 | PRJ-005-ACT-05 | 2025-03-10 | Contractor | CON-003 | Plumbing Contract | VEN-008 | 1 | Contract | 120104.46 | 120376.89 | 21667.84 | 142044.73 | Partially Paid | Medium
EXP-04179 | PRJ-005 | PRJ-005-ACT-10 | 2025-03-10 | Material | MAT-008 | Tiles | VEN-008 | 5.25 | Sq Ft | 410.01 | 396.94 | 71.45 | 468.39 | Paid | Low
EXP-04180 | PRJ-005 | PRJ-005-ACT-08 | 2025-03-10 | Other | OTH-001 | Permit | VEN-012 | 1 | Lot | 16852.29 | 17937.92 | 3228.83 | 21166.75 | Paid | Medium
EXP-04181 | PRJ-005 | PRJ-005-ACT-04 | 2025-03-10 | Equipment | EQ-004 | Scaffolding | VEN-012 | 3 | Day | 7842.35 | 8116.76 | 1461.02 | 9577.78 | Partially Paid | Low
EXP-04182 | PRJ-005 | PRJ-005-ACT-09 | 2025-03-15 | Labour | LAB-004 | Electrician | VEN-005 | 24 | Worker | 19353.38 | 20277.14 | 3649.89 | 23927.03 | Paid | Medium
EXP-04183 | PRJ-005 | PRJ-005-ACT-02 | 2025-03-15 | Material | MAT-009 | Paint | VEN-008 | 9.4 | Litre | 2044.52 | 1984.31 | 357.18 | 2341.49 | Paid | Medium
EXP-04184 | PRJ-005 | PRJ-005-ACT-08 | 2025-03-15 | Labour | LAB-006 | Painter | VEN-005 | 31 | Worker | 49777.98 | 48686.54 | 8763.58 | 57450.12 | Paid | Low
EXP-04185 | PRJ-005 | PRJ-005-ACT-09 | 2025-03-15 | Material | MAT-002 | Steel | VEN-012 | 6.85 | Ton | 418572.42 | 419134.21 | 75444.16 | 494578.37 | Paid | Medium
EXP-04186 | PRJ-005 | PRJ-005-ACT-01 | 2025-03-15 | Material | MAT-002 | Steel | VEN-012 | 3.38 | Ton | 188212.92 | 183166.59 | 32969.99 | 216136.58 | Paid | Low
EXP-04187 | PRJ-005 | PRJ-005-ACT-07 | 2025-03-15 | Material | MAT-004 | Aggregate | VEN-005 | 7.12 | Ton | 9992.86 | 9778.9 | 1760.2 | 11539.1 | Paid | Low
EXP-04188 | PRJ-005 | PRJ-005-ACT-07 | 2025-03-15 | Labour | LAB-005 | Plumber | VEN-012 | 26 | Worker | 22673.44 | 24605.02 | 4428.9 | 29033.92 | Paid | Medium
EXP-04189 | PRJ-005 | PRJ-005-ACT-06 | 2025-03-15 | Contractor | CON-003 | Plumbing Contract | VEN-012 | 1 | Contract | 144588.79 | 151415.39 | 27254.77 | 178670.16 | Paid | Medium
EXP-04190 | PRJ-005 | PRJ-005-ACT-05 | 2025-03-15 | Material | MAT-003 | Sand | VEN-005 | 7.27 | Ton | 15930.75 | 14758.11 | 2656.46 | 17414.57 | Paid | Medium
EXP-04191 | PRJ-005 | PRJ-005-ACT-09 | 2025-03-15 | Material | MAT-008 | Tiles | VEN-012 | 22.48 | Sq Ft | 1658.95 | 1610.58 | 289.9 | 1900.48 | Paid | Medium
EXP-04192 | PRJ-005 | PRJ-005-ACT-02 | 2025-03-20 | Material | MAT-001 | Cement | VEN-005 | 6.33 | Bag | 3490.42 | 3714.04 | 668.53 | 4382.57 | Paid | Low
EXP-04193 | PRJ-005 | PRJ-005-ACT-02 | 2025-03-20 | Labour | LAB-003 | Carpenter | VEN-005 | 34 | Worker | 45862.19 | 45810.82 | 8245.95 | 54056.77 | Paid | Low
EXP-04194 | PRJ-005 | PRJ-005-ACT-05 | 2025-03-20 | Labour | LAB-005 | Plumber | VEN-012 | 19 | Worker | 17814.98 | 18680.46 | 3362.48 | 22042.94 | Paid | High
EXP-04195 | PRJ-005 | PRJ-005-ACT-05 | 2025-03-20 | Material | MAT-002 | Steel | VEN-008 | 3.45 | Ton | 252831.55 | 234132.34 | 42143.82 | 276276.16 | Paid | Medium
EXP-04196 | PRJ-005 | PRJ-005-ACT-04 | 2025-03-20 | Material | MAT-001 | Cement | VEN-005 | 3.2 | Bag | 1843 | 1870.59 | 336.71 | 2207.3 | Paid | Medium
EXP-04197 | PRJ-005 | PRJ-005-ACT-09 | 2025-03-20 | Material | MAT-004 | Aggregate | VEN-012 | 7.91 | Ton | 11519.49 | 11871.63 | 2136.89 | 14008.52 | Paid | Low
EXP-04198 | PRJ-005 | PRJ-005-ACT-05 | 2025-03-20 | Labour | LAB-004 | Electrician | VEN-008 | 4 | Worker | 4729.02 | 4791.59 | 862.49 | 5654.08 | Paid | Low
EXP-04199 | PRJ-005 | PRJ-005-ACT-01 | 2025-03-20 | Labour | LAB-001 | Mason | VEN-005 | 28 | Worker | 34232.05 | 32147.64 | 5786.58 | 37934.22 | Paid | Low
EXP-04200 | PRJ-005 | PRJ-005-ACT-05 | 2025-03-25 | Material | MAT-006 | Electrical Cable | VEN-005 | 10.41 | Meter | 891.41 | 898.94 | 161.81 | 1060.75 | Pending | Low
EXP-04201 | PRJ-005 | PRJ-005-ACT-08 | 2025-03-25 | Equipment | EQ-003 | Concrete Mixer | VEN-005 | 5 | Day | 23958.96 | 23490.45 | 4228.28 | 27718.73 | Paid | Low
EXP-04202 | PRJ-005 | PRJ-005-ACT-05 | 2025-03-25 | Equipment | EQ-001 | Crane | VEN-012 | 4 | Day | 62669.06 | 66728.58 | 12011.14 | 78739.72 | Partially Paid | Medium
EXP-04203 | PRJ-005 | PRJ-005-ACT-06 | 2025-03-25 | Other | OTH-001 | Transport | VEN-005 | 1 | Lot | 16746.57 | 17070.67 | 3072.72 | 20143.39 | Paid | Low
EXP-04204 | PRJ-005 | PRJ-005-ACT-10 | 2025-03-25 | Material | MAT-003 | Sand | VEN-008 | 9.8 | Ton | 18098.53 | 17942.73 | 3229.69 | 21172.42 | Paid | Low
EXP-04205 | PRJ-005 | PRJ-005-ACT-08 | 2025-03-25 | Labour | LAB-002 | Helper | VEN-005 | 10 | Worker | 11186.37 | 11608.96 | 2089.61 | 13698.57 | Paid | Medium
EXP-04206 | PRJ-005 | PRJ-005-ACT-10 | 2025-03-25 | Material | MAT-010 | Glass | VEN-005 | 3.01 | Sq Ft | 531.63 | 525.47 | 94.58 | 620.05 | Paid | Low
EXP-04207 | PRJ-005 | PRJ-005-ACT-04 | 2025-03-25 | Material | MAT-004 | Aggregate | VEN-012 | 8.56 | Ton | 12705.09 | 13378.31 | 2408.1 | 15786.41 | Partially Paid | Medium
EXP-04208 | PRJ-005 | PRJ-005-ACT-07 | 2025-03-25 | Material | MAT-010 | Glass | VEN-008 | 5.33 | Sq Ft | 768.1 | 741.45 | 133.46 | 874.91 | Paid | Medium
EXP-04209 | PRJ-005 | PRJ-005-ACT-08 | 2025-03-30 | Material | MAT-006 | Electrical Cable | VEN-012 | 11.31 | Meter | 819.3 | 835.58 | 150.4 | 985.98 | Paid | Low
EXP-04210 | PRJ-005 | PRJ-005-ACT-05 | 2025-03-30 | Contractor | CON-001 | Civil Structure Contract | VEN-012 | 1 | Contract | 227288.62 | 237667.13 | 42780.08 | 280447.21 | Paid | Medium
EXP-04211 | PRJ-005 | PRJ-005-ACT-03 | 2025-03-30 | Labour | LAB-002 | Helper | VEN-008 | 12 | Worker | 12828.71 | 13140.53 | 2365.3 | 15505.83 | Partially Paid | Low
EXP-04212 | PRJ-005 | PRJ-005-ACT-08 | 2025-03-30 | Other | OTH-001 | Site Office | VEN-005 | 1 | Lot | 17665.69 | 17205.78 | 3097.04 | 20302.82 | Paid | High
EXP-04213 | PRJ-005 | PRJ-005-ACT-06 | 2025-03-30 | Material | MAT-005 | Bricks | VEN-005 | 4.74 | Piece | 38.76 | 37.68 | 6.78 | 44.46 | Paid | Medium
EXP-04214 | PRJ-005 | PRJ-005-ACT-06 | 2025-03-30 | Contractor | CON-004 | Finishing Contract | VEN-012 | 1 | Contract | 285154.4 | 290091.59 | 52216.49 | 342308.08 | Paid | Low
EXP-04215 | PRJ-005 | PRJ-005-ACT-03 | 2025-03-30 | Contractor | CON-004 | Finishing Contract | VEN-012 | 1 | Contract | 218590.03 | 237381.48 | 42728.67 | 280110.15 | Paid | Low
EXP-04216 | PRJ-005 | PRJ-005-ACT-05 | 2025-03-30 | Equipment | EQ-003 | Concrete Mixer | VEN-012 | 4 | Day | 17102.66 | 17925.51 | 3226.59 | 21152.1 | Paid | Low
EXP-04217 | PRJ-005 | PRJ-005-ACT-03 | 2025-04-04 | Material | MAT-005 | Bricks | VEN-008 | 6.22 | Piece | 55.99 | 60.05 | 10.81 | 70.86 | Paid | Medium
EXP-04218 | PRJ-005 | PRJ-005-ACT-07 | 2025-04-04 | Equipment | EQ-003 | Concrete Mixer | VEN-008 | 2 | Day | 7832.82 | 8262.59 | 1487.27 | 9749.86 | Paid | Low
EXP-04219 | PRJ-005 | PRJ-005-ACT-08 | 2025-04-04 | Material | MAT-009 | Paint | VEN-005 | 8.12 | Litre | 1807.44 | 1902.28 | 342.41 | 2244.69 | Paid | High
EXP-04220 | PRJ-005 | PRJ-005-ACT-04 | 2025-04-04 | Labour | LAB-002 | Helper | VEN-012 | 21 | Worker | 36079.15 | 34169.26 | 6150.47 | 40319.73 | Paid | Medium
EXP-04221 | PRJ-005 | PRJ-005-ACT-01 | 2025-04-04 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 307162.93 | 301875.64 | 54337.62 | 356213.26 | Paid | Medium
EXP-04222 | PRJ-005 | PRJ-005-ACT-10 | 2025-04-04 | Material | MAT-005 | Bricks | VEN-005 | 3.72 | Piece | 36.7 | 35.49 | 6.39 | 41.88 | Paid | Low
EXP-04223 | PRJ-005 | PRJ-005-ACT-05 | 2025-04-04 | Contractor | CON-004 | Finishing Contract | VEN-008 | 1 | Contract | 462428.46 | 430518.58 | 77493.34 | 508011.92 | Paid | Low
EXP-04224 | PRJ-005 | PRJ-005-ACT-02 | 2025-04-04 | Material | MAT-009 | Paint | VEN-008 | 18.09 | Litre | 4014.06 | 3720.17 | 669.63 | 4389.8 | Paid | Medium
EXP-04225 | PRJ-005 | PRJ-005-ACT-08 | 2025-04-04 | Contractor | CON-001 | Civil Structure Contract | VEN-012 | 1 | Contract | 287627.4 | 286385.59 | 51549.41 | 337935 | Paid | Low
EXP-04226 | PRJ-005 | PRJ-005-ACT-03 | 2025-04-04 | Labour | LAB-004 | Electrician | VEN-012 | 32 | Worker | 50947.23 | 49251.71 | 8865.31 | 58117.02 | Paid | Medium
EXP-04227 | PRJ-005 | PRJ-005-ACT-07 | 2025-04-09 | Material | MAT-009 | Paint | VEN-005 | 16.16 | Litre | 3206.9 | 3084.01 | 555.12 | 3639.13 | Paid | Low
EXP-04228 | PRJ-005 | PRJ-005-ACT-08 | 2025-04-09 | Material | MAT-001 | Cement | VEN-005 | 13.01 | Bag | 7585.75 | 7551.96 | 1359.35 | 8911.31 | Paid | Low
EXP-04229 | PRJ-005 | PRJ-005-ACT-05 | 2025-04-09 | Material | MAT-006 | Electrical Cable | VEN-008 | 5.59 | Meter | 497.82 | 463.73 | 83.47 | 547.2 | Paid | Medium
EXP-04230 | PRJ-005 | PRJ-005-ACT-02 | 2025-04-09 | Material | MAT-010 | Glass | VEN-008 | 7.24 | Sq Ft | 1196.65 | 1126.86 | 202.83 | 1329.69 | Paid | Medium
EXP-04231 | PRJ-005 | PRJ-005-ACT-07 | 2025-04-09 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 254898.15 | 240869.57 | 43356.52 | 284226.09 | Paid | Medium
EXP-04232 | PRJ-005 | PRJ-005-ACT-04 | 2025-04-09 | Material | MAT-004 | Aggregate | VEN-005 | 26.76 | Ton | 39955.19 | 39935.17 | 7188.33 | 47123.5 | Pending | Low
EXP-04233 | PRJ-005 | PRJ-005-ACT-09 | 2025-04-14 | Labour | LAB-006 | Painter | VEN-012 | 17 | Worker | 27251.88 | 26206.64 | 4717.2 | 30923.84 | Paid | Low
EXP-04234 | PRJ-005 | PRJ-005-ACT-03 | 2025-04-14 | Material | MAT-008 | Tiles | VEN-012 | 10.55 | Sq Ft | 892.4 | 845.88 | 152.26 | 998.14 | Paid | Medium
EXP-04235 | PRJ-005 | PRJ-005-ACT-01 | 2025-04-14 | Material | MAT-009 | Paint | VEN-008 | 6.47 | Litre | 1440.88 | 1522.9 | 274.12 | 1797.02 | Paid | Low
EXP-04236 | PRJ-005 | PRJ-005-ACT-07 | 2025-04-14 | Contractor | CON-002 | Electrical Contract | VEN-008 | 1 | Contract | 267971.7 | 260899.73 | 46961.95 | 307861.68 | Paid | Low
EXP-04237 | PRJ-005 | PRJ-005-ACT-02 | 2025-04-14 | Labour | LAB-001 | Mason | VEN-005 | 30 | Worker | 44468.53 | 42079.37 | 7574.29 | 49653.66 | Paid | Medium
EXP-04238 | PRJ-005 | PRJ-005-ACT-05 | 2025-04-14 | Labour | LAB-006 | Painter | VEN-005 | 14 | Worker | 8895.56 | 9497.39 | 1709.53 | 11206.92 | Pending | Medium
EXP-04239 | PRJ-005 | PRJ-005-ACT-08 | 2025-04-19 | Material | MAT-009 | Paint | VEN-005 | 14.2 | Litre | 3441.01 | 3321.08 | 597.79 | 3918.87 | Paid | Medium
EXP-04240 | PRJ-005 | PRJ-005-ACT-01 | 2025-04-19 | Equipment | EQ-001 | Crane | VEN-008 | 3 | Day | 49649.5 | 49888.56 | 8979.94 | 58868.5 | Paid | High
EXP-04241 | PRJ-005 | PRJ-005-ACT-07 | 2025-04-19 | Material | MAT-005 | Bricks | VEN-012 | 2.95 | Piece | 24.4 | 22.97 | 4.13 | 27.1 | Paid | Medium
EXP-04242 | PRJ-005 | PRJ-005-ACT-10 | 2025-04-19 | Material | MAT-010 | Glass | VEN-005 | 9.41 | Sq Ft | 1407.32 | 1520.37 | 273.67 | 1794.04 | Partially Paid | Low
EXP-04243 | PRJ-005 | PRJ-005-ACT-09 | 2025-04-19 | Contractor | CON-002 | Electrical Contract | VEN-008 | 1 | Contract | 476423.69 | 449394.43 | 80891 | 530285.43 | Paid | Low
EXP-04244 | PRJ-005 | PRJ-005-ACT-04 | 2025-04-19 | Contractor | CON-002 | Electrical Contract | VEN-008 | 1 | Contract | 113076.32 | 108460.12 | 19522.82 | 127982.94 | Partially Paid | High
EXP-04245 | PRJ-005 | PRJ-005-ACT-06 | 2025-04-24 | Material | MAT-009 | Paint | VEN-008 | 12.63 | Litre | 2756.85 | 2661.01 | 478.98 | 3139.99 | Paid | Low
EXP-04246 | PRJ-005 | PRJ-005-ACT-09 | 2025-04-24 | Material | MAT-010 | Glass | VEN-005 | 3.14 | Sq Ft | 559.68 | 568.28 | 102.29 | 670.57 | Paid | Medium
EXP-04247 | PRJ-005 | PRJ-005-ACT-04 | 2025-04-24 | Contractor | CON-001 | Civil Structure Contract | VEN-012 | 1 | Contract | 334880.93 | 332275.39 | 59809.57 | 392084.96 | Paid | Low
EXP-04248 | PRJ-005 | PRJ-005-ACT-01 | 2025-04-24 | Material | MAT-010 | Glass | VEN-008 | 5.94 | Sq Ft | 1044.85 | 1026.53 | 184.78 | 1211.31 | Partially Paid | Medium
EXP-04249 | PRJ-005 | PRJ-005-ACT-02 | 2025-04-24 | Labour | LAB-001 | Mason | VEN-008 | 21 | Worker | 31590.69 | 34045.69 | 6128.22 | 40173.91 | Paid | Medium
EXP-04250 | PRJ-005 | PRJ-005-ACT-08 | 2025-04-24 | Contractor | CON-002 | Electrical Contract | VEN-012 | 1 | Contract | 274509.07 | 286464.73 | 51563.65 | 338028.38 | Paid | High
EXP-04251 | PRJ-005 | PRJ-005-ACT-05 | 2025-04-24 | Contractor | CON-001 | Civil Structure Contract | VEN-008 | 1 | Contract | 297370.43 | 296474.17 | 53365.35 | 349839.52 | Paid | Medium
EXP-04252 | PRJ-005 | PRJ-005-ACT-10 | 2025-04-24 | Material | MAT-006 | Electrical Cable | VEN-005 | 5.01 | Meter | 380.94 | 382.1 | 68.78 | 450.88 | Paid | High
EXP-04253 | PRJ-005 | PRJ-005-ACT-04 | 2025-04-24 | Labour | LAB-003 | Carpenter | VEN-005 | 29 | Worker | 30525.69 | 32479.79 | 5846.36 | 38326.15 | Paid | Low
EXP-04254 | PRJ-005 | PRJ-005-ACT-01 | 2025-04-29 | Material | MAT-004 | Aggregate | VEN-005 | 4.62 | Ton | 6698.73 | 6619.58 | 1191.52 | 7811.1 | Paid | Low
EXP-04255 | PRJ-005 | PRJ-005-ACT-05 | 2025-04-29 | Material | MAT-004 | Aggregate | VEN-005 | 9.71 | Ton | 15871.78 | 15373.33 | 2767.2 | 18140.53 | Paid | High
EXP-04256 | PRJ-005 | PRJ-005-ACT-03 | 2025-04-29 | Material | MAT-006 | Electrical Cable | VEN-012 | 4.69 | Meter | 381.93 | 373.97 | 67.31 | 441.28 | Paid | Low
EXP-04257 | PRJ-005 | PRJ-005-ACT-03 | 2025-04-29 | Material | MAT-009 | Paint | VEN-008 | 2.52 | Litre | 579.99 | 564.54 | 101.62 | 666.16 | Paid | Medium
EXP-04258 | PRJ-005 | PRJ-005-ACT-01 | 2025-04-29 | Contractor | CON-004 | Finishing Contract | VEN-008 | 1 | Contract | 267432.75 | 275673.19 | 49621.17 | 325294.36 | Paid | Low
EXP-04259 | PRJ-005 | PRJ-005-ACT-05 | 2025-04-29 | Material | MAT-002 | Steel | VEN-008 | 26.58 | Ton | 1510993.25 | 1542825.03 | 277708.51 | 1820533.54 | Paid | Low
EXP-04260 | PRJ-005 | PRJ-005-ACT-02 | 2025-04-29 | Material | MAT-009 | Paint | VEN-005 | 2.55 | Litre | 584.68 | 582.3 | 104.81 | 687.11 | Paid | Medium
EXP-04261 | PRJ-005 | PRJ-005-ACT-06 | 2025-05-04 | Material | MAT-004 | Aggregate | VEN-005 | 4.25 | Ton | 5630.61 | 5831.54 | 1049.68 | 6881.22 | Partially Paid | High
EXP-04262 | PRJ-005 | PRJ-005-ACT-04 | 2025-05-04 | Contractor | CON-004 | Finishing Contract | VEN-012 | 1 | Contract | 260128.37 | 245793.39 | 44242.81 | 290036.2 | Paid | Low
EXP-04263 | PRJ-005 | PRJ-005-ACT-09 | 2025-05-04 | Material | MAT-001 | Cement | VEN-005 | 5.6 | Bag | 2942.57 | 3101.76 | 558.32 | 3660.08 | Paid | Medium
EXP-04264 | PRJ-005 | PRJ-005-ACT-06 | 2025-05-04 | Labour | LAB-002 | Helper | VEN-005 | 29 | Worker | 44534.63 | 48152.68 | 8667.48 | 56820.16 | Partially Paid | Medium
EXP-04265 | PRJ-005 | PRJ-005-ACT-03 | 2025-05-04 | Material | MAT-010 | Glass | VEN-008 | 7.01 | Sq Ft | 1071.33 | 1157.58 | 208.36 | 1365.94 | Paid | Low
EXP-04266 | PRJ-005 | PRJ-005-ACT-01 | 2025-05-04 | Equipment | EQ-004 | Scaffolding | VEN-008 | 2 | Day | 5347.77 | 5493.81 | 988.89 | 6482.7 | Paid | Low
EXP-04267 | PRJ-005 | PRJ-005-ACT-02 | 2025-05-04 | Material | MAT-004 | Aggregate | VEN-008 | 4.4 | Ton | 6691.87 | 6869.34 | 1236.48 | 8105.82 | Partially Paid | Low
EXP-04268 | PRJ-005 | PRJ-005-ACT-05 | 2025-05-04 | Material | MAT-008 | Tiles | VEN-012 | 19.49 | Sq Ft | 1370.69 | 1413.01 | 254.34 | 1667.35 | Paid | Medium
EXP-04269 | PRJ-005 | PRJ-005-ACT-06 | 2025-05-04 | Other | OTH-001 | Miscellaneous | VEN-012 | 1 | Lot | 67032.27 | 70312.97 | 12656.33 | 82969.3 | Paid | Low
EXP-04270 | PRJ-005 | PRJ-005-ACT-10 | 2025-05-09 | Contractor | CON-002 | Electrical Contract | VEN-005 | 1 | Contract | 290634.61 | 282263.33 | 50807.4 | 333070.73 | Paid | Medium
EXP-04271 | PRJ-005 | PRJ-005-ACT-04 | 2025-05-09 | Material | MAT-010 | Glass | VEN-008 | 16.85 | Sq Ft | 2498.5 | 2686.03 | 483.49 | 3169.52 | Paid | Medium
EXP-04272 | PRJ-005 | PRJ-005-ACT-06 | 2025-05-09 | Material | MAT-009 | Paint | VEN-008 | 8.71 | Litre | 1877.17 | 2002.06 | 360.37 | 2362.43 | Paid | Low
EXP-04273 | PRJ-005 | PRJ-005-ACT-10 | 2025-05-09 | Labour | LAB-005 | Plumber | VEN-005 | 11 | Worker | 14597.9 | 15675.82 | 2821.65 | 18497.47 | Partially Paid | Medium
EXP-04274 | PRJ-005 | PRJ-005-ACT-02 | 2025-05-09 | Material | MAT-009 | Paint | VEN-005 | 32.62 | Litre | 7192.47 | 7610.81 | 1369.95 | 8980.76 | Pending | High
EXP-04275 | PRJ-005 | PRJ-005-ACT-08 | 2025-05-09 | Other | OTH-001 | Transport | VEN-012 | 1 | Lot | 59679.97 | 59163.42 | 10649.42 | 69812.84 | Paid | Medium
EXP-04276 | PRJ-005 | PRJ-005-ACT-02 | 2025-05-09 | Contractor | CON-003 | Plumbing Contract | VEN-005 | 1 | Contract | 184684.77 | 171823.11 | 30928.16 | 202751.27 | Partially Paid | Low
EXP-04277 | PRJ-005 | PRJ-005-ACT-02 | 2025-05-09 | Contractor | CON-003 | Plumbing Contract | VEN-005 | 1 | Contract | 229979.9 | 223900.97 | 40302.17 | 264203.14 | Paid | High
EXP-04278 | PRJ-005 | PRJ-005-ACT-01 | 2025-05-09 | Contractor | CON-002 | Electrical Contract | VEN-008 | 1 | Contract | 216743.38 | 225471.82 | 40584.93 | 266056.75 | Pending | Medium
EXP-04279 | PRJ-005 | PRJ-005-ACT-08 | 2025-05-09 | Material | MAT-007 | PVC Pipe | VEN-012 | 10.6 | Meter | 1262.18 | 1248.3 | 224.69 | 1472.99 | Paid | Low
EXP-04280 | PRJ-005 | PRJ-005-ACT-08 | 2025-05-14 | Material | MAT-010 | Glass | VEN-008 | 3.81 | Sq Ft | 493.41 | 527.21 | 94.9 | 622.11 | Paid | Low
EXP-04281 | PRJ-005 | PRJ-005-ACT-10 | 2025-05-14 | Other | OTH-001 | Permit | VEN-012 | 1 | Lot | 30816.04 | 29023.89 | 5224.3 | 34248.19 | Paid | Medium
EXP-04282 | PRJ-005 | PRJ-005-ACT-04 | 2025-05-14 | Material | MAT-005 | Bricks | VEN-008 | 14.83 | Piece | 134.52 | 132.82 | 23.91 | 156.73 | Paid | Low
EXP-04283 | PRJ-005 | PRJ-005-ACT-01 | 2025-05-14 | Contractor | CON-004 | Finishing Contract | VEN-008 | 1 | Contract | 94172.21 | 88007.34 | 15841.32 | 103848.66 | Paid | Low
EXP-04284 | PRJ-005 | PRJ-005-ACT-03 | 2025-05-14 | Contractor | CON-002 | Electrical Contract | VEN-008 | 1 | Contract | 113450.35 | 109814.7 | 19766.65 | 129581.35 | Paid | Low
EXP-04285 | PRJ-005 | PRJ-005-ACT-06 | 2025-05-14 | Material | MAT-010 | Glass | VEN-012 | 5.81 | Sq Ft | 902.91 | 966.99 | 174.06 | 1141.05 | Paid | Low
EXP-04286 | PRJ-005 | PRJ-005-ACT-03 | 2025-05-14 | Material | MAT-002 | Steel | VEN-005 | 8.5 | Ton | 491985.21 | 465359.46 | 83764.7 | 549124.16 | Paid | Low
EXP-04287 | PRJ-005 | PRJ-005-ACT-08 | 2025-05-19 | Labour | LAB-004 | Electrician | VEN-008 | 10 | Worker | 8998.53 | 9558.38 | 1720.51 | 11278.89 | Paid | Medium
EXP-04288 | PRJ-005 | PRJ-005-ACT-08 | 2025-05-19 | Material | MAT-002 | Steel | VEN-008 | 6.08 | Ton | 389328.15 | 364998.82 | 65699.79 | 430698.61 | Paid | Low
EXP-04289 | PRJ-005 | PRJ-005-ACT-07 | 2025-05-19 | Material | MAT-005 | Bricks | VEN-012 | 3.92 | Piece | 28.59 | 30.17 | 5.43 | 35.6 | Paid | High
EXP-04290 | PRJ-005 | PRJ-005-ACT-10 | 2025-05-19 | Material | MAT-002 | Steel | VEN-005 | 5.39 | Ton | 356273.76 | 333231.91 | 59981.74 | 393213.65 | Paid | Low
EXP-04291 | PRJ-005 | PRJ-005-ACT-10 | 2025-05-19 | Material | MAT-004 | Aggregate | VEN-005 | 6.71 | Ton | 10620.77 | 10667.99 | 1920.24 | 12588.23 | Partially Paid | Low
EXP-04292 | PRJ-005 | PRJ-005-ACT-07 | 2025-05-19 | Labour | LAB-002 | Helper | VEN-005 | 12 | Worker | 10108.06 | 10412.83 | 1874.31 | 12287.14 | Paid | Low
EXP-04293 | PRJ-005 | PRJ-005-ACT-02 | 2025-05-19 | Labour | LAB-005 | Plumber | VEN-008 | 28 | Worker | 47198.81 | 50143.26 | 9025.79 | 59169.05 | Paid | High
EXP-04294 | PRJ-005 | PRJ-005-ACT-01 | 2025-05-19 | Labour | LAB-004 | Electrician | VEN-008 | 19 | Worker | 25086.81 | 24312.54 | 4376.26 | 28688.8 | Paid | Low
EXP-04295 | PRJ-005 | PRJ-005-ACT-01 | 2025-05-19 | Material | MAT-009 | Paint | VEN-005 | 5.47 | Litre | 1148.24 | 1073.54 | 193.24 | 1266.78 | Paid | Low
EXP-04296 | PRJ-005 | PRJ-005-ACT-03 | 2025-05-24 | Contractor | CON-002 | Electrical Contract | VEN-008 | 1 | Contract | 99334.04 | 101455.13 | 18261.92 | 119717.05 | Paid | Medium
EXP-04297 | PRJ-005 | PRJ-005-ACT-09 | 2025-05-24 | Labour | LAB-003 | Carpenter | VEN-008 | 31 | Worker | 22155.83 | 23279.37 | 4190.29 | 27469.66 | Paid | Low
EXP-04298 | PRJ-005 | PRJ-005-ACT-04 | 2025-05-24 | Labour | LAB-004 | Electrician | VEN-012 | 23 | Worker | 26026.22 | 24119.05 | 4341.43 | 28460.48 | Paid | Medium
EXP-04299 | PRJ-005 | PRJ-005-ACT-02 | 2025-05-24 | Contractor | CON-002 | Electrical Contract | VEN-012 | 1 | Contract | 124542.42 | 132423.03 | 23836.15 | 156259.18 | Paid | Medium
EXP-04300 | PRJ-005 | PRJ-005-ACT-04 | 2025-05-24 | Material | MAT-004 | Aggregate | VEN-005 | 16.03 | Ton | 24480.84 | 26561.6 | 4781.09 | 31342.69 | Partially Paid | Low
EXP-04301 | PRJ-005 | PRJ-005-ACT-08 | 2025-05-24 | Equipment | EQ-001 | Crane | VEN-012 | 4 | Day | 67309.93 | 67152.91 | 12087.52 | 79240.43 | Paid | Medium
EXP-04302 | PRJ-005 | PRJ-005-ACT-09 | 2025-05-29 | Labour | LAB-002 | Helper | VEN-005 | 16 | Worker | 13842.72 | 14760.2 | 2656.84 | 17417.04 | Paid | Medium
EXP-04303 | PRJ-005 | PRJ-005-ACT-01 | 2025-05-29 | Material | MAT-006 | Electrical Cable | VEN-012 | 40.02 | Meter | 3085.58 | 3036.16 | 546.51 | 3582.67 | Pending | High
EXP-04304 | PRJ-005 | PRJ-005-ACT-10 | 2025-05-29 | Contractor | CON-003 | Plumbing Contract | VEN-008 | 1 | Contract | 219177.86 | 209976.87 | 37795.84 | 247772.71 | Paid | Medium
EXP-04305 | PRJ-005 | PRJ-005-ACT-06 | 2025-05-29 | Material | MAT-007 | PVC Pipe | VEN-005 | 24.68 | Meter | 2891.91 | 2913.26 | 524.39 | 3437.65 | Paid | High
EXP-04306 | PRJ-005 | PRJ-005-ACT-03 | 2025-05-29 | Labour | LAB-004 | Electrician | VEN-005 | 6 | Worker | 7156.01 | 7447.54 | 1340.56 | 8788.1 | Paid | Low
EXP-04307 | PRJ-005 | PRJ-005-ACT-06 | 2025-05-29 | Material | MAT-010 | Glass | VEN-005 | 3.58 | Sq Ft | 586.62 | 622.47 | 112.04 | 734.51 | Paid | Low
EXP-04308 | PRJ-005 | PRJ-005-ACT-09 | 2025-05-29 | Material | MAT-002 | Steel | VEN-005 | 5.5 | Ton | 358605.04 | 358189.56 | 64474.12 | 422663.68 | Partially Paid | Low
EXP-04309 | PRJ-005 | PRJ-005-ACT-04 | 2025-05-29 | Contractor | CON-004 | Finishing Contract | VEN-012 | 1 | Contract | 113145.51 | 108979.42 | 19616.3 | 128595.72 | Paid | Medium
EXP-04310 | PRJ-005 | PRJ-005-ACT-03 | 2025-06-03 | Equipment | EQ-004 | Scaffolding | VEN-012 | 3 | Day | 7028.25 | 7109.11 | 1279.64 | 8388.75 | Paid | Low
EXP-04311 | PRJ-005 | PRJ-005-ACT-10 | 2025-06-03 | Equipment | EQ-002 | Excavator | VEN-008 | 2 | Day | 25395.95 | 25267.59 | 4548.17 | 29815.76 | Paid | Low
EXP-04312 | PRJ-005 | PRJ-005-ACT-04 | 2025-06-03 | Material | MAT-010 | Glass | VEN-008 | 2.03 | Sq Ft | 309.01 | 317.98 | 57.24 | 375.22 | Paid | High
EXP-04313 | PRJ-005 | PRJ-005-ACT-08 | 2025-06-03 | Material | MAT-007 | PVC Pipe | VEN-012 | 4.65 | Meter | 589.52 | 556.97 | 100.25 | 657.22 | Partially Paid | Low
EXP-04314 | PRJ-005 | PRJ-005-ACT-10 | 2025-06-03 | Material | MAT-007 | PVC Pipe | VEN-008 | 30.77 | Meter | 3804.85 | 3736.53 | 672.58 | 4409.11 | Paid | High
EXP-04315 | PRJ-005 | PRJ-005-ACT-06 | 2025-06-03 | Contractor | CON-004 | Finishing Contract | VEN-012 | 1 | Contract | 406793.31 | 377233.55 | 67902.04 | 445135.59 | Partially Paid | Low
EXP-04316 | PRJ-005 | PRJ-005-ACT-04 | 2025-06-03 | Material | MAT-005 | Bricks | VEN-005 | 10.23 | Piece | 91.31 | 87.52 | 15.75 | 103.27 | Paid | Medium
EXP-04317 | PRJ-005 | PRJ-005-ACT-05 | 2025-06-08 | Labour | LAB-003 | Carpenter | VEN-005 | 29 | Worker | 34148.33 | 36116.59 | 6500.99 | 42617.58 | Partially Paid | Medium
EXP-04318 | PRJ-005 | PRJ-005-ACT-10 | 2025-06-08 | Contractor | CON-004 | Finishing Contract | VEN-012 | 1 | Contract | 370521.71 | 370926.4 | 66766.75 | 437693.15 | Paid | Low
EXP-04319 | PRJ-005 | PRJ-005-ACT-03 | 2025-06-08 | Equipment | EQ-004 | Scaffolding | VEN-008 | 2 | Day | 5256.59 | 5193.74 | 934.87 | 6128.61 | Paid | Low
EXP-04320 | PRJ-005 | PRJ-005-ACT-04 | 2025-06-08 | Other | OTH-001 | Transport | VEN-012 | 1 | Lot | 47779.44 | 45346.23 | 8162.32 | 53508.55 | Paid | Low
EXP-04321 | PRJ-005 | PRJ-005-ACT-05 | 2025-06-08 | Material | MAT-004 | Aggregate | VEN-008 | 11.99 | Ton | 18713.3 | 18035.64 | 3246.42 | 21282.06 | Paid | Low
EXP-04322 | PRJ-005 | PRJ-005-ACT-05 | 2025-06-08 | Equipment | EQ-004 | Scaffolding | VEN-008 | 5 | Day | 13322.24 | 13622.39 | 2452.03 | 16074.42 | Paid | Low
EXP-04323 | PRJ-005 | PRJ-005-ACT-02 | 2025-06-13 | Contractor | CON-001 | Civil Structure Contract | VEN-008 | 1 | Contract | 396534.17 | 410329.24 | 73859.26 | 484188.5 | Paid | High
EXP-04324 | PRJ-005 | PRJ-005-ACT-02 | 2025-06-13 | Material | MAT-005 | Bricks | VEN-008 | 3.41 | Piece | 26.27 | 26.9 | 4.84 | 31.74 | Paid | High
EXP-04325 | PRJ-005 | PRJ-005-ACT-09 | 2025-06-13 | Material | MAT-008 | Tiles | VEN-005 | 23.78 | Sq Ft | 1865.58 | 1909.59 | 343.73 | 2253.32 | Paid | Low
EXP-04326 | PRJ-005 | PRJ-005-ACT-03 | 2025-06-13 | Labour | LAB-005 | Plumber | VEN-005 | 22 | Worker | 18841.36 | 18499.8 | 3329.96 | 21829.76 | Pending | Low
EXP-04327 | PRJ-005 | PRJ-005-ACT-03 | 2025-06-13 | Labour | LAB-002 | Helper | VEN-008 | 14 | Worker | 23232.63 | 24870.13 | 4476.62 | 29346.75 | Partially Paid | Low
EXP-04328 | PRJ-005 | PRJ-005-ACT-07 | 2025-06-13 | Material | MAT-001 | Cement | VEN-012 | 3.94 | Bag | 1967.57 | 1880.38 | 338.47 | 2218.85 | Paid | Low
EXP-04329 | PRJ-005 | PRJ-005-ACT-10 | 2025-06-13 | Labour | LAB-005 | Plumber | VEN-008 | 19 | Worker | 27049.76 | 28418.27 | 5115.29 | 33533.56 | Paid | Low
EXP-04330 | PRJ-005 | PRJ-005-ACT-07 | 2025-06-18 | Labour | LAB-002 | Helper | VEN-008 | 17 | Worker | 28103.63 | 27107.8 | 4879.4 | 31987.2 | Paid | Medium
EXP-04331 | PRJ-005 | PRJ-005-ACT-07 | 2025-06-18 | Contractor | CON-003 | Plumbing Contract | VEN-012 | 1 | Contract | 280596.27 | 287248.63 | 51704.75 | 338953.38 | Paid | Medium
EXP-04332 | PRJ-005 | PRJ-005-ACT-02 | 2025-06-18 | Equipment | EQ-003 | Concrete Mixer | VEN-012 | 1 | Day | 3943.73 | 4148.35 | 746.7 | 4895.05 | Paid | Low
EXP-04333 | PRJ-005 | PRJ-005-ACT-07 | 2025-06-18 | Contractor | CON-003 | Plumbing Contract | VEN-005 | 1 | Contract | 138549.95 | 139080.55 | 25034.5 | 164115.05 | Paid | Medium
EXP-04334 | PRJ-005 | PRJ-005-ACT-09 | 2025-06-18 | Material | MAT-007 | PVC Pipe | VEN-005 | 23.44 | Meter | 3102.86 | 2945.37 | 530.17 | 3475.54 | Paid | Low
EXP-04335 | PRJ-005 | PRJ-005-ACT-09 | 2025-06-18 | Material | MAT-009 | Paint | VEN-008 | 12.18 | Litre | 2746.53 | 2705.36 | 486.96 | 3192.32 | Paid | Low
EXP-04336 | PRJ-005 | PRJ-005-ACT-06 | 2025-06-18 | Labour | LAB-003 | Carpenter | VEN-012 | 23 | Worker | 31764.29 | 33024.69 | 5944.44 | 38969.13 | Paid | Low
EXP-04337 | PRJ-005 | PRJ-005-ACT-03 | 2025-06-18 | Material | MAT-005 | Bricks | VEN-008 | 2.45 | Piece | 23.21 | 23.93 | 4.31 | 28.24 | Paid | Low
EXP-04338 | PRJ-005 | PRJ-005-ACT-02 | 2025-06-18 | Contractor | CON-002 | Electrical Contract | VEN-005 | 1 | Contract | 149845.77 | 155765.02 | 28037.7 | 183802.72 | Paid | Low
EXP-04339 | PRJ-005 | PRJ-005-ACT-04 | 2025-06-23 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 417833.32 | 396674.69 | 71401.44 | 468076.13 | Paid | Medium
EXP-04340 | PRJ-005 | PRJ-005-ACT-04 | 2025-06-23 | Other | OTH-001 | Site Office | VEN-008 | 1 | Lot | 50496.85 | 53404.24 | 9612.76 | 63017 | Paid | Low
EXP-04341 | PRJ-005 | PRJ-005-ACT-02 | 2025-06-23 | Contractor | CON-003 | Plumbing Contract | VEN-012 | 1 | Contract | 388038.07 | 368600.82 | 66348.15 | 434948.97 | Paid | Low
EXP-04342 | PRJ-005 | PRJ-005-ACT-08 | 2025-06-23 | Contractor | CON-002 | Electrical Contract | VEN-008 | 1 | Contract | 284039.04 | 295759.67 | 53236.74 | 348996.41 | Pending | Low
EXP-04343 | PRJ-005 | PRJ-005-ACT-04 | 2025-06-23 | Equipment | EQ-003 | Concrete Mixer | VEN-005 | 2 | Day | 8894.2 | 8648.26 | 1556.69 | 10204.95 | Paid | Medium
EXP-04344 | PRJ-005 | PRJ-005-ACT-05 | 2025-06-23 | Contractor | CON-003 | Plumbing Contract | VEN-005 | 1 | Contract | 99547.88 | 104473.79 | 18805.28 | 123279.07 | Pending | Medium
EXP-04345 | PRJ-005 | PRJ-005-ACT-09 | 2025-06-23 | Contractor | CON-001 | Civil Structure Contract | VEN-012 | 1 | Contract | 286230.53 | 283081.8 | 50954.72 | 334036.52 | Paid | Low
EXP-04346 | PRJ-005 | PRJ-005-ACT-07 | 2025-06-23 | Equipment | EQ-003 | Concrete Mixer | VEN-005 | 3 | Day | 14745.97 | 14703.51 | 2646.63 | 17350.14 | Paid | Medium
EXP-04347 | PRJ-005 | PRJ-005-ACT-07 | 2025-06-23 | Labour | LAB-006 | Painter | VEN-008 | 12 | Worker | 14011.66 | 13133.86 | 2364.09 | 15497.95 | Paid | High
EXP-04348 | PRJ-005 | PRJ-005-ACT-01 | 2025-06-23 | Labour | LAB-002 | Helper | VEN-008 | 13 | Worker | 12998.53 | 13104.73 | 2358.85 | 15463.58 | Paid | Low
EXP-04349 | PRJ-005 | PRJ-005-ACT-03 | 2025-06-28 | Material | MAT-001 | Cement | VEN-008 | 14.46 | Bag | 7223.68 | 6716.26 | 1208.93 | 7925.19 | Paid | Low
EXP-04350 | PRJ-005 | PRJ-005-ACT-02 | 2025-06-28 | Material | MAT-005 | Bricks | VEN-005 | 17.74 | Piece | 143.29 | 155.71 | 28.03 | 183.74 | Paid | Low
EXP-04351 | PRJ-005 | PRJ-005-ACT-10 | 2025-06-28 | Material | MAT-003 | Sand | VEN-008 | 5.32 | Ton | 9318.93 | 9286.12 | 1671.5 | 10957.62 | Paid | Low
EXP-04352 | PRJ-005 | PRJ-005-ACT-01 | 2025-06-28 | Material | MAT-008 | Tiles | VEN-005 | 9.88 | Sq Ft | 621.37 | 650.44 | 117.08 | 767.52 | Paid | Low
EXP-04353 | PRJ-005 | PRJ-005-ACT-05 | 2025-06-28 | Equipment | EQ-004 | Scaffolding | VEN-005 | 4 | Day | 8626.58 | 9372.84 | 1687.11 | 11059.95 | Paid | Medium
EXP-04354 | PRJ-005 | PRJ-005-ACT-10 | 2025-06-28 | Material | MAT-004 | Aggregate | VEN-008 | 15.04 | Ton | 25620.34 | 23973.36 | 4315.2 | 28288.56 | Paid | Medium
EXP-04355 | PRJ-005 | PRJ-005-ACT-04 | 2025-06-28 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 412940.19 | 448416.42 | 80714.96 | 529131.38 | Paid | Medium
EXP-04356 | PRJ-005 | PRJ-005-ACT-04 | 2025-06-28 | Material | MAT-009 | Paint | VEN-008 | 4.31 | Litre | 824.18 | 819.24 | 147.46 | 966.7 | Paid | Medium
EXP-04357 | PRJ-005 | PRJ-005-ACT-09 | 2025-06-28 | Labour | LAB-006 | Painter | VEN-005 | 19 | Worker | 32628.18 | 30779.97 | 5540.39 | 36320.36 | Paid | Medium
EXP-04358 | PRJ-005 | PRJ-005-ACT-04 | 2025-06-28 | Material | MAT-003 | Sand | VEN-008 | 10.79 | Ton | 20556.49 | 21852.71 | 3933.49 | 25786.2 | Paid | Low
EXP-04359 | PRJ-005 | PRJ-005-ACT-03 | 2025-07-03 | Contractor | CON-002 | Electrical Contract | VEN-005 | 1 | Contract | 239720.9 | 231277.07 | 41629.87 | 272906.94 | Paid | Low
EXP-04360 | PRJ-005 | PRJ-005-ACT-09 | 2025-07-03 | Equipment | EQ-003 | Concrete Mixer | VEN-008 | 5 | Day | 21943.51 | 21099.54 | 3797.92 | 24897.46 | Paid | Low
EXP-04361 | PRJ-005 | PRJ-005-ACT-03 | 2025-07-03 | Material | MAT-006 | Electrical Cable | VEN-008 | 2 | Meter | 149.53 | 144.65 | 26.04 | 170.69 | Paid | High
EXP-04362 | PRJ-005 | PRJ-005-ACT-10 | 2025-07-03 | Labour | LAB-002 | Helper | VEN-012 | 17 | Worker | 14633.07 | 13969.52 | 2514.51 | 16484.03 | Paid | Low
EXP-04363 | PRJ-005 | PRJ-005-ACT-03 | 2025-07-03 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 281322.78 | 263168.85 | 47370.39 | 310539.24 | Paid | Medium
EXP-04364 | PRJ-005 | PRJ-005-ACT-04 | 2025-07-03 | Material | MAT-003 | Sand | VEN-005 | 36.89 | Ton | 64668.61 | 66392.59 | 11950.67 | 78343.26 | Paid | High
EXP-04365 | PRJ-005 | PRJ-005-ACT-05 | 2025-07-03 | Material | MAT-002 | Steel | VEN-008 | 36.05 | Ton | 593439.72 | 574658.8 | 103438.58 | 678097.38 | Paid | Low
EXP-04366 | PRJ-005 | PRJ-005-ACT-09 | 2025-07-03 | Contractor | CON-002 | Electrical Contract | VEN-012 | 1 | Contract | 339419.36 | 337327.95 | 60719.03 | 398046.98 | Paid | Medium
EXP-04367 | PRJ-005 | PRJ-005-ACT-07 | 2025-07-03 | Material | MAT-004 | Aggregate | VEN-012 | 4.39 | Ton | 6403.78 | 5983.1 | 1076.96 | 7060.06 | Paid | Medium
EXP-04368 | PRJ-005 | PRJ-005-ACT-02 | 2025-07-03 | Material | MAT-002 | Steel | VEN-008 | 8.04 | Ton | 534272.76 | 517166.75 | 93090.01 | 610256.76 | Paid | Low
EXP-04369 | PRJ-005 | PRJ-005-ACT-01 | 2025-07-08 | Labour | LAB-006 | Painter | VEN-005 | 23 | Worker | 36011.82 | 33526.94 | 6034.85 | 39561.79 | Paid | Medium
EXP-04370 | PRJ-005 | PRJ-005-ACT-10 | 2025-07-08 | Material | MAT-008 | Tiles | VEN-005 | 8.28 | Sq Ft | 723.82 | 672.42 | 121.04 | 793.46 | Paid | Low
EXP-04371 | PRJ-005 | PRJ-005-ACT-07 | 2025-07-08 | Material | MAT-005 | Bricks | VEN-005 | 3.52 | Piece | 32.44 | 32.93 | 5.93 | 38.86 | Paid | High
EXP-04372 | PRJ-005 | PRJ-005-ACT-02 | 2025-07-08 | Material | MAT-010 | Glass | VEN-008 | 2.08 | Sq Ft | 333.71 | 317.82 | 57.21 | 375.03 | Partially Paid | Low
EXP-04373 | PRJ-005 | PRJ-005-ACT-02 | 2025-07-08 | Contractor | CON-003 | Plumbing Contract | VEN-008 | 1 | Contract | 285971.16 | 310832.94 | 55949.93 | 366782.87 | Partially Paid | Medium
EXP-04374 | PRJ-005 | PRJ-005-ACT-09 | 2025-07-08 | Other | OTH-001 | Site Office | VEN-008 | 1 | Lot | 18494.4 | 17601.56 | 3168.28 | 20769.84 | Paid | Low
EXP-04375 | PRJ-005 | PRJ-005-ACT-01 | 2025-07-08 | Labour | LAB-002 | Helper | VEN-012 | 23 | Worker | 16686.32 | 16444.63 | 2960.03 | 19404.66 | Paid | Low
EXP-04376 | PRJ-005 | PRJ-005-ACT-03 | 2025-07-13 | Material | MAT-001 | Cement | VEN-008 | 33.58 | Bag | 16223.44 | 17255.86 | 3106.05 | 20361.91 | Paid | Low
EXP-04377 | PRJ-005 | PRJ-005-ACT-04 | 2025-07-13 | Contractor | CON-001 | Civil Structure Contract | VEN-005 | 1 | Contract | 349049.31 | 359787.28 | 64761.71 | 424548.99 | Paid | Low
EXP-04378 | PRJ-005 | PRJ-005-ACT-09 | 2025-07-13 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 347797.13 | 357561.95 | 64361.15 | 421923.1 | Paid | High
EXP-04379 | PRJ-005 | PRJ-005-ACT-02 | 2025-07-13 | Labour | LAB-004 | Electrician | VEN-005 | 15 | Worker | 22259.07 | 21007.67 | 3781.38 | 24789.05 | Paid | Low
EXP-04380 | PRJ-005 | PRJ-005-ACT-10 | 2025-07-13 | Material | MAT-010 | Glass | VEN-012 | 8.44 | Sq Ft | 1497.95 | 1508.46 | 271.52 | 1779.98 | Paid | Medium
EXP-04381 | PRJ-005 | PRJ-005-ACT-09 | 2025-07-13 | Material | MAT-009 | Paint | VEN-005 | 16.5 | Litre | 3575.84 | 3710.02 | 667.8 | 4377.82 | Paid | Low
EXP-04382 | PRJ-005 | PRJ-005-ACT-03 | 2025-07-13 | Material | MAT-003 | Sand | VEN-008 | 4.07 | Ton | 6537.25 | 6256.65 | 1126.2 | 7382.85 | Partially Paid | Medium
EXP-04383 | PRJ-005 | PRJ-005-ACT-05 | 2025-07-18 | Equipment | EQ-001 | Crane | VEN-005 | 3 | Day | 61896.07 | 58288 | 10491.84 | 68779.84 | Paid | Low
EXP-04384 | PRJ-005 | PRJ-005-ACT-10 | 2025-07-18 | Material | MAT-002 | Steel | VEN-012 | 2.22 | Ton | 138405.07 | 137314.49 | 24716.61 | 162031.1 | Paid | Low
EXP-04385 | PRJ-005 | PRJ-005-ACT-08 | 2025-07-18 | Material | MAT-007 | PVC Pipe | VEN-008 | 27.18 | Meter | 2580.02 | 2792.93 | 502.73 | 3295.66 | Paid | Low
EXP-04386 | PRJ-005 | PRJ-005-ACT-01 | 2025-07-18 | Labour | LAB-003 | Carpenter | VEN-008 | 31 | Worker | 27801.19 | 26368.74 | 4746.37 | 31115.11 | Partially Paid | Low
EXP-04387 | PRJ-005 | PRJ-005-ACT-05 | 2025-07-18 | Contractor | CON-004 | Finishing Contract | VEN-008 | 1 | Contract | 188553.73 | 193454.35 | 34821.78 | 228276.13 | Paid | Low
EXP-04388 | PRJ-005 | PRJ-005-ACT-09 | 2025-07-18 | Material | MAT-009 | Paint | VEN-005 | 1 | Litre | 171.6 | 182.28 | 32.81 | 215.09 | Paid | Low
EXP-04389 | PRJ-005 | PRJ-005-ACT-05 | 2025-07-18 | Contractor | CON-002 | Electrical Contract | VEN-008 | 1 | Contract | 261725.71 | 242836.41 | 43710.55 | 286546.96 | Paid | Low
EXP-04390 | PRJ-005 | PRJ-005-ACT-10 | 2025-07-18 | Material | MAT-006 | Electrical Cable | VEN-005 | 5.81 | Meter | 538.63 | 525.89 | 94.66 | 620.55 | Paid | Low
EXP-04391 | PRJ-005 | PRJ-005-ACT-10 | 2025-07-18 | Material | MAT-010 | Glass | VEN-005 | 9.95 | Sq Ft | 1494.69 | 1527.87 | 275.02 | 1802.89 | Paid | Medium
EXP-04392 | PRJ-005 | PRJ-005-ACT-01 | 2025-07-23 | Equipment | EQ-003 | Concrete Mixer | VEN-008 | 7 | Day | 29666.51 | 32145.28 | 5786.15 | 37931.43 | Paid | Medium
EXP-04393 | PRJ-005 | PRJ-005-ACT-02 | 2025-07-23 | Labour | LAB-006 | Painter | VEN-008 | 18 | Worker | 13167.73 | 13330.35 | 2399.46 | 15729.81 | Paid | Medium
EXP-04394 | PRJ-005 | PRJ-005-ACT-01 | 2025-07-23 | Material | MAT-010 | Glass | VEN-012 | 7.27 | Sq Ft | 1098.46 | 1158.71 | 208.57 | 1367.28 | Paid | Low
EXP-04395 | PRJ-005 | PRJ-005-ACT-03 | 2025-07-23 | Labour | LAB-004 | Electrician | VEN-005 | 12 | Worker | 18212.11 | 17612.68 | 3170.28 | 20782.96 | Paid | Low
EXP-04396 | PRJ-005 | PRJ-005-ACT-04 | 2025-07-23 | Contractor | CON-004 | Finishing Contract | VEN-008 | 1 | Contract | 345468.51 | 324676.66 | 58441.8 | 383118.46 | Paid | Medium
EXP-04397 | PRJ-005 | PRJ-005-ACT-01 | 2025-07-23 | Contractor | CON-004 | Finishing Contract | VEN-008 | 1 | Contract | 246404.27 | 231243.45 | 41623.82 | 272867.27 | Pending | Low
EXP-04398 | PRJ-005 | PRJ-005-ACT-07 | 2025-07-23 | Material | MAT-005 | Bricks | VEN-008 | 45.57 | Piece | 430.04 | 419.11 | 75.44 | 494.55 | Paid | Medium
EXP-04399 | PRJ-005 | PRJ-005-ACT-08 | 2025-07-23 | Contractor | CON-002 | Electrical Contract | VEN-008 | 1 | Contract | 103484.61 | 107229.01 | 19301.22 | 126530.23 | Paid | Low
EXP-04400 | PRJ-005 | PRJ-005-ACT-04 | 2025-07-28 | Contractor | CON-003 | Plumbing Contract | VEN-012 | 1 | Contract | 313987.16 | 299125.18 | 53842.53 | 352967.71 | Paid | High
EXP-04401 | PRJ-005 | PRJ-005-ACT-09 | 2025-07-28 | Equipment | EQ-003 | Concrete Mixer | VEN-012 | 6 | Day | 26013.32 | 26382.2 | 4748.8 | 31131 | Paid | Low
EXP-04402 | PRJ-005 | PRJ-005-ACT-03 | 2025-07-28 | Material | MAT-009 | Paint | VEN-012 | 1.09 | Litre | 227.87 | 220.05 | 39.61 | 259.66 | Paid | Low
EXP-04403 | PRJ-005 | PRJ-005-ACT-02 | 2025-07-28 | Material | MAT-001 | Cement | VEN-005 | 12.47 | Bag | 6877.42 | 7449.14 | 1340.85 | 8789.99 | Partially Paid | Medium
EXP-04404 | PRJ-005 | PRJ-005-ACT-05 | 2025-07-28 | Equipment | EQ-004 | Scaffolding | VEN-012 | 3 | Day | 8292.23 | 8018.34 | 1443.3 | 9461.64 | Paid | Low
EXP-04405 | PRJ-005 | PRJ-005-ACT-07 | 2025-07-28 | Material | MAT-007 | PVC Pipe | VEN-008 | 16.25 | Meter | 2077.17 | 2114.62 | 380.63 | 2495.25 | Paid | Low
EXP-04406 | PRJ-005 | PRJ-005-ACT-03 | 2025-07-28 | Material | MAT-002 | Steel | VEN-008 | 2.78 | Ton | 175699.57 | 186394.02 | 33550.92 | 219944.94 | Paid | Medium
EXP-04407 | PRJ-005 | PRJ-005-ACT-02 | 2025-07-28 | Labour | LAB-006 | Painter | VEN-012 | 20 | Worker | 22027.47 | 22670.58 | 4080.7 | 26751.28 | Paid | Low
EXP-04408 | PRJ-005 | PRJ-005-ACT-10 | 2025-07-28 | Material | MAT-002 | Steel | VEN-012 | 2.63 | Ton | 168546.55 | 172769.68 | 31098.54 | 203868.22 | Paid | Low
EXP-04409 | PRJ-005 | PRJ-005-ACT-09 | 2025-07-28 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 436624.49 | 448952.37 | 80811.43 | 529763.8 | Paid | Low
EXP-04410 | PRJ-005 | PRJ-005-ACT-06 | 2025-08-02 | Contractor | CON-004 | Finishing Contract | VEN-008 | 1 | Contract | 263362.88 | 253493.62 | 45628.85 | 299122.47 | Paid | Medium
EXP-04411 | PRJ-005 | PRJ-005-ACT-10 | 2025-08-02 | Labour | LAB-004 | Electrician | VEN-012 | 6 | Worker | 6640.76 | 6286.55 | 1131.58 | 7418.13 | Paid | Low
EXP-04412 | PRJ-005 | PRJ-005-ACT-08 | 2025-08-02 | Material | MAT-009 | Paint | VEN-005 | 17.82 | Litre | 3867.49 | 4145.49 | 746.19 | 4891.68 | Paid | Medium
EXP-04413 | PRJ-005 | PRJ-005-ACT-10 | 2025-08-02 | Labour | LAB-002 | Helper | VEN-005 | 17 | Worker | 29401.26 | 28535.59 | 5136.41 | 33672 | Paid | Low
EXP-04414 | PRJ-005 | PRJ-005-ACT-07 | 2025-08-02 | Material | MAT-004 | Aggregate | VEN-005 | 30.86 | Ton | 47464.76 | 47374.73 | 8527.45 | 55902.18 | Pending | Low
EXP-04415 | PRJ-005 | PRJ-005-ACT-02 | 2025-08-02 | Material | MAT-010 | Glass | VEN-008 | 20.07 | Sq Ft | 2745.68 | 2873.4 | 517.21 | 3390.61 | Partially Paid | Medium
EXP-04416 | PRJ-005 | PRJ-005-ACT-10 | 2025-08-02 | Labour | LAB-006 | Painter | VEN-008 | 5 | Worker | 6191.04 | 6552.4 | 1179.43 | 7731.83 | Paid | Low
EXP-04417 | PRJ-005 | PRJ-005-ACT-10 | 2025-08-07 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 470023.84 | 436541.61 | 78577.49 | 515119.1 | Paid | Medium
EXP-04418 | PRJ-005 | PRJ-005-ACT-09 | 2025-08-07 | Equipment | EQ-002 | Excavator | VEN-008 | 7 | Day | 94598.98 | 101077.82 | 18194.01 | 119271.83 | Paid | Medium
EXP-04419 | PRJ-005 | PRJ-005-ACT-04 | 2025-08-07 | Labour | LAB-001 | Mason | VEN-012 | 22 | Worker | 16250.19 | 15660.96 | 2818.97 | 18479.93 | Paid | Low
EXP-04420 | PRJ-005 | PRJ-005-ACT-04 | 2025-08-07 | Equipment | EQ-004 | Scaffolding | VEN-008 | 7 | Day | 16795.27 | 16382.13 | 2948.78 | 19330.91 | Paid | Low
EXP-04421 | PRJ-005 | PRJ-005-ACT-09 | 2025-08-07 | Contractor | CON-002 | Electrical Contract | VEN-012 | 1 | Contract | 297073.06 | 312875.43 | 56317.58 | 369193.01 | Paid | High
EXP-04422 | PRJ-005 | PRJ-005-ACT-04 | 2025-08-07 | Material | MAT-002 | Steel | VEN-008 | 3.66 | Ton | 212613.99 | 212791.67 | 38302.5 | 251094.17 | Paid | Medium
EXP-04423 | PRJ-005 | PRJ-005-ACT-09 | 2025-08-07 | Contractor | CON-002 | Electrical Contract | VEN-008 | 1 | Contract | 237694.73 | 220614.8 | 39710.66 | 260325.46 | Paid | Medium
EXP-04424 | PRJ-005 | PRJ-005-ACT-05 | 2025-08-07 | Other | OTH-001 | Transport | VEN-008 | 1 | Lot | 8314.71 | 7708.26 | 1387.49 | 9095.75 | Pending | Low
EXP-04425 | PRJ-005 | PRJ-005-ACT-06 | 2025-08-07 | Material | MAT-003 | Sand | VEN-012 | 2.86 | Ton | 4502.35 | 4668.46 | 840.32 | 5508.78 | Paid | Medium
EXP-04426 | PRJ-005 | PRJ-005-ACT-09 | 2025-08-07 | Other | OTH-001 | Safety | VEN-008 | 1 | Lot | 60063.47 | 55951.66 | 10071.3 | 66022.96 | Paid | High
EXP-04427 | PRJ-005 | PRJ-005-ACT-02 | 2025-08-12 | Contractor | CON-003 | Plumbing Contract | VEN-008 | 1 | Contract | 180755.05 | 191551.15 | 34479.21 | 226030.36 | Paid | Medium
EXP-04428 | PRJ-005 | PRJ-005-ACT-08 | 2025-08-12 | Labour | LAB-002 | Helper | VEN-012 | 23 | Worker | 33138.4 | 35311.3 | 6356.03 | 41667.33 | Paid | Low
EXP-04429 | PRJ-005 | PRJ-005-ACT-04 | 2025-08-12 | Material | MAT-010 | Glass | VEN-012 | 47.72 | Sq Ft | 6909.65 | 6789.23 | 1222.06 | 8011.29 | Paid | Medium
EXP-04430 | PRJ-005 | PRJ-005-ACT-10 | 2025-08-12 | Labour | LAB-004 | Electrician | VEN-005 | 33 | Worker | 56763.82 | 57792.1 | 10402.58 | 68194.68 | Partially Paid | Medium
EXP-04431 | PRJ-005 | PRJ-005-ACT-06 | 2025-08-12 | Material | MAT-003 | Sand | VEN-005 | 10.35 | Ton | 18179.05 | 17831.08 | 3209.59 | 21040.67 | Paid | Medium
EXP-04432 | PRJ-005 | PRJ-005-ACT-08 | 2025-08-12 | Other | OTH-001 | Permit | VEN-012 | 1 | Lot | 55984.11 | 56546.95 | 10178.45 | 66725.4 | Partially Paid | Low
EXP-04433 | PRJ-005 | PRJ-005-ACT-04 | 2025-08-12 | Labour | LAB-003 | Carpenter | VEN-005 | 25 | Worker | 33629.51 | 32835.74 | 5910.43 | 38746.17 | Paid | Medium
EXP-04434 | PRJ-005 | PRJ-005-ACT-02 | 2025-08-12 | Material | MAT-003 | Sand | VEN-005 | 8.31 | Ton | 12547.54 | 13551.45 | 2439.26 | 15990.71 | Paid | High
EXP-04435 | PRJ-005 | PRJ-005-ACT-10 | 2025-08-12 | Contractor | CON-003 | Plumbing Contract | VEN-008 | 1 | Contract | 458770.46 | 428756.32 | 77176.14 | 505932.46 | Partially Paid | Low
EXP-04436 | PRJ-005 | PRJ-005-ACT-06 | 2025-08-12 | Material | MAT-008 | Tiles | VEN-008 | 15.41 | Sq Ft | 1130.46 | 1162.36 | 209.22 | 1371.58 | Paid | Low
EXP-04437 | PRJ-005 | PRJ-005-ACT-06 | 2025-08-17 | Material | MAT-006 | Electrical Cable | VEN-012 | 4.73 | Meter | 364.01 | 360.81 | 64.95 | 425.76 | Partially Paid | Low
EXP-04438 | PRJ-005 | PRJ-005-ACT-07 | 2025-08-17 | Contractor | CON-001 | Civil Structure Contract | VEN-005 | 1 | Contract | 294118.31 | 317461.03 | 57142.99 | 374604.02 | Paid | Low
EXP-04439 | PRJ-005 | PRJ-005-ACT-03 | 2025-08-17 | Material | MAT-005 | Bricks | VEN-005 | 14.78 | Piece | 141.03 | 149.51 | 26.91 | 176.42 | Paid | Low
EXP-04440 | PRJ-005 | PRJ-005-ACT-05 | 2025-08-17 | Material | MAT-004 | Aggregate | VEN-008 | 28.53 | Ton | 47063.98 | 45792.81 | 8242.71 | 54035.52 | Paid | Medium
EXP-04441 | PRJ-005 | PRJ-005-ACT-06 | 2025-08-17 | Contractor | CON-001 | Civil Structure Contract | VEN-008 | 1 | Contract | 137151.91 | 131295.85 | 23633.25 | 154929.1 | Paid | Low
EXP-04442 | PRJ-005 | PRJ-005-ACT-03 | 2025-08-17 | Material | MAT-003 | Sand | VEN-008 | 6.59 | Ton | 11725.28 | 11187.58 | 2013.76 | 13201.34 | Partially Paid | Low
EXP-04443 | PRJ-005 | PRJ-005-ACT-04 | 2025-08-22 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 412061.37 | 411569.33 | 74082.48 | 485651.81 | Paid | Medium
EXP-04444 | PRJ-005 | PRJ-005-ACT-08 | 2025-08-22 | Labour | LAB-004 | Electrician | VEN-005 | 33 | Worker | 37823 | 40011.44 | 7202.06 | 47213.5 | Paid | Medium
EXP-04445 | PRJ-005 | PRJ-005-ACT-09 | 2025-08-22 | Contractor | CON-002 | Electrical Contract | VEN-005 | 1 | Contract | 355783.12 | 354164.13 | 63749.54 | 417913.67 | Paid | Low
EXP-04446 | PRJ-005 | PRJ-005-ACT-01 | 2025-08-22 | Material | MAT-005 | Bricks | VEN-008 | 4.77 | Piece | 36.65 | 37.66 | 6.78 | 44.44 | Pending | Low
EXP-04447 | PRJ-005 | PRJ-005-ACT-07 | 2025-08-22 | Material | MAT-007 | PVC Pipe | VEN-005 | 5.36 | Meter | 582.58 | 576.92 | 103.85 | 680.77 | Paid | Low
EXP-04448 | PRJ-005 | PRJ-005-ACT-09 | 2025-08-22 | Contractor | CON-003 | Plumbing Contract | VEN-005 | 1 | Contract | 126603.77 | 125030.11 | 22505.42 | 147535.53 | Paid | Low
EXP-04449 | PRJ-005 | PRJ-005-ACT-05 | 2025-08-22 | Contractor | CON-001 | Civil Structure Contract | VEN-008 | 1 | Contract | 125343.03 | 121278.51 | 21830.13 | 143108.64 | Partially Paid | Low
EXP-04450 | PRJ-005 | PRJ-005-ACT-05 | 2025-08-22 | Contractor | CON-002 | Electrical Contract | VEN-012 | 1 | Contract | 280007.5 | 273168.33 | 49170.3 | 322338.63 | Paid | Medium
EXP-04451 | PRJ-005 | PRJ-005-ACT-06 | 2025-08-22 | Labour | LAB-004 | Electrician | VEN-008 | 25 | Worker | 23580.73 | 23110.76 | 4159.94 | 27270.7 | Paid | Medium
EXP-04452 | PRJ-005 | PRJ-005-ACT-02 | 2025-08-27 | Contractor | CON-002 | Electrical Contract | VEN-008 | 1 | Contract | 302292.74 | 311434.23 | 56058.16 | 367492.39 | Paid | Low
EXP-04453 | PRJ-005 | PRJ-005-ACT-05 | 2025-08-27 | Material | MAT-004 | Aggregate | VEN-012 | 12.67 | Ton | 17155.9 | 17903.23 | 3222.58 | 21125.81 | Paid | Low
EXP-04454 | PRJ-005 | PRJ-005-ACT-01 | 2025-08-27 | Material | MAT-003 | Sand | VEN-005 | 7.3 | Ton | 11233.58 | 11203.07 | 2016.55 | 13219.62 | Paid | Low
EXP-04455 | PRJ-005 | PRJ-005-ACT-07 | 2025-08-27 | Material | MAT-004 | Aggregate | VEN-008 | 15.45 | Ton | 23416.15 | 24443.51 | 4399.83 | 28843.34 | Paid | Low
EXP-04456 | PRJ-005 | PRJ-005-ACT-01 | 2025-08-27 | Labour | LAB-006 | Painter | VEN-012 | 32 | Worker | 51088.86 | 54335.15 | 9780.33 | 64115.48 | Paid | Medium
EXP-04457 | PRJ-005 | PRJ-005-ACT-03 | 2025-08-27 | Material | MAT-007 | PVC Pipe | VEN-005 | 3.39 | Meter | 407.86 | 387.09 | 69.68 | 456.77 | Paid | Low
EXP-04458 | PRJ-005 | PRJ-005-ACT-08 | 2025-08-27 | Labour | LAB-001 | Mason | VEN-012 | 15 | Worker | 18866.06 | 18654.3 | 3357.77 | 22012.07 | Paid | Low
EXP-04459 | PRJ-005 | PRJ-005-ACT-09 | 2025-08-27 | Labour | LAB-006 | Painter | VEN-008 | 18 | Worker | 34357.52 | 32288.8 | 5811.98 | 38100.78 | Paid | Medium
EXP-04460 | PRJ-005 | PRJ-005-ACT-10 | 2025-08-27 | Contractor | CON-004 | Finishing Contract | VEN-008 | 1 | Contract | 251432.23 | 245808.83 | 44245.59 | 290054.42 | Partially Paid | Medium
EXP-04461 | PRJ-005 | PRJ-005-ACT-05 | 2025-09-01 | Material | MAT-010 | Glass | VEN-012 | 15.13 | Sq Ft | 2818.17 | 2673.42 | 481.22 | 3154.64 | Paid | Low
EXP-04462 | PRJ-005 | PRJ-005-ACT-10 | 2025-09-01 | Contractor | CON-004 | Finishing Contract | VEN-008 | 1 | Contract | 320326.15 | 304473.44 | 54805.22 | 359278.66 | Paid | Medium
EXP-04463 | PRJ-005 | PRJ-005-ACT-04 | 2025-09-01 | Material | MAT-003 | Sand | VEN-012 | 4.45 | Ton | 7673.57 | 7387.95 | 1329.83 | 8717.78 | Pending | Low
EXP-04464 | PRJ-005 | PRJ-005-ACT-03 | 2025-09-01 | Contractor | CON-003 | Plumbing Contract | VEN-012 | 1 | Contract | 415943.12 | 425463.64 | 76583.46 | 502047.1 | Paid | Medium
EXP-04465 | PRJ-005 | PRJ-005-ACT-03 | 2025-09-01 | Material | MAT-001 | Cement | VEN-005 | 3.82 | Bag | 1861.93 | 1821.56 | 327.88 | 2149.44 | Paid | Low
EXP-04466 | PRJ-005 | PRJ-005-ACT-06 | 2025-09-01 | Contractor | CON-002 | Electrical Contract | VEN-005 | 1 | Contract | 103209.16 | 105275.38 | 18949.57 | 124224.95 | Paid | Low
EXP-04467 | PRJ-005 | PRJ-005-ACT-05 | 2025-09-06 | Material | MAT-010 | Glass | VEN-012 | 13.96 | Sq Ft | 2392.01 | 2292.99 | 412.74 | 2705.73 | Pending | Medium
EXP-04468 | PRJ-005 | PRJ-005-ACT-04 | 2025-09-06 | Material | MAT-007 | PVC Pipe | VEN-005 | 16.46 | Meter | 2176.96 | 2134.83 | 384.27 | 2519.1 | Paid | Medium
EXP-04469 | PRJ-005 | PRJ-005-ACT-05 | 2025-09-06 | Labour | LAB-004 | Electrician | VEN-005 | 24 | Worker | 40593.35 | 39735.64 | 7152.42 | 46888.06 | Paid | Low
EXP-04470 | PRJ-005 | PRJ-005-ACT-02 | 2025-09-06 | Material | MAT-001 | Cement | VEN-012 | 14.48 | Bag | 8860.87 | 8370.42 | 1506.68 | 9877.1 | Paid | Low
EXP-04471 | PRJ-005 | PRJ-005-ACT-03 | 2025-09-06 | Material | MAT-006 | Electrical Cable | VEN-005 | 8.69 | Meter | 739.91 | 765.12 | 137.72 | 902.84 | Partially Paid | Medium
EXP-04472 | PRJ-005 | PRJ-005-ACT-08 | 2025-09-06 | Labour | LAB-003 | Carpenter | VEN-012 | 34 | Worker | 56622.72 | 54872.74 | 9877.09 | 64749.83 | Paid | High
EXP-04473 | PRJ-005 | PRJ-005-ACT-07 | 2025-09-06 | Material | MAT-006 | Electrical Cable | VEN-012 | 7.37 | Meter | 738.79 | 684.77 | 123.26 | 808.03 | Partially Paid | Medium
EXP-04474 | PRJ-005 | PRJ-005-ACT-03 | 2025-09-06 | Equipment | EQ-003 | Concrete Mixer | VEN-005 | 5 | Day | 25133.44 | 23364.76 | 4205.66 | 27570.42 | Paid | Low
EXP-04475 | PRJ-005 | PRJ-005-ACT-05 | 2025-09-06 | Material | MAT-003 | Sand | VEN-005 | 7.2 | Ton | 10932 | 11088.82 | 1995.99 | 13084.81 | Paid | Low
EXP-04476 | PRJ-005 | PRJ-005-ACT-10 | 2025-09-11 | Material | MAT-006 | Electrical Cable | VEN-012 | 8.59 | Meter | 624.83 | 646.24 | 116.32 | 762.56 | Paid | Medium
EXP-04477 | PRJ-005 | PRJ-005-ACT-10 | 2025-09-11 | Material | MAT-007 | PVC Pipe | VEN-012 | 32.15 | Meter | 3746.71 | 3805.7 | 685.03 | 4490.73 | Paid | Medium
EXP-04478 | PRJ-005 | PRJ-005-ACT-10 | 2025-09-11 | Equipment | EQ-003 | Concrete Mixer | VEN-005 | 6 | Day | 24489.17 | 26284.24 | 4731.16 | 31015.4 | Paid | High
EXP-04479 | PRJ-005 | PRJ-005-ACT-02 | 2025-09-11 | Equipment | EQ-003 | Concrete Mixer | VEN-008 | 4 | Day | 18033.86 | 17291.85 | 3112.53 | 20404.38 | Paid | Medium
EXP-04480 | PRJ-005 | PRJ-005-ACT-02 | 2025-09-11 | Material | MAT-010 | Glass | VEN-005 | 40.56 | Sq Ft | 6464.98 | 6457.82 | 1162.41 | 7620.23 | Paid | Medium
EXP-04481 | PRJ-005 | PRJ-005-ACT-01 | 2025-09-11 | Material | MAT-003 | Sand | VEN-008 | 12.48 | Ton | 22071.95 | 23554.92 | 4239.89 | 27794.81 | Paid | Low
EXP-04482 | PRJ-005 | PRJ-005-ACT-08 | 2025-09-11 | Material | MAT-009 | Paint | VEN-012 | 20.17 | Litre | 4430.8 | 4194.63 | 755.03 | 4949.66 | Partially Paid | Low
EXP-04483 | PRJ-005 | PRJ-005-ACT-08 | 2025-09-11 | Material | MAT-003 | Sand | VEN-012 | 14.53 | Ton | 29366.98 | 30043.9 | 5407.9 | 35451.8 | Paid | Medium
EXP-04484 | PRJ-005 | PRJ-005-ACT-08 | 2025-09-11 | Material | MAT-003 | Sand | VEN-012 | 15.83 | Ton | 27996.74 | 29831.88 | 5369.74 | 35201.62 | Paid | Low
EXP-04485 | PRJ-005 | PRJ-005-ACT-02 | 2025-09-16 | Material | MAT-008 | Tiles | VEN-005 | 36.08 | Sq Ft | 2861.88 | 2797.48 | 503.55 | 3301.03 | Paid | High
EXP-04486 | PRJ-005 | PRJ-005-ACT-01 | 2025-09-16 | Material | MAT-004 | Aggregate | VEN-008 | 3.59 | Ton | 5988.68 | 5696.33 | 1025.34 | 6721.67 | Paid | Low
EXP-04487 | PRJ-005 | PRJ-005-ACT-09 | 2025-09-16 | Contractor | CON-003 | Plumbing Contract | VEN-012 | 1 | Contract | 240428.91 | 258577.38 | 46543.93 | 305121.31 | Paid | Low
EXP-04488 | PRJ-005 | PRJ-005-ACT-06 | 2025-09-16 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 389958.09 | 368718.88 | 66369.4 | 435088.28 | Partially Paid | Medium
EXP-04489 | PRJ-005 | PRJ-005-ACT-10 | 2025-09-16 | Material | MAT-009 | Paint | VEN-012 | 8.77 | Litre | 1823.7 | 1886.7 | 339.61 | 2226.31 | Paid | Medium
EXP-04490 | PRJ-005 | PRJ-005-ACT-03 | 2025-09-16 | Labour | LAB-001 | Mason | VEN-008 | 17 | Worker | 16772.07 | 16386.36 | 2949.54 | 19335.9 | Paid | High
EXP-04491 | PRJ-005 | PRJ-005-ACT-06 | 2025-09-16 | Material | MAT-008 | Tiles | VEN-012 | 5.62 | Sq Ft | 402.61 | 393.08 | 70.75 | 463.83 | Paid | Medium
EXP-04492 | PRJ-005 | PRJ-005-ACT-08 | 2025-09-16 | Contractor | CON-004 | Finishing Contract | VEN-008 | 1 | Contract | 193288.45 | 188541.03 | 33937.39 | 222478.42 | Paid | Medium
EXP-04493 | PRJ-005 | PRJ-005-ACT-01 | 2025-09-16 | Labour | LAB-004 | Electrician | VEN-008 | 4 | Worker | 6210.13 | 5917.4 | 1065.13 | 6982.53 | Paid | Low
EXP-04494 | PRJ-005 | PRJ-005-ACT-06 | 2025-09-21 | Material | MAT-009 | Paint | VEN-005 | 2.4 | Litre | 438.84 | 447.09 | 80.48 | 527.57 | Paid | Medium
EXP-04495 | PRJ-005 | PRJ-005-ACT-02 | 2025-09-21 | Labour | LAB-005 | Plumber | VEN-005 | 5 | Worker | 7619.94 | 8142.81 | 1465.71 | 9608.52 | Paid | Low
EXP-04496 | PRJ-005 | PRJ-005-ACT-08 | 2025-09-21 | Labour | LAB-003 | Carpenter | VEN-008 | 18 | Worker | 19173.03 | 18100.79 | 3258.14 | 21358.93 | Paid | Low
EXP-04497 | PRJ-005 | PRJ-005-ACT-10 | 2025-09-21 | Material | MAT-008 | Tiles | VEN-012 | 3.36 | Sq Ft | 246.6 | 235.26 | 42.35 | 277.61 | Paid | Medium
EXP-04498 | PRJ-005 | PRJ-005-ACT-04 | 2025-09-21 | Labour | LAB-002 | Helper | VEN-005 | 29 | Worker | 40618.81 | 43597.25 | 7847.51 | 51444.76 | Paid | Medium
EXP-04499 | PRJ-005 | PRJ-005-ACT-10 | 2025-09-21 | Material | MAT-006 | Electrical Cable | VEN-005 | 17.27 | Meter | 1607.08 | 1534.01 | 276.12 | 1810.13 | Paid | High
EXP-04500 | PRJ-005 | PRJ-005-ACT-03 | 2025-09-21 | Material | MAT-003 | Sand | VEN-005 | 45.9 | Ton | 86672.4 | 89437.34 | 16098.72 | 105536.06 | Paid | High
EXP-04501 | PRJ-005 | PRJ-005-ACT-07 | 2025-09-21 | Material | MAT-001 | Cement | VEN-008 | 24.28 | Bag | 12697.2 | 13647.69 | 2456.58 | 16104.27 | Paid | High
EXP-04502 | PRJ-005 | PRJ-005-ACT-10 | 2025-09-21 | Material | MAT-007 | PVC Pipe | VEN-008 | 15.9 | Meter | 1659.01 | 1659.34 | 298.68 | 1958.02 | Paid | Medium
EXP-04503 | PRJ-005 | PRJ-005-ACT-09 | 2025-09-21 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 227109.1 | 233697.68 | 42065.58 | 275763.26 | Paid | Medium
EXP-04504 | PRJ-005 | PRJ-005-ACT-04 | 2025-09-26 | Contractor | CON-002 | Electrical Contract | VEN-008 | 1 | Contract | 418552.14 | 447942.06 | 80629.57 | 528571.63 | Partially Paid | High
EXP-04505 | PRJ-005 | PRJ-005-ACT-02 | 2025-09-26 | Contractor | CON-004 | Finishing Contract | VEN-012 | 1 | Contract | 305191.09 | 314963.94 | 56693.51 | 371657.45 | Paid | Low
EXP-04506 | PRJ-005 | PRJ-005-ACT-03 | 2025-09-26 | Material | MAT-001 | Cement | VEN-012 | 4.2 | Bag | 1861.98 | 1942.17 | 349.59 | 2291.76 | Paid | Medium
EXP-04507 | PRJ-005 | PRJ-005-ACT-10 | 2025-09-26 | Labour | LAB-001 | Mason | VEN-008 | 22 | Worker | 37634.13 | 38544.05 | 6937.93 | 45481.98 | Paid | Medium
EXP-04508 | PRJ-005 | PRJ-005-ACT-08 | 2025-09-26 | Labour | LAB-005 | Plumber | VEN-005 | 5 | Worker | 6258.6 | 6004.57 | 1080.82 | 7085.39 | Paid | Low
EXP-04509 | PRJ-005 | PRJ-005-ACT-03 | 2025-09-26 | Material | MAT-005 | Bricks | VEN-012 | 9.41 | Piece | 93.54 | 91.54 | 16.48 | 108.02 | Partially Paid | Low
EXP-04510 | PRJ-005 | PRJ-005-ACT-02 | 2025-09-26 | Other | OTH-001 | Miscellaneous | VEN-005 | 1 | Lot | 35904.02 | 33595.39 | 6047.17 | 39642.56 | Paid | Medium
EXP-04511 | PRJ-005 | PRJ-005-ACT-05 | 2025-09-26 | Contractor | CON-003 | Plumbing Contract | VEN-008 | 1 | Contract | 298766.45 | 321246.67 | 57824.4 | 379071.07 | Pending | Medium
EXP-04512 | PRJ-005 | PRJ-005-ACT-08 | 2025-10-01 | Material | MAT-009 | Paint | VEN-008 | 1.21 | Litre | 263.48 | 277.75 | 49.99 | 327.74 | Paid | Medium
EXP-04513 | PRJ-005 | PRJ-005-ACT-05 | 2025-10-01 | Material | MAT-010 | Glass | VEN-012 | 13.68 | Sq Ft | 2185.69 | 2230.96 | 401.57 | 2632.53 | Paid | Medium
EXP-04514 | PRJ-005 | PRJ-005-ACT-01 | 2025-10-01 | Material | MAT-009 | Paint | VEN-008 | 7.55 | Litre | 1366.72 | 1447.94 | 260.63 | 1708.57 | Paid | High
EXP-04515 | PRJ-005 | PRJ-005-ACT-03 | 2025-10-01 | Equipment | EQ-002 | Excavator | VEN-008 | 5 | Day | 64525.53 | 69062.6 | 12431.27 | 81493.87 | Pending | Medium
EXP-04516 | PRJ-005 | PRJ-005-ACT-07 | 2025-10-01 | Labour | LAB-002 | Helper | VEN-012 | 32 | Worker | 29362.04 | 29131.17 | 5243.61 | 34374.78 | Paid | Low
EXP-04517 | PRJ-005 | PRJ-005-ACT-09 | 2025-10-01 | Labour | LAB-004 | Electrician | VEN-008 | 31 | Worker | 53741.02 | 52691.05 | 9484.39 | 62175.44 | Paid | Medium
EXP-04518 | PRJ-005 | PRJ-005-ACT-02 | 2025-10-01 | Contractor | CON-004 | Finishing Contract | VEN-012 | 1 | Contract | 139926.35 | 150196.9 | 27035.44 | 177232.34 | Paid | Medium
EXP-04519 | PRJ-005 | PRJ-005-ACT-01 | 2025-10-01 | Material | MAT-007 | PVC Pipe | VEN-012 | 17.61 | Meter | 1942.32 | 1975.98 | 355.68 | 2331.66 | Paid | Medium
EXP-04520 | PRJ-005 | PRJ-005-ACT-05 | 2025-10-01 | Contractor | CON-001 | Civil Structure Contract | VEN-008 | 1 | Contract | 157694.38 | 153080.71 | 27554.53 | 180635.24 | Pending | Medium
EXP-04521 | PRJ-005 | PRJ-005-ACT-09 | 2025-10-06 | Material | MAT-009 | Paint | VEN-005 | 2.99 | Litre | 525.21 | 539.46 | 97.1 | 636.56 | Paid | Medium
EXP-04522 | PRJ-005 | PRJ-005-ACT-08 | 2025-10-06 | Material | MAT-002 | Steel | VEN-008 | 5.88 | Ton | 405615.05 | 376354.88 | 67743.88 | 444098.76 | Paid | Low
EXP-04523 | PRJ-005 | PRJ-005-ACT-07 | 2025-10-06 | Material | MAT-001 | Cement | VEN-012 | 3.48 | Bag | 1511.8 | 1605.57 | 289 | 1894.57 | Paid | Medium
EXP-04524 | PRJ-005 | PRJ-005-ACT-09 | 2025-10-06 | Material | MAT-007 | PVC Pipe | VEN-005 | 11.2 | Meter | 1361.81 | 1297.34 | 233.52 | 1530.86 | Paid | Medium
EXP-04525 | PRJ-005 | PRJ-005-ACT-03 | 2025-10-06 | Contractor | CON-003 | Plumbing Contract | VEN-012 | 1 | Contract | 170676.09 | 171445.95 | 30860.27 | 202306.22 | Paid | Low
EXP-04526 | PRJ-005 | PRJ-005-ACT-08 | 2025-10-06 | Labour | LAB-002 | Helper | VEN-012 | 25 | Worker | 18551.4 | 19184.11 | 3453.14 | 22637.25 | Paid | Low
EXP-04527 | PRJ-005 | PRJ-005-ACT-09 | 2025-10-06 | Labour | LAB-004 | Electrician | VEN-008 | 9 | Worker | 15248.93 | 15396.64 | 2771.4 | 18168.04 | Partially Paid | Low
EXP-04528 | PRJ-005 | PRJ-005-ACT-06 | 2025-10-06 | Material | MAT-010 | Glass | VEN-008 | 6.68 | Sq Ft | 1105.48 | 1067.07 | 192.07 | 1259.14 | Paid | Low
EXP-04529 | PRJ-005 | PRJ-005-ACT-09 | 2025-10-06 | Material | MAT-008 | Tiles | VEN-012 | 56.76 | Sq Ft | 4987.36 | 4891.46 | 880.46 | 5771.92 | Paid | Low
EXP-04530 | PRJ-005 | PRJ-005-ACT-06 | 2025-10-06 | Labour | LAB-005 | Plumber | VEN-005 | 4 | Worker | 4061.59 | 4083.41 | 735.01 | 4818.42 | Paid | Medium
EXP-04531 | PRJ-005 | PRJ-005-ACT-09 | 2025-10-11 | Contractor | CON-001 | Civil Structure Contract | VEN-012 | 1 | Contract | 293574.62 | 281021.66 | 50583.9 | 331605.56 | Paid | Low
EXP-04532 | PRJ-005 | PRJ-005-ACT-02 | 2025-10-11 | Labour | LAB-001 | Mason | VEN-012 | 8 | Worker | 12634.66 | 13632.72 | 2453.89 | 16086.61 | Paid | Low
EXP-04533 | PRJ-005 | PRJ-005-ACT-07 | 2025-10-11 | Material | MAT-006 | Electrical Cable | VEN-005 | 4.75 | Meter | 344.55 | 353.31 | 63.6 | 416.91 | Paid | Low
EXP-04534 | PRJ-005 | PRJ-005-ACT-05 | 2025-10-11 | Equipment | EQ-002 | Excavator | VEN-012 | 6 | Day | 85086.69 | 84937.67 | 15288.78 | 100226.45 | Paid | Low
EXP-04535 | PRJ-005 | PRJ-005-ACT-07 | 2025-10-11 | Material | MAT-006 | Electrical Cable | VEN-005 | 29.43 | Meter | 2372.71 | 2479.28 | 446.27 | 2925.55 | Paid | High
EXP-04536 | PRJ-005 | PRJ-005-ACT-07 | 2025-10-11 | Material | MAT-003 | Sand | VEN-005 | 37.65 | Ton | 67943.49 | 66814.48 | 12026.61 | 78841.09 | Partially Paid | Low
EXP-04537 | PRJ-005 | PRJ-005-ACT-06 | 2025-10-11 | Equipment | EQ-004 | Scaffolding | VEN-008 | 1 | Day | 2904.54 | 2709.59 | 487.73 | 3197.32 | Partially Paid | Medium
EXP-04538 | PRJ-005 | PRJ-005-ACT-01 | 2025-10-16 | Material | MAT-006 | Electrical Cable | VEN-012 | 8.15 | Meter | 666.28 | 636.82 | 114.63 | 751.45 | Pending | High
EXP-04539 | PRJ-005 | PRJ-005-ACT-09 | 2025-10-16 | Material | MAT-009 | Paint | VEN-012 | 15.44 | Litre | 2885.25 | 3053.68 | 549.66 | 3603.34 | Paid | Medium
EXP-04540 | PRJ-005 | PRJ-005-ACT-05 | 2025-10-16 | Material | MAT-010 | Glass | VEN-005 | 19.48 | Sq Ft | 2809.68 | 2701.81 | 486.33 | 3188.14 | Paid | Low
EXP-04541 | PRJ-005 | PRJ-005-ACT-07 | 2025-10-16 | Contractor | CON-002 | Electrical Contract | VEN-012 | 1 | Contract | 242136.07 | 233094 | 41956.92 | 275050.92 | Paid | Low
EXP-04542 | PRJ-005 | PRJ-005-ACT-07 | 2025-10-16 | Material | MAT-003 | Sand | VEN-012 | 21.84 | Ton | 37305.87 | 39498.49 | 7109.73 | 46608.22 | Paid | Medium
EXP-04543 | PRJ-005 | PRJ-005-ACT-06 | 2025-10-16 | Material | MAT-010 | Glass | VEN-005 | 38.81 | Sq Ft | 6760.43 | 6804.78 | 1224.86 | 8029.64 | Pending | Low
EXP-04544 | PRJ-005 | PRJ-005-ACT-10 | 2025-10-21 | Equipment | EQ-004 | Scaffolding | VEN-012 | 2 | Day | 4715.19 | 4612.48 | 830.25 | 5442.73 | Paid | Low
EXP-04545 | PRJ-005 | PRJ-005-ACT-04 | 2025-10-21 | Other | OTH-001 | Safety | VEN-008 | 1 | Lot | 63453.18 | 67722.64 | 12190.08 | 79912.72 | Paid | Low
EXP-04546 | PRJ-005 | PRJ-005-ACT-03 | 2025-10-21 | Equipment | EQ-001 | Crane | VEN-008 | 6 | Day | 112708.62 | 111871.81 | 20136.93 | 132008.74 | Paid | Low
EXP-04547 | PRJ-005 | PRJ-005-ACT-09 | 2025-10-21 | Labour | LAB-001 | Mason | VEN-005 | 30 | Worker | 23952.93 | 24629.94 | 4433.39 | 29063.33 | Paid | Low
EXP-04548 | PRJ-005 | PRJ-005-ACT-05 | 2025-10-21 | Labour | LAB-005 | Plumber | VEN-008 | 20 | Worker | 22413.47 | 23305.48 | 4194.99 | 27500.47 | Partially Paid | Low
EXP-04549 | PRJ-005 | PRJ-005-ACT-01 | 2025-10-21 | Contractor | CON-004 | Finishing Contract | VEN-012 | 1 | Contract | 274892.15 | 265042.84 | 47707.71 | 312750.55 | Pending | Low
EXP-04550 | PRJ-005 | PRJ-005-ACT-06 | 2025-10-21 | Material | MAT-009 | Paint | VEN-005 | 14.18 | Litre | 3172.78 | 3218.07 | 579.25 | 3797.32 | Paid | High
EXP-04551 | PRJ-005 | PRJ-005-ACT-10 | 2025-10-26 | Contractor | CON-001 | Civil Structure Contract | VEN-005 | 1 | Contract | 221497.15 | 225234.85 | 40542.27 | 265777.12 | Paid | Medium
EXP-04552 | PRJ-005 | PRJ-005-ACT-10 | 2025-10-26 | Material | MAT-002 | Steel | VEN-008 | 30.96 | Ton | 1662880.33 | 1791591.24 | 322486.42 | 2114077.66 | Paid | Medium
EXP-04553 | PRJ-005 | PRJ-005-ACT-02 | 2025-10-26 | Material | MAT-003 | Sand | VEN-012 | 10.45 | Ton | 17176.62 | 17703.76 | 3186.68 | 20890.44 | Partially Paid | High
EXP-04554 | PRJ-005 | PRJ-005-ACT-05 | 2025-10-26 | Material | MAT-004 | Aggregate | VEN-005 | 2.45 | Ton | 3376.39 | 3244.89 | 584.08 | 3828.97 | Paid | Medium
EXP-04555 | PRJ-005 | PRJ-005-ACT-04 | 2025-10-26 | Labour | LAB-005 | Plumber | VEN-005 | 6 | Worker | 10314.95 | 9825.5 | 1768.59 | 11594.09 | Paid | Medium
EXP-04556 | PRJ-005 | PRJ-005-ACT-07 | 2025-10-26 | Labour | LAB-003 | Carpenter | VEN-008 | 29 | Worker | 20713.93 | 20212.88 | 3638.32 | 23851.2 | Paid | Medium
EXP-04557 | PRJ-005 | PRJ-005-ACT-10 | 2025-10-26 | Equipment | EQ-003 | Concrete Mixer | VEN-008 | 2 | Day | 9660.1 | 9034.27 | 1626.17 | 10660.44 | Paid | Low
EXP-04558 | PRJ-005 | PRJ-005-ACT-10 | 2025-10-26 | Contractor | CON-001 | Civil Structure Contract | VEN-012 | 1 | Contract | 207659.81 | 214331.95 | 38579.75 | 252911.7 | Paid | Low
EXP-04559 | PRJ-005 | PRJ-005-ACT-02 | 2025-10-26 | Labour | LAB-002 | Helper | VEN-008 | 25 | Worker | 20027.28 | 20785.09 | 3741.32 | 24526.41 | Paid | High
EXP-04560 | PRJ-005 | PRJ-005-ACT-06 | 2025-10-31 | Material | MAT-008 | Tiles | VEN-012 | 4.05 | Sq Ft | 262.51 | 258.35 | 46.5 | 304.85 | Partially Paid | Low
EXP-04561 | PRJ-005 | PRJ-005-ACT-01 | 2025-10-31 | Material | MAT-008 | Tiles | VEN-008 | 24.06 | Sq Ft | 1980.41 | 1987.53 | 357.76 | 2345.29 | Paid | Medium
EXP-04562 | PRJ-005 | PRJ-005-ACT-02 | 2025-10-31 | Material | MAT-006 | Electrical Cable | VEN-008 | 6.32 | Meter | 443.39 | 481.48 | 86.67 | 568.15 | Paid | Low
EXP-04563 | PRJ-005 | PRJ-005-ACT-04 | 2025-10-31 | Equipment | EQ-001 | Crane | VEN-012 | 1 | Day | 17903.95 | 17576.5 | 3163.77 | 20740.27 | Paid | Low
EXP-04564 | PRJ-005 | PRJ-005-ACT-10 | 2025-10-31 | Material | MAT-001 | Cement | VEN-012 | 7.66 | Bag | 4380.6 | 4466.12 | 803.9 | 5270.02 | Paid | Low
EXP-04565 | PRJ-005 | PRJ-005-ACT-08 | 2025-10-31 | Material | MAT-002 | Steel | VEN-012 | 34.82 | Ton | 284522.72 | 299723.94 | 53950.31 | 353674.25 | Pending | High
EXP-04566 | PRJ-005 | PRJ-005-ACT-02 | 2025-11-05 | Material | MAT-002 | Steel | VEN-012 | 44.26 | Ton | 448954.33 | 472756.95 | 85096.25 | 557853.2 | Paid | Low
EXP-04567 | PRJ-005 | PRJ-005-ACT-08 | 2025-11-05 | Material | MAT-009 | Paint | VEN-012 | 2.99 | Litre | 614.18 | 639.8 | 115.16 | 754.96 | Paid | Low
EXP-04568 | PRJ-005 | PRJ-005-ACT-02 | 2025-11-05 | Material | MAT-002 | Steel | VEN-005 | 10.07 | Ton | 591090.21 | 597444.76 | 107540.06 | 704984.82 | Paid | Medium
EXP-04569 | PRJ-005 | PRJ-005-ACT-03 | 2025-11-05 | Labour | LAB-001 | Mason | VEN-012 | 31 | Worker | 44855.53 | 42287.32 | 7611.72 | 49899.04 | Paid | High
EXP-04570 | PRJ-005 | PRJ-005-ACT-08 | 2025-11-05 | Material | MAT-003 | Sand | VEN-008 | 5.51 | Ton | 8763.79 | 8866.27 | 1595.93 | 10462.2 | Paid | Low
EXP-04571 | PRJ-005 | PRJ-005-ACT-07 | 2025-11-05 | Contractor | CON-002 | Electrical Contract | VEN-012 | 1 | Contract | 127973.91 | 121994.72 | 21959.05 | 143953.77 | Paid | Low
EXP-04572 | PRJ-005 | PRJ-005-ACT-06 | 2025-11-10 | Material | MAT-006 | Electrical Cable | VEN-005 | 9.24 | Meter | 753.75 | 712.83 | 128.31 | 841.14 | Paid | Low
EXP-04573 | PRJ-005 | PRJ-005-ACT-05 | 2025-11-10 | Material | MAT-010 | Glass | VEN-012 | 11.89 | Sq Ft | 1697.19 | 1834.93 | 330.29 | 2165.22 | Partially Paid | Low
EXP-04574 | PRJ-005 | PRJ-005-ACT-01 | 2025-11-10 | Material | MAT-003 | Sand | VEN-005 | 20.36 | Ton | 33947.76 | 36261.89 | 6527.14 | 42789.03 | Partially Paid | Low
EXP-04575 | PRJ-005 | PRJ-005-ACT-02 | 2025-11-10 | Labour | LAB-003 | Carpenter | VEN-008 | 25 | Worker | 17383.65 | 16410.53 | 2953.9 | 19364.43 | Paid | Low
EXP-04576 | PRJ-005 | PRJ-005-ACT-01 | 2025-11-10 | Material | MAT-001 | Cement | VEN-005 | 6.07 | Bag | 3152.56 | 3089.71 | 556.15 | 3645.86 | Partially Paid | Low
EXP-04577 | PRJ-005 | PRJ-005-ACT-06 | 2025-11-10 | Labour | LAB-003 | Carpenter | VEN-008 | 23 | Worker | 28683.49 | 29228.86 | 5261.19 | 34490.05 | Paid | Low
EXP-04578 | PRJ-005 | PRJ-005-ACT-05 | 2025-11-15 | Material | MAT-001 | Cement | VEN-012 | 7.03 | Bag | 3304.71 | 3194.37 | 574.99 | 3769.36 | Paid | Low
EXP-04579 | PRJ-005 | PRJ-005-ACT-08 | 2025-11-15 | Labour | LAB-001 | Mason | VEN-012 | 17 | Worker | 23387.62 | 25155.94 | 4528.07 | 29684.01 | Paid | Low
EXP-04580 | PRJ-005 | PRJ-005-ACT-10 | 2025-11-15 | Equipment | EQ-002 | Excavator | VEN-005 | 5 | Day | 61564.8 | 65477.38 | 11785.93 | 77263.31 | Pending | Low
EXP-04581 | PRJ-005 | PRJ-005-ACT-06 | 2025-11-15 | Labour | LAB-005 | Plumber | VEN-008 | 18 | Worker | 19364.96 | 19953.17 | 3591.57 | 23544.74 | Paid | Low
EXP-04582 | PRJ-005 | PRJ-005-ACT-01 | 2025-11-15 | Equipment | EQ-001 | Crane | VEN-012 | 3 | Day | 55152.84 | 55356.13 | 9964.1 | 65320.23 | Pending | Low
EXP-04583 | PRJ-005 | PRJ-005-ACT-09 | 2025-11-15 | Other | OTH-001 | Miscellaneous | VEN-012 | 1 | Lot | 13086.22 | 12950.28 | 2331.05 | 15281.33 | Paid | Medium
EXP-04584 | PRJ-005 | PRJ-005-ACT-01 | 2025-11-15 | Material | MAT-007 | PVC Pipe | VEN-008 | 3.05 | Meter | 417.79 | 405.77 | 73.04 | 478.81 | Partially Paid | Low
EXP-04585 | PRJ-005 | PRJ-005-ACT-05 | 2025-11-15 | Contractor | CON-004 | Finishing Contract | VEN-012 | 1 | Contract | 158080.38 | 149557.95 | 26920.43 | 176478.38 | Pending | Medium
EXP-04586 | PRJ-005 | PRJ-005-ACT-09 | 2025-11-20 | Material | MAT-009 | Paint | VEN-012 | 16.28 | Litre | 3461.99 | 3736.38 | 672.55 | 4408.93 | Partially Paid | Low
EXP-04587 | PRJ-005 | PRJ-005-ACT-09 | 2025-11-20 | Contractor | CON-004 | Finishing Contract | VEN-008 | 1 | Contract | 195226.57 | 209321.71 | 37677.91 | 246999.62 | Paid | Low
EXP-04588 | PRJ-005 | PRJ-005-ACT-07 | 2025-11-20 | Labour | LAB-004 | Electrician | VEN-008 | 10 | Worker | 9548.46 | 9873.75 | 1777.27 | 11651.02 | Paid | Low
EXP-04589 | PRJ-005 | PRJ-005-ACT-01 | 2025-11-20 | Labour | LAB-004 | Electrician | VEN-005 | 13 | Worker | 13738.61 | 13493.33 | 2428.8 | 15922.13 | Paid | High
EXP-04590 | PRJ-005 | PRJ-005-ACT-04 | 2025-11-20 | Material | MAT-002 | Steel | VEN-008 | 31.65 | Ton | 393889.54 | 412062.74 | 74171.29 | 486234.03 | Paid | Low
EXP-04591 | PRJ-005 | PRJ-005-ACT-09 | 2025-11-20 | Contractor | CON-003 | Plumbing Contract | VEN-005 | 1 | Contract | 139900.53 | 131354.84 | 23643.87 | 154998.71 | Paid | Low
EXP-04592 | PRJ-005 | PRJ-005-ACT-03 | 2025-11-20 | Labour | LAB-006 | Painter | VEN-005 | 4 | Worker | 5725.75 | 5359.81 | 964.77 | 6324.58 | Paid | Low
EXP-04593 | PRJ-005 | PRJ-005-ACT-02 | 2025-11-20 | Labour | LAB-001 | Mason | VEN-005 | 13 | Worker | 19721.62 | 21173.22 | 3811.18 | 24984.4 | Paid | Low
EXP-04594 | PRJ-005 | PRJ-005-ACT-10 | 2025-11-20 | Material | MAT-003 | Sand | VEN-012 | 1.99 | Ton | 3169.02 | 3200.88 | 576.16 | 3777.04 | Paid | Low
EXP-04595 | PRJ-005 | PRJ-005-ACT-09 | 2025-11-25 | Contractor | CON-003 | Plumbing Contract | VEN-008 | 1 | Contract | 303002.86 | 325226.31 | 58540.74 | 383767.05 | Paid | Low
EXP-04596 | PRJ-005 | PRJ-005-ACT-04 | 2025-11-25 | Other | OTH-001 | Safety | VEN-012 | 1 | Lot | 52022.76 | 49183.59 | 8853.05 | 58036.64 | Paid | Low
EXP-04597 | PRJ-005 | PRJ-005-ACT-03 | 2025-11-25 | Material | MAT-001 | Cement | VEN-005 | 3.06 | Bag | 1311.91 | 1416.32 | 254.94 | 1671.26 | Paid | Medium
EXP-04598 | PRJ-005 | PRJ-005-ACT-10 | 2025-11-25 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 92101.11 | 92104.49 | 16578.81 | 108683.3 | Partially Paid | Low
EXP-04599 | PRJ-005 | PRJ-005-ACT-07 | 2025-11-25 | Labour | LAB-001 | Mason | VEN-008 | 24 | Worker | 17824.86 | 19229.91 | 3461.38 | 22691.29 | Paid | Medium
EXP-04600 | PRJ-005 | PRJ-005-ACT-10 | 2025-11-25 | Material | MAT-003 | Sand | VEN-008 | 1.05 | Ton | 1829.1 | 1769.85 | 318.57 | 2088.42 | Paid | Low
EXP-04601 | PRJ-005 | PRJ-005-ACT-02 | 2025-11-30 | Material | MAT-001 | Cement | VEN-005 | 33.63 | Bag | 17361.13 | 18673.09 | 3361.16 | 22034.25 | Paid | Low
EXP-04602 | PRJ-005 | PRJ-005-ACT-01 | 2025-11-30 | Material | MAT-003 | Sand | VEN-012 | 45.05 | Ton | 83812.1 | 83528.78 | 15035.18 | 98563.96 | Paid | Medium
EXP-04603 | PRJ-005 | PRJ-005-ACT-06 | 2025-11-30 | Other | OTH-001 | Transport | VEN-005 | 1 | Lot | 15074.61 | 15961.2 | 2873.02 | 18834.22 | Paid | Medium
EXP-04604 | PRJ-005 | PRJ-005-ACT-01 | 2025-11-30 | Material | MAT-001 | Cement | VEN-008 | 5.86 | Bag | 3627.5 | 3402.64 | 612.48 | 4015.12 | Paid | High
EXP-04605 | PRJ-005 | PRJ-005-ACT-04 | 2025-11-30 | Material | MAT-007 | PVC Pipe | VEN-005 | 14.05 | Meter | 1810.67 | 1888.13 | 339.86 | 2227.99 | Paid | Medium
EXP-04606 | PRJ-005 | PRJ-005-ACT-01 | 2025-11-30 | Contractor | CON-001 | Civil Structure Contract | VEN-008 | 1 | Contract | 284218.32 | 296594.8 | 53387.06 | 349981.86 | Partially Paid | Low
EXP-04607 | PRJ-005 | PRJ-005-ACT-06 | 2025-12-05 | Material | MAT-001 | Cement | VEN-005 | 4.15 | Bag | 2609.19 | 2418.63 | 435.35 | 2853.98 | Paid | Low
EXP-04608 | PRJ-005 | PRJ-005-ACT-08 | 2025-12-05 | Material | MAT-007 | PVC Pipe | VEN-012 | 11.54 | Meter | 1371.99 | 1312.89 | 236.32 | 1549.21 | Paid | Low
EXP-04609 | PRJ-005 | PRJ-005-ACT-03 | 2025-12-05 | Material | MAT-004 | Aggregate | VEN-008 | 23.46 | Ton | 40609.24 | 38436.37 | 6918.55 | 45354.92 | Paid | Low
EXP-04610 | PRJ-005 | PRJ-005-ACT-05 | 2025-12-05 | Labour | LAB-003 | Carpenter | VEN-005 | 16 | Worker | 26091.89 | 27033.47 | 4866.02 | 31899.49 | Pending | Medium
EXP-04611 | PRJ-005 | PRJ-005-ACT-10 | 2025-12-05 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 241589.47 | 257285.28 | 46311.35 | 303596.63 | Pending | Medium
EXP-04612 | PRJ-005 | PRJ-005-ACT-09 | 2025-12-05 | Labour | LAB-005 | Plumber | VEN-008 | 9 | Worker | 12408.24 | 11500.11 | 2070.02 | 13570.13 | Paid | Low
EXP-04613 | PRJ-005 | PRJ-005-ACT-06 | 2025-12-10 | Equipment | EQ-002 | Excavator | VEN-008 | 4 | Day | 51571.77 | 51923.28 | 9346.19 | 61269.47 | Paid | Medium
EXP-04614 | PRJ-005 | PRJ-005-ACT-03 | 2025-12-10 | Contractor | CON-002 | Electrical Contract | VEN-012 | 1 | Contract | 107148.38 | 113378.26 | 20408.09 | 133786.35 | Paid | Low
EXP-04615 | PRJ-005 | PRJ-005-ACT-04 | 2025-12-10 | Material | MAT-002 | Steel | VEN-012 | 10.49 | Ton | 678854.95 | 693947.42 | 124910.54 | 818857.96 | Paid | Medium
EXP-04616 | PRJ-005 | PRJ-005-ACT-10 | 2025-12-10 | Equipment | EQ-002 | Excavator | VEN-008 | 4 | Day | 58789.56 | 57478.37 | 10346.11 | 67824.48 | Paid | Low
EXP-04617 | PRJ-005 | PRJ-005-ACT-07 | 2025-12-10 | Labour | LAB-003 | Carpenter | VEN-008 | 11 | Worker | 11057.02 | 10880.82 | 1958.55 | 12839.37 | Paid | Medium
EXP-04618 | PRJ-005 | PRJ-005-ACT-09 | 2025-12-10 | Material | MAT-001 | Cement | VEN-008 | 17.97 | Bag | 8648.52 | 9015.7 | 1622.83 | 10638.53 | Paid | Low
EXP-04619 | PRJ-005 | PRJ-005-ACT-02 | 2025-12-10 | Material | MAT-003 | Sand | VEN-012 | 6.32 | Ton | 9819.86 | 9670.21 | 1740.64 | 11410.85 | Paid | Low
EXP-04620 | PRJ-005 | PRJ-005-ACT-05 | 2025-12-10 | Material | MAT-002 | Steel | VEN-012 | 7.36 | Ton | 391686.2 | 400194.71 | 72035.05 | 472229.76 | Partially Paid | Medium
EXP-04621 | PRJ-005 | PRJ-005-ACT-10 | 2025-12-15 | Other | OTH-001 | Safety | VEN-005 | 1 | Lot | 35864.68 | 34589.27 | 6226.07 | 40815.34 | Paid | Low
EXP-04622 | PRJ-005 | PRJ-005-ACT-04 | 2025-12-15 | Other | OTH-001 | Miscellaneous | VEN-008 | 1 | Lot | 60368.59 | 57783.56 | 10401.04 | 68184.6 | Paid | Low
EXP-04623 | PRJ-005 | PRJ-005-ACT-06 | 2025-12-15 | Material | MAT-006 | Electrical Cable | VEN-008 | 5.72 | Meter | 525.39 | 532.92 | 95.93 | 628.85 | Paid | Low
EXP-04624 | PRJ-005 | PRJ-005-ACT-07 | 2025-12-15 | Labour | LAB-006 | Painter | VEN-012 | 21 | Worker | 16078.72 | 17194.72 | 3095.05 | 20289.77 | Paid | High
EXP-04625 | PRJ-005 | PRJ-005-ACT-02 | 2025-12-15 | Other | OTH-001 | Safety | VEN-008 | 1 | Lot | 20861.61 | 19371.08 | 3486.79 | 22857.87 | Pending | Low
EXP-04626 | PRJ-005 | PRJ-005-ACT-10 | 2025-12-15 | Contractor | CON-002 | Electrical Contract | VEN-005 | 1 | Contract | 375730.53 | 408216.65 | 73479 | 481695.65 | Paid | Low
EXP-04627 | PRJ-005 | PRJ-005-ACT-02 | 2025-12-15 | Labour | LAB-003 | Carpenter | VEN-008 | 27 | Worker | 31997.3 | 30390.78 | 5470.34 | 35861.12 | Paid | Low
EXP-04628 | PRJ-005 | PRJ-005-ACT-09 | 2025-12-20 | Material | MAT-008 | Tiles | VEN-005 | 16.51 | Sq Ft | 1234.82 | 1234.69 | 222.24 | 1456.93 | Paid | Low
EXP-04629 | PRJ-005 | PRJ-005-ACT-04 | 2025-12-20 | Labour | LAB-003 | Carpenter | VEN-008 | 16 | Worker | 30254.53 | 28582.72 | 5144.89 | 33727.61 | Partially Paid | Medium
EXP-04630 | PRJ-005 | PRJ-005-ACT-04 | 2025-12-20 | Material | MAT-010 | Glass | VEN-012 | 29.53 | Sq Ft | 5179.16 | 5379.28 | 968.27 | 6347.55 | Paid | Low
EXP-04631 | PRJ-005 | PRJ-005-ACT-02 | 2025-12-20 | Material | MAT-006 | Electrical Cable | VEN-005 | 9.13 | Meter | 713.53 | 698.79 | 125.78 | 824.57 | Pending | Medium
EXP-04632 | PRJ-005 | PRJ-005-ACT-10 | 2025-12-20 | Material | MAT-007 | PVC Pipe | VEN-012 | 18.24 | Meter | 2468.72 | 2293.5 | 412.83 | 2706.33 | Partially Paid | Medium
EXP-04633 | PRJ-005 | PRJ-005-ACT-09 | 2025-12-20 | Contractor | CON-003 | Plumbing Contract | VEN-008 | 1 | Contract | 284948.33 | 286673.59 | 51601.25 | 338274.84 | Partially Paid | Low
EXP-04634 | PRJ-005 | PRJ-005-ACT-07 | 2025-12-20 | Material | MAT-007 | PVC Pipe | VEN-012 | 14 | Meter | 1505.69 | 1542.4 | 277.63 | 1820.03 | Paid | Medium
EXP-04635 | PRJ-005 | PRJ-005-ACT-06 | 2025-12-25 | Contractor | CON-003 | Plumbing Contract | VEN-008 | 1 | Contract | 300892.41 | 287970.82 | 51834.75 | 339805.57 | Partially Paid | Low
EXP-04636 | PRJ-005 | PRJ-005-ACT-06 | 2025-12-25 | Material | MAT-001 | Cement | VEN-008 | 26.19 | Bag | 13202.04 | 13563.1 | 2441.36 | 16004.46 | Paid | Low
EXP-04637 | PRJ-005 | PRJ-005-ACT-07 | 2025-12-25 | Equipment | EQ-004 | Scaffolding | VEN-005 | 7 | Day | 17411.3 | 17829.81 | 3209.37 | 21039.18 | Paid | Low
EXP-04638 | PRJ-005 | PRJ-005-ACT-06 | 2025-12-25 | Contractor | CON-004 | Finishing Contract | VEN-008 | 1 | Contract | 394207.49 | 419256.95 | 75466.25 | 494723.2 | Paid | Low
EXP-04639 | PRJ-005 | PRJ-005-ACT-07 | 2025-12-25 | Contractor | CON-003 | Plumbing Contract | VEN-005 | 1 | Contract | 125820.27 | 123936.89 | 22308.64 | 146245.53 | Partially Paid | Medium
EXP-04640 | PRJ-005 | PRJ-005-ACT-08 | 2025-12-25 | Material | MAT-010 | Glass | VEN-012 | 11.82 | Sq Ft | 2143.7 | 2044.76 | 368.06 | 2412.82 | Paid | Low
EXP-04641 | PRJ-005 | PRJ-005-ACT-01 | 2025-12-25 | Material | MAT-008 | Tiles | VEN-008 | 2.84 | Sq Ft | 207.29 | 216.95 | 39.05 | 256 | Pending | Medium
EXP-04642 | PRJ-005 | PRJ-005-ACT-04 | 2025-12-25 | Other | OTH-001 | Miscellaneous | VEN-005 | 1 | Lot | 61666.6 | 64652.43 | 11637.44 | 76289.87 | Paid | Medium
EXP-04643 | PRJ-005 | PRJ-005-ACT-10 | 2025-12-25 | Labour | LAB-003 | Carpenter | VEN-008 | 14 | Worker | 21910.05 | 22865.03 | 4115.71 | 26980.74 | Paid | Medium
EXP-04644 | PRJ-005 | PRJ-005-ACT-04 | 2025-12-25 | Contractor | CON-002 | Electrical Contract | VEN-012 | 1 | Contract | 423806.15 | 448108.48 | 80659.53 | 528768.01 | Paid | Low
EXP-04645 | PRJ-005 | PRJ-005-ACT-03 | 2025-12-30 | Material | MAT-003 | Sand | VEN-012 | 17.61 | Ton | 28462.53 | 30527.83 | 5495.01 | 36022.84 | Paid | Medium
EXP-04646 | PRJ-005 | PRJ-005-ACT-08 | 2025-12-30 | Material | MAT-003 | Sand | VEN-012 | 27.84 | Ton | 47325.48 | 47678.69 | 8582.16 | 56260.85 | Paid | Medium
EXP-04647 | PRJ-005 | PRJ-005-ACT-01 | 2025-12-30 | Labour | LAB-004 | Electrician | VEN-008 | 24 | Worker | 36561.57 | 38705.46 | 6966.98 | 45672.44 | Paid | Medium
EXP-04648 | PRJ-005 | PRJ-005-ACT-08 | 2025-12-30 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 148448.32 | 158085.57 | 28455.4 | 186540.97 | Paid | Medium
EXP-04649 | PRJ-005 | PRJ-005-ACT-07 | 2025-12-30 | Equipment | EQ-001 | Crane | VEN-012 | 1 | Day | 17791.2 | 17377.37 | 3127.93 | 20505.3 | Paid | Low
EXP-04650 | PRJ-005 | PRJ-005-ACT-04 | 2025-12-30 | Contractor | CON-003 | Plumbing Contract | VEN-012 | 1 | Contract | 129888.47 | 123502.74 | 22230.49 | 145733.23 | Partially Paid | Low
EXP-04651 | PRJ-005 | PRJ-005-ACT-01 | 2025-12-30 | Material | MAT-005 | Bricks | VEN-012 | 8.14 | Piece | 64.79 | 63.37 | 11.41 | 74.78 | Paid | Medium
EXP-04652 | PRJ-005 | PRJ-005-ACT-02 | 2025-12-30 | Other | OTH-001 | Transport | VEN-008 | 1 | Lot | 6795.74 | 6782.21 | 1220.8 | 8003.01 | Paid | Low
EXP-04653 | PRJ-005 | PRJ-005-ACT-04 | 2025-12-30 | Labour | LAB-002 | Helper | VEN-008 | 34 | Worker | 46536.71 | 45366.32 | 8165.94 | 53532.26 | Paid | Low
EXP-04654 | PRJ-005 | PRJ-005-ACT-07 | 2025-12-30 | Labour | LAB-005 | Plumber | VEN-005 | 10 | Worker | 7214.24 | 7777.24 | 1399.9 | 9177.14 | Paid | Low
EXP-04655 | PRJ-005 | PRJ-005-ACT-07 | 2026-01-04 | Equipment | EQ-004 | Scaffolding | VEN-012 | 5 | Day | 10997.06 | 11494.15 | 2068.95 | 13563.1 | Paid | Medium
EXP-04656 | PRJ-005 | PRJ-005-ACT-01 | 2026-01-04 | Material | MAT-008 | Tiles | VEN-012 | 35.08 | Sq Ft | 2201.3 | 2320.55 | 417.7 | 2738.25 | Paid | Low
EXP-04657 | PRJ-005 | PRJ-005-ACT-04 | 2026-01-04 | Other | OTH-001 | Safety | VEN-012 | 1 | Lot | 70630.64 | 69582.24 | 12524.8 | 82107.04 | Paid | Low
EXP-04658 | PRJ-005 | PRJ-005-ACT-09 | 2026-01-04 | Equipment | EQ-003 | Concrete Mixer | VEN-005 | 2 | Day | 9017.74 | 9586.44 | 1725.56 | 11312 | Paid | Low
EXP-04659 | PRJ-005 | PRJ-005-ACT-07 | 2026-01-04 | Labour | LAB-006 | Painter | VEN-005 | 30 | Worker | 29948.28 | 29918.4 | 5385.31 | 35303.71 | Paid | High
EXP-04660 | PRJ-005 | PRJ-005-ACT-02 | 2026-01-04 | Labour | LAB-005 | Plumber | VEN-012 | 13 | Worker | 15124.38 | 15783.86 | 2841.09 | 18624.95 | Paid | Medium
EXP-04661 | PRJ-005 | PRJ-005-ACT-10 | 2026-01-04 | Labour | LAB-004 | Electrician | VEN-005 | 22 | Worker | 21330.75 | 22595.28 | 4067.15 | 26662.43 | Partially Paid | Low
EXP-04662 | PRJ-005 | PRJ-005-ACT-04 | 2026-01-04 | Material | MAT-005 | Bricks | VEN-008 | 2.8 | Piece | 23.89 | 25.72 | 4.63 | 30.35 | Paid | Low
EXP-04663 | PRJ-005 | PRJ-005-ACT-10 | 2026-01-09 | Material | MAT-001 | Cement | VEN-005 | 3.51 | Bag | 2097.47 | 1985.76 | 357.44 | 2343.2 | Paid | Medium
EXP-04664 | PRJ-005 | PRJ-005-ACT-06 | 2026-01-09 | Labour | LAB-004 | Electrician | VEN-008 | 13 | Worker | 23905.05 | 23382.62 | 4208.87 | 27591.49 | Paid | Medium
EXP-04665 | PRJ-005 | PRJ-005-ACT-02 | 2026-01-09 | Labour | LAB-004 | Electrician | VEN-008 | 23 | Worker | 15230.16 | 15962.8 | 2873.3 | 18836.1 | Paid | Low
EXP-04666 | PRJ-005 | PRJ-005-ACT-10 | 2026-01-09 | Material | MAT-007 | PVC Pipe | VEN-012 | 7.43 | Meter | 1026.22 | 986.74 | 177.61 | 1164.35 | Paid | Low
EXP-04667 | PRJ-005 | PRJ-005-ACT-08 | 2026-01-09 | Material | MAT-008 | Tiles | VEN-008 | 19.3 | Sq Ft | 1405.78 | 1473.11 | 265.16 | 1738.27 | Paid | Low
EXP-04668 | PRJ-005 | PRJ-005-ACT-02 | 2026-01-09 | Labour | LAB-004 | Electrician | VEN-008 | 17 | Worker | 12419.14 | 12952.84 | 2331.51 | 15284.35 | Paid | Low
EXP-04669 | PRJ-005 | PRJ-005-ACT-08 | 2026-01-09 | Material | MAT-010 | Glass | VEN-008 | 17.34 | Sq Ft | 2755.99 | 2612.2 | 470.2 | 3082.4 | Paid | Low
EXP-04670 | PRJ-005 | PRJ-005-ACT-03 | 2026-01-09 | Equipment | EQ-002 | Excavator | VEN-005 | 2 | Day | 28741.15 | 26888.93 | 4840.01 | 31728.94 | Paid | Low
EXP-04671 | PRJ-005 | PRJ-005-ACT-02 | 2026-01-14 | Material | MAT-004 | Aggregate | VEN-008 | 31.84 | Ton | 44511.93 | 44884.56 | 8079.22 | 52963.78 | Paid | Low
EXP-04672 | PRJ-005 | PRJ-005-ACT-03 | 2026-01-14 | Equipment | EQ-001 | Crane | VEN-005 | 4 | Day | 82938.8 | 78979.66 | 14216.34 | 93196 | Paid | Medium
EXP-04673 | PRJ-005 | PRJ-005-ACT-07 | 2026-01-14 | Material | MAT-010 | Glass | VEN-012 | 5.78 | Sq Ft | 988.67 | 924.63 | 166.43 | 1091.06 | Paid | Low
EXP-04674 | PRJ-005 | PRJ-005-ACT-10 | 2026-01-14 | Material | MAT-005 | Bricks | VEN-008 | 14.34 | Piece | 133.55 | 126.13 | 22.7 | 148.83 | Pending | Low
EXP-04675 | PRJ-005 | PRJ-005-ACT-08 | 2026-01-14 | Labour | LAB-006 | Painter | VEN-008 | 7 | Worker | 11693.55 | 10876.78 | 1957.82 | 12834.6 | Paid | Low
EXP-04676 | PRJ-005 | PRJ-005-ACT-04 | 2026-01-14 | Contractor | CON-003 | Plumbing Contract | VEN-012 | 1 | Contract | 213125.43 | 212916.05 | 38324.89 | 251240.94 | Paid | Low
EXP-04677 | PRJ-005 | PRJ-005-ACT-01 | 2026-01-14 | Contractor | CON-004 | Finishing Contract | VEN-012 | 1 | Contract | 439609.08 | 427620.41 | 76971.67 | 504592.08 | Paid | Low
EXP-04678 | PRJ-005 | PRJ-005-ACT-04 | 2026-01-14 | Labour | LAB-005 | Plumber | VEN-005 | 31 | Worker | 39547.3 | 40067.39 | 7212.13 | 47279.52 | Partially Paid | Low
EXP-04679 | PRJ-005 | PRJ-005-ACT-10 | 2026-01-19 | Labour | LAB-006 | Painter | VEN-005 | 4 | Worker | 7526.17 | 7060.11 | 1270.82 | 8330.93 | Paid | Low
EXP-04680 | PRJ-005 | PRJ-005-ACT-04 | 2026-01-19 | Equipment | EQ-004 | Scaffolding | VEN-012 | 6 | Day | 16456.74 | 16280.67 | 2930.52 | 19211.19 | Paid | Medium
EXP-04681 | PRJ-005 | PRJ-005-ACT-02 | 2026-01-19 | Other | OTH-001 | Safety | VEN-008 | 1 | Lot | 38422.89 | 39991.21 | 7198.42 | 47189.63 | Paid | High
EXP-04682 | PRJ-005 | PRJ-005-ACT-04 | 2026-01-19 | Material | MAT-007 | PVC Pipe | VEN-005 | 112.8 | Meter | 13394.85 | 13594.09 | 2446.94 | 16041.03 | Paid | Medium
EXP-04683 | PRJ-005 | PRJ-005-ACT-03 | 2026-01-19 | Material | MAT-002 | Steel | VEN-012 | 20.95 | Ton | 1208651.7 | 1126963.87 | 202853.5 | 1329817.37 | Paid | High
EXP-04684 | PRJ-005 | PRJ-005-ACT-09 | 2026-01-19 | Material | MAT-005 | Bricks | VEN-008 | 8.54 | Piece | 79.43 | 85.78 | 15.44 | 101.22 | Paid | Medium
EXP-04685 | PRJ-005 | PRJ-005-ACT-01 | 2026-01-19 | Contractor | CON-003 | Plumbing Contract | VEN-008 | 1 | Contract | 301508.24 | 299924.72 | 53986.45 | 353911.17 | Paid | Medium
EXP-04686 | PRJ-005 | PRJ-005-ACT-07 | 2026-01-19 | Contractor | CON-001 | Civil Structure Contract | VEN-005 | 1 | Contract | 341842.63 | 366880.28 | 66038.45 | 432918.73 | Paid | High
EXP-04687 | PRJ-005 | PRJ-005-ACT-06 | 2026-01-19 | Material | MAT-006 | Electrical Cable | VEN-012 | 20.67 | Meter | 1919.37 | 1780.87 | 320.56 | 2101.43 | Partially Paid | Medium
EXP-04688 | PRJ-005 | PRJ-005-ACT-06 | 2026-01-19 | Material | MAT-003 | Sand | VEN-008 | 3.44 | Ton | 6400.84 | 6581.9 | 1184.74 | 7766.64 | Paid | Medium
EXP-04689 | PRJ-005 | PRJ-005-ACT-08 | 2026-01-24 | Equipment | EQ-004 | Scaffolding | VEN-008 | 5 | Day | 13016.51 | 12993.41 | 2338.81 | 15332.22 | Paid | Medium
EXP-04690 | PRJ-005 | PRJ-005-ACT-05 | 2026-01-24 | Labour | LAB-006 | Painter | VEN-012 | 24 | Worker | 41115.85 | 38127.86 | 6863.01 | 44990.87 | Paid | Low
EXP-04691 | PRJ-005 | PRJ-005-ACT-09 | 2026-01-24 | Material | MAT-006 | Electrical Cable | VEN-005 | 9.7 | Meter | 894.2 | 847.78 | 152.6 | 1000.38 | Paid | Low
EXP-04692 | PRJ-005 | PRJ-005-ACT-02 | 2026-01-24 | Equipment | EQ-001 | Crane | VEN-008 | 5 | Day | 86648.66 | 86734.43 | 15612.2 | 102346.63 | Paid | Low
EXP-04693 | PRJ-005 | PRJ-005-ACT-06 | 2026-01-24 | Material | MAT-003 | Sand | VEN-008 | 20.08 | Ton | 40775.4 | 38862.02 | 6995.16 | 45857.18 | Paid | Medium
EXP-04694 | PRJ-005 | PRJ-005-ACT-08 | 2026-01-24 | Labour | LAB-006 | Painter | VEN-012 | 15 | Worker | 20853.13 | 20958.78 | 3772.58 | 24731.36 | Paid | Low
EXP-04695 | PRJ-005 | PRJ-005-ACT-03 | 2026-01-24 | Contractor | CON-001 | Civil Structure Contract | VEN-008 | 1 | Contract | 239365.03 | 234033.64 | 42126.06 | 276159.7 | Paid | Low
EXP-04696 | PRJ-005 | PRJ-005-ACT-05 | 2026-01-24 | Equipment | EQ-004 | Scaffolding | VEN-005 | 6 | Day | 14299.89 | 14732.88 | 2651.92 | 17384.8 | Paid | Low
EXP-04697 | PRJ-005 | PRJ-005-ACT-05 | 2026-01-29 | Material | MAT-007 | PVC Pipe | VEN-012 | 3.54 | Meter | 349.07 | 376.64 | 67.8 | 444.44 | Partially Paid | Low
EXP-04698 | PRJ-005 | PRJ-005-ACT-06 | 2026-01-29 | Material | MAT-006 | Electrical Cable | VEN-008 | 17.36 | Meter | 1539.08 | 1603.88 | 288.7 | 1892.58 | Paid | Low
EXP-04699 | PRJ-005 | PRJ-005-ACT-04 | 2026-01-29 | Labour | LAB-001 | Mason | VEN-005 | 8 | Worker | 8933.38 | 8574.82 | 1543.47 | 10118.29 | Paid | Low
EXP-04700 | PRJ-005 | PRJ-005-ACT-02 | 2026-01-29 | Material | MAT-007 | PVC Pipe | VEN-005 | 12.2 | Meter | 1490.64 | 1475.31 | 265.56 | 1740.87 | Pending | Low
EXP-04701 | PRJ-005 | PRJ-005-ACT-10 | 2026-01-29 | Contractor | CON-001 | Civil Structure Contract | VEN-005 | 1 | Contract | 236950.02 | 232552.93 | 41859.53 | 274412.46 | Paid | Medium
EXP-04702 | PRJ-005 | PRJ-005-ACT-01 | 2026-01-29 | Other | OTH-001 | Site Office | VEN-008 | 1 | Lot | 57924.7 | 54054.59 | 9729.83 | 63784.42 | Paid | Medium
EXP-04703 | PRJ-005 | PRJ-005-ACT-07 | 2026-01-29 | Material | MAT-009 | Paint | VEN-012 | 4.15 | Litre | 703.21 | 751.66 | 135.3 | 886.96 | Paid | Low
EXP-04704 | PRJ-005 | PRJ-005-ACT-06 | 2026-01-29 | Material | MAT-004 | Aggregate | VEN-012 | 15.52 | Ton | 20196.83 | 21242.91 | 3823.72 | 25066.63 | Pending | Medium
EXP-04705 | PRJ-005 | PRJ-005-ACT-06 | 2026-01-29 | Equipment | EQ-001 | Crane | VEN-008 | 6 | Day | 97853.17 | 103131.15 | 18563.61 | 121694.76 | Paid | Medium
EXP-04706 | PRJ-005 | PRJ-005-ACT-02 | 2026-01-29 | Labour | LAB-004 | Electrician | VEN-008 | 19 | Worker | 31646.85 | 33229.58 | 5981.32 | 39210.9 | Partially Paid | High
EXP-04707 | PRJ-005 | PRJ-005-ACT-03 | 2026-02-03 | Other | OTH-001 | Site Office | VEN-008 | 1 | Lot | 70498.82 | 71903.91 | 12942.7 | 84846.61 | Paid | Medium
EXP-04708 | PRJ-005 | PRJ-005-ACT-04 | 2026-02-03 | Equipment | EQ-004 | Scaffolding | VEN-008 | 5 | Day | 12753.09 | 12526.83 | 2254.83 | 14781.66 | Paid | Low
EXP-04709 | PRJ-005 | PRJ-005-ACT-09 | 2026-02-03 | Material | MAT-006 | Electrical Cable | VEN-012 | 14.73 | Meter | 1314.3 | 1264.04 | 227.53 | 1491.57 | Paid | Low
EXP-04710 | PRJ-005 | PRJ-005-ACT-06 | 2026-02-03 | Material | MAT-002 | Steel | VEN-005 | 7.82 | Ton | 448928.2 | 487574.23 | 87763.36 | 575337.59 | Paid | Low
EXP-04711 | PRJ-005 | PRJ-005-ACT-07 | 2026-02-03 | Equipment | EQ-001 | Crane | VEN-012 | 4 | Day | 70502.35 | 68760.33 | 12376.86 | 81137.19 | Paid | Low
EXP-04712 | PRJ-005 | PRJ-005-ACT-10 | 2026-02-03 | Material | MAT-007 | PVC Pipe | VEN-012 | 18.92 | Meter | 2150.73 | 2065.87 | 371.86 | 2437.73 | Partially Paid | Low
EXP-04713 | PRJ-005 | PRJ-005-ACT-04 | 2026-02-03 | Material | MAT-003 | Sand | VEN-008 | 17.95 | Ton | 28895.79 | 28174.28 | 5071.37 | 33245.65 | Pending | Low
EXP-04714 | PRJ-005 | PRJ-005-ACT-07 | 2026-02-03 | Material | MAT-005 | Bricks | VEN-008 | 22.72 | Piece | 192.17 | 183.81 | 33.09 | 216.9 | Pending | Medium
EXP-04715 | PRJ-005 | PRJ-005-ACT-09 | 2026-02-03 | Other | OTH-001 | Permit | VEN-012 | 1 | Lot | 17006.38 | 17709.32 | 3187.68 | 20897 | Paid | Low
EXP-04716 | PRJ-005 | PRJ-005-ACT-08 | 2026-02-08 | Material | MAT-005 | Bricks | VEN-005 | 8.71 | Piece | 72.84 | 77.48 | 13.95 | 91.43 | Pending | Medium
EXP-04717 | PRJ-005 | PRJ-005-ACT-07 | 2026-02-08 | Contractor | CON-002 | Electrical Contract | VEN-005 | 1 | Contract | 272747.23 | 268195.17 | 48275.13 | 316470.3 | Paid | Low
EXP-04718 | PRJ-005 | PRJ-005-ACT-04 | 2026-02-08 | Material | MAT-003 | Sand | VEN-012 | 16.89 | Ton | 31286.07 | 33731.45 | 6071.66 | 39803.11 | Paid | Low
EXP-04719 | PRJ-005 | PRJ-005-ACT-07 | 2026-02-08 | Contractor | CON-003 | Plumbing Contract | VEN-005 | 1 | Contract | 277028.77 | 294511.52 | 53012.07 | 347523.59 | Paid | Low
EXP-04720 | PRJ-005 | PRJ-005-ACT-10 | 2026-02-08 | Equipment | EQ-002 | Excavator | VEN-008 | 7 | Day | 109364.4 | 102748.89 | 18494.8 | 121243.69 | Paid | Low
EXP-04721 | PRJ-005 | PRJ-005-ACT-06 | 2026-02-08 | Contractor | CON-003 | Plumbing Contract | VEN-005 | 1 | Contract | 384322.94 | 362442.92 | 65239.73 | 427682.65 | Paid | Low
EXP-04722 | PRJ-005 | PRJ-005-ACT-10 | 2026-02-13 | Contractor | CON-002 | Electrical Contract | VEN-005 | 1 | Contract | 78051.66 | 77189.97 | 13894.19 | 91084.16 | Paid | Low
EXP-04723 | PRJ-005 | PRJ-005-ACT-07 | 2026-02-13 | Labour | LAB-004 | Electrician | VEN-005 | 12 | Worker | 11970 | 11268.21 | 2028.28 | 13296.49 | Partially Paid | Low
EXP-04724 | PRJ-005 | PRJ-005-ACT-01 | 2026-02-13 | Contractor | CON-003 | Plumbing Contract | VEN-005 | 1 | Contract | 116108.61 | 111047 | 19988.46 | 131035.46 | Partially Paid | Medium
EXP-04725 | PRJ-005 | PRJ-005-ACT-02 | 2026-02-13 | Labour | LAB-003 | Carpenter | VEN-012 | 19 | Worker | 22468.14 | 21602.93 | 3888.53 | 25491.46 | Paid | Medium
EXP-04726 | PRJ-005 | PRJ-005-ACT-04 | 2026-02-13 | Labour | LAB-004 | Electrician | VEN-012 | 31 | Worker | 45876.02 | 47725.06 | 8590.51 | 56315.57 | Paid | Medium
EXP-04727 | PRJ-005 | PRJ-005-ACT-02 | 2026-02-13 | Labour | LAB-006 | Painter | VEN-005 | 5 | Worker | 6485.22 | 7030.39 | 1265.47 | 8295.86 | Paid | Medium
EXP-04728 | PRJ-005 | PRJ-005-ACT-07 | 2026-02-13 | Contractor | CON-002 | Electrical Contract | VEN-005 | 1 | Contract | 352192.8 | 347208.98 | 62497.62 | 409706.6 | Paid | Medium
EXP-04729 | PRJ-005 | PRJ-005-ACT-06 | 2026-02-18 | Material | MAT-006 | Electrical Cable | VEN-008 | 4.38 | Meter | 361.99 | 349.83 | 62.97 | 412.8 | Paid | Low
EXP-04730 | PRJ-005 | PRJ-005-ACT-05 | 2026-02-18 | Material | MAT-005 | Bricks | VEN-005 | 9.98 | Piece | 81.6 | 82.08 | 14.77 | 96.85 | Paid | Medium
EXP-04731 | PRJ-005 | PRJ-005-ACT-03 | 2026-02-18 | Labour | LAB-003 | Carpenter | VEN-008 | 4 | Worker | 6454.36 | 6738.74 | 1212.97 | 7951.71 | Paid | Low
EXP-04732 | PRJ-005 | PRJ-005-ACT-05 | 2026-02-18 | Equipment | EQ-001 | Crane | VEN-005 | 1 | Day | 19082.56 | 18852.18 | 3393.39 | 22245.57 | Paid | Low
EXP-04733 | PRJ-005 | PRJ-005-ACT-01 | 2026-02-18 | Material | MAT-006 | Electrical Cable | VEN-005 | 5.83 | Meter | 541.12 | 551.52 | 99.27 | 650.79 | Paid | Medium
EXP-04734 | PRJ-005 | PRJ-005-ACT-10 | 2026-02-18 | Labour | LAB-004 | Electrician | VEN-012 | 14 | Worker | 23797.77 | 23352.77 | 4203.5 | 27556.27 | Paid | Medium
EXP-04735 | PRJ-005 | PRJ-005-ACT-01 | 2026-02-18 | Contractor | CON-004 | Finishing Contract | VEN-008 | 1 | Contract | 262887.53 | 283633.5 | 51054.03 | 334687.53 | Paid | High
EXP-04736 | PRJ-005 | PRJ-005-ACT-08 | 2026-02-18 | Material | MAT-003 | Sand | VEN-008 | 33.15 | Ton | 54149.55 | 51506.75 | 9271.22 | 60777.97 | Paid | Low
EXP-04737 | PRJ-005 | PRJ-005-ACT-01 | 2026-02-18 | Material | MAT-007 | PVC Pipe | VEN-008 | 23.01 | Meter | 2722.17 | 2775.82 | 499.65 | 3275.47 | Paid | Low
EXP-04738 | PRJ-005 | PRJ-005-ACT-08 | 2026-02-23 | Material | MAT-005 | Bricks | VEN-012 | 26.76 | Piece | 263.89 | 248.61 | 44.75 | 293.36 | Paid | Low
EXP-04739 | PRJ-005 | PRJ-005-ACT-03 | 2026-02-23 | Contractor | CON-001 | Civil Structure Contract | VEN-012 | 1 | Contract | 148718.85 | 148507.32 | 26731.32 | 175238.64 | Paid | Medium
EXP-04740 | PRJ-005 | PRJ-005-ACT-01 | 2026-02-23 | Contractor | CON-002 | Electrical Contract | VEN-008 | 1 | Contract | 84663.44 | 90363.86 | 16265.49 | 106629.35 | Paid | Medium
EXP-04741 | PRJ-005 | PRJ-005-ACT-10 | 2026-02-23 | Equipment | EQ-003 | Concrete Mixer | VEN-005 | 4 | Day | 16940.7 | 18164.07 | 3269.53 | 21433.6 | Paid | High
EXP-04742 | PRJ-005 | PRJ-005-ACT-05 | 2026-02-23 | Material | MAT-006 | Electrical Cable | VEN-012 | 5.64 | Meter | 424.51 | 452.83 | 81.51 | 534.34 | Paid | Low
EXP-04743 | PRJ-005 | PRJ-005-ACT-08 | 2026-02-23 | Material | MAT-006 | Electrical Cable | VEN-012 | 4.17 | Meter | 402.45 | 382.54 | 68.86 | 451.4 | Paid | Medium
EXP-04744 | PRJ-005 | PRJ-005-ACT-09 | 2026-02-23 | Labour | LAB-005 | Plumber | VEN-008 | 15 | Worker | 25535.24 | 26911.92 | 4844.15 | 31756.07 | Paid | Low
EXP-04745 | PRJ-005 | PRJ-005-ACT-07 | 2026-02-28 | Other | OTH-001 | Safety | VEN-012 | 1 | Lot | 15779.23 | 15411.11 | 2774 | 18185.11 | Partially Paid | Low
EXP-04746 | PRJ-005 | PRJ-005-ACT-02 | 2026-02-28 | Labour | LAB-005 | Plumber | VEN-005 | 24 | Worker | 41535.48 | 40696.84 | 7325.43 | 48022.27 | Paid | Low
EXP-04747 | PRJ-005 | PRJ-005-ACT-06 | 2026-02-28 | Material | MAT-003 | Sand | VEN-005 | 6.78 | Ton | 11261.36 | 10659.89 | 1918.78 | 12578.67 | Pending | Low
EXP-04748 | PRJ-005 | PRJ-005-ACT-08 | 2026-02-28 | Labour | LAB-002 | Helper | VEN-005 | 26 | Worker | 30104.96 | 28016.95 | 5043.05 | 33060 | Paid | Medium
EXP-04749 | PRJ-005 | PRJ-005-ACT-07 | 2026-02-28 | Material | MAT-005 | Bricks | VEN-012 | 28.51 | Piece | 223.69 | 242.42 | 43.64 | 286.06 | Partially Paid | High
EXP-04750 | PRJ-005 | PRJ-005-ACT-07 | 2026-02-28 | Material | MAT-002 | Steel | VEN-008 | 13.36 | Ton | 801728.81 | 757931.91 | 136427.74 | 894359.65 | Paid | Low
EXP-04751 | PRJ-005 | PRJ-005-ACT-09 | 2026-03-05 | Material | MAT-003 | Sand | VEN-005 | 7.48 | Ton | 13994.68 | 14906.22 | 2683.12 | 17589.34 | Paid | Low
EXP-04752 | PRJ-005 | PRJ-005-ACT-07 | 2026-03-05 | Labour | LAB-002 | Helper | VEN-005 | 22 | Worker | 27507.83 | 27985.06 | 5037.31 | 33022.37 | Paid | Medium
EXP-04753 | PRJ-005 | PRJ-005-ACT-02 | 2026-03-05 | Equipment | EQ-001 | Crane | VEN-008 | 5 | Day | 92443.62 | 90534.13 | 16296.14 | 106830.27 | Paid | Low
EXP-04754 | PRJ-005 | PRJ-005-ACT-05 | 2026-03-05 | Contractor | CON-004 | Finishing Contract | VEN-012 | 1 | Contract | 294641.29 | 283092.88 | 50956.72 | 334049.6 | Paid | Medium
EXP-04755 | PRJ-005 | PRJ-005-ACT-07 | 2026-03-05 | Labour | LAB-002 | Helper | VEN-012 | 13 | Worker | 18817.26 | 19018.03 | 3423.25 | 22441.28 | Paid | Medium
EXP-04756 | PRJ-005 | PRJ-005-ACT-04 | 2026-03-05 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 202395.81 | 193011.78 | 34742.12 | 227753.9 | Paid | Medium
EXP-04757 | PRJ-005 | PRJ-005-ACT-04 | 2026-03-05 | Other | OTH-001 | Site Office | VEN-012 | 1 | Lot | 63718.65 | 65273.74 | 11749.27 | 77023.01 | Paid | Low
EXP-04758 | PRJ-005 | PRJ-005-ACT-04 | 2026-03-10 | Equipment | EQ-002 | Excavator | VEN-008 | 4 | Day | 55708.66 | 53143.92 | 9565.91 | 62709.83 | Paid | Low
EXP-04759 | PRJ-005 | PRJ-005-ACT-05 | 2026-03-10 | Material | MAT-005 | Bricks | VEN-012 | 18.26 | Piece | 180.12 | 182.16 | 32.79 | 214.95 | Paid | Medium
EXP-04760 | PRJ-005 | PRJ-005-ACT-09 | 2026-03-10 | Other | OTH-001 | Site Office | VEN-008 | 1 | Lot | 29926.03 | 28705.08 | 5166.91 | 33871.99 | Paid | Low
EXP-04761 | PRJ-005 | PRJ-005-ACT-09 | 2026-03-10 | Equipment | EQ-003 | Concrete Mixer | VEN-005 | 4 | Day | 15783.78 | 17090.4 | 3076.27 | 20166.67 | Paid | Low
EXP-04762 | PRJ-005 | PRJ-005-ACT-05 | 2026-03-10 | Labour | LAB-002 | Helper | VEN-008 | 28 | Worker | 21687.6 | 20444.71 | 3680.05 | 24124.76 | Paid | Low
EXP-04763 | PRJ-005 | PRJ-005-ACT-10 | 2026-03-10 | Contractor | CON-003 | Plumbing Contract | VEN-005 | 1 | Contract | 367060.38 | 389954.27 | 70191.77 | 460146.04 | Paid | Low
EXP-04764 | PRJ-005 | PRJ-005-ACT-09 | 2026-03-10 | Contractor | CON-004 | Finishing Contract | VEN-008 | 1 | Contract | 434200.33 | 407579.22 | 73364.26 | 480943.48 | Paid | High
EXP-04765 | PRJ-005 | PRJ-005-ACT-01 | 2026-03-15 | Contractor | CON-003 | Plumbing Contract | VEN-008 | 1 | Contract | 345125.86 | 325488.51 | 58587.93 | 384076.44 | Paid | Medium
EXP-04766 | PRJ-005 | PRJ-005-ACT-10 | 2026-03-15 | Material | MAT-003 | Sand | VEN-008 | 29.87 | Ton | 53978.92 | 54800.67 | 9864.12 | 64664.79 | Paid | Low
EXP-04767 | PRJ-005 | PRJ-005-ACT-03 | 2026-03-15 | Material | MAT-005 | Bricks | VEN-008 | 12.93 | Piece | 128.75 | 133.47 | 24.02 | 157.49 | Partially Paid | Low
EXP-04768 | PRJ-005 | PRJ-005-ACT-02 | 2026-03-15 | Other | OTH-001 | Transport | VEN-008 | 1 | Lot | 28486.48 | 27847.39 | 5012.53 | 32859.92 | Paid | High
EXP-04769 | PRJ-005 | PRJ-005-ACT-02 | 2026-03-15 | Contractor | CON-002 | Electrical Contract | VEN-012 | 1 | Contract | 408082.55 | 398297.17 | 71693.49 | 469990.66 | Paid | Low
EXP-04770 | PRJ-005 | PRJ-005-ACT-03 | 2026-03-15 | Labour | LAB-005 | Plumber | VEN-012 | 29 | Worker | 34983.75 | 35209.59 | 6337.73 | 41547.32 | Partially Paid | Low
EXP-04771 | PRJ-005 | PRJ-005-ACT-05 | 2026-03-15 | Labour | LAB-003 | Carpenter | VEN-005 | 11 | Worker | 14554.05 | 15504.31 | 2790.78 | 18295.09 | Paid | Low
EXP-04772 | PRJ-005 | PRJ-005-ACT-05 | 2026-03-15 | Material | MAT-006 | Electrical Cable | VEN-005 | 5.88 | Meter | 560.66 | 564.31 | 101.58 | 665.89 | Paid | Medium
EXP-04773 | PRJ-005 | PRJ-005-ACT-07 | 2026-03-15 | Contractor | CON-002 | Electrical Contract | VEN-008 | 1 | Contract | 312794.98 | 299021.47 | 53823.86 | 352845.33 | Pending | Low
EXP-04774 | PRJ-005 | PRJ-005-ACT-03 | 2026-03-15 | Labour | LAB-005 | Plumber | VEN-012 | 25 | Worker | 40703.25 | 40351.5 | 7263.27 | 47614.77 | Paid | Low
EXP-04775 | PRJ-005 | PRJ-005-ACT-03 | 2026-03-20 | Material | MAT-009 | Paint | VEN-008 | 11.25 | Litre | 2321.7 | 2478.83 | 446.19 | 2925.02 | Paid | Low
EXP-04776 | PRJ-005 | PRJ-005-ACT-06 | 2026-03-20 | Equipment | EQ-003 | Concrete Mixer | VEN-005 | 2 | Day | 8591.4 | 9105.55 | 1639 | 10744.55 | Paid | Low
EXP-04777 | PRJ-005 | PRJ-005-ACT-03 | 2026-03-20 | Equipment | EQ-004 | Scaffolding | VEN-008 | 3 | Day | 7124.51 | 7598.92 | 1367.81 | 8966.73 | Partially Paid | Low
EXP-04778 | PRJ-005 | PRJ-005-ACT-01 | 2026-03-20 | Material | MAT-007 | PVC Pipe | VEN-008 | 17.12 | Meter | 2066.3 | 1965.33 | 353.76 | 2319.09 | Paid | Low
EXP-04779 | PRJ-005 | PRJ-005-ACT-02 | 2026-03-20 | Contractor | CON-003 | Plumbing Contract | VEN-008 | 1 | Contract | 406315.73 | 426009.91 | 76681.78 | 502691.69 | Partially Paid | Medium
EXP-04780 | PRJ-005 | PRJ-005-ACT-07 | 2026-03-20 | Material | MAT-009 | Paint | VEN-005 | 1.7 | Litre | 413.57 | 387.93 | 69.83 | 457.76 | Paid | Medium
EXP-04781 | PRJ-005 | PRJ-005-ACT-08 | 2026-03-25 | Contractor | CON-004 | Finishing Contract | VEN-012 | 1 | Contract | 342679.59 | 320768.68 | 57738.36 | 378507.04 | Paid | Medium
EXP-04782 | PRJ-005 | PRJ-005-ACT-02 | 2026-03-25 | Other | OTH-001 | Site Office | VEN-012 | 1 | Lot | 21111.41 | 20566.86 | 3702.03 | 24268.89 | Pending | Medium
EXP-04783 | PRJ-005 | PRJ-005-ACT-01 | 2026-03-25 | Labour | LAB-006 | Painter | VEN-012 | 17 | Worker | 25068.16 | 25995.69 | 4679.22 | 30674.91 | Paid | Medium
EXP-04784 | PRJ-005 | PRJ-005-ACT-08 | 2026-03-25 | Material | MAT-008 | Tiles | VEN-008 | 12.93 | Sq Ft | 1089.58 | 1097.52 | 197.55 | 1295.07 | Paid | Medium
EXP-04785 | PRJ-005 | PRJ-005-ACT-01 | 2026-03-25 | Contractor | CON-001 | Civil Structure Contract | VEN-008 | 1 | Contract | 151272.96 | 146890.04 | 26440.21 | 173330.25 | Paid | Low
EXP-04786 | PRJ-005 | PRJ-005-ACT-05 | 2026-03-25 | Material | MAT-007 | PVC Pipe | VEN-005 | 6.17 | Meter | 786.69 | 769.77 | 138.56 | 908.33 | Paid | Low
EXP-04787 | PRJ-005 | PRJ-005-ACT-09 | 2026-03-25 | Contractor | CON-004 | Finishing Contract | VEN-012 | 1 | Contract | 83930.08 | 78776.95 | 14179.85 | 92956.8 | Paid | Low
EXP-04788 | PRJ-005 | PRJ-005-ACT-04 | 2026-03-25 | Contractor | CON-004 | Finishing Contract | VEN-005 | 1 | Contract | 243915.01 | 228183.11 | 41072.96 | 269256.07 | Paid | Medium
EXP-04789 | PRJ-005 | PRJ-005-ACT-04 | 2026-03-30 | Labour | LAB-005 | Plumber | VEN-008 | 9 | Worker | 14102.7 | 14303.52 | 2574.63 | 16878.15 | Paid | Low
EXP-04790 | PRJ-005 | PRJ-005-ACT-04 | 2026-03-30 | Contractor | CON-002 | Electrical Contract | VEN-012 | 1 | Contract | 439816.97 | 446200.52 | 80316.09 | 526516.61 | Paid | High
EXP-04791 | PRJ-005 | PRJ-005-ACT-04 | 2026-03-30 | Contractor | CON-001 | Civil Structure Contract | VEN-012 | 1 | Contract | 125693.35 | 130378.17 | 23468.07 | 153846.24 | Paid | Low
EXP-04792 | PRJ-005 | PRJ-005-ACT-07 | 2026-03-30 | Material | MAT-010 | Glass | VEN-008 | 2.3 | Sq Ft | 312.32 | 321.68 | 57.9 | 379.58 | Paid | Low
EXP-04793 | PRJ-005 | PRJ-005-ACT-10 | 2026-03-30 | Contractor | CON-003 | Plumbing Contract | VEN-005 | 1 | Contract | 284507.5 | 286682.15 | 51602.79 | 338284.94 | Paid | Medium
EXP-04794 | PRJ-005 | PRJ-005-ACT-01 | 2026-03-30 | Labour | LAB-005 | Plumber | VEN-005 | 13 | Worker | 15799.86 | 14898.85 | 2681.79 | 17580.64 | Partially Paid | Low
EXP-04795 | PRJ-005 | PRJ-005-ACT-05 | 2026-03-30 | Material | MAT-005 | Bricks | VEN-008 | 9.99 | Piece | 99.77 | 95.17 | 17.13 | 112.3 | Partially Paid | Medium
EXP-04796 | PRJ-005 | PRJ-005-ACT-05 | 2026-03-30 | Contractor | CON-001 | Civil Structure Contract | VEN-012 | 1 | Contract | 291262.02 | 298308.95 | 53695.61 | 352004.56 | Pending | Low
EXP-04797 | PRJ-005 | PRJ-005-ACT-02 | 2026-03-30 | Contractor | CON-001 | Civil Structure Contract | VEN-012 | 1 | Contract | 414659.78 | 416954.22 | 75051.76 | 492005.98 | Paid | Low
EXP-04798 | PRJ-006 | PRJ-006-ACT-10 | 2025-06-01 | Material | MAT-003 | Sand | VEN-015 | 10.44 | Ton | 17812.03 | 16964.89 | 3053.68 | 20018.57 | Partially Paid | Low
EXP-04799 | PRJ-006 | PRJ-006-ACT-09 | 2025-06-01 | Contractor | CON-001 | Civil Structure Contract | VEN-016 | 1 | Contract | 175518.29 | 166861.73 | 30035.11 | 196896.84 | Paid | Medium
EXP-04800 | PRJ-006 | PRJ-006-ACT-05 | 2025-06-01 | Labour | LAB-006 | Painter | VEN-015 | 26 | Worker | 40912.4 | 40793.84 | 7342.89 | 48136.73 | Paid | Low
EXP-04801 | PRJ-006 | PRJ-006-ACT-01 | 2025-06-01 | Labour | LAB-004 | Electrician | VEN-013 | 16 | Worker | 10624.77 | 10674.07 | 1921.33 | 12595.4 | Paid | High
EXP-04802 | PRJ-006 | PRJ-006-ACT-06 | 2025-06-01 | Labour | LAB-006 | Painter | VEN-013 | 23 | Worker | 21933.66 | 20719.88 | 3729.58 | 24449.46 | Paid | Low
EXP-04803 | PRJ-006 | PRJ-006-ACT-05 | 2025-06-01 | Contractor | CON-004 | Finishing Contract | VEN-016 | 1 | Contract | 188099.56 | 187289.21 | 33712.06 | 221001.27 | Paid | Medium
EXP-04804 | PRJ-006 | PRJ-006-ACT-10 | 2025-06-06 | Contractor | CON-001 | Civil Structure Contract | VEN-013 | 1 | Contract | 177341.38 | 192278.35 | 34610.1 | 226888.45 | Paid | Low
EXP-04805 | PRJ-006 | PRJ-006-ACT-02 | 2025-06-06 | Labour | LAB-002 | Helper | VEN-016 | 11 | Worker | 7053.42 | 7190.24 | 1294.24 | 8484.48 | Paid | Low
EXP-04806 | PRJ-006 | PRJ-006-ACT-07 | 2025-06-06 | Contractor | CON-001 | Civil Structure Contract | VEN-013 | 1 | Contract | 379102.16 | 379133.29 | 68243.99 | 447377.28 | Paid | Medium
EXP-04807 | PRJ-006 | PRJ-006-ACT-10 | 2025-06-06 | Labour | LAB-003 | Carpenter | VEN-014 | 17 | Worker | 20625.66 | 20225.81 | 3640.65 | 23866.46 | Pending | Low
EXP-04808 | PRJ-006 | PRJ-006-ACT-03 | 2025-06-06 | Labour | LAB-004 | Electrician | VEN-013 | 19 | Worker | 23278.32 | 24996.69 | 4499.4 | 29496.09 | Paid | Medium
EXP-04809 | PRJ-006 | PRJ-006-ACT-01 | 2025-06-06 | Contractor | CON-002 | Electrical Contract | VEN-014 | 1 | Contract | 173644.43 | 188550.8 | 33939.14 | 222489.94 | Paid | Low
EXP-04810 | PRJ-006 | PRJ-006-ACT-04 | 2025-06-06 | Labour | LAB-002 | Helper | VEN-016 | 30 | Worker | 50776.01 | 52291.42 | 9412.46 | 61703.88 | Partially Paid | Low
EXP-04811 | PRJ-006 | PRJ-006-ACT-08 | 2025-06-06 | Contractor | CON-004 | Finishing Contract | VEN-014 | 1 | Contract | 151443.99 | 160763.8 | 28937.48 | 189701.28 | Paid | Low
EXP-04812 | PRJ-006 | PRJ-006-ACT-03 | 2025-06-06 | Contractor | CON-001 | Civil Structure Contract | VEN-015 | 1 | Contract | 87179.19 | 86360.5 | 15544.89 | 101905.39 | Paid | Medium
EXP-04813 | PRJ-006 | PRJ-006-ACT-05 | 2025-06-11 | Material | MAT-007 | PVC Pipe | VEN-013 | 3.2 | Meter | 367.29 | 356.56 | 64.18 | 420.74 | Paid | Medium
EXP-04814 | PRJ-006 | PRJ-006-ACT-03 | 2025-06-11 | Material | MAT-005 | Bricks | VEN-015 | 2.55 | Piece | 22.16 | 21.77 | 3.92 | 25.69 | Paid | Medium
EXP-04815 | PRJ-006 | PRJ-006-ACT-05 | 2025-06-11 | Material | MAT-010 | Glass | VEN-013 | 5.6 | Sq Ft | 972.67 | 944.23 | 169.96 | 1114.19 | Paid | Low
EXP-04816 | PRJ-006 | PRJ-006-ACT-06 | 2025-06-11 | Labour | LAB-006 | Painter | VEN-015 | 12 | Worker | 10292.12 | 10285.67 | 1851.42 | 12137.09 | Paid | Low
EXP-04817 | PRJ-006 | PRJ-006-ACT-10 | 2025-06-11 | Material | MAT-004 | Aggregate | VEN-013 | 5.32 | Ton | 8414.77 | 9132.99 | 1643.94 | 10776.93 | Paid | High
EXP-04818 | PRJ-006 | PRJ-006-ACT-01 | 2025-06-11 | Material | MAT-009 | Paint | VEN-015 | 7.75 | Litre | 1537.89 | 1470.89 | 264.76 | 1735.65 | Partially Paid | Low
EXP-04819 | PRJ-006 | PRJ-006-ACT-03 | 2025-06-16 | Material | MAT-001 | Cement | VEN-013 | 29.17 | Bag | 15296.3 | 15893.34 | 2860.8 | 18754.14 | Paid | High
EXP-04820 | PRJ-006 | PRJ-006-ACT-03 | 2025-06-16 | Labour | LAB-002 | Helper | VEN-015 | 32 | Worker | 52359.2 | 55607.52 | 10009.35 | 65616.87 | Partially Paid | Low
EXP-04821 | PRJ-006 | PRJ-006-ACT-02 | 2025-06-16 | Material | MAT-001 | Cement | VEN-016 | 5.04 | Bag | 2709.9 | 2827.7 | 508.99 | 3336.69 | Paid | Low
EXP-04822 | PRJ-006 | PRJ-006-ACT-05 | 2025-06-16 | Equipment | EQ-002 | Excavator | VEN-016 | 2 | Day | 29511.37 | 29706.17 | 5347.11 | 35053.28 | Paid | Medium
EXP-04823 | PRJ-006 | PRJ-006-ACT-08 | 2025-06-16 | Labour | LAB-006 | Painter | VEN-014 | 27 | Worker | 24513.51 | 24350.34 | 4383.06 | 28733.4 | Paid | Low
EXP-04824 | PRJ-006 | PRJ-006-ACT-07 | 2025-06-16 | Contractor | CON-002 | Electrical Contract | VEN-015 | 1 | Contract | 207665.12 | 192615.16 | 34670.73 | 227285.89 | Paid | Low
EXP-04825 | PRJ-006 | PRJ-006-ACT-08 | 2025-06-16 | Contractor | CON-004 | Finishing Contract | VEN-014 | 1 | Contract | 239104.76 | 250633.77 | 45114.08 | 295747.85 | Paid | Low
EXP-04826 | PRJ-006 | PRJ-006-ACT-03 | 2025-06-21 | Material | MAT-005 | Bricks | VEN-015 | 3.98 | Piece | 34.75 | 34.98 | 6.3 | 41.28 | Paid | Low
EXP-04827 | PRJ-006 | PRJ-006-ACT-10 | 2025-06-21 | Material | MAT-009 | Paint | VEN-016 | 31.27 | Litre | 6273.3 | 6311.93 | 1136.15 | 7448.08 | Paid | Low
EXP-04828 | PRJ-006 | PRJ-006-ACT-08 | 2025-06-21 | Equipment | EQ-003 | Concrete Mixer | VEN-015 | 3 | Day | 12957.98 | 12541.55 | 2257.48 | 14799.03 | Paid | High
EXP-04829 | PRJ-006 | PRJ-006-ACT-01 | 2025-06-21 | Material | MAT-005 | Bricks | VEN-015 | 2.2 | Piece | 21.02 | 19.6 | 3.53 | 23.13 | Paid | Low
EXP-04830 | PRJ-006 | PRJ-006-ACT-08 | 2025-06-21 | Material | MAT-005 | Bricks | VEN-015 | 11.51 | Piece | 118.46 | 118.27 | 21.29 | 139.56 | Paid | Medium
EXP-04831 | PRJ-006 | PRJ-006-ACT-02 | 2025-06-21 | Contractor | CON-003 | Plumbing Contract | VEN-013 | 1 | Contract | 394714.21 | 378123.53 | 68062.24 | 446185.77 | Paid | High
EXP-04832 | PRJ-006 | PRJ-006-ACT-08 | 2025-06-21 | Material | MAT-002 | Steel | VEN-015 | 11.66 | Ton | 732267.35 | 740461.32 | 133283.04 | 873744.36 | Paid | Low
EXP-04833 | PRJ-006 | PRJ-006-ACT-06 | 2025-06-21 | Material | MAT-010 | Glass | VEN-015 | 28.37 | Sq Ft | 5015.02 | 4982.76 | 896.9 | 5879.66 | Paid | Medium
EXP-04834 | PRJ-006 | PRJ-006-ACT-03 | 2025-06-21 | Material | MAT-009 | Paint | VEN-016 | 5.94 | Litre | 1351.27 | 1417.06 | 255.07 | 1672.13 | Paid | Low
EXP-04835 | PRJ-006 | PRJ-006-ACT-06 | 2025-06-26 | Material | MAT-004 | Aggregate | VEN-013 | 9.15 | Ton | 14672.71 | 15326.65 | 2758.8 | 18085.45 | Pending | Low
EXP-04836 | PRJ-006 | PRJ-006-ACT-08 | 2025-06-26 | Material | MAT-009 | Paint | VEN-014 | 11.6 | Litre | 2136.08 | 2270.99 | 408.78 | 2679.77 | Paid | Low
EXP-04837 | PRJ-006 | PRJ-006-ACT-06 | 2025-06-26 | Contractor | CON-002 | Electrical Contract | VEN-013 | 1 | Contract | 73792.71 | 77993.86 | 14038.89 | 92032.75 | Paid | Low
EXP-04838 | PRJ-006 | PRJ-006-ACT-01 | 2025-06-26 | Material | MAT-005 | Bricks | VEN-013 | 5.44 | Piece | 51.21 | 48.14 | 8.67 | 56.81 | Paid | Medium
EXP-04839 | PRJ-006 | PRJ-006-ACT-10 | 2025-06-26 | Equipment | EQ-002 | Excavator | VEN-016 | 4 | Day | 59067.98 | 60331.7 | 10859.71 | 71191.41 | Paid | Low
EXP-04840 | PRJ-006 | PRJ-006-ACT-08 | 2025-06-26 | Labour | LAB-004 | Electrician | VEN-014 | 5 | Worker | 5316.62 | 5281.35 | 950.64 | 6231.99 | Paid | Medium
EXP-04841 | PRJ-006 | PRJ-006-ACT-03 | 2025-06-26 | Material | MAT-008 | Tiles | VEN-014 | 3.43 | Sq Ft | 285.24 | 290.59 | 52.31 | 342.9 | Paid | High
EXP-04842 | PRJ-006 | PRJ-006-ACT-10 | 2025-06-26 | Material | MAT-009 | Paint | VEN-015 | 14.25 | Litre | 3066.88 | 3054.98 | 549.9 | 3604.88 | Paid | Low
EXP-04843 | PRJ-006 | PRJ-006-ACT-10 | 2025-07-01 | Equipment | EQ-002 | Excavator | VEN-013 | 4 | Day | 53063.79 | 50411.41 | 9074.05 | 59485.46 | Partially Paid | Low
EXP-04844 | PRJ-006 | PRJ-006-ACT-02 | 2025-07-01 | Equipment | EQ-002 | Excavator | VEN-016 | 2 | Day | 29230.37 | 29184.02 | 5253.12 | 34437.14 | Paid | Low
EXP-04845 | PRJ-006 | PRJ-006-ACT-08 | 2025-07-01 | Contractor | CON-003 | Plumbing Contract | VEN-013 | 1 | Contract | 198502.08 | 184355.09 | 33183.92 | 217539.01 | Partially Paid | Low
EXP-04846 | PRJ-006 | PRJ-006-ACT-10 | 2025-07-01 | Material | MAT-002 | Steel | VEN-016 | 41.29 | Ton | 2176395.43 | 2344509.86 | 422011.77 | 2766521.63 | Paid | Low
EXP-04847 | PRJ-006 | PRJ-006-ACT-08 | 2025-07-01 | Labour | LAB-003 | Carpenter | VEN-014 | 13 | Worker | 9537.08 | 9052.53 | 1629.46 | 10681.99 | Paid | Low
EXP-04848 | PRJ-006 | PRJ-006-ACT-08 | 2025-07-01 | Contractor | CON-001 | Civil Structure Contract | VEN-016 | 1 | Contract | 191090.14 | 205171.4 | 36930.85 | 242102.25 | Paid | Medium
EXP-04849 | PRJ-006 | PRJ-006-ACT-07 | 2025-07-01 | Material | MAT-004 | Aggregate | VEN-014 | 13.87 | Ton | 23169.19 | 22302.69 | 4014.48 | 26317.17 | Paid | Low
EXP-04850 | PRJ-006 | PRJ-006-ACT-08 | 2025-07-01 | Material | MAT-006 | Electrical Cable | VEN-013 | 1 | Meter | 87.67 | 95.19 | 17.13 | 112.32 | Partially Paid | Medium
EXP-04851 | PRJ-006 | PRJ-006-ACT-04 | 2025-07-01 | Equipment | EQ-002 | Excavator | VEN-014 | 2 | Day | 28536.33 | 30512.14 | 5492.19 | 36004.33 | Paid | Low
EXP-04852 | PRJ-006 | PRJ-006-ACT-10 | 2025-07-06 | Material | MAT-004 | Aggregate | VEN-015 | 11.52 | Ton | 16399.82 | 16624.88 | 2992.48 | 19617.36 | Pending | Low
EXP-04853 | PRJ-006 | PRJ-006-ACT-10 | 2025-07-06 | Labour | LAB-004 | Electrician | VEN-016 | 6 | Worker | 10159.73 | 9889.51 | 1780.11 | 11669.62 | Paid | Low
EXP-04854 | PRJ-006 | PRJ-006-ACT-10 | 2025-07-06 | Material | MAT-006 | Electrical Cable | VEN-016 | 9.69 | Meter | 993.18 | 937.19 | 168.69 | 1105.88 | Paid | High
EXP-04855 | PRJ-006 | PRJ-006-ACT-10 | 2025-07-06 | Equipment | EQ-004 | Scaffolding | VEN-015 | 4 | Day | 9519.35 | 9182.15 | 1652.79 | 10834.94 | Pending | Low
EXP-04856 | PRJ-006 | PRJ-006-ACT-04 | 2025-07-06 | Labour | LAB-003 | Carpenter | VEN-016 | 16 | Worker | 26569.82 | 27293.02 | 4912.74 | 32205.76 | Paid | Low
EXP-04857 | PRJ-006 | PRJ-006-ACT-04 | 2025-07-06 | Contractor | CON-002 | Electrical Contract | VEN-015 | 1 | Contract | 228600.65 | 232124.52 | 41782.41 | 273906.93 | Partially Paid | Low
EXP-04858 | PRJ-006 | PRJ-006-ACT-02 | 2025-07-06 | Material | MAT-005 | Bricks | VEN-013 | 16.4 | Piece | 144.67 | 144.16 | 25.95 | 170.11 | Paid | Low
EXP-04859 | PRJ-006 | PRJ-006-ACT-08 | 2025-07-06 | Material | MAT-002 | Steel | VEN-016 | 3.66 | Ton | 259607.81 | 241025.53 | 43384.6 | 284410.13 | Partially Paid | Medium
EXP-04860 | PRJ-006 | PRJ-006-ACT-09 | 2025-07-11 | Equipment | EQ-001 | Crane | VEN-016 | 7 | Day | 127120.25 | 120305.76 | 21655.04 | 141960.8 | Paid | Low
EXP-04861 | PRJ-006 | PRJ-006-ACT-08 | 2025-07-11 | Material | MAT-003 | Sand | VEN-016 | 19.88 | Ton | 39758.35 | 36886.21 | 6639.52 | 43525.73 | Paid | Low
EXP-04862 | PRJ-006 | PRJ-006-ACT-10 | 2025-07-11 | Contractor | CON-003 | Plumbing Contract | VEN-014 | 1 | Contract | 157969.62 | 157546.03 | 28358.29 | 185904.32 | Paid | Low
EXP-04863 | PRJ-006 | PRJ-006-ACT-05 | 2025-07-11 | Contractor | CON-001 | Civil Structure Contract | VEN-014 | 1 | Contract | 425547.17 | 412254.43 | 74205.8 | 486460.23 | Paid | Low
EXP-04864 | PRJ-006 | PRJ-006-ACT-05 | 2025-07-11 | Material | MAT-005 | Bricks | VEN-015 | 6.59 | Piece | 58.69 | 56.51 | 10.17 | 66.68 | Paid | Medium
EXP-04865 | PRJ-006 | PRJ-006-ACT-06 | 2025-07-11 | Material | MAT-006 | Electrical Cable | VEN-016 | 8.91 | Meter | 746.68 | 771.78 | 138.92 | 910.7 | Pending | Medium
EXP-04866 | PRJ-006 | PRJ-006-ACT-10 | 2025-07-11 | Labour | LAB-006 | Painter | VEN-015 | 9 | Worker | 14956.17 | 16006.14 | 2881.11 | 18887.25 | Pending | Medium
EXP-04867 | PRJ-006 | PRJ-006-ACT-10 | 2025-07-11 | Labour | LAB-003 | Carpenter | VEN-014 | 12 | Worker | 20454.42 | 21359.3 | 3844.67 | 25203.97 | Partially Paid | Low
EXP-04868 | PRJ-006 | PRJ-006-ACT-08 | 2025-07-11 | Contractor | CON-004 | Finishing Contract | VEN-013 | 1 | Contract | 179574.3 | 166842.16 | 30031.59 | 196873.75 | Paid | Low
EXP-04869 | PRJ-006 | PRJ-006-ACT-05 | 2025-07-16 | Other | OTH-001 | Permit | VEN-014 | 1 | Lot | 53655.66 | 56972.92 | 10255.13 | 67228.05 | Paid | Low
EXP-04870 | PRJ-006 | PRJ-006-ACT-10 | 2025-07-16 | Contractor | CON-002 | Electrical Contract | VEN-014 | 1 | Contract | 397024.28 | 404405.83 | 72793.05 | 477198.88 | Paid | Low
EXP-04871 | PRJ-006 | PRJ-006-ACT-09 | 2025-07-16 | Labour | LAB-002 | Helper | VEN-016 | 10 | Worker | 11008.71 | 11305.32 | 2034.96 | 13340.28 | Pending | Low
EXP-04872 | PRJ-006 | PRJ-006-ACT-01 | 2025-07-16 | Labour | LAB-004 | Electrician | VEN-016 | 18 | Worker | 19599.82 | 20511.32 | 3692.04 | 24203.36 | Paid | Low
EXP-04873 | PRJ-006 | PRJ-006-ACT-10 | 2025-07-16 | Labour | LAB-004 | Electrician | VEN-015 | 20 | Worker | 20745.65 | 21095.6 | 3797.21 | 24892.81 | Paid | Medium
EXP-04874 | PRJ-006 | PRJ-006-ACT-06 | 2025-07-16 | Equipment | EQ-003 | Concrete Mixer | VEN-015 | 5 | Day | 23965.93 | 24240.68 | 4363.32 | 28604 | Paid | Medium
EXP-04875 | PRJ-006 | PRJ-006-ACT-09 | 2025-07-16 | Labour | LAB-001 | Mason | VEN-016 | 25 | Worker | 23597.34 | 22487.51 | 4047.75 | 26535.26 | Paid | Low
EXP-04876 | PRJ-006 | PRJ-006-ACT-08 | 2025-07-16 | Material | MAT-002 | Steel | VEN-014 | 11.84 | Ton | 803344.01 | 831312.43 | 149636.24 | 980948.67 | Paid | Medium
EXP-04877 | PRJ-006 | PRJ-006-ACT-01 | 2025-07-21 | Labour | LAB-004 | Electrician | VEN-015 | 25 | Worker | 34664.66 | 33065.79 | 5951.84 | 39017.63 | Paid | Medium
EXP-04878 | PRJ-006 | PRJ-006-ACT-03 | 2025-07-21 | Equipment | EQ-003 | Concrete Mixer | VEN-016 | 4 | Day | 16279.39 | 17626.55 | 3172.78 | 20799.33 | Paid | Low
EXP-04879 | PRJ-006 | PRJ-006-ACT-06 | 2025-07-21 | Contractor | CON-003 | Plumbing Contract | VEN-014 | 1 | Contract | 218615.19 | 219333.56 | 39480.04 | 258813.6 | Partially Paid | Medium
EXP-04880 | PRJ-006 | PRJ-006-ACT-09 | 2025-07-21 | Labour | LAB-003 | Carpenter | VEN-015 | 34 | Worker | 49950.74 | 46457.98 | 8362.44 | 54820.42 | Paid | Medium
EXP-04881 | PRJ-006 | PRJ-006-ACT-03 | 2025-07-21 | Material | MAT-002 | Steel | VEN-013 | 1.19 | Ton | 76667.58 | 78560.12 | 14140.82 | 92700.94 | Paid | Low
EXP-04882 | PRJ-006 | PRJ-006-ACT-08 | 2025-07-21 | Material | MAT-010 | Glass | VEN-014 | 30.73 | Sq Ft | 4699.81 | 4554.59 | 819.83 | 5374.42 | Paid | Low
EXP-04883 | PRJ-006 | PRJ-006-ACT-03 | 2025-07-21 | Equipment | EQ-004 | Scaffolding | VEN-013 | 3 | Day | 6559.15 | 6946.7 | 1250.41 | 8197.11 | Paid | Low
EXP-04884 | PRJ-006 | PRJ-006-ACT-10 | 2025-07-26 | Labour | LAB-002 | Helper | VEN-014 | 25 | Worker | 16723.63 | 16979.62 | 3056.33 | 20035.95 | Paid | Medium
EXP-04885 | PRJ-006 | PRJ-006-ACT-03 | 2025-07-26 | Other | OTH-001 | Safety | VEN-015 | 1 | Lot | 80544.87 | 75514.15 | 13592.55 | 89106.7 | Paid | Low
EXP-04886 | PRJ-006 | PRJ-006-ACT-08 | 2025-07-26 | Material | MAT-008 | Tiles | VEN-016 | 1.46 | Sq Ft | 94 | 95.02 | 17.1 | 112.12 | Paid | Medium
EXP-04887 | PRJ-006 | PRJ-006-ACT-07 | 2025-07-26 | Labour | LAB-004 | Electrician | VEN-015 | 20 | Worker | 33675.8 | 34645.99 | 6236.28 | 40882.27 | Paid | Low
EXP-04888 | PRJ-006 | PRJ-006-ACT-03 | 2025-07-26 | Material | MAT-004 | Aggregate | VEN-013 | 9.78 | Ton | 15236.27 | 14465.35 | 2603.76 | 17069.11 | Partially Paid | Medium
EXP-04889 | PRJ-006 | PRJ-006-ACT-07 | 2025-07-26 | Labour | LAB-003 | Carpenter | VEN-014 | 19 | Worker | 13016.14 | 13901.39 | 2502.25 | 16403.64 | Paid | Low
EXP-04890 | PRJ-006 | PRJ-006-ACT-07 | 2025-07-26 | Material | MAT-004 | Aggregate | VEN-014 | 15.13 | Ton | 23213.79 | 23391.61 | 4210.49 | 27602.1 | Paid | Medium
EXP-04891 | PRJ-006 | PRJ-006-ACT-10 | 2025-07-31 | Equipment | EQ-001 | Crane | VEN-013 | 5 | Day | 91777.77 | 93879.08 | 16898.23 | 110777.31 | Paid | Medium
EXP-04892 | PRJ-006 | PRJ-006-ACT-02 | 2025-07-31 | Material | MAT-005 | Bricks | VEN-014 | 21.75 | Piece | 192.65 | 198.27 | 35.69 | 233.96 | Paid | Medium
EXP-04893 | PRJ-006 | PRJ-006-ACT-01 | 2025-07-31 | Material | MAT-008 | Tiles | VEN-013 | 4.94 | Sq Ft | 348.06 | 366.73 | 66.01 | 432.74 | Paid | Low
EXP-04894 | PRJ-006 | PRJ-006-ACT-06 | 2025-07-31 | Equipment | EQ-002 | Excavator | VEN-015 | 7 | Day | 92389.05 | 91297.98 | 16433.64 | 107731.62 | Paid | Low
EXP-04895 | PRJ-006 | PRJ-006-ACT-05 | 2025-07-31 | Contractor | CON-001 | Civil Structure Contract | VEN-014 | 1 | Contract | 168805.43 | 179516.81 | 32313.03 | 211829.84 | Paid | Low
EXP-04896 | PRJ-006 | PRJ-006-ACT-02 | 2025-07-31 | Material | MAT-005 | Bricks | VEN-015 | 8.6 | Piece | 67.87 | 71.52 | 12.87 | 84.39 | Pending | Low
EXP-04897 | PRJ-006 | PRJ-006-ACT-04 | 2025-07-31 | Material | MAT-010 | Glass | VEN-014 | 7.27 | Sq Ft | 1002.38 | 1066.06 | 191.89 | 1257.95 | Paid | Medium
EXP-04898 | PRJ-006 | PRJ-006-ACT-07 | 2025-07-31 | Material | MAT-005 | Bricks | VEN-016 | 2.93 | Piece | 30.02 | 29.72 | 5.35 | 35.07 | Paid | Medium
EXP-04899 | PRJ-006 | PRJ-006-ACT-10 | 2025-07-31 | Labour | LAB-001 | Mason | VEN-015 | 4 | Worker | 3969.71 | 4032.19 | 725.79 | 4757.98 | Paid | Medium
EXP-04900 | PRJ-006 | PRJ-006-ACT-08 | 2025-08-05 | Labour | LAB-004 | Electrician | VEN-015 | 14 | Worker | 22818.59 | 23088.72 | 4155.97 | 27244.69 | Paid | Medium
EXP-04901 | PRJ-006 | PRJ-006-ACT-05 | 2025-08-05 | Equipment | EQ-002 | Excavator | VEN-014 | 1 | Day | 13332.05 | 12623.47 | 2272.22 | 14895.69 | Paid | Medium
EXP-04902 | PRJ-006 | PRJ-006-ACT-10 | 2025-08-05 | Labour | LAB-002 | Helper | VEN-013 | 30 | Worker | 33971 | 33956.29 | 6112.13 | 40068.42 | Partially Paid | High
EXP-04903 | PRJ-006 | PRJ-006-ACT-08 | 2025-08-05 | Material | MAT-005 | Bricks | VEN-014 | 6.89 | Piece | 65.7 | 67.36 | 12.12 | 79.48 | Paid | Medium
EXP-04904 | PRJ-006 | PRJ-006-ACT-08 | 2025-08-05 | Labour | LAB-005 | Plumber | VEN-015 | 17 | Worker | 20844.2 | 21632.87 | 3893.92 | 25526.79 | Paid | Medium
EXP-04905 | PRJ-006 | PRJ-006-ACT-05 | 2025-08-05 | Material | MAT-001 | Cement | VEN-016 | 2.69 | Bag | 1275.64 | 1249.67 | 224.94 | 1474.61 | Paid | Low
EXP-04906 | PRJ-006 | PRJ-006-ACT-05 | 2025-08-05 | Other | OTH-001 | Transport | VEN-013 | 1 | Lot | 77756.41 | 72000.85 | 12960.15 | 84961 | Partially Paid | Low
EXP-04907 | PRJ-006 | PRJ-006-ACT-06 | 2025-08-05 | Material | MAT-009 | Paint | VEN-016 | 9.31 | Litre | 2048.41 | 2171.33 | 390.84 | 2562.17 | Paid | Low
EXP-04908 | PRJ-006 | PRJ-006-ACT-05 | 2025-08-10 | Material | MAT-006 | Electrical Cable | VEN-016 | 7.24 | Meter | 546.96 | 590.37 | 106.27 | 696.64 | Paid | Medium
EXP-04909 | PRJ-006 | PRJ-006-ACT-06 | 2025-08-10 | Labour | LAB-005 | Plumber | VEN-015 | 15 | Worker | 13462.6 | 14058.99 | 2530.62 | 16589.61 | Partially Paid | Medium
EXP-04910 | PRJ-006 | PRJ-006-ACT-08 | 2025-08-10 | Contractor | CON-004 | Finishing Contract | VEN-013 | 1 | Contract | 428090.21 | 418444.24 | 75319.96 | 493764.2 | Paid | Medium
EXP-04911 | PRJ-006 | PRJ-006-ACT-08 | 2025-08-10 | Labour | LAB-002 | Helper | VEN-015 | 9 | Worker | 11130.34 | 11159.61 | 2008.73 | 13168.34 | Paid | Low
EXP-04912 | PRJ-006 | PRJ-006-ACT-07 | 2025-08-10 | Labour | LAB-001 | Mason | VEN-013 | 33 | Worker | 28085.09 | 29781.86 | 5360.73 | 35142.59 | Paid | Low
EXP-04913 | PRJ-006 | PRJ-006-ACT-02 | 2025-08-10 | Material | MAT-004 | Aggregate | VEN-015 | 7.25 | Ton | 12773.5 | 12425.23 | 2236.54 | 14661.77 | Paid | Medium
EXP-04914 | PRJ-006 | PRJ-006-ACT-06 | 2025-08-10 | Material | MAT-009 | Paint | VEN-014 | 31.53 | Litre | 6662.73 | 7089.2 | 1276.06 | 8365.26 | Paid | Low
EXP-04915 | PRJ-006 | PRJ-006-ACT-03 | 2025-08-15 | Material | MAT-006 | Electrical Cable | VEN-015 | 11.87 | Meter | 967.41 | 932.3 | 167.81 | 1100.11 | Paid | Low
EXP-04916 | PRJ-006 | PRJ-006-ACT-06 | 2025-08-15 | Labour | LAB-002 | Helper | VEN-015 | 12 | Worker | 19481.28 | 20081.6 | 3614.69 | 23696.29 | Paid | Low
EXP-04917 | PRJ-006 | PRJ-006-ACT-01 | 2025-08-15 | Material | MAT-007 | PVC Pipe | VEN-013 | 14.4 | Meter | 1676.51 | 1758.95 | 316.61 | 2075.56 | Paid | Low
EXP-04918 | PRJ-006 | PRJ-006-ACT-07 | 2025-08-15 | Equipment | EQ-003 | Concrete Mixer | VEN-015 | 2 | Day | 8605.71 | 8762.22 | 1577.2 | 10339.42 | Partially Paid | Low
EXP-04919 | PRJ-006 | PRJ-006-ACT-08 | 2025-08-15 | Material | MAT-003 | Sand | VEN-015 | 19.99 | Ton | 34164.88 | 36001.13 | 6480.2 | 42481.33 | Partially Paid | Low
EXP-04920 | PRJ-006 | PRJ-006-ACT-04 | 2025-08-15 | Material | MAT-005 | Bricks | VEN-013 | 21.91 | Piece | 198.59 | 200.1 | 36.02 | 236.12 | Paid | Low
EXP-04921 | PRJ-006 | PRJ-006-ACT-09 | 2025-08-20 | Contractor | CON-002 | Electrical Contract | VEN-016 | 1 | Contract | 363755.73 | 341312.14 | 61436.19 | 402748.33 | Paid | Low
EXP-04922 | PRJ-006 | PRJ-006-ACT-10 | 2025-08-20 | Material | MAT-006 | Electrical Cable | VEN-015 | 5.08 | Meter | 428.81 | 462.09 | 83.18 | 545.27 | Paid | High
EXP-04923 | PRJ-006 | PRJ-006-ACT-06 | 2025-08-20 | Material | MAT-006 | Electrical Cable | VEN-016 | 12.24 | Meter | 1189.18 | 1178.41 | 212.11 | 1390.52 | Paid | Low
EXP-04924 | PRJ-006 | PRJ-006-ACT-01 | 2025-08-20 | Equipment | EQ-002 | Excavator | VEN-014 | 1 | Day | 14543.93 | 14238.57 | 2562.94 | 16801.51 | Paid | Low
EXP-04925 | PRJ-006 | PRJ-006-ACT-10 | 2025-08-20 | Material | MAT-005 | Bricks | VEN-016 | 20.63 | Piece | 162.43 | 171.12 | 30.8 | 201.92 | Partially Paid | Medium
EXP-04926 | PRJ-006 | PRJ-006-ACT-04 | 2025-08-20 | Contractor | CON-002 | Electrical Contract | VEN-013 | 1 | Contract | 320657.06 | 301613.47 | 54290.42 | 355903.89 | Partially Paid | Low
EXP-04927 | PRJ-006 | PRJ-006-ACT-04 | 2025-08-25 | Other | OTH-001 | Miscellaneous | VEN-013 | 1 | Lot | 78311.8 | 79492.37 | 14308.63 | 93801 | Paid | High
EXP-04928 | PRJ-006 | PRJ-006-ACT-04 | 2025-08-25 | Labour | LAB-004 | Electrician | VEN-015 | 10 | Worker | 16676.42 | 15560.97 | 2800.97 | 18361.94 | Paid | Low
EXP-04929 | PRJ-006 | PRJ-006-ACT-04 | 2025-08-25 | Material | MAT-001 | Cement | VEN-016 | 4.05 | Bag | 2344.79 | 2310.27 | 415.85 | 2726.12 | Partially Paid | Medium
EXP-04930 | PRJ-006 | PRJ-006-ACT-09 | 2025-08-25 | Material | MAT-007 | PVC Pipe | VEN-016 | 5.41 | Meter | 591.76 | 613.39 | 110.41 | 723.8 | Paid | Medium
EXP-04931 | PRJ-006 | PRJ-006-ACT-03 | 2025-08-25 | Contractor | CON-003 | Plumbing Contract | VEN-013 | 1 | Contract | 83214.34 | 89619.02 | 16131.42 | 105750.44 | Paid | Medium
EXP-04932 | PRJ-006 | PRJ-006-ACT-08 | 2025-08-25 | Labour | LAB-004 | Electrician | VEN-014 | 29 | Worker | 22972.45 | 23236.59 | 4182.59 | 27419.18 | Paid | Low
EXP-04933 | PRJ-006 | PRJ-006-ACT-08 | 2025-08-25 | Contractor | CON-004 | Finishing Contract | VEN-016 | 1 | Contract | 353972.54 | 342331.14 | 61619.61 | 403950.75 | Paid | Low
EXP-04934 | PRJ-006 | PRJ-006-ACT-04 | 2025-08-25 | Contractor | CON-003 | Plumbing Contract | VEN-014 | 1 | Contract | 145852.32 | 141903.65 | 25542.66 | 167446.31 | Paid | Low
EXP-04935 | PRJ-006 | PRJ-006-ACT-08 | 2025-08-30 | Contractor | CON-003 | Plumbing Contract | VEN-014 | 1 | Contract | 348714.42 | 369310.07 | 66475.81 | 435785.88 | Paid | High
EXP-04936 | PRJ-006 | PRJ-006-ACT-09 | 2025-08-30 | Material | MAT-006 | Electrical Cable | VEN-015 | 6.54 | Meter | 505.39 | 474.82 | 85.47 | 560.29 | Paid | Low
EXP-04937 | PRJ-006 | PRJ-006-ACT-05 | 2025-08-30 | Material | MAT-007 | PVC Pipe | VEN-013 | 7.47 | Meter | 918.05 | 923.74 | 166.27 | 1090.01 | Paid | Medium
EXP-04938 | PRJ-006 | PRJ-006-ACT-03 | 2025-08-30 | Contractor | CON-003 | Plumbing Contract | VEN-013 | 1 | Contract | 90178.22 | 96586.92 | 17385.65 | 113972.57 | Paid | Medium
EXP-04939 | PRJ-006 | PRJ-006-ACT-10 | 2025-08-30 | Material | MAT-010 | Glass | VEN-014 | 10.8 | Sq Ft | 1811.19 | 1792.4 | 322.63 | 2115.03 | Paid | Low
EXP-04940 | PRJ-006 | PRJ-006-ACT-10 | 2025-08-30 | Labour | LAB-002 | Helper | VEN-013 | 6 | Worker | 10149.55 | 10566.41 | 1901.95 | 12468.36 | Paid | Low
EXP-04941 | PRJ-006 | PRJ-006-ACT-08 | 2025-08-30 | Material | MAT-003 | Sand | VEN-016 | 6.94 | Ton | 12587.99 | 12902.91 | 2322.52 | 15225.43 | Paid | High
EXP-04942 | PRJ-006 | PRJ-006-ACT-07 | 2025-08-30 | Contractor | CON-004 | Finishing Contract | VEN-016 | 1 | Contract | 470317.57 | 441833.22 | 79529.98 | 521363.2 | Paid | Low
EXP-04943 | PRJ-006 | PRJ-006-ACT-09 | 2025-09-04 | Material | MAT-004 | Aggregate | VEN-014 | 7.46 | Ton | 12808.14 | 12666.34 | 2279.94 | 14946.28 | Paid | Low
EXP-04944 | PRJ-006 | PRJ-006-ACT-06 | 2025-09-04 | Contractor | CON-003 | Plumbing Contract | VEN-013 | 1 | Contract | 387274.7 | 399006.51 | 71821.17 | 470827.68 | Paid | Medium
EXP-04945 | PRJ-006 | PRJ-006-ACT-07 | 2025-09-04 | Contractor | CON-004 | Finishing Contract | VEN-015 | 1 | Contract | 98201.68 | 93809.74 | 16885.75 | 110695.49 | Paid | Low
EXP-04946 | PRJ-006 | PRJ-006-ACT-02 | 2025-09-04 | Material | MAT-003 | Sand | VEN-014 | 6.65 | Ton | 14297.64 | 13488.55 | 2427.94 | 15916.49 | Paid | Low
EXP-04947 | PRJ-006 | PRJ-006-ACT-04 | 2025-09-04 | Labour | LAB-002 | Helper | VEN-014 | 16 | Worker | 29035.15 | 27231.88 | 4901.74 | 32133.62 | Partially Paid | Medium
EXP-04948 | PRJ-006 | PRJ-006-ACT-07 | 2025-09-04 | Equipment | EQ-003 | Concrete Mixer | VEN-016 | 7 | Day | 31405.44 | 31375.64 | 5647.62 | 37023.26 | Paid | Low
EXP-04949 | PRJ-006 | PRJ-006-ACT-10 | 2025-09-04 | Material | MAT-004 | Aggregate | VEN-015 | 7.21 | Ton | 11339.46 | 10631.05 | 1913.59 | 12544.64 | Paid | Low
EXP-04950 | PRJ-006 | PRJ-006-ACT-03 | 2025-09-09 | Other | OTH-001 | Safety | VEN-014 | 1 | Lot | 53492.76 | 49817.97 | 8967.23 | 58785.2 | Paid | Low
EXP-04951 | PRJ-006 | PRJ-006-ACT-08 | 2025-09-09 | Material | MAT-007 | PVC Pipe | VEN-014 | 9.61 | Meter | 969.61 | 1049.6 | 188.93 | 1238.53 | Paid | Medium
EXP-04952 | PRJ-006 | PRJ-006-ACT-01 | 2025-09-09 | Other | OTH-001 | Transport | VEN-014 | 1 | Lot | 67085.81 | 66004.51 | 11880.81 | 77885.32 | Paid | High
EXP-04953 | PRJ-006 | PRJ-006-ACT-06 | 2025-09-09 | Labour | LAB-002 | Helper | VEN-015 | 5 | Worker | 7137.65 | 6835.47 | 1230.38 | 8065.85 | Paid | Medium
EXP-04954 | PRJ-006 | PRJ-006-ACT-08 | 2025-09-09 | Labour | LAB-001 | Mason | VEN-015 | 12 | Worker | 10001.09 | 9897.9 | 1781.62 | 11679.52 | Paid | Low
EXP-04955 | PRJ-006 | PRJ-006-ACT-09 | 2025-09-09 | Material | MAT-004 | Aggregate | VEN-015 | 6.79 | Ton | 10753.21 | 11288.24 | 2031.88 | 13320.12 | Paid | High
EXP-04956 | PRJ-006 | PRJ-006-ACT-03 | 2025-09-14 | Labour | LAB-005 | Plumber | VEN-016 | 4 | Worker | 5223.44 | 4933.13 | 887.96 | 5821.09 | Paid | Medium
EXP-04957 | PRJ-006 | PRJ-006-ACT-01 | 2025-09-14 | Material | MAT-001 | Cement | VEN-013 | 2.83 | Bag | 1721.28 | 1682.33 | 302.82 | 1985.15 | Paid | Low
EXP-04958 | PRJ-006 | PRJ-006-ACT-04 | 2025-09-14 | Material | MAT-008 | Tiles | VEN-015 | 24.66 | Sq Ft | 1901.34 | 1881.25 | 338.62 | 2219.87 | Paid | Low
EXP-04959 | PRJ-006 | PRJ-006-ACT-08 | 2025-09-14 | Material | MAT-005 | Bricks | VEN-013 | 22.16 | Piece | 163.41 | 174.81 | 31.47 | 206.28 | Paid | Medium
EXP-04960 | PRJ-006 | PRJ-006-ACT-07 | 2025-09-14 | Contractor | CON-003 | Plumbing Contract | VEN-016 | 1 | Contract | 105680.2 | 107121.3 | 19281.83 | 126403.13 | Paid | Low
EXP-04961 | PRJ-006 | PRJ-006-ACT-09 | 2025-09-14 | Contractor | CON-004 | Finishing Contract | VEN-015 | 1 | Contract | 144247.26 | 154057.2 | 27730.3 | 181787.5 | Partially Paid | Low
EXP-04962 | PRJ-006 | PRJ-006-ACT-09 | 2025-09-19 | Material | MAT-003 | Sand | VEN-013 | 17.68 | Ton | 26239.43 | 27406.24 | 4933.12 | 32339.36 | Paid | Low
EXP-04963 | PRJ-006 | PRJ-006-ACT-07 | 2025-09-19 | Material | MAT-006 | Electrical Cable | VEN-015 | 4.98 | Meter | 393.48 | 419.02 | 75.42 | 494.44 | Pending | Low
EXP-04964 | PRJ-006 | PRJ-006-ACT-06 | 2025-09-19 | Material | MAT-003 | Sand | VEN-013 | 7.2 | Ton | 13119.45 | 13102.43 | 2358.44 | 15460.87 | Paid | Low
EXP-04965 | PRJ-006 | PRJ-006-ACT-01 | 2025-09-19 | Contractor | CON-002 | Electrical Contract | VEN-015 | 1 | Contract | 386152.15 | 394969.99 | 71094.6 | 466064.59 | Paid | Low
EXP-04966 | PRJ-006 | PRJ-006-ACT-07 | 2025-09-19 | Material | MAT-008 | Tiles | VEN-016 | 7.65 | Sq Ft | 517.59 | 538.34 | 96.9 | 635.24 | Partially Paid | High
EXP-04967 | PRJ-006 | PRJ-006-ACT-08 | 2025-09-19 | Contractor | CON-004 | Finishing Contract | VEN-013 | 1 | Contract | 146763.15 | 159277.19 | 28669.89 | 187947.08 | Paid | Low
EXP-04968 | PRJ-006 | PRJ-006-ACT-10 | 2025-09-19 | Material | MAT-002 | Steel | VEN-014 | 36.4 | Ton | 2004026.95 | 1941806.19 | 349525.11 | 2291331.3 | Paid | Low
EXP-04969 | PRJ-006 | PRJ-006-ACT-03 | 2025-09-19 | Material | MAT-001 | Cement | VEN-013 | 17.38 | Bag | 7916.97 | 8512.26 | 1532.21 | 10044.47 | Partially Paid | Low
EXP-04970 | PRJ-006 | PRJ-006-ACT-04 | 2025-09-24 | Material | MAT-007 | PVC Pipe | VEN-015 | 15.42 | Meter | 1825.01 | 1901.59 | 342.29 | 2243.88 | Paid | Low
EXP-04971 | PRJ-006 | PRJ-006-ACT-05 | 2025-09-24 | Contractor | CON-004 | Finishing Contract | VEN-014 | 1 | Contract | 319493.01 | 301112.37 | 54200.23 | 355312.6 | Paid | High
EXP-04972 | PRJ-006 | PRJ-006-ACT-07 | 2025-09-24 | Contractor | CON-004 | Finishing Contract | VEN-015 | 1 | Contract | 285345.56 | 294847.14 | 53072.49 | 347919.63 | Paid | Medium
EXP-04973 | PRJ-006 | PRJ-006-ACT-06 | 2025-09-24 | Material | MAT-006 | Electrical Cable | VEN-016 | 30.94 | Meter | 2820.53 | 2925.36 | 526.56 | 3451.92 | Paid | Low
EXP-04974 | PRJ-006 | PRJ-006-ACT-04 | 2025-09-24 | Labour | LAB-004 | Electrician | VEN-014 | 23 | Worker | 25658.94 | 24404.59 | 4392.83 | 28797.42 | Paid | Low
EXP-04975 | PRJ-006 | PRJ-006-ACT-07 | 2025-09-24 | Equipment | EQ-003 | Concrete Mixer | VEN-016 | 4 | Day | 18194.59 | 19560.13 | 3520.82 | 23080.95 | Paid | Medium
EXP-04976 | PRJ-006 | PRJ-006-ACT-09 | 2025-09-24 | Material | MAT-006 | Electrical Cable | VEN-013 | 12.93 | Meter | 1217.61 | 1226.54 | 220.78 | 1447.32 | Paid | Low
EXP-04977 | PRJ-006 | PRJ-006-ACT-10 | 2025-09-24 | Material | MAT-009 | Paint | VEN-016 | 45.83 | Litre | 9071.47 | 8776.92 | 1579.85 | 10356.77 | Paid | Low
EXP-04978 | PRJ-006 | PRJ-006-ACT-05 | 2025-09-29 | Contractor | CON-001 | Civil Structure Contract | VEN-014 | 1 | Contract | 98956.03 | 98325.66 | 17698.62 | 116024.28 | Paid | Low
EXP-04979 | PRJ-006 | PRJ-006-ACT-08 | 2025-09-29 | Material | MAT-006 | Electrical Cable | VEN-015 | 5.79 | Meter | 468.68 | 467.51 | 84.15 | 551.66 | Paid | Low
EXP-04980 | PRJ-006 | PRJ-006-ACT-07 | 2025-09-29 | Labour | LAB-005 | Plumber | VEN-015 | 7 | Worker | 8061.31 | 8138.53 | 1464.94 | 9603.47 | Paid | Low
EXP-04981 | PRJ-006 | PRJ-006-ACT-01 | 2025-09-29 | Material | MAT-002 | Steel | VEN-013 | 7.8 | Ton | 463680.02 | 456810.77 | 82225.94 | 539036.71 | Paid | Medium
EXP-04982 | PRJ-006 | PRJ-006-ACT-10 | 2025-09-29 | Equipment | EQ-002 | Excavator | VEN-013 | 3 | Day | 35608.78 | 37849.91 | 6812.98 | 44662.89 | Paid | Low
EXP-04983 | PRJ-006 | PRJ-006-ACT-02 | 2025-09-29 | Material | MAT-003 | Sand | VEN-016 | 3.76 | Ton | 6228.79 | 6273.46 | 1129.22 | 7402.68 | Partially Paid | Low
EXP-04984 | PRJ-006 | PRJ-006-ACT-07 | 2025-09-29 | Contractor | CON-003 | Plumbing Contract | VEN-013 | 1 | Contract | 222975.45 | 221236.56 | 39822.58 | 261059.14 | Paid | Medium
EXP-04985 | PRJ-006 | PRJ-006-ACT-08 | 2025-09-29 | Material | MAT-008 | Tiles | VEN-016 | 2.62 | Sq Ft | 228.05 | 223.44 | 40.22 | 263.66 | Paid | Low
EXP-04986 | PRJ-006 | PRJ-006-ACT-08 | 2025-09-29 | Labour | LAB-001 | Mason | VEN-013 | 8 | Worker | 7454.27 | 7866.37 | 1415.95 | 9282.32 | Paid | Low
EXP-04987 | PRJ-006 | PRJ-006-ACT-02 | 2025-10-04 | Labour | LAB-006 | Painter | VEN-013 | 7 | Worker | 11741.13 | 11998.99 | 2159.82 | 14158.81 | Paid | Low
EXP-04988 | PRJ-006 | PRJ-006-ACT-03 | 2025-10-04 | Labour | LAB-001 | Mason | VEN-015 | 4 | Worker | 3787.92 | 3806.08 | 685.09 | 4491.17 | Pending | Low
EXP-04989 | PRJ-006 | PRJ-006-ACT-08 | 2025-10-04 | Contractor | CON-004 | Finishing Contract | VEN-016 | 1 | Contract | 247933.75 | 263338.8 | 47400.98 | 310739.78 | Paid | Low
EXP-04990 | PRJ-006 | PRJ-006-ACT-08 | 2025-10-04 | Labour | LAB-006 | Painter | VEN-016 | 27 | Worker | 19630.75 | 20056.01 | 3610.08 | 23666.09 | Paid | Low
EXP-04991 | PRJ-006 | PRJ-006-ACT-03 | 2025-10-04 | Other | OTH-001 | Safety | VEN-016 | 1 | Lot | 52723.72 | 56370.09 | 10146.62 | 66516.71 | Partially Paid | Medium
EXP-04992 | PRJ-006 | PRJ-006-ACT-06 | 2025-10-04 | Equipment | EQ-003 | Concrete Mixer | VEN-013 | 2 | Day | 7876.08 | 8154.67 | 1467.84 | 9622.51 | Paid | Medium
EXP-04993 | PRJ-006 | PRJ-006-ACT-05 | 2025-10-04 | Labour | LAB-005 | Plumber | VEN-014 | 11 | Worker | 11542.76 | 10890.03 | 1960.21 | 12850.24 | Paid | Low
EXP-04994 | PRJ-006 | PRJ-006-ACT-08 | 2025-10-09 | Contractor | CON-003 | Plumbing Contract | VEN-013 | 1 | Contract | 274085.69 | 286923.9 | 51646.3 | 338570.2 | Paid | Low
EXP-04995 | PRJ-006 | PRJ-006-ACT-07 | 2025-10-09 | Labour | LAB-002 | Helper | VEN-015 | 22 | Worker | 28782.76 | 30454.81 | 5481.87 | 35936.68 | Paid | Medium
EXP-04996 | PRJ-006 | PRJ-006-ACT-01 | 2025-10-09 | Material | MAT-008 | Tiles | VEN-013 | 12.94 | Sq Ft | 954.55 | 936.31 | 168.54 | 1104.85 | Paid | Low
EXP-04997 | PRJ-006 | PRJ-006-ACT-04 | 2025-10-09 | Other | OTH-001 | Miscellaneous | VEN-016 | 1 | Lot | 16608.07 | 17523.75 | 3154.28 | 20678.03 | Paid | Low
EXP-04998 | PRJ-006 | PRJ-006-ACT-07 | 2025-10-09 | Material | MAT-008 | Tiles | VEN-015 | 7.8 | Sq Ft | 600.67 | 562.31 | 101.22 | 663.53 | Paid | Low
EXP-04999 | PRJ-006 | PRJ-006-ACT-02 | 2025-10-09 | Contractor | CON-001 | Civil Structure Contract | VEN-014 | 1 | Contract | 410343.97 | 430413.95 | 77474.51 | 507888.46 | Paid | Medium
EXP-05000 | PRJ-006 | PRJ-006-ACT-02 | 2025-10-09 | Material | MAT-002 | Steel | VEN-016 | 24.47 | Ton | 1239463.07 | 1292148.49 | 232586.73 | 1524735.22 | Paid | High
EXP-05001 | PRJ-006 | PRJ-006-ACT-01 | 2025-10-09 | Material | MAT-006 | Electrical Cable | VEN-013 | 14.2 | Meter | 1100.91 | 1087.84 | 195.81 | 1283.65 | Paid | Low
EXP-05002 | PRJ-006 | PRJ-006-ACT-08 | 2025-10-09 | Material | MAT-009 | Paint | VEN-014 | 12.35 | Litre | 2265.36 | 2225.36 | 400.56 | 2625.92 | Paid | Medium
EXP-05003 | PRJ-006 | PRJ-006-ACT-03 | 2025-10-14 | Material | MAT-007 | PVC Pipe | VEN-013 | 15.74 | Meter | 1785.69 | 1817.64 | 327.18 | 2144.82 | Paid | High
EXP-05004 | PRJ-006 | PRJ-006-ACT-03 | 2025-10-14 | Contractor | CON-004 | Finishing Contract | VEN-013 | 1 | Contract | 232091.11 | 242730.35 | 43691.46 | 286421.81 | Paid | Medium
EXP-05005 | PRJ-006 | PRJ-006-ACT-09 | 2025-10-14 | Equipment | EQ-001 | Crane | VEN-015 | 3 | Day | 55581.26 | 56563.45 | 10181.42 | 66744.87 | Paid | Medium
EXP-05006 | PRJ-006 | PRJ-006-ACT-07 | 2025-10-14 | Equipment | EQ-002 | Excavator | VEN-016 | 2 | Day | 29131.92 | 28905.46 | 5202.98 | 34108.44 | Paid | Medium
EXP-05007 | PRJ-006 | PRJ-006-ACT-07 | 2025-10-14 | Contractor | CON-003 | Plumbing Contract | VEN-013 | 1 | Contract | 364388.52 | 353965.45 | 63713.78 | 417679.23 | Paid | Medium
EXP-05008 | PRJ-006 | PRJ-006-ACT-06 | 2025-10-14 | Labour | LAB-003 | Carpenter | VEN-015 | 15 | Worker | 20471.02 | 21940.18 | 3949.23 | 25889.41 | Paid | Low
EXP-05009 | PRJ-006 | PRJ-006-ACT-05 | 2025-10-14 | Contractor | CON-002 | Electrical Contract | VEN-015 | 1 | Contract | 279174.11 | 263082.94 | 47354.93 | 310437.87 | Paid | Low
EXP-05010 | PRJ-006 | PRJ-006-ACT-10 | 2025-10-14 | Material | MAT-010 | Glass | VEN-014 | 8.61 | Sq Ft | 1287.41 | 1317.35 | 237.12 | 1554.47 | Paid | Low
EXP-05011 | PRJ-006 | PRJ-006-ACT-03 | 2025-10-14 | Material | MAT-007 | PVC Pipe | VEN-016 | 7.64 | Meter | 843.08 | 792.73 | 142.69 | 935.42 | Paid | Low
EXP-05012 | PRJ-006 | PRJ-006-ACT-05 | 2025-10-19 | Labour | LAB-004 | Electrician | VEN-016 | 12 | Worker | 9260.9 | 8835.87 | 1590.46 | 10426.33 | Paid | Low
EXP-05013 | PRJ-006 | PRJ-006-ACT-09 | 2025-10-19 | Material | MAT-009 | Paint | VEN-015 | 5.44 | Litre | 955.08 | 1035.6 | 186.41 | 1222.01 | Paid | Medium
EXP-05014 | PRJ-006 | PRJ-006-ACT-02 | 2025-10-19 | Equipment | EQ-002 | Excavator | VEN-016 | 7 | Day | 85312.71 | 90976.84 | 16375.83 | 107352.67 | Paid | Low
EXP-05015 | PRJ-006 | PRJ-006-ACT-09 | 2025-10-19 | Equipment | EQ-001 | Crane | VEN-014 | 2 | Day | 36119.08 | 36542.56 | 6577.66 | 43120.22 | Paid | Low
EXP-05016 | PRJ-006 | PRJ-006-ACT-02 | 2025-10-19 | Labour | LAB-002 | Helper | VEN-014 | 10 | Worker | 12201.01 | 11881.75 | 2138.72 | 14020.47 | Paid | Low
EXP-05017 | PRJ-006 | PRJ-006-ACT-09 | 2025-10-19 | Other | OTH-001 | Site Office | VEN-015 | 1 | Lot | 6803.89 | 6994.82 | 1259.07 | 8253.89 | Paid | Low
EXP-05018 | PRJ-006 | PRJ-006-ACT-04 | 2025-10-19 | Labour | LAB-002 | Helper | VEN-016 | 25 | Worker | 39573.94 | 40994.03 | 7378.93 | 48372.96 | Paid | High
EXP-05019 | PRJ-006 | PRJ-006-ACT-03 | 2025-10-19 | Contractor | CON-003 | Plumbing Contract | VEN-014 | 1 | Contract | 111833.99 | 104185.28 | 18753.35 | 122938.63 | Paid | Low
EXP-05020 | PRJ-006 | PRJ-006-ACT-02 | 2025-10-19 | Material | MAT-003 | Sand | VEN-015 | 10.63 | Ton | 17567.53 | 17766.8 | 3198.02 | 20964.82 | Paid | Medium
EXP-05021 | PRJ-006 | PRJ-006-ACT-07 | 2025-10-24 | Contractor | CON-003 | Plumbing Contract | VEN-016 | 1 | Contract | 324603.4 | 338211.34 | 60878.04 | 399089.38 | Paid | Low
EXP-05022 | PRJ-006 | PRJ-006-ACT-01 | 2025-10-24 | Material | MAT-009 | Paint | VEN-014 | 15.32 | Litre | 3757.61 | 3635.75 | 654.43 | 4290.18 | Paid | Low
EXP-05023 | PRJ-006 | PRJ-006-ACT-02 | 2025-10-24 | Material | MAT-009 | Paint | VEN-016 | 12.43 | Litre | 2762.71 | 2750.44 | 495.08 | 3245.52 | Partially Paid | Low
EXP-05024 | PRJ-006 | PRJ-006-ACT-07 | 2025-10-24 | Contractor | CON-004 | Finishing Contract | VEN-014 | 1 | Contract | 214648.52 | 220316.29 | 39656.93 | 259973.22 | Paid | Low
EXP-05025 | PRJ-006 | PRJ-006-ACT-06 | 2025-10-24 | Material | MAT-009 | Paint | VEN-016 | 28.07 | Litre | 6521.15 | 6551.67 | 1179.3 | 7730.97 | Paid | Low
EXP-05026 | PRJ-006 | PRJ-006-ACT-01 | 2025-10-24 | Material | MAT-003 | Sand | VEN-015 | 7.64 | Ton | 13117.27 | 12205.16 | 2196.93 | 14402.09 | Paid | Low
EXP-05027 | PRJ-006 | PRJ-006-ACT-09 | 2025-10-29 | Contractor | CON-003 | Plumbing Contract | VEN-015 | 1 | Contract | 250054.81 | 270681.49 | 48722.67 | 319404.16 | Paid | Low
EXP-05028 | PRJ-006 | PRJ-006-ACT-07 | 2025-10-29 | Contractor | CON-003 | Plumbing Contract | VEN-015 | 1 | Contract | 365568.39 | 358509.28 | 64531.67 | 423040.95 | Paid | Medium
EXP-05029 | PRJ-006 | PRJ-006-ACT-03 | 2025-10-29 | Material | MAT-007 | PVC Pipe | VEN-013 | 12.56 | Meter | 1413.56 | 1456.85 | 262.23 | 1719.08 | Paid | High
EXP-05030 | PRJ-006 | PRJ-006-ACT-06 | 2025-10-29 | Contractor | CON-001 | Civil Structure Contract | VEN-015 | 1 | Contract | 209957.11 | 204009.96 | 36721.79 | 240731.75 | Paid | Low
EXP-05031 | PRJ-006 | PRJ-006-ACT-02 | 2025-10-29 | Contractor | CON-001 | Civil Structure Contract | VEN-015 | 1 | Contract | 409869.02 | 429355.44 | 77283.98 | 506639.42 | Paid | Low
EXP-05032 | PRJ-006 | PRJ-006-ACT-01 | 2025-10-29 | Contractor | CON-004 | Finishing Contract | VEN-015 | 1 | Contract | 469167.98 | 435832.79 | 78449.9 | 514282.69 | Paid | Low
EXP-05033 | PRJ-006 | PRJ-006-ACT-03 | 2025-10-29 | Contractor | CON-001 | Civil Structure Contract | VEN-013 | 1 | Contract | 290936 | 290056.13 | 52210.1 | 342266.23 | Partially Paid | Medium
EXP-05034 | PRJ-006 | PRJ-006-ACT-04 | 2025-10-29 | Contractor | CON-004 | Finishing Contract | VEN-016 | 1 | Contract | 181793.46 | 170170.37 | 30630.67 | 200801.04 | Paid | Low
EXP-05035 | PRJ-006 | PRJ-006-ACT-05 | 2025-10-29 | Contractor | CON-001 | Civil Structure Contract | VEN-016 | 1 | Contract | 339146.81 | 323759.69 | 58276.74 | 382036.43 | Paid | Low
EXP-05036 | PRJ-006 | PRJ-006-ACT-07 | 2025-11-03 | Material | MAT-002 | Steel | VEN-014 | 24.3 | Ton | 1398639.05 | 1307394.06 | 235330.93 | 1542724.99 | Paid | Low
EXP-05037 | PRJ-006 | PRJ-006-ACT-07 | 2025-11-03 | Material | MAT-007 | PVC Pipe | VEN-013 | 15.12 | Meter | 2155.18 | 2075.92 | 373.67 | 2449.59 | Paid | Low
EXP-05038 | PRJ-006 | PRJ-006-ACT-02 | 2025-11-03 | Equipment | EQ-004 | Scaffolding | VEN-014 | 1 | Day | 2355.92 | 2470.84 | 444.75 | 2915.59 | Paid | Medium
EXP-05039 | PRJ-006 | PRJ-006-ACT-05 | 2025-11-03 | Material | MAT-007 | PVC Pipe | VEN-014 | 5.57 | Meter | 542.81 | 568.23 | 102.28 | 670.51 | Paid | Low
EXP-05040 | PRJ-006 | PRJ-006-ACT-05 | 2025-11-03 | Equipment | EQ-003 | Concrete Mixer | VEN-014 | 1 | Day | 4519.96 | 4282.39 | 770.83 | 5053.22 | Paid | Low
EXP-05041 | PRJ-006 | PRJ-006-ACT-07 | 2025-11-03 | Labour | LAB-004 | Electrician | VEN-016 | 10 | Worker | 10229.75 | 10377.64 | 1867.98 | 12245.62 | Paid | Medium
EXP-05042 | PRJ-006 | PRJ-006-ACT-05 | 2025-11-08 | Material | MAT-002 | Steel | VEN-013 | 5.54 | Ton | 366500.4 | 392158.38 | 70588.51 | 462746.89 | Paid | Low
EXP-05043 | PRJ-006 | PRJ-006-ACT-10 | 2025-11-08 | Material | MAT-007 | PVC Pipe | VEN-013 | 11.84 | Meter | 1339.76 | 1267.95 | 228.23 | 1496.18 | Paid | Medium
EXP-05044 | PRJ-006 | PRJ-006-ACT-03 | 2025-11-08 | Material | MAT-010 | Glass | VEN-014 | 2.55 | Sq Ft | 435.68 | 441.56 | 79.48 | 521.04 | Paid | Low
EXP-05045 | PRJ-006 | PRJ-006-ACT-09 | 2025-11-08 | Material | MAT-001 | Cement | VEN-015 | 5.03 | Bag | 2669.68 | 2523.96 | 454.31 | 2978.27 | Paid | Medium
EXP-05046 | PRJ-006 | PRJ-006-ACT-01 | 2025-11-08 | Other | OTH-001 | Safety | VEN-013 | 1 | Lot | 8127.61 | 7831.72 | 1409.71 | 9241.43 | Pending | Low
EXP-05047 | PRJ-006 | PRJ-006-ACT-04 | 2025-11-08 | Material | MAT-010 | Glass | VEN-013 | 2.73 | Sq Ft | 431.34 | 434.37 | 78.19 | 512.56 | Paid | Medium
EXP-05048 | PRJ-006 | PRJ-006-ACT-08 | 2025-11-13 | Equipment | EQ-001 | Crane | VEN-016 | 7 | Day | 145556.35 | 138356.61 | 24904.19 | 163260.8 | Paid | Medium
EXP-05049 | PRJ-006 | PRJ-006-ACT-07 | 2025-11-13 | Labour | LAB-002 | Helper | VEN-013 | 21 | Worker | 28619.73 | 26651.24 | 4797.22 | 31448.46 | Paid | Low
EXP-05050 | PRJ-006 | PRJ-006-ACT-01 | 2025-11-13 | Contractor | CON-001 | Civil Structure Contract | VEN-016 | 1 | Contract | 362816.53 | 343946.5 | 61910.37 | 405856.87 | Paid | Low
EXP-05051 | PRJ-006 | PRJ-006-ACT-09 | 2025-11-13 | Contractor | CON-004 | Finishing Contract | VEN-016 | 1 | Contract | 337158.99 | 338037.79 | 60846.8 | 398884.59 | Paid | Medium
EXP-05052 | PRJ-006 | PRJ-006-ACT-10 | 2025-11-13 | Material | MAT-002 | Steel | VEN-013 | 10.36 | Ton | 618023.07 | 637253.28 | 114705.59 | 751958.87 | Paid | Low
EXP-05053 | PRJ-006 | PRJ-006-ACT-03 | 2025-11-13 | Material | MAT-003 | Sand | VEN-016 | 11.46 | Ton | 21467.04 | 23322.5 | 4198.05 | 27520.55 | Paid | Low
EXP-05054 | PRJ-006 | PRJ-006-ACT-02 | 2025-11-13 | Equipment | EQ-003 | Concrete Mixer | VEN-015 | 2 | Day | 9075.06 | 8834.47 | 1590.2 | 10424.67 | Paid | High
EXP-05055 | PRJ-006 | PRJ-006-ACT-08 | 2025-11-18 | Material | MAT-002 | Steel | VEN-014 | 2.87 | Ton | 145970.8 | 156975.28 | 28255.55 | 185230.83 | Paid | Medium
EXP-05056 | PRJ-006 | PRJ-006-ACT-06 | 2025-11-18 | Material | MAT-008 | Tiles | VEN-013 | 5.32 | Sq Ft | 381.8 | 358.05 | 64.45 | 422.5 | Paid | Medium
EXP-05057 | PRJ-006 | PRJ-006-ACT-06 | 2025-11-18 | Labour | LAB-004 | Electrician | VEN-015 | 9 | Worker | 10684.13 | 10192.52 | 1834.65 | 12027.17 | Paid | Low
EXP-05058 | PRJ-006 | PRJ-006-ACT-08 | 2025-11-18 | Equipment | EQ-004 | Scaffolding | VEN-016 | 6 | Day | 14855.79 | 15352.98 | 2763.54 | 18116.52 | Paid | Low
EXP-05059 | PRJ-006 | PRJ-006-ACT-03 | 2025-11-18 | Material | MAT-007 | PVC Pipe | VEN-016 | 25.26 | Meter | 2637.27 | 2811.89 | 506.14 | 3318.03 | Paid | Medium
EXP-05060 | PRJ-006 | PRJ-006-ACT-02 | 2025-11-18 | Other | OTH-001 | Permit | VEN-014 | 1 | Lot | 63352.07 | 63754.02 | 11475.72 | 75229.74 | Paid | Low
EXP-05061 | PRJ-006 | PRJ-006-ACT-10 | 2025-11-18 | Contractor | CON-001 | Civil Structure Contract | VEN-015 | 1 | Contract | 177382.8 | 171968.81 | 30954.39 | 202923.2 | Paid | Medium
EXP-05062 | PRJ-006 | PRJ-006-ACT-01 | 2025-11-18 | Labour | LAB-003 | Carpenter | VEN-013 | 12 | Worker | 12053.15 | 12795.91 | 2303.26 | 15099.17 | Paid | Medium
EXP-05063 | PRJ-006 | PRJ-006-ACT-04 | 2025-11-18 | Other | OTH-001 | Transport | VEN-015 | 1 | Lot | 59091.17 | 56644.68 | 10196.04 | 66840.72 | Paid | High
EXP-05064 | PRJ-006 | PRJ-006-ACT-05 | 2025-11-23 | Material | MAT-006 | Electrical Cable | VEN-016 | 12.58 | Meter | 929.4 | 987.06 | 177.67 | 1164.73 | Paid | High
EXP-05065 | PRJ-006 | PRJ-006-ACT-02 | 2025-11-23 | Contractor | CON-001 | Civil Structure Contract | VEN-013 | 1 | Contract | 166202.79 | 158183.75 | 28473.08 | 186656.83 | Partially Paid | Low
EXP-05066 | PRJ-006 | PRJ-006-ACT-08 | 2025-11-23 | Equipment | EQ-002 | Excavator | VEN-016 | 6 | Day | 81397.94 | 83582.47 | 15044.84 | 98627.31 | Paid | Low
EXP-05067 | PRJ-006 | PRJ-006-ACT-09 | 2025-11-23 | Equipment | EQ-004 | Scaffolding | VEN-014 | 1 | Day | 2360.43 | 2445.36 | 440.16 | 2885.52 | Paid | Low
EXP-05068 | PRJ-006 | PRJ-006-ACT-01 | 2025-11-23 | Material | MAT-004 | Aggregate | VEN-013 | 17.68 | Ton | 22562.32 | 23804.78 | 4284.86 | 28089.64 | Paid | Medium
EXP-05069 | PRJ-006 | PRJ-006-ACT-06 | 2025-11-23 | Material | MAT-005 | Bricks | VEN-014 | 1.79 | Piece | 17.1 | 17.15 | 3.09 | 20.24 | Partially Paid | Low
EXP-05070 | PRJ-006 | PRJ-006-ACT-05 | 2025-11-23 | Material | MAT-003 | Sand | VEN-014 | 18.79 | Ton | 37841.88 | 38562.19 | 6941.19 | 45503.38 | Paid | Low
EXP-05071 | PRJ-006 | PRJ-006-ACT-05 | 2025-11-23 | Equipment | EQ-003 | Concrete Mixer | VEN-013 | 2 | Day | 8922.83 | 9057.4 | 1630.33 | 10687.73 | Paid | High
EXP-05072 | PRJ-006 | PRJ-006-ACT-05 | 2025-11-28 | Material | MAT-010 | Glass | VEN-016 | 6.93 | Sq Ft | 1239.46 | 1202.67 | 216.48 | 1419.15 | Paid | Medium
EXP-05073 | PRJ-006 | PRJ-006-ACT-10 | 2025-11-28 | Material | MAT-007 | PVC Pipe | VEN-016 | 9.86 | Meter | 1366.31 | 1353.6 | 243.65 | 1597.25 | Paid | Medium
EXP-05074 | PRJ-006 | PRJ-006-ACT-01 | 2025-11-28 | Material | MAT-002 | Steel | VEN-016 | 10.75 | Ton | 651583.79 | 676569.8 | 121782.56 | 798352.36 | Paid | Low
EXP-05075 | PRJ-006 | PRJ-006-ACT-10 | 2025-11-28 | Contractor | CON-002 | Electrical Contract | VEN-016 | 1 | Contract | 193767.6 | 197111.85 | 35480.13 | 232591.98 | Paid | High
EXP-05076 | PRJ-006 | PRJ-006-ACT-03 | 2025-11-28 | Material | MAT-008 | Tiles | VEN-013 | 3.61 | Sq Ft | 267.49 | 286.42 | 51.56 | 337.98 | Paid | Medium
EXP-05077 | PRJ-006 | PRJ-006-ACT-04 | 2025-11-28 | Material | MAT-009 | Paint | VEN-014 | 17.73 | Litre | 3043.36 | 3283.11 | 590.96 | 3874.07 | Paid | High
EXP-05078 | PRJ-006 | PRJ-006-ACT-05 | 2025-11-28 | Other | OTH-001 | Transport | VEN-016 | 1 | Lot | 43462.34 | 41783.69 | 7521.06 | 49304.75 | Pending | Low
EXP-05079 | PRJ-006 | PRJ-006-ACT-05 | 2025-11-28 | Labour | LAB-005 | Plumber | VEN-016 | 33 | Worker | 34944.75 | 35967.76 | 6474.2 | 42441.96 | Paid | Low
EXP-05080 | PRJ-006 | PRJ-006-ACT-08 | 2025-12-03 | Contractor | CON-002 | Electrical Contract | VEN-014 | 1 | Contract | 104368.9 | 110839.38 | 19951.09 | 130790.47 | Paid | Low
EXP-05081 | PRJ-006 | PRJ-006-ACT-02 | 2025-12-03 | Labour | LAB-002 | Helper | VEN-015 | 14 | Worker | 22478.43 | 24246.81 | 4364.43 | 28611.24 | Paid | Medium
EXP-05082 | PRJ-006 | PRJ-006-ACT-08 | 2025-12-03 | Labour | LAB-002 | Helper | VEN-014 | 24 | Worker | 19318.21 | 19252.73 | 3465.49 | 22718.22 | Paid | Low
EXP-05083 | PRJ-006 | PRJ-006-ACT-06 | 2025-12-03 | Material | MAT-004 | Aggregate | VEN-016 | 17.95 | Ton | 24679.72 | 25957.81 | 4672.41 | 30630.22 | Paid | Low
EXP-05084 | PRJ-006 | PRJ-006-ACT-02 | 2025-12-03 | Material | MAT-007 | PVC Pipe | VEN-014 | 15.35 | Meter | 2013.79 | 1933.42 | 348.02 | 2281.44 | Paid | Medium
EXP-05085 | PRJ-006 | PRJ-006-ACT-04 | 2025-12-03 | Material | MAT-006 | Electrical Cable | VEN-013 | 6 | Meter | 561.78 | 549.52 | 98.91 | 648.43 | Paid | Low
EXP-05086 | PRJ-006 | PRJ-006-ACT-06 | 2025-12-03 | Labour | LAB-002 | Helper | VEN-016 | 27 | Worker | 38441.05 | 39163.06 | 7049.35 | 46212.41 | Pending | Low
EXP-05087 | PRJ-006 | PRJ-006-ACT-10 | 2025-12-08 | Material | MAT-007 | PVC Pipe | VEN-014 | 33.96 | Meter | 4082.47 | 4208.94 | 757.61 | 4966.55 | Paid | Medium
EXP-05088 | PRJ-006 | PRJ-006-ACT-08 | 2025-12-08 | Material | MAT-002 | Steel | VEN-016 | 6.32 | Ton | 393803.55 | 413183.5 | 74373.03 | 487556.53 | Paid | Medium
EXP-05089 | PRJ-006 | PRJ-006-ACT-04 | 2025-12-08 | Material | MAT-004 | Aggregate | VEN-015 | 4.31 | Ton | 6814.56 | 6752.8 | 1215.5 | 7968.3 | Paid | Low
EXP-05090 | PRJ-006 | PRJ-006-ACT-08 | 2025-12-08 | Material | MAT-004 | Aggregate | VEN-013 | 3.12 | Ton | 4432.27 | 4555.33 | 819.96 | 5375.29 | Paid | Low
EXP-05091 | PRJ-006 | PRJ-006-ACT-10 | 2025-12-08 | Material | MAT-010 | Glass | VEN-014 | 16.44 | Sq Ft | 2135.53 | 2254.5 | 405.81 | 2660.31 | Paid | Low
EXP-05092 | PRJ-006 | PRJ-006-ACT-01 | 2025-12-08 | Equipment | EQ-003 | Concrete Mixer | VEN-015 | 2 | Day | 8479.57 | 9181.71 | 1652.71 | 10834.42 | Paid | Low
EXP-05093 | PRJ-006 | PRJ-006-ACT-08 | 2025-12-08 | Contractor | CON-001 | Civil Structure Contract | VEN-013 | 1 | Contract | 404962.16 | 399774.71 | 71959.45 | 471734.16 | Paid | Medium
EXP-05094 | PRJ-006 | PRJ-006-ACT-01 | 2025-12-08 | Labour | LAB-005 | Plumber | VEN-013 | 16 | Worker | 15791.18 | 15226.31 | 2740.74 | 17967.05 | Paid | Medium
EXP-05095 | PRJ-006 | PRJ-006-ACT-09 | 2025-12-13 | Material | MAT-006 | Electrical Cable | VEN-013 | 5.83 | Meter | 496.9 | 535.95 | 96.47 | 632.42 | Partially Paid | Medium
EXP-05096 | PRJ-006 | PRJ-006-ACT-07 | 2025-12-13 | Material | MAT-004 | Aggregate | VEN-015 | 18.12 | Ton | 28802.92 | 29866.23 | 5375.92 | 35242.15 | Paid | High
EXP-05097 | PRJ-006 | PRJ-006-ACT-07 | 2025-12-13 | Contractor | CON-004 | Finishing Contract | VEN-015 | 1 | Contract | 216681.44 | 208555.51 | 37539.99 | 246095.5 | Paid | High
EXP-05098 | PRJ-006 | PRJ-006-ACT-08 | 2025-12-13 | Labour | LAB-002 | Helper | VEN-016 | 24 | Worker | 21781.89 | 23305.99 | 4195.08 | 27501.07 | Paid | Low
EXP-05099 | PRJ-006 | PRJ-006-ACT-06 | 2025-12-13 | Labour | LAB-005 | Plumber | VEN-014 | 10 | Worker | 18851.22 | 17916 | 3224.88 | 21140.88 | Paid | High
EXP-05100 | PRJ-006 | PRJ-006-ACT-10 | 2025-12-13 | Material | MAT-008 | Tiles | VEN-013 | 9.39 | Sq Ft | 724.43 | 768.94 | 138.41 | 907.35 | Paid | Low
EXP-05101 | PRJ-006 | PRJ-006-ACT-06 | 2025-12-18 | Labour | LAB-001 | Mason | VEN-014 | 14 | Worker | 18896.84 | 20093.5 | 3616.83 | 23710.33 | Paid | Low
EXP-05102 | PRJ-006 | PRJ-006-ACT-04 | 2025-12-18 | Labour | LAB-001 | Mason | VEN-016 | 21 | Worker | 37409.35 | 35516.01 | 6392.88 | 41908.89 | Partially Paid | Low
EXP-05103 | PRJ-006 | PRJ-006-ACT-08 | 2025-12-18 | Material | MAT-008 | Tiles | VEN-013 | 23.59 | Sq Ft | 1548.97 | 1519.35 | 273.48 | 1792.83 | Paid | Medium
EXP-05104 | PRJ-006 | PRJ-006-ACT-10 | 2025-12-18 | Material | MAT-001 | Cement | VEN-015 | 6.37 | Bag | 3209.18 | 3291.41 | 592.45 | 3883.86 | Paid | Low
EXP-05105 | PRJ-006 | PRJ-006-ACT-08 | 2025-12-18 | Contractor | CON-003 | Plumbing Contract | VEN-016 | 1 | Contract | 346426.37 | 345412.03 | 62174.17 | 407586.2 | Paid | Low
EXP-05106 | PRJ-006 | PRJ-006-ACT-03 | 2025-12-18 | Material | MAT-010 | Glass | VEN-015 | 22.71 | Sq Ft | 3787.01 | 3542.14 | 637.59 | 4179.73 | Paid | Low
EXP-05107 | PRJ-006 | PRJ-006-ACT-08 | 2025-12-23 | Material | MAT-001 | Cement | VEN-013 | 9.65 | Bag | 5432.47 | 5118.03 | 921.25 | 6039.28 | Paid | Medium
EXP-05108 | PRJ-006 | PRJ-006-ACT-05 | 2025-12-23 | Contractor | CON-001 | Civil Structure Contract | VEN-016 | 1 | Contract | 212615.03 | 203795.49 | 36683.19 | 240478.68 | Paid | Medium
EXP-05109 | PRJ-006 | PRJ-006-ACT-06 | 2025-12-23 | Equipment | EQ-002 | Excavator | VEN-015 | 6 | Day | 83167.05 | 87660.06 | 15778.81 | 103438.87 | Paid | Medium
EXP-05110 | PRJ-006 | PRJ-006-ACT-04 | 2025-12-23 | Material | MAT-001 | Cement | VEN-016 | 8.48 | Bag | 4964.38 | 4724.5 | 850.41 | 5574.91 | Paid | Low
EXP-05111 | PRJ-006 | PRJ-006-ACT-06 | 2025-12-23 | Labour | LAB-001 | Mason | VEN-013 | 29 | Worker | 27797.81 | 30177.94 | 5432.03 | 35609.97 | Paid | Medium
EXP-05112 | PRJ-006 | PRJ-006-ACT-06 | 2025-12-23 | Contractor | CON-003 | Plumbing Contract | VEN-015 | 1 | Contract | 148016.66 | 148417.43 | 26715.14 | 175132.57 | Paid | Low
EXP-05113 | PRJ-006 | PRJ-006-ACT-03 | 2025-12-28 | Contractor | CON-004 | Finishing Contract | VEN-015 | 1 | Contract | 209926.98 | 199152.47 | 35847.44 | 234999.91 | Paid | Low
EXP-05114 | PRJ-006 | PRJ-006-ACT-03 | 2025-12-28 | Material | MAT-006 | Electrical Cable | VEN-014 | 4.2 | Meter | 324.7 | 338.06 | 60.85 | 398.91 | Paid | Medium
EXP-05115 | PRJ-006 | PRJ-006-ACT-03 | 2025-12-28 | Labour | LAB-004 | Electrician | VEN-013 | 31 | Worker | 28168.45 | 28091.38 | 5056.45 | 33147.83 | Partially Paid | Medium
EXP-05116 | PRJ-006 | PRJ-006-ACT-10 | 2025-12-28 | Other | OTH-001 | Permit | VEN-015 | 1 | Lot | 21300.18 | 21882.91 | 3938.92 | 25821.83 | Paid | High
EXP-05117 | PRJ-006 | PRJ-006-ACT-06 | 2025-12-28 | Material | MAT-003 | Sand | VEN-013 | 4.53 | Ton | 8663.91 | 8658.75 | 1558.58 | 10217.33 | Partially Paid | Low
EXP-05118 | PRJ-006 | PRJ-006-ACT-06 | 2025-12-28 | Contractor | CON-001 | Civil Structure Contract | VEN-013 | 1 | Contract | 398891.58 | 374085.26 | 67335.35 | 441420.61 | Paid | Medium
EXP-05119 | PRJ-006 | PRJ-006-ACT-03 | 2025-12-28 | Material | MAT-002 | Steel | VEN-013 | 7.2 | Ton | 356194.23 | 381452.07 | 68661.37 | 450113.44 | Paid | Low
EXP-05120 | PRJ-006 | PRJ-006-ACT-07 | 2025-12-28 | Contractor | CON-001 | Civil Structure Contract | VEN-014 | 1 | Contract | 146262.5 | 155376.95 | 27967.85 | 183344.8 | Paid | Low
EXP-05121 | PRJ-006 | PRJ-006-ACT-05 | 2025-12-28 | Contractor | CON-002 | Electrical Contract | VEN-015 | 1 | Contract | 308646.91 | 309751.17 | 55755.21 | 365506.38 | Paid | High
EXP-05122 | PRJ-006 | PRJ-006-ACT-09 | 2026-01-02 | Material | MAT-003 | Sand | VEN-014 | 30.84 | Ton | 57241.25 | 54598.47 | 9827.72 | 64426.19 | Paid | Low
EXP-05123 | PRJ-006 | PRJ-006-ACT-01 | 2026-01-02 | Equipment | EQ-001 | Crane | VEN-013 | 5 | Day | 88702.78 | 84087.15 | 15135.69 | 99222.84 | Paid | Medium
EXP-05124 | PRJ-006 | PRJ-006-ACT-10 | 2026-01-02 | Labour | LAB-002 | Helper | VEN-014 | 20 | Worker | 14500.15 | 14298.34 | 2573.7 | 16872.04 | Paid | Medium
EXP-05125 | PRJ-006 | PRJ-006-ACT-08 | 2026-01-02 | Labour | LAB-006 | Painter | VEN-015 | 6 | Worker | 7474.61 | 7270.88 | 1308.76 | 8579.64 | Paid | Low
EXP-05126 | PRJ-006 | PRJ-006-ACT-04 | 2026-01-02 | Equipment | EQ-003 | Concrete Mixer | VEN-013 | 6 | Day | 27319.11 | 25350.66 | 4563.12 | 29913.78 | Paid | Low
EXP-05127 | PRJ-006 | PRJ-006-ACT-02 | 2026-01-02 | Labour | LAB-006 | Painter | VEN-013 | 18 | Worker | 19224.23 | 18812.27 | 3386.21 | 22198.48 | Partially Paid | Low
EXP-05128 | PRJ-006 | PRJ-006-ACT-04 | 2026-01-02 | Labour | LAB-005 | Plumber | VEN-016 | 31 | Worker | 36612.72 | 37978.82 | 6836.19 | 44815.01 | Pending | Low
EXP-05129 | PRJ-006 | PRJ-006-ACT-09 | 2026-01-02 | Material | MAT-005 | Bricks | VEN-014 | 5.53 | Piece | 43.76 | 44.68 | 8.04 | 52.72 | Paid | Low
EXP-05130 | PRJ-006 | PRJ-006-ACT-08 | 2026-01-02 | Labour | LAB-006 | Painter | VEN-014 | 8 | Worker | 6623.94 | 7141.24 | 1285.42 | 8426.66 | Paid | Medium
EXP-05131 | PRJ-006 | PRJ-006-ACT-01 | 2026-01-07 | Material | MAT-001 | Cement | VEN-014 | 7.62 | Bag | 3730.55 | 3840.4 | 691.27 | 4531.67 | Paid | Low
EXP-05132 | PRJ-006 | PRJ-006-ACT-09 | 2026-01-07 | Material | MAT-010 | Glass | VEN-016 | 5.35 | Sq Ft | 994.37 | 951.08 | 171.19 | 1122.27 | Paid | Medium
EXP-05133 | PRJ-006 | PRJ-006-ACT-09 | 2026-01-07 | Labour | LAB-001 | Mason | VEN-015 | 28 | Worker | 26943.49 | 25241.29 | 4543.43 | 29784.72 | Paid | Medium
EXP-05134 | PRJ-006 | PRJ-006-ACT-04 | 2026-01-07 | Material | MAT-001 | Cement | VEN-014 | 8.44 | Bag | 3810.68 | 4075.87 | 733.66 | 4809.53 | Paid | Low
EXP-05135 | PRJ-006 | PRJ-006-ACT-06 | 2026-01-07 | Equipment | EQ-004 | Scaffolding | VEN-013 | 1 | Day | 2169.48 | 2357.41 | 424.33 | 2781.74 | Paid | Low
EXP-05136 | PRJ-006 | PRJ-006-ACT-04 | 2026-01-07 | Labour | LAB-006 | Painter | VEN-015 | 11 | Worker | 9321.71 | 9147.01 | 1646.46 | 10793.47 | Paid | Low
EXP-05137 | PRJ-006 | PRJ-006-ACT-03 | 2026-01-07 | Material | MAT-008 | Tiles | VEN-013 | 7.88 | Sq Ft | 653.9 | 646.25 | 116.32 | 762.57 | Partially Paid | Low
EXP-05138 | PRJ-006 | PRJ-006-ACT-09 | 2026-01-12 | Labour | LAB-002 | Helper | VEN-014 | 13 | Worker | 12020.48 | 12183.21 | 2192.98 | 14376.19 | Paid | Low
EXP-05139 | PRJ-006 | PRJ-006-ACT-10 | 2026-01-12 | Contractor | CON-003 | Plumbing Contract | VEN-014 | 1 | Contract | 201009.68 | 193221.5 | 34779.87 | 228001.37 | Paid | High
EXP-05140 | PRJ-006 | PRJ-006-ACT-05 | 2026-01-12 | Material | MAT-002 | Steel | VEN-013 | 9.68 | Ton | 709879.38 | 660802.41 | 118944.43 | 779746.84 | Paid | Medium
EXP-05141 | PRJ-006 | PRJ-006-ACT-05 | 2026-01-12 | Contractor | CON-003 | Plumbing Contract | VEN-014 | 1 | Contract | 127695.46 | 122046.18 | 21968.31 | 144014.49 | Pending | Low
EXP-05142 | PRJ-006 | PRJ-006-ACT-09 | 2026-01-12 | Labour | LAB-002 | Helper | VEN-014 | 24 | Worker | 40014.56 | 38877.77 | 6998 | 45875.77 | Paid | Low
EXP-05143 | PRJ-006 | PRJ-006-ACT-02 | 2026-01-12 | Contractor | CON-001 | Civil Structure Contract | VEN-016 | 1 | Contract | 175996.49 | 169958.93 | 30592.61 | 200551.54 | Paid | Medium
EXP-05144 | PRJ-006 | PRJ-006-ACT-03 | 2026-01-12 | Other | OTH-001 | Transport | VEN-013 | 1 | Lot | 68004.37 | 67318.21 | 12117.28 | 79435.49 | Paid | Medium
EXP-05145 | PRJ-006 | PRJ-006-ACT-02 | 2026-01-17 | Contractor | CON-002 | Electrical Contract | VEN-014 | 1 | Contract | 338166.98 | 323163.55 | 58169.44 | 381332.99 | Paid | Low
EXP-05146 | PRJ-006 | PRJ-006-ACT-05 | 2026-01-17 | Labour | LAB-006 | Painter | VEN-015 | 7 | Worker | 6485.54 | 6352.81 | 1143.51 | 7496.32 | Paid | Low
EXP-05147 | PRJ-006 | PRJ-006-ACT-08 | 2026-01-17 | Labour | LAB-002 | Helper | VEN-015 | 29 | Worker | 50105.36 | 51921.87 | 9345.94 | 61267.81 | Paid | Medium
EXP-05148 | PRJ-006 | PRJ-006-ACT-05 | 2026-01-17 | Material | MAT-010 | Glass | VEN-013 | 12.5 | Sq Ft | 2248.48 | 2186.3 | 393.53 | 2579.83 | Paid | Low
EXP-05149 | PRJ-006 | PRJ-006-ACT-08 | 2026-01-17 | Contractor | CON-004 | Finishing Contract | VEN-014 | 1 | Contract | 258330.73 | 264862.33 | 47675.22 | 312537.55 | Paid | Low
EXP-05150 | PRJ-006 | PRJ-006-ACT-07 | 2026-01-17 | Equipment | EQ-001 | Crane | VEN-015 | 6 | Day | 120086.85 | 118472.21 | 21325 | 139797.21 | Pending | Medium
EXP-05151 | PRJ-006 | PRJ-006-ACT-09 | 2026-01-17 | Contractor | CON-004 | Finishing Contract | VEN-015 | 1 | Contract | 165665.39 | 158986.16 | 28617.51 | 187603.67 | Paid | Low
EXP-05152 | PRJ-006 | PRJ-006-ACT-09 | 2026-01-17 | Contractor | CON-002 | Electrical Contract | VEN-013 | 1 | Contract | 202386.37 | 188453.51 | 33921.63 | 222375.14 | Paid | Low
EXP-05153 | PRJ-006 | PRJ-006-ACT-07 | 2026-01-22 | Contractor | CON-001 | Civil Structure Contract | VEN-013 | 1 | Contract | 353965.2 | 383723.74 | 69070.27 | 452794.01 | Paid | Medium
EXP-05154 | PRJ-006 | PRJ-006-ACT-05 | 2026-01-22 | Labour | LAB-004 | Electrician | VEN-013 | 17 | Worker | 17221.45 | 16593.44 | 2986.82 | 19580.26 | Paid | Medium
EXP-05155 | PRJ-006 | PRJ-006-ACT-01 | 2026-01-22 | Contractor | CON-001 | Civil Structure Contract | VEN-013 | 1 | Contract | 370973.59 | 356047.29 | 64088.51 | 420135.8 | Paid | Low
EXP-05156 | PRJ-006 | PRJ-006-ACT-01 | 2026-01-22 | Material | MAT-002 | Steel | VEN-013 | 3.42 | Ton | 182754.83 | 184987.55 | 33297.76 | 218285.31 | Paid | Medium
EXP-05157 | PRJ-006 | PRJ-006-ACT-04 | 2026-01-22 | Material | MAT-006 | Electrical Cable | VEN-013 | 4.04 | Meter | 315.49 | 324.38 | 58.39 | 382.77 | Paid | Low
EXP-05158 | PRJ-006 | PRJ-006-ACT-09 | 2026-01-22 | Material | MAT-002 | Steel | VEN-016 | 15.03 | Ton | 814373.55 | 836410.94 | 150553.97 | 986964.91 | Paid | Low
EXP-05159 | PRJ-006 | PRJ-006-ACT-06 | 2026-01-22 | Labour | LAB-004 | Electrician | VEN-014 | 5 | Worker | 3652.74 | 3695.39 | 665.17 | 4360.56 | Paid | Low
EXP-05160 | PRJ-006 | PRJ-006-ACT-04 | 2026-01-22 | Other | OTH-001 | Miscellaneous | VEN-013 | 1 | Lot | 60581.06 | 61013.08 | 10982.35 | 71995.43 | Pending | Low
EXP-05161 | PRJ-006 | PRJ-006-ACT-10 | 2026-01-27 | Material | MAT-007 | PVC Pipe | VEN-013 | 3.34 | Meter | 420.54 | 456.75 | 82.22 | 538.97 | Paid | Low
EXP-05162 | PRJ-006 | PRJ-006-ACT-08 | 2026-01-27 | Labour | LAB-003 | Carpenter | VEN-016 | 20 | Worker | 27010.88 | 28253.53 | 5085.64 | 33339.17 | Paid | Low
EXP-05163 | PRJ-006 | PRJ-006-ACT-07 | 2026-01-27 | Labour | LAB-004 | Electrician | VEN-014 | 33 | Worker | 40826.81 | 43167.06 | 7770.07 | 50937.13 | Paid | Medium
EXP-05164 | PRJ-006 | PRJ-006-ACT-06 | 2026-01-27 | Contractor | CON-004 | Finishing Contract | VEN-013 | 1 | Contract | 424944.23 | 412611.65 | 74270.1 | 486881.75 | Paid | Low
EXP-05165 | PRJ-006 | PRJ-006-ACT-04 | 2026-01-27 | Labour | LAB-001 | Mason | VEN-013 | 17 | Worker | 26022.39 | 25923.94 | 4666.31 | 30590.25 | Pending | Medium
EXP-05166 | PRJ-006 | PRJ-006-ACT-03 | 2026-01-27 | Labour | LAB-005 | Plumber | VEN-013 | 15 | Worker | 11634.35 | 12178.98 | 2192.22 | 14371.2 | Paid | High
EXP-05167 | PRJ-006 | PRJ-006-ACT-05 | 2026-02-01 | Material | MAT-006 | Electrical Cable | VEN-015 | 5.52 | Meter | 407.63 | 424.73 | 76.45 | 501.18 | Partially Paid | Medium
EXP-05168 | PRJ-006 | PRJ-006-ACT-06 | 2026-02-01 | Contractor | CON-003 | Plumbing Contract | VEN-016 | 1 | Contract | 418426.61 | 404590.93 | 72826.37 | 477417.3 | Paid | Low
EXP-05169 | PRJ-006 | PRJ-006-ACT-07 | 2026-02-01 | Contractor | CON-003 | Plumbing Contract | VEN-015 | 1 | Contract | 256083.64 | 272364.23 | 49025.56 | 321389.79 | Paid | Low
EXP-05170 | PRJ-006 | PRJ-006-ACT-04 | 2026-02-01 | Material | MAT-003 | Sand | VEN-013 | 38.4 | Ton | 63047.47 | 63532.98 | 11435.94 | 74968.92 | Partially Paid | Medium
EXP-05171 | PRJ-006 | PRJ-006-ACT-10 | 2026-02-01 | Other | OTH-001 | Safety | VEN-014 | 1 | Lot | 29309.2 | 28041.09 | 5047.4 | 33088.49 | Paid | Medium
EXP-05172 | PRJ-006 | PRJ-006-ACT-01 | 2026-02-01 | Labour | LAB-005 | Plumber | VEN-015 | 11 | Worker | 18207.75 | 19263.2 | 3467.38 | 22730.58 | Paid | Low
EXP-05173 | PRJ-006 | PRJ-006-ACT-05 | 2026-02-01 | Labour | LAB-002 | Helper | VEN-016 | 12 | Worker | 13356.54 | 13959.65 | 2512.74 | 16472.39 | Paid | High
EXP-05174 | PRJ-006 | PRJ-006-ACT-03 | 2026-02-06 | Material | MAT-001 | Cement | VEN-016 | 5.35 | Bag | 2268.49 | 2388.12 | 429.86 | 2817.98 | Paid | Medium
EXP-05175 | PRJ-006 | PRJ-006-ACT-01 | 2026-02-06 | Labour | LAB-001 | Mason | VEN-014 | 32 | Worker | 47544.2 | 47439.55 | 8539.12 | 55978.67 | Paid | Medium
EXP-05176 | PRJ-006 | PRJ-006-ACT-09 | 2026-02-06 | Labour | LAB-002 | Helper | VEN-015 | 25 | Worker | 37103.29 | 36191.59 | 6514.49 | 42706.08 | Paid | Low
EXP-05177 | PRJ-006 | PRJ-006-ACT-05 | 2026-02-06 | Contractor | CON-001 | Civil Structure Contract | VEN-013 | 1 | Contract | 475586.81 | 447262.54 | 80507.26 | 527769.8 | Partially Paid | Low
EXP-05178 | PRJ-006 | PRJ-006-ACT-09 | 2026-02-06 | Material | MAT-001 | Cement | VEN-015 | 16.32 | Bag | 8755.19 | 8710.03 | 1567.81 | 10277.84 | Paid | Low
EXP-05179 | PRJ-006 | PRJ-006-ACT-08 | 2026-02-06 | Labour | LAB-006 | Painter | VEN-014 | 24 | Worker | 21900.64 | 21084.35 | 3795.18 | 24879.53 | Partially Paid | Low
EXP-05180 | PRJ-006 | PRJ-006-ACT-09 | 2026-02-11 | Labour | LAB-002 | Helper | VEN-014 | 12 | Worker | 20738.57 | 20865.48 | 3755.79 | 24621.27 | Paid | Low
EXP-05181 | PRJ-006 | PRJ-006-ACT-02 | 2026-02-11 | Labour | LAB-001 | Mason | VEN-015 | 16 | Worker | 12192.96 | 13032.83 | 2345.91 | 15378.74 | Paid | High
EXP-05182 | PRJ-006 | PRJ-006-ACT-08 | 2026-02-11 | Labour | LAB-001 | Mason | VEN-015 | 9 | Worker | 15129.02 | 14517.2 | 2613.1 | 17130.3 | Paid | Low
EXP-05183 | PRJ-006 | PRJ-006-ACT-05 | 2026-02-11 | Other | OTH-001 | Transport | VEN-013 | 1 | Lot | 40588.62 | 43383.69 | 7809.06 | 51192.75 | Paid | Medium
EXP-05184 | PRJ-006 | PRJ-006-ACT-08 | 2026-02-11 | Material | MAT-005 | Bricks | VEN-016 | 11.88 | Piece | 114.06 | 108.21 | 19.48 | 127.69 | Partially Paid | High
EXP-05185 | PRJ-006 | PRJ-006-ACT-03 | 2026-02-11 | Material | MAT-009 | Paint | VEN-013 | 28.95 | Litre | 7329.99 | 6938.87 | 1249 | 8187.87 | Paid | Low
EXP-05186 | PRJ-006 | PRJ-006-ACT-06 | 2026-02-11 | Equipment | EQ-002 | Excavator | VEN-013 | 7 | Day | 107462.89 | 103192.4 | 18574.63 | 121767.03 | Paid | Low
EXP-05187 | PRJ-006 | PRJ-006-ACT-02 | 2026-02-16 | Contractor | CON-004 | Finishing Contract | VEN-015 | 1 | Contract | 383327.31 | 404491.43 | 72808.46 | 477299.89 | Paid | Low
EXP-05188 | PRJ-006 | PRJ-006-ACT-03 | 2026-02-16 | Material | MAT-003 | Sand | VEN-016 | 8.83 | Ton | 13615.52 | 14084.71 | 2535.25 | 16619.96 | Partially Paid | Low
EXP-05189 | PRJ-006 | PRJ-006-ACT-02 | 2026-02-16 | Labour | LAB-005 | Plumber | VEN-015 | 18 | Worker | 27504.04 | 26054.25 | 4689.76 | 30744.01 | Paid | Low
EXP-05190 | PRJ-006 | PRJ-006-ACT-05 | 2026-02-16 | Contractor | CON-002 | Electrical Contract | VEN-014 | 1 | Contract | 248345.43 | 252165.52 | 45389.79 | 297555.31 | Paid | Low
EXP-05191 | PRJ-006 | PRJ-006-ACT-07 | 2026-02-16 | Equipment | EQ-002 | Excavator | VEN-014 | 1 | Day | 11753.77 | 12741.58 | 2293.48 | 15035.06 | Paid | Low
EXP-05192 | PRJ-006 | PRJ-006-ACT-02 | 2026-02-16 | Equipment | EQ-002 | Excavator | VEN-015 | 7 | Day | 93442.5 | 89211.63 | 16058.09 | 105269.72 | Partially Paid | Low
EXP-05193 | PRJ-006 | PRJ-006-ACT-09 | 2026-02-16 | Contractor | CON-002 | Electrical Contract | VEN-016 | 1 | Contract | 293051.83 | 299167.27 | 53850.11 | 353017.38 | Paid | High
EXP-05194 | PRJ-006 | PRJ-006-ACT-06 | 2026-02-16 | Material | MAT-008 | Tiles | VEN-016 | 34.31 | Sq Ft | 2390.24 | 2533.85 | 456.09 | 2989.94 | Paid | High
EXP-05195 | PRJ-006 | PRJ-006-ACT-09 | 2026-02-21 | Material | MAT-006 | Electrical Cable | VEN-015 | 11.06 | Meter | 1002.4 | 1007.77 | 181.4 | 1189.17 | Paid | High
EXP-05196 | PRJ-006 | PRJ-006-ACT-03 | 2026-02-21 | Material | MAT-006 | Electrical Cable | VEN-015 | 5.44 | Meter | 432.56 | 429.3 | 77.27 | 506.57 | Paid | Low
EXP-05197 | PRJ-006 | PRJ-006-ACT-05 | 2026-02-21 | Labour | LAB-001 | Mason | VEN-015 | 17 | Worker | 25299.24 | 26170.88 | 4710.76 | 30881.64 | Paid | Low
EXP-05198 | PRJ-006 | PRJ-006-ACT-10 | 2026-02-21 | Material | MAT-002 | Steel | VEN-016 | 3.56 | Ton | 195255.9 | 193982.59 | 34916.87 | 228899.46 | Paid | Low
EXP-05199 | PRJ-006 | PRJ-006-ACT-03 | 2026-02-21 | Contractor | CON-002 | Electrical Contract | VEN-013 | 1 | Contract | 214914.31 | 200519.76 | 36093.56 | 236613.32 | Paid | Low
EXP-05200 | PRJ-006 | PRJ-006-ACT-01 | 2026-02-21 | Contractor | CON-004 | Finishing Contract | VEN-013 | 1 | Contract | 170162.55 | 182916.77 | 32925.02 | 215841.79 | Paid | Medium
EXP-05201 | PRJ-006 | PRJ-006-ACT-05 | 2026-02-21 | Labour | LAB-003 | Carpenter | VEN-015 | 31 | Worker | 41299.55 | 41416.11 | 7454.9 | 48871.01 | Paid | Low
EXP-05202 | PRJ-006 | PRJ-006-ACT-04 | 2026-02-26 | Material | MAT-004 | Aggregate | VEN-013 | 12.38 | Ton | 20782.83 | 21055.24 | 3789.94 | 24845.18 | Paid | Medium
EXP-05203 | PRJ-006 | PRJ-006-ACT-10 | 2026-02-26 | Material | MAT-002 | Steel | VEN-015 | 9.01 | Ton | 609861.64 | 578494.74 | 104129.05 | 682623.79 | Paid | Low
EXP-05204 | PRJ-006 | PRJ-006-ACT-10 | 2026-02-26 | Labour | LAB-002 | Helper | VEN-015 | 14 | Worker | 13655.2 | 13414.51 | 2414.61 | 15829.12 | Paid | Medium
EXP-05205 | PRJ-006 | PRJ-006-ACT-08 | 2026-02-26 | Equipment | EQ-004 | Scaffolding | VEN-013 | 2 | Day | 4991.92 | 5258.14 | 946.47 | 6204.61 | Paid | Low
EXP-05206 | PRJ-006 | PRJ-006-ACT-01 | 2026-02-26 | Material | MAT-001 | Cement | VEN-015 | 42.74 | Bag | 22043.08 | 20485.07 | 3687.31 | 24172.38 | Paid | High
EXP-05207 | PRJ-006 | PRJ-006-ACT-06 | 2026-02-26 | Material | MAT-001 | Cement | VEN-013 | 5.36 | Bag | 2835.14 | 2884.55 | 519.22 | 3403.77 | Paid | High
EXP-05208 | PRJ-006 | PRJ-006-ACT-04 | 2026-02-26 | Material | MAT-003 | Sand | VEN-015 | 4.97 | Ton | 9538.7 | 9486.14 | 1707.51 | 11193.65 | Paid | Medium
EXP-05209 | PRJ-006 | PRJ-006-ACT-02 | 2026-03-03 | Material | MAT-007 | PVC Pipe | VEN-014 | 6.51 | Meter | 738.52 | 691.72 | 124.51 | 816.23 | Paid | Low
EXP-05210 | PRJ-006 | PRJ-006-ACT-09 | 2026-03-03 | Contractor | CON-002 | Electrical Contract | VEN-015 | 1 | Contract | 353730.31 | 343100.2 | 61758.04 | 404858.24 | Paid | Low
EXP-05211 | PRJ-006 | PRJ-006-ACT-01 | 2026-03-03 | Material | MAT-010 | Glass | VEN-013 | 4.85 | Sq Ft | 801.46 | 772.37 | 139.03 | 911.4 | Partially Paid | High
EXP-05212 | PRJ-006 | PRJ-006-ACT-06 | 2026-03-03 | Contractor | CON-003 | Plumbing Contract | VEN-014 | 1 | Contract | 296841.17 | 313713.86 | 56468.49 | 370182.35 | Paid | Low
EXP-05213 | PRJ-006 | PRJ-006-ACT-03 | 2026-03-03 | Labour | LAB-002 | Helper | VEN-013 | 16 | Worker | 23316.35 | 23563.33 | 4241.4 | 27804.73 | Paid | High
EXP-05214 | PRJ-006 | PRJ-006-ACT-05 | 2026-03-03 | Material | MAT-010 | Glass | VEN-013 | 2.11 | Sq Ft | 335.39 | 349.65 | 62.94 | 412.59 | Paid | Low
EXP-05215 | PRJ-006 | PRJ-006-ACT-05 | 2026-03-03 | Contractor | CON-003 | Plumbing Contract | VEN-013 | 1 | Contract | 312168.03 | 290705.7 | 52327.03 | 343032.73 | Pending | Low
EXP-05216 | PRJ-006 | PRJ-006-ACT-03 | 2026-03-03 | Material | MAT-009 | Paint | VEN-014 | 22.44 | Litre | 5185.76 | 4983.66 | 897.06 | 5880.72 | Paid | Low
EXP-05217 | PRJ-006 | PRJ-006-ACT-01 | 2026-03-03 | Material | MAT-006 | Electrical Cable | VEN-016 | 6.53 | Meter | 509.16 | 548.03 | 98.65 | 646.68 | Partially Paid | Low
EXP-05218 | PRJ-006 | PRJ-006-ACT-06 | 2026-03-08 | Labour | LAB-004 | Electrician | VEN-016 | 10 | Worker | 13688.23 | 12997.75 | 2339.59 | 15337.34 | Paid | Low
EXP-05219 | PRJ-006 | PRJ-006-ACT-06 | 2026-03-08 | Contractor | CON-004 | Finishing Contract | VEN-015 | 1 | Contract | 252498.72 | 274218.66 | 49359.36 | 323578.02 | Paid | Low
EXP-05220 | PRJ-006 | PRJ-006-ACT-05 | 2026-03-08 | Labour | LAB-006 | Painter | VEN-014 | 26 | Worker | 29406.44 | 31812.56 | 5726.26 | 37538.82 | Paid | Medium
EXP-05221 | PRJ-006 | PRJ-006-ACT-02 | 2026-03-08 | Material | MAT-007 | PVC Pipe | VEN-015 | 8.46 | Meter | 1049.36 | 1138.31 | 204.9 | 1343.21 | Paid | Medium
EXP-05222 | PRJ-006 | PRJ-006-ACT-04 | 2026-03-08 | Labour | LAB-003 | Carpenter | VEN-014 | 32 | Worker | 46144.06 | 48903.66 | 8802.66 | 57706.32 | Paid | Low
EXP-05223 | PRJ-006 | PRJ-006-ACT-06 | 2026-03-08 | Labour | LAB-004 | Electrician | VEN-013 | 27 | Worker | 46361.87 | 45566.83 | 8202.03 | 53768.86 | Paid | Low
EXP-05224 | PRJ-006 | PRJ-006-ACT-10 | 2026-03-13 | Other | OTH-001 | Transport | VEN-016 | 1 | Lot | 29855.19 | 30937.31 | 5568.72 | 36506.03 | Pending | Low
EXP-05225 | PRJ-006 | PRJ-006-ACT-06 | 2026-03-13 | Equipment | EQ-004 | Scaffolding | VEN-013 | 5 | Day | 13675.58 | 13048.28 | 2348.69 | 15396.97 | Paid | Low
EXP-05226 | PRJ-006 | PRJ-006-ACT-07 | 2026-03-13 | Contractor | CON-001 | Civil Structure Contract | VEN-014 | 1 | Contract | 119674.18 | 122747.32 | 22094.52 | 144841.84 | Paid | Medium
EXP-05227 | PRJ-006 | PRJ-006-ACT-08 | 2026-03-13 | Contractor | CON-001 | Civil Structure Contract | VEN-016 | 1 | Contract | 259491.3 | 249276.9 | 44869.84 | 294146.74 | Paid | Low
EXP-05228 | PRJ-006 | PRJ-006-ACT-02 | 2026-03-13 | Material | MAT-007 | PVC Pipe | VEN-015 | 10.33 | Meter | 1143.87 | 1159.86 | 208.77 | 1368.63 | Paid | Medium
EXP-05229 | PRJ-006 | PRJ-006-ACT-02 | 2026-03-13 | Contractor | CON-001 | Civil Structure Contract | VEN-013 | 1 | Contract | 174544.21 | 183866.81 | 33096.03 | 216962.84 | Paid | Low
EXP-05230 | PRJ-006 | PRJ-006-ACT-01 | 2026-03-18 | Other | OTH-001 | Safety | VEN-013 | 1 | Lot | 15598.15 | 15166.94 | 2730.05 | 17896.99 | Paid | Low
EXP-05231 | PRJ-006 | PRJ-006-ACT-04 | 2026-03-18 | Equipment | EQ-002 | Excavator | VEN-014 | 5 | Day | 73161 | 74160.8 | 13348.94 | 87509.74 | Paid | Low
EXP-05232 | PRJ-006 | PRJ-006-ACT-04 | 2026-03-18 | Contractor | CON-002 | Electrical Contract | VEN-013 | 1 | Contract | 104795.84 | 112865.88 | 20315.86 | 133181.74 | Paid | Medium
EXP-05233 | PRJ-006 | PRJ-006-ACT-01 | 2026-03-18 | Labour | LAB-005 | Plumber | VEN-014 | 6 | Worker | 9247.06 | 9148.43 | 1646.72 | 10795.15 | Paid | Low
EXP-05234 | PRJ-006 | PRJ-006-ACT-03 | 2026-03-18 | Material | MAT-001 | Cement | VEN-014 | 46.42 | Bag | 21032.01 | 22765.87 | 4097.86 | 26863.73 | Paid | Low
EXP-05235 | PRJ-006 | PRJ-006-ACT-01 | 2026-03-18 | Equipment | EQ-001 | Crane | VEN-014 | 2 | Day | 37878.49 | 38963.47 | 7013.42 | 45976.89 | Partially Paid | Low
EXP-05236 | PRJ-006 | PRJ-006-ACT-05 | 2026-03-23 | Material | MAT-009 | Paint | VEN-015 | 3.26 | Litre | 697.08 | 756.88 | 136.24 | 893.12 | Paid | Low
EXP-05237 | PRJ-006 | PRJ-006-ACT-07 | 2026-03-23 | Equipment | EQ-002 | Excavator | VEN-016 | 7 | Day | 100225.33 | 103649.54 | 18656.92 | 122306.46 | Paid | Medium
EXP-05238 | PRJ-006 | PRJ-006-ACT-10 | 2026-03-23 | Contractor | CON-001 | Civil Structure Contract | VEN-015 | 1 | Contract | 297864.14 | 287377.45 | 51727.94 | 339105.39 | Paid | Medium
EXP-05239 | PRJ-006 | PRJ-006-ACT-10 | 2026-03-23 | Other | OTH-001 | Site Office | VEN-013 | 1 | Lot | 78859.78 | 75021.17 | 13503.81 | 88524.98 | Paid | Low
EXP-05240 | PRJ-006 | PRJ-006-ACT-02 | 2026-03-23 | Material | MAT-001 | Cement | VEN-015 | 16.53 | Bag | 8080.79 | 7597.21 | 1367.5 | 8964.71 | Paid | Low
EXP-05241 | PRJ-006 | PRJ-006-ACT-03 | 2026-03-23 | Labour | LAB-006 | Painter | VEN-015 | 17 | Worker | 12396.21 | 12586.35 | 2265.54 | 14851.89 | Partially Paid | Medium
EXP-05242 | PRJ-006 | PRJ-006-ACT-05 | 2026-03-23 | Material | MAT-009 | Paint | VEN-015 | 8.2 | Litre | 1498.24 | 1536.43 | 276.56 | 1812.99 | Paid | Low
EXP-05243 | PRJ-006 | PRJ-006-ACT-06 | 2026-03-28 | Material | MAT-005 | Bricks | VEN-015 | 2.72 | Piece | 26.61 | 24.86 | 4.47 | 29.33 | Paid | Low
EXP-05244 | PRJ-006 | PRJ-006-ACT-09 | 2026-03-28 | Labour | LAB-004 | Electrician | VEN-016 | 33 | Worker | 47629.92 | 44345.45 | 7982.18 | 52327.63 | Paid | Low
EXP-05245 | PRJ-006 | PRJ-006-ACT-01 | 2026-03-28 | Equipment | EQ-004 | Scaffolding | VEN-013 | 5 | Day | 12535.18 | 12134.06 | 2184.13 | 14318.19 | Paid | Low
EXP-05246 | PRJ-006 | PRJ-006-ACT-02 | 2026-03-28 | Contractor | CON-004 | Finishing Contract | VEN-014 | 1 | Contract | 134251.24 | 135823.38 | 24448.21 | 160271.59 | Paid | Medium
EXP-05247 | PRJ-006 | PRJ-006-ACT-04 | 2026-03-28 | Contractor | CON-001 | Civil Structure Contract | VEN-016 | 1 | Contract | 134718.76 | 145368.2 | 26166.28 | 171534.48 | Paid | Low
EXP-05248 | PRJ-006 | PRJ-006-ACT-08 | 2026-03-28 | Material | MAT-002 | Steel | VEN-015 | 4.84 | Ton | 244046.08 | 263957.17 | 47512.29 | 311469.46 | Partially Paid | Low
EXP-05249 | PRJ-006 | PRJ-006-ACT-03 | 2026-03-28 | Equipment | EQ-004 | Scaffolding | VEN-015 | 2 | Day | 4882.46 | 4995.79 | 899.24 | 5895.03 | Paid | Low
EXP-05250 | PRJ-006 | PRJ-006-ACT-01 | 2026-04-02 | Labour | LAB-006 | Painter | VEN-013 | 7 | Worker | 7970.72 | 8490.9 | 1528.36 | 10019.26 | Paid | High
EXP-05251 | PRJ-006 | PRJ-006-ACT-05 | 2026-04-02 | Contractor | CON-002 | Electrical Contract | VEN-013 | 1 | Contract | 84435.73 | 90783.62 | 16341.05 | 107124.67 | Paid | Medium
EXP-05252 | PRJ-006 | PRJ-006-ACT-07 | 2026-04-02 | Material | MAT-001 | Cement | VEN-013 | 7.4 | Bag | 3863.34 | 3912.72 | 704.29 | 4617.01 | Paid | Medium
EXP-05253 | PRJ-006 | PRJ-006-ACT-10 | 2026-04-02 | Labour | LAB-003 | Carpenter | VEN-014 | 12 | Worker | 8949.86 | 9007.02 | 1621.26 | 10628.28 | Paid | Low
EXP-05254 | PRJ-006 | PRJ-006-ACT-05 | 2026-04-02 | Material | MAT-008 | Tiles | VEN-015 | 12.84 | Sq Ft | 1036.57 | 1025.14 | 184.53 | 1209.67 | Partially Paid | Low
EXP-05255 | PRJ-006 | PRJ-006-ACT-10 | 2026-04-02 | Material | MAT-006 | Electrical Cable | VEN-016 | 10.42 | Meter | 957.37 | 944.12 | 169.94 | 1114.06 | Paid | Low
EXP-05256 | PRJ-006 | PRJ-006-ACT-03 | 2026-04-02 | Material | MAT-002 | Steel | VEN-015 | 4.61 | Ton | 333215.35 | 314701.89 | 56646.34 | 371348.23 | Paid | Medium
EXP-05257 | PRJ-006 | PRJ-006-ACT-10 | 2026-04-07 | Labour | LAB-003 | Carpenter | VEN-013 | 20 | Worker | 13542.5 | 14634.44 | 2634.2 | 17268.64 | Paid | Medium
EXP-05258 | PRJ-006 | PRJ-006-ACT-03 | 2026-04-07 | Equipment | EQ-001 | Crane | VEN-016 | 6 | Day | 111217.14 | 103150.47 | 18567.08 | 121717.55 | Paid | Low
EXP-05259 | PRJ-006 | PRJ-006-ACT-04 | 2026-04-07 | Material | MAT-009 | Paint | VEN-016 | 36.7 | Litre | 7439.43 | 7342.08 | 1321.57 | 8663.65 | Paid | Low
EXP-05260 | PRJ-006 | PRJ-006-ACT-06 | 2026-04-07 | Labour | LAB-001 | Mason | VEN-013 | 22 | Worker | 23658.66 | 23476.66 | 4225.8 | 27702.46 | Paid | Low
EXP-05261 | PRJ-006 | PRJ-006-ACT-02 | 2026-04-07 | Material | MAT-005 | Bricks | VEN-014 | 4.5 | Piece | 45.18 | 45.24 | 8.14 | 53.38 | Pending | Low
EXP-05262 | PRJ-006 | PRJ-006-ACT-05 | 2026-04-07 | Labour | LAB-006 | Painter | VEN-013 | 7 | Worker | 10302.81 | 10396.4 | 1871.35 | 12267.75 | Partially Paid | Low
EXP-05263 | PRJ-006 | PRJ-006-ACT-09 | 2026-04-07 | Contractor | CON-003 | Plumbing Contract | VEN-015 | 1 | Contract | 201296.83 | 205129.62 | 36923.33 | 242052.95 | Paid | Medium
EXP-05264 | PRJ-006 | PRJ-006-ACT-09 | 2026-04-07 | Material | MAT-009 | Paint | VEN-013 | 5.3 | Litre | 1275.94 | 1187.23 | 213.7 | 1400.93 | Paid | Medium
EXP-05265 | PRJ-006 | PRJ-006-ACT-07 | 2026-04-12 | Labour | LAB-003 | Carpenter | VEN-015 | 5 | Worker | 8941.19 | 8660.06 | 1558.81 | 10218.87 | Paid | Medium
EXP-05266 | PRJ-006 | PRJ-006-ACT-05 | 2026-04-12 | Labour | LAB-006 | Painter | VEN-016 | 19 | Worker | 23139.01 | 21838.47 | 3930.92 | 25769.39 | Paid | Low
EXP-05267 | PRJ-006 | PRJ-006-ACT-10 | 2026-04-12 | Labour | LAB-006 | Painter | VEN-015 | 8 | Worker | 12148.23 | 12055.26 | 2169.95 | 14225.21 | Paid | High
EXP-05268 | PRJ-006 | PRJ-006-ACT-01 | 2026-04-12 | Equipment | EQ-002 | Excavator | VEN-014 | 5 | Day | 70828.27 | 76788.3 | 13821.89 | 90610.19 | Paid | High
EXP-05269 | PRJ-006 | PRJ-006-ACT-02 | 2026-04-12 | Material | MAT-004 | Aggregate | VEN-016 | 9.92 | Ton | 15214.32 | 15508.9 | 2791.6 | 18300.5 | Paid | Medium
EXP-05270 | PRJ-006 | PRJ-006-ACT-10 | 2026-04-12 | Material | MAT-010 | Glass | VEN-014 | 18.07 | Sq Ft | 3159.56 | 2973.43 | 535.22 | 3508.65 | Paid | Low
EXP-05271 | PRJ-006 | PRJ-006-ACT-03 | 2026-04-12 | Labour | LAB-002 | Helper | VEN-015 | 12 | Worker | 15890.46 | 15512.87 | 2792.32 | 18305.19 | Paid | Medium
EXP-05272 | PRJ-006 | PRJ-006-ACT-06 | 2026-04-17 | Contractor | CON-004 | Finishing Contract | VEN-016 | 1 | Contract | 91325.58 | 87156.71 | 15688.21 | 102844.92 | Paid | Low
EXP-05273 | PRJ-006 | PRJ-006-ACT-09 | 2026-04-17 | Material | MAT-008 | Tiles | VEN-016 | 8.84 | Sq Ft | 597.13 | 627.13 | 112.88 | 740.01 | Paid | Medium
EXP-05274 | PRJ-006 | PRJ-006-ACT-04 | 2026-04-17 | Material | MAT-001 | Cement | VEN-016 | 7.15 | Bag | 4040.49 | 4218.33 | 759.3 | 4977.63 | Paid | Medium
EXP-05275 | PRJ-006 | PRJ-006-ACT-10 | 2026-04-17 | Contractor | CON-002 | Electrical Contract | VEN-013 | 1 | Contract | 163253.58 | 176096.61 | 31697.39 | 207794 | Paid | Low
EXP-05276 | PRJ-006 | PRJ-006-ACT-03 | 2026-04-17 | Material | MAT-010 | Glass | VEN-014 | 4.61 | Sq Ft | 629.94 | 671.12 | 120.8 | 791.92 | Paid | Low
EXP-05277 | PRJ-006 | PRJ-006-ACT-03 | 2026-04-17 | Other | OTH-001 | Transport | VEN-014 | 1 | Lot | 62458.34 | 65803.78 | 11844.68 | 77648.46 | Paid | Medium
EXP-05278 | PRJ-006 | PRJ-006-ACT-01 | 2026-04-17 | Material | MAT-008 | Tiles | VEN-016 | 28.6 | Sq Ft | 1790.39 | 1832.36 | 329.82 | 2162.18 | Paid | Low
EXP-05279 | PRJ-006 | PRJ-006-ACT-09 | 2026-04-17 | Material | MAT-007 | PVC Pipe | VEN-015 | 16.36 | Meter | 2030.28 | 2085.15 | 375.33 | 2460.48 | Paid | Low
EXP-05280 | PRJ-006 | PRJ-006-ACT-05 | 2026-04-17 | Material | MAT-006 | Electrical Cable | VEN-015 | 2.51 | Meter | 206.46 | 194.35 | 34.98 | 229.33 | Paid | Low
EXP-05281 | PRJ-006 | PRJ-006-ACT-05 | 2026-04-22 | Material | MAT-004 | Aggregate | VEN-015 | 4.68 | Ton | 6789.34 | 7070.29 | 1272.65 | 8342.94 | Paid | Medium
EXP-05282 | PRJ-006 | PRJ-006-ACT-02 | 2026-04-22 | Contractor | CON-003 | Plumbing Contract | VEN-013 | 1 | Contract | 212626.57 | 205227.82 | 36941.01 | 242168.83 | Paid | Medium
EXP-05283 | PRJ-006 | PRJ-006-ACT-03 | 2026-04-22 | Equipment | EQ-002 | Excavator | VEN-016 | 2 | Day | 28193.51 | 30302.22 | 5454.4 | 35756.62 | Partially Paid | Medium
EXP-05284 | PRJ-006 | PRJ-006-ACT-01 | 2026-04-22 | Contractor | CON-001 | Civil Structure Contract | VEN-016 | 1 | Contract | 408535.59 | 409468.05 | 73704.25 | 483172.3 | Paid | Medium
EXP-05285 | PRJ-006 | PRJ-006-ACT-04 | 2026-04-22 | Material | MAT-006 | Electrical Cable | VEN-014 | 6.46 | Meter | 572.29 | 599.64 | 107.94 | 707.58 | Paid | Low
EXP-05286 | PRJ-006 | PRJ-006-ACT-05 | 2026-04-22 | Contractor | CON-003 | Plumbing Contract | VEN-015 | 1 | Contract | 434648.77 | 449561.84 | 80921.13 | 530482.97 | Partially Paid | Medium
EXP-05287 | PRJ-006 | PRJ-006-ACT-07 | 2026-04-22 | Other | OTH-001 | Safety | VEN-014 | 1 | Lot | 42608.87 | 43264.76 | 7787.66 | 51052.42 | Paid | High
EXP-05288 | PRJ-006 | PRJ-006-ACT-06 | 2026-04-22 | Material | MAT-009 | Paint | VEN-013 | 10.57 | Litre | 2204.93 | 2170.55 | 390.7 | 2561.25 | Paid | Low
EXP-05289 | PRJ-006 | PRJ-006-ACT-05 | 2026-04-27 | Equipment | EQ-002 | Excavator | VEN-016 | 2 | Day | 29981.71 | 29648.94 | 5336.81 | 34985.75 | Paid | Low
EXP-05290 | PRJ-006 | PRJ-006-ACT-10 | 2026-04-27 | Labour | LAB-001 | Mason | VEN-013 | 22 | Worker | 16465.49 | 17719.03 | 3189.43 | 20908.46 | Paid | Low
EXP-05291 | PRJ-006 | PRJ-006-ACT-07 | 2026-04-27 | Material | MAT-010 | Glass | VEN-016 | 9.19 | Sq Ft | 1580.34 | 1503.79 | 270.68 | 1774.47 | Paid | Low
EXP-05292 | PRJ-006 | PRJ-006-ACT-03 | 2026-04-27 | Material | MAT-004 | Aggregate | VEN-014 | 9.7 | Ton | 16440.33 | 15423.41 | 2776.21 | 18199.62 | Paid | Low
EXP-05293 | PRJ-006 | PRJ-006-ACT-02 | 2026-04-27 | Contractor | CON-004 | Finishing Contract | VEN-013 | 1 | Contract | 335301.04 | 364346.66 | 65582.4 | 429929.06 | Partially Paid | Low
EXP-05294 | PRJ-006 | PRJ-006-ACT-08 | 2026-04-27 | Equipment | EQ-003 | Concrete Mixer | VEN-014 | 5 | Day | 22838.05 | 21906.73 | 3943.21 | 25849.94 | Paid | Medium
EXP-05295 | PRJ-006 | PRJ-006-ACT-06 | 2026-04-27 | Contractor | CON-003 | Plumbing Contract | VEN-016 | 1 | Contract | 182644.23 | 177766.77 | 31998.02 | 209764.79 | Paid | Low
EXP-05296 | PRJ-006 | PRJ-006-ACT-07 | 2026-04-27 | Material | MAT-001 | Cement | VEN-016 | 5.89 | Bag | 3040.18 | 2850.1 | 513.02 | 3363.12 | Paid | Low
EXP-05297 | PRJ-006 | PRJ-006-ACT-04 | 2026-04-27 | Other | OTH-001 | Permit | VEN-015 | 1 | Lot | 49583.34 | 52774.8 | 9499.46 | 62274.26 | Paid | Low
EXP-05298 | PRJ-006 | PRJ-006-ACT-08 | 2026-05-02 | Other | OTH-001 | Miscellaneous | VEN-014 | 1 | Lot | 65096.45 | 61646.75 | 11096.41 | 72743.16 | Paid | Low
EXP-05299 | PRJ-006 | PRJ-006-ACT-02 | 2026-05-02 | Equipment | EQ-004 | Scaffolding | VEN-015 | 3 | Day | 7546.1 | 7442.28 | 1339.61 | 8781.89 | Paid | Low
EXP-05300 | PRJ-006 | PRJ-006-ACT-10 | 2026-05-02 | Equipment | EQ-002 | Excavator | VEN-015 | 3 | Day | 43233.89 | 41662.18 | 7499.19 | 49161.37 | Paid | Medium
EXP-05301 | PRJ-006 | PRJ-006-ACT-09 | 2026-05-02 | Contractor | CON-002 | Electrical Contract | VEN-015 | 1 | Contract | 236915.89 | 237410.4 | 42733.87 | 280144.27 | Paid | Medium
EXP-05302 | PRJ-006 | PRJ-006-ACT-08 | 2026-05-02 | Labour | LAB-001 | Mason | VEN-013 | 13 | Worker | 10409.92 | 10237.23 | 1842.7 | 12079.93 | Paid | Low
EXP-05303 | PRJ-006 | PRJ-006-ACT-03 | 2026-05-02 | Material | MAT-002 | Steel | VEN-015 | 13.72 | Ton | 927743.71 | 955138.18 | 171924.87 | 1127063.05 | Paid | Low
EXP-05304 | PRJ-006 | PRJ-006-ACT-03 | 2026-05-02 | Labour | LAB-003 | Carpenter | VEN-016 | 29 | Worker | 41947.83 | 41252.91 | 7425.52 | 48678.43 | Paid | Medium
EXP-05305 | PRJ-006 | PRJ-006-ACT-08 | 2026-05-07 | Labour | LAB-005 | Plumber | VEN-014 | 23 | Worker | 30851.2 | 29383.88 | 5289.1 | 34672.98 | Paid | High
EXP-05306 | PRJ-006 | PRJ-006-ACT-06 | 2026-05-07 | Material | MAT-006 | Electrical Cable | VEN-014 | 4.7 | Meter | 382.4 | 373.48 | 67.23 | 440.71 | Paid | Low
EXP-05307 | PRJ-006 | PRJ-006-ACT-02 | 2026-05-07 | Material | MAT-004 | Aggregate | VEN-016 | 17.56 | Ton | 27829.11 | 26304.77 | 4734.86 | 31039.63 | Paid | High
EXP-05308 | PRJ-006 | PRJ-006-ACT-06 | 2026-05-07 | Equipment | EQ-003 | Concrete Mixer | VEN-015 | 4 | Day | 16478.98 | 16830.11 | 3029.42 | 19859.53 | Paid | Medium
EXP-05309 | PRJ-006 | PRJ-006-ACT-10 | 2026-05-07 | Material | MAT-002 | Steel | VEN-016 | 3.27 | Ton | 217808.27 | 221744.21 | 39913.96 | 261658.17 | Paid | Medium
EXP-05310 | PRJ-006 | PRJ-006-ACT-01 | 2026-05-07 | Contractor | CON-003 | Plumbing Contract | VEN-014 | 1 | Contract | 178092.75 | 191680.77 | 34502.54 | 226183.31 | Paid | Medium
EXP-05311 | PRJ-006 | PRJ-006-ACT-03 | 2026-05-07 | Material | MAT-005 | Bricks | VEN-015 | 3.37 | Piece | 31.12 | 30.04 | 5.41 | 35.45 | Paid | Medium
EXP-05312 | PRJ-006 | PRJ-006-ACT-03 | 2026-05-12 | Labour | LAB-005 | Plumber | VEN-014 | 5 | Worker | 8995.37 | 8512.54 | 1532.26 | 10044.8 | Paid | Medium
EXP-05313 | PRJ-006 | PRJ-006-ACT-06 | 2026-05-12 | Material | MAT-009 | Paint | VEN-015 | 9.58 | Litre | 1762.58 | 1882.27 | 338.81 | 2221.08 | Paid | Low
EXP-05314 | PRJ-006 | PRJ-006-ACT-08 | 2026-05-12 | Contractor | CON-001 | Civil Structure Contract | VEN-016 | 1 | Contract | 119421.11 | 128024.8 | 23044.46 | 151069.26 | Partially Paid | Low
EXP-05315 | PRJ-006 | PRJ-006-ACT-03 | 2026-05-12 | Contractor | CON-002 | Electrical Contract | VEN-014 | 1 | Contract | 129785.86 | 120434.32 | 21678.18 | 142112.5 | Paid | Low
EXP-05316 | PRJ-006 | PRJ-006-ACT-04 | 2026-05-12 | Material | MAT-006 | Electrical Cable | VEN-014 | 6.42 | Meter | 489.56 | 476.71 | 85.81 | 562.52 | Paid | Low
EXP-05317 | PRJ-006 | PRJ-006-ACT-01 | 2026-05-12 | Equipment | EQ-002 | Excavator | VEN-016 | 4 | Day | 47489.49 | 51202.76 | 9216.5 | 60419.26 | Paid | Medium
EXP-05318 | PRJ-006 | PRJ-006-ACT-04 | 2026-05-12 | Labour | LAB-001 | Mason | VEN-013 | 19 | Worker | 22677.24 | 21453.79 | 3861.68 | 25315.47 | Paid | Low
EXP-05319 | PRJ-006 | PRJ-006-ACT-06 | 2026-05-12 | Contractor | CON-004 | Finishing Contract | VEN-013 | 1 | Contract | 214610.36 | 207129.1 | 37283.24 | 244412.34 | Paid | Low
EXP-05320 | PRJ-006 | PRJ-006-ACT-10 | 2026-05-17 | Contractor | CON-002 | Electrical Contract | VEN-016 | 1 | Contract | 120669.2 | 113682.47 | 20462.84 | 134145.31 | Paid | Low
EXP-05321 | PRJ-006 | PRJ-006-ACT-05 | 2026-05-17 | Material | MAT-004 | Aggregate | VEN-015 | 7.28 | Ton | 12989.32 | 12508.03 | 2251.45 | 14759.48 | Partially Paid | Low
EXP-05322 | PRJ-006 | PRJ-006-ACT-02 | 2026-05-17 | Material | MAT-001 | Cement | VEN-014 | 6.81 | Bag | 4180.01 | 4030.75 | 725.53 | 4756.28 | Paid | Medium
EXP-05323 | PRJ-006 | PRJ-006-ACT-09 | 2026-05-17 | Material | MAT-003 | Sand | VEN-015 | 15.06 | Ton | 21761.54 | 23486.7 | 4227.61 | 27714.31 | Paid | Medium
EXP-05324 | PRJ-006 | PRJ-006-ACT-09 | 2026-05-17 | Contractor | CON-001 | Civil Structure Contract | VEN-016 | 1 | Contract | 337696.12 | 343153.48 | 61767.63 | 404921.11 | Partially Paid | Low
EXP-05325 | PRJ-006 | PRJ-006-ACT-06 | 2026-05-17 | Material | MAT-006 | Electrical Cable | VEN-013 | 1.86 | Meter | 185.64 | 174.21 | 31.36 | 205.57 | Paid | High
EXP-05326 | PRJ-006 | PRJ-006-ACT-08 | 2026-05-17 | Labour | LAB-001 | Mason | VEN-013 | 14 | Worker | 13263.86 | 12951.83 | 2331.33 | 15283.16 | Paid | Low
EXP-05327 | PRJ-006 | PRJ-006-ACT-09 | 2026-05-22 | Material | MAT-005 | Bricks | VEN-015 | 10.03 | Piece | 75.91 | 79.5 | 14.31 | 93.81 | Partially Paid | Low
EXP-05328 | PRJ-006 | PRJ-006-ACT-10 | 2026-05-22 | Material | MAT-006 | Electrical Cable | VEN-013 | 12.22 | Meter | 1115.47 | 1103.31 | 198.6 | 1301.91 | Paid | Low
EXP-05329 | PRJ-006 | PRJ-006-ACT-01 | 2026-05-22 | Labour | LAB-006 | Painter | VEN-013 | 25 | Worker | 18854.96 | 19243.36 | 3463.8 | 22707.16 | Paid | Medium
EXP-05330 | PRJ-006 | PRJ-006-ACT-05 | 2026-05-22 | Labour | LAB-005 | Plumber | VEN-014 | 23 | Worker | 20831.94 | 19454.71 | 3501.85 | 22956.56 | Partially Paid | Medium
EXP-05331 | PRJ-006 | PRJ-006-ACT-01 | 2026-05-22 | Material | MAT-006 | Electrical Cable | VEN-013 | 17.75 | Meter | 1318.43 | 1312.91 | 236.32 | 1549.23 | Paid | Low
EXP-05332 | PRJ-006 | PRJ-006-ACT-04 | 2026-05-22 | Material | MAT-008 | Tiles | VEN-014 | 15.7 | Sq Ft | 1252.87 | 1167.75 | 210.19 | 1377.94 | Paid | Low
EXP-05333 | PRJ-006 | PRJ-006-ACT-08 | 2026-05-22 | Contractor | CON-001 | Civil Structure Contract | VEN-013 | 1 | Contract | 91324.96 | 91750.67 | 16515.12 | 108265.79 | Pending | Low
EXP-05334 | PRJ-006 | PRJ-006-ACT-07 | 2026-05-27 | Material | MAT-010 | Glass | VEN-013 | 34.55 | Sq Ft | 5582.68 | 5223.77 | 940.28 | 6164.05 | Paid | Low
EXP-05335 | PRJ-006 | PRJ-006-ACT-08 | 2026-05-27 | Material | MAT-007 | PVC Pipe | VEN-016 | 10.63 | Meter | 1037.8 | 1110.49 | 199.89 | 1310.38 | Paid | Medium
EXP-05336 | PRJ-006 | PRJ-006-ACT-01 | 2026-05-27 | Contractor | CON-004 | Finishing Contract | VEN-016 | 1 | Contract | 210224.47 | 225017.99 | 40503.24 | 265521.23 | Paid | Medium
EXP-05337 | PRJ-006 | PRJ-006-ACT-04 | 2026-05-27 | Other | OTH-001 | Miscellaneous | VEN-016 | 1 | Lot | 62052.68 | 63284.11 | 11391.14 | 74675.25 | Paid | Medium
EXP-05338 | PRJ-006 | PRJ-006-ACT-02 | 2026-05-27 | Labour | LAB-003 | Carpenter | VEN-014 | 17 | Worker | 19536.95 | 18589.49 | 3346.11 | 21935.6 | Paid | Low
EXP-05339 | PRJ-006 | PRJ-006-ACT-07 | 2026-05-27 | Contractor | CON-001 | Civil Structure Contract | VEN-015 | 1 | Contract | 306263.44 | 295409.43 | 53173.7 | 348583.13 | Partially Paid | High
EXP-05340 | PRJ-006 | PRJ-006-ACT-07 | 2026-05-27 | Contractor | CON-001 | Civil Structure Contract | VEN-015 | 1 | Contract | 251046.75 | 243653.46 | 43857.62 | 287511.08 | Paid | Medium
EXP-05341 | PRJ-006 | PRJ-006-ACT-10 | 2026-06-01 | Material | MAT-006 | Electrical Cable | VEN-014 | 10.41 | Meter | 845.7 | 857.93 | 154.43 | 1012.36 | Paid | Low
EXP-05342 | PRJ-006 | PRJ-006-ACT-04 | 2026-06-01 | Labour | LAB-004 | Electrician | VEN-015 | 22 | Worker | 32402.73 | 33359.33 | 6004.68 | 39364.01 | Paid | Medium
EXP-05343 | PRJ-006 | PRJ-006-ACT-01 | 2026-06-01 | Material | MAT-001 | Cement | VEN-013 | 8.47 | Bag | 4161.91 | 3974.64 | 715.44 | 4690.08 | Pending | Low
EXP-05344 | PRJ-006 | PRJ-006-ACT-03 | 2026-06-01 | Contractor | CON-001 | Civil Structure Contract | VEN-014 | 1 | Contract | 389754.58 | 385464.01 | 69383.52 | 454847.53 | Paid | Medium
EXP-05345 | PRJ-006 | PRJ-006-ACT-05 | 2026-06-01 | Contractor | CON-004 | Finishing Contract | VEN-014 | 1 | Contract | 384373.65 | 374740.52 | 67453.29 | 442193.81 | Paid | Medium
EXP-05346 | PRJ-006 | PRJ-006-ACT-05 | 2026-06-01 | Contractor | CON-003 | Plumbing Contract | VEN-013 | 1 | Contract | 363529.85 | 360879.3 | 64958.27 | 425837.57 | Partially Paid | Low
EXP-05347 | PRJ-006 | PRJ-006-ACT-03 | 2026-06-01 | Material | MAT-010 | Glass | VEN-013 | 9.94 | Sq Ft | 1425 | 1411.22 | 254.02 | 1665.24 | Pending | Medium
EXP-05348 | PRJ-006 | PRJ-006-ACT-06 | 2026-06-01 | Material | MAT-002 | Steel | VEN-013 | 6.21 | Ton | 399146.52 | 397048.88 | 71468.8 | 468517.68 | Partially Paid | Low
EXP-05349 | PRJ-006 | PRJ-006-ACT-06 | 2026-06-01 | Other | OTH-001 | Permit | VEN-015 | 1 | Lot | 44045.28 | 42939.71 | 7729.15 | 50668.86 | Paid | Medium
EXP-05350 | PRJ-006 | PRJ-006-ACT-01 | 2026-06-06 | Material | MAT-003 | Sand | VEN-013 | 24.87 | Ton | 50094.76 | 50474.74 | 9085.45 | 59560.19 | Paid | Medium
EXP-05351 | PRJ-006 | PRJ-006-ACT-08 | 2026-06-06 | Material | MAT-009 | Paint | VEN-014 | 7.1 | Litre | 1662.95 | 1624.16 | 292.35 | 1916.51 | Paid | Medium
EXP-05352 | PRJ-006 | PRJ-006-ACT-08 | 2026-06-06 | Material | MAT-009 | Paint | VEN-013 | 4.2 | Litre | 1043.22 | 979.15 | 176.25 | 1155.4 | Paid | Low
EXP-05353 | PRJ-006 | PRJ-006-ACT-07 | 2026-06-06 | Material | MAT-009 | Paint | VEN-015 | 9.98 | Litre | 2055.31 | 2199.81 | 395.97 | 2595.78 | Partially Paid | Low
EXP-05354 | PRJ-006 | PRJ-006-ACT-07 | 2026-06-06 | Material | MAT-003 | Sand | VEN-016 | 20.97 | Ton | 33915.23 | 35938.8 | 6468.98 | 42407.78 | Paid | Medium
EXP-05355 | PRJ-006 | PRJ-006-ACT-09 | 2026-06-06 | Contractor | CON-001 | Civil Structure Contract | VEN-015 | 1 | Contract | 286979.11 | 292602.15 | 52668.39 | 345270.54 | Paid | Medium
EXP-05356 | PRJ-006 | PRJ-006-ACT-07 | 2026-06-06 | Contractor | CON-003 | Plumbing Contract | VEN-013 | 1 | Contract | 371546.06 | 358818.98 | 64587.42 | 423406.4 | Paid | Medium
EXP-05357 | PRJ-006 | PRJ-006-ACT-03 | 2026-06-06 | Contractor | CON-002 | Electrical Contract | VEN-016 | 1 | Contract | 283321.47 | 305176.59 | 54931.79 | 360108.38 | Paid | Low
EXP-05358 | PRJ-006 | PRJ-006-ACT-09 | 2026-06-06 | Equipment | EQ-004 | Scaffolding | VEN-015 | 1 | Day | 2681.9 | 2600.38 | 468.07 | 3068.45 | Partially Paid | Medium
EXP-05359 | PRJ-006 | PRJ-006-ACT-02 | 2026-06-11 | Material | MAT-004 | Aggregate | VEN-015 | 6.42 | Ton | 9951.4 | 10169.89 | 1830.58 | 12000.47 | Paid | Low
EXP-05360 | PRJ-006 | PRJ-006-ACT-10 | 2026-06-11 | Labour | LAB-005 | Plumber | VEN-015 | 27 | Worker | 29861.4 | 29436.67 | 5298.6 | 34735.27 | Paid | High
EXP-05361 | PRJ-006 | PRJ-006-ACT-01 | 2026-06-11 | Contractor | CON-003 | Plumbing Contract | VEN-015 | 1 | Contract | 383906.84 | 376530.66 | 67775.52 | 444306.18 | Paid | High
EXP-05362 | PRJ-006 | PRJ-006-ACT-04 | 2026-06-11 | Contractor | CON-002 | Electrical Contract | VEN-015 | 1 | Contract | 412551.34 | 397749.08 | 71594.83 | 469343.91 | Pending | Medium
EXP-05363 | PRJ-006 | PRJ-006-ACT-03 | 2026-06-11 | Labour | LAB-002 | Helper | VEN-016 | 13 | Worker | 20650.84 | 21151.63 | 3807.29 | 24958.92 | Partially Paid | Low
EXP-05364 | PRJ-006 | PRJ-006-ACT-04 | 2026-06-11 | Material | MAT-007 | PVC Pipe | VEN-014 | 13.94 | Meter | 1792.57 | 1833.94 | 330.11 | 2164.05 | Paid | Medium
EXP-05365 | PRJ-006 | PRJ-006-ACT-07 | 2026-06-11 | Equipment | EQ-002 | Excavator | VEN-016 | 6 | Day | 83294.01 | 85758.35 | 15436.5 | 101194.85 | Paid | Low
EXP-05366 | PRJ-006 | PRJ-006-ACT-01 | 2026-06-11 | Contractor | CON-001 | Civil Structure Contract | VEN-016 | 1 | Contract | 456457.15 | 443057.05 | 79750.27 | 522807.32 | Paid | Low
EXP-05367 | PRJ-006 | PRJ-006-ACT-06 | 2026-06-11 | Material | MAT-007 | PVC Pipe | VEN-013 | 3.37 | Meter | 402.04 | 436.47 | 78.56 | 515.03 | Paid | Low
EXP-05368 | PRJ-006 | PRJ-006-ACT-02 | 2026-06-16 | Material | MAT-007 | PVC Pipe | VEN-014 | 44.12 | Meter | 5279.93 | 5625.8 | 1012.64 | 6638.44 | Paid | Low
EXP-05369 | PRJ-006 | PRJ-006-ACT-09 | 2026-06-16 | Labour | LAB-001 | Mason | VEN-013 | 33 | Worker | 41014.08 | 41642.21 | 7495.6 | 49137.81 | Partially Paid | Medium
EXP-05370 | PRJ-006 | PRJ-006-ACT-04 | 2026-06-16 | Contractor | CON-004 | Finishing Contract | VEN-013 | 1 | Contract | 342097.85 | 363650.34 | 65457.06 | 429107.4 | Pending | Medium
EXP-05371 | PRJ-006 | PRJ-006-ACT-07 | 2026-06-16 | Material | MAT-001 | Cement | VEN-014 | 11.52 | Bag | 6498.61 | 6672.8 | 1201.1 | 7873.9 | Paid | Medium
EXP-05372 | PRJ-006 | PRJ-006-ACT-09 | 2026-06-16 | Material | MAT-004 | Aggregate | VEN-015 | 6.14 | Ton | 8481.82 | 8672.49 | 1561.05 | 10233.54 | Paid | High
EXP-05373 | PRJ-006 | PRJ-006-ACT-08 | 2026-06-16 | Other | OTH-001 | Permit | VEN-016 | 1 | Lot | 52424.14 | 49928.4 | 8987.11 | 58915.51 | Paid | Low
EXP-05374 | PRJ-006 | PRJ-006-ACT-10 | 2026-06-16 | Material | MAT-004 | Aggregate | VEN-015 | 8.69 | Ton | 10910.8 | 11204.04 | 2016.73 | 13220.77 | Paid | Low
EXP-05375 | PRJ-006 | PRJ-006-ACT-03 | 2026-06-16 | Contractor | CON-001 | Civil Structure Contract | VEN-016 | 1 | Contract | 316207.87 | 311330.01 | 56039.4 | 367369.41 | Paid | Medium
EXP-05376 | PRJ-006 | PRJ-006-ACT-10 | 2026-06-21 | Material | MAT-001 | Cement | VEN-015 | 14.47 | Bag | 7039.91 | 7647.55 | 1376.56 | 9024.11 | Partially Paid | Low
EXP-05377 | PRJ-006 | PRJ-006-ACT-06 | 2026-06-21 | Material | MAT-006 | Electrical Cable | VEN-016 | 4.26 | Meter | 360.82 | 338.06 | 60.85 | 398.91 | Paid | Medium
EXP-05378 | PRJ-006 | PRJ-006-ACT-06 | 2026-06-21 | Contractor | CON-001 | Civil Structure Contract | VEN-013 | 1 | Contract | 167840.38 | 181334.14 | 32640.15 | 213974.29 | Partially Paid | Medium
EXP-05379 | PRJ-006 | PRJ-006-ACT-04 | 2026-06-21 | Material | MAT-008 | Tiles | VEN-016 | 4.68 | Sq Ft | 308.36 | 311.52 | 56.07 | 367.59 | Partially Paid | High
EXP-05380 | PRJ-006 | PRJ-006-ACT-09 | 2026-06-21 | Contractor | CON-001 | Civil Structure Contract | VEN-016 | 1 | Contract | 295268.24 | 283160.63 | 50968.91 | 334129.54 | Paid | Low
EXP-05381 | PRJ-006 | PRJ-006-ACT-03 | 2026-06-21 | Material | MAT-006 | Electrical Cable | VEN-016 | 17.63 | Meter | 1519.07 | 1615.65 | 290.82 | 1906.47 | Paid | Low
EXP-05382 | PRJ-006 | PRJ-006-ACT-04 | 2026-06-21 | Contractor | CON-003 | Plumbing Contract | VEN-016 | 1 | Contract | 428499.76 | 401926.26 | 72346.73 | 474272.99 | Partially Paid | High
EXP-05383 | PRJ-006 | PRJ-006-ACT-03 | 2026-06-21 | Equipment | EQ-001 | Crane | VEN-013 | 4 | Day | 66342.53 | 67502.68 | 12150.48 | 79653.16 | Paid | Low
EXP-05384 | PRJ-006 | PRJ-006-ACT-10 | 2026-06-26 | Material | MAT-005 | Bricks | VEN-014 | 9.01 | Piece | 71.87 | 68.99 | 12.42 | 81.41 | Paid | Medium
EXP-05385 | PRJ-006 | PRJ-006-ACT-02 | 2026-06-26 | Material | MAT-009 | Paint | VEN-016 | 2.61 | Litre | 460.95 | 472.32 | 85.02 | 557.34 | Partially Paid | Low
EXP-05386 | PRJ-006 | PRJ-006-ACT-10 | 2026-06-26 | Material | MAT-009 | Paint | VEN-016 | 15.56 | Litre | 4029.02 | 3740.83 | 673.35 | 4414.18 | Paid | Medium
EXP-05387 | PRJ-006 | PRJ-006-ACT-09 | 2026-06-26 | Labour | LAB-004 | Electrician | VEN-015 | 15 | Worker | 19682.12 | 18978.67 | 3416.16 | 22394.83 | Paid | Medium
EXP-05388 | PRJ-006 | PRJ-006-ACT-05 | 2026-06-26 | Labour | LAB-003 | Carpenter | VEN-013 | 6 | Worker | 8927.59 | 8395.24 | 1511.14 | 9906.38 | Paid | Low
EXP-05389 | PRJ-006 | PRJ-006-ACT-03 | 2026-06-26 | Material | MAT-010 | Glass | VEN-015 | 10.86 | Sq Ft | 1802.63 | 1844.27 | 331.97 | 2176.24 | Paid | High
EXP-05390 | PRJ-006 | PRJ-006-ACT-08 | 2026-06-26 | Labour | LAB-006 | Painter | VEN-014 | 34 | Worker | 47548.1 | 48113.74 | 8660.47 | 56774.21 | Paid | Low
EXP-05391 | PRJ-006 | PRJ-006-ACT-06 | 2026-07-01 | Labour | LAB-002 | Helper | VEN-013 | 32 | Worker | 29813.84 | 30748.91 | 5534.8 | 36283.71 | Paid | High
EXP-05392 | PRJ-006 | PRJ-006-ACT-08 | 2026-07-01 | Material | MAT-006 | Electrical Cable | VEN-014 | 5.24 | Meter | 452.53 | 427.92 | 77.03 | 504.95 | Paid | Low
EXP-05393 | PRJ-006 | PRJ-006-ACT-06 | 2026-07-01 | Equipment | EQ-001 | Crane | VEN-014 | 1 | Day | 18081.14 | 17135.58 | 3084.4 | 20219.98 | Paid | Low
EXP-05394 | PRJ-006 | PRJ-006-ACT-04 | 2026-07-01 | Equipment | EQ-003 | Concrete Mixer | VEN-015 | 3 | Day | 12047.23 | 12219.45 | 2199.5 | 14418.95 | Paid | Medium
EXP-05395 | PRJ-006 | PRJ-006-ACT-01 | 2026-07-01 | Material | MAT-009 | Paint | VEN-013 | 11.62 | Litre | 2504.06 | 2447.41 | 440.53 | 2887.94 | Paid | Low
EXP-05396 | PRJ-006 | PRJ-006-ACT-05 | 2026-07-01 | Equipment | EQ-004 | Scaffolding | VEN-014 | 7 | Day | 16167.08 | 16095.24 | 2897.14 | 18992.38 | Partially Paid | Medium
EXP-05397 | PRJ-006 | PRJ-006-ACT-05 | 2026-07-06 | Equipment | EQ-001 | Crane | VEN-015 | 6 | Day | 93999.07 | 99099.18 | 17837.85 | 116937.03 | Paid | Low
EXP-05398 | PRJ-006 | PRJ-006-ACT-07 | 2026-07-06 | Material | MAT-002 | Steel | VEN-016 | 4.3 | Ton | 278639.61 | 274861.61 | 49475.09 | 324336.7 | Partially Paid | Low
EXP-05399 | PRJ-006 | PRJ-006-ACT-07 | 2026-07-06 | Material | MAT-005 | Bricks | VEN-014 | 27.38 | Piece | 240.66 | 252.45 | 45.44 | 297.89 | Paid | High
EXP-05400 | PRJ-006 | PRJ-006-ACT-03 | 2026-07-06 | Contractor | CON-002 | Electrical Contract | VEN-013 | 1 | Contract | 265769.23 | 252316.57 | 45416.98 | 297733.55 | Paid | Medium
EXP-05401 | PRJ-006 | PRJ-006-ACT-08 | 2026-07-06 | Material | MAT-006 | Electrical Cable | VEN-013 | 12.03 | Meter | 1048.5 | 982.04 | 176.77 | 1158.81 | Paid | Medium
EXP-05402 | PRJ-006 | PRJ-006-ACT-06 | 2026-07-06 | Material | MAT-010 | Glass | VEN-014 | 21.59 | Sq Ft | 3283.13 | 3111.66 | 560.1 | 3671.76 | Paid | Low
EXP-05403 | PRJ-006 | PRJ-006-ACT-04 | 2026-07-06 | Material | MAT-006 | Electrical Cable | VEN-014 | 12.41 | Meter | 1249.85 | 1187.39 | 213.73 | 1401.12 | Partially Paid | Low
EXP-05404 | PRJ-006 | PRJ-006-ACT-03 | 2026-07-06 | Material | MAT-008 | Tiles | VEN-015 | 16.15 | Sq Ft | 1032.24 | 1046.19 | 188.31 | 1234.5 | Paid | High
EXP-05405 | PRJ-006 | PRJ-006-ACT-10 | 2026-07-06 | Material | MAT-006 | Electrical Cable | VEN-015 | 18.4 | Meter | 1606 | 1497.55 | 269.56 | 1767.11 | Paid | Low
EXP-05406 | PRJ-006 | PRJ-006-ACT-09 | 2026-07-11 | Labour | LAB-001 | Mason | VEN-015 | 30 | Worker | 32980.83 | 34791.66 | 6262.5 | 41054.16 | Paid | Medium
EXP-05407 | PRJ-006 | PRJ-006-ACT-03 | 2026-07-11 | Contractor | CON-002 | Electrical Contract | VEN-013 | 1 | Contract | 268110.1 | 288377.52 | 51907.95 | 340285.47 | Paid | Low
EXP-05408 | PRJ-006 | PRJ-006-ACT-07 | 2026-07-11 | Contractor | CON-003 | Plumbing Contract | VEN-015 | 1 | Contract | 349913.23 | 375875.72 | 67657.63 | 443533.35 | Paid | High
EXP-05409 | PRJ-006 | PRJ-006-ACT-10 | 2026-07-11 | Labour | LAB-003 | Carpenter | VEN-015 | 29 | Worker | 32888.72 | 33994.93 | 6119.09 | 40114.02 | Paid | Medium
EXP-05410 | PRJ-006 | PRJ-006-ACT-03 | 2026-07-11 | Material | MAT-005 | Bricks | VEN-013 | 7.82 | Piece | 74.31 | 71.3 | 12.83 | 84.13 | Paid | Medium
EXP-05411 | PRJ-006 | PRJ-006-ACT-05 | 2026-07-11 | Contractor | CON-002 | Electrical Contract | VEN-015 | 1 | Contract | 348092.68 | 368240.18 | 66283.23 | 434523.41 | Paid | Medium
EXP-05412 | PRJ-006 | PRJ-006-ACT-07 | 2026-07-16 | Labour | LAB-002 | Helper | VEN-013 | 32 | Worker | 34275.61 | 32048.67 | 5768.76 | 37817.43 | Partially Paid | Medium
EXP-05413 | PRJ-006 | PRJ-006-ACT-07 | 2026-07-16 | Labour | LAB-001 | Mason | VEN-016 | 11 | Worker | 7751.01 | 7414.01 | 1334.52 | 8748.53 | Paid | Medium
EXP-05414 | PRJ-006 | PRJ-006-ACT-03 | 2026-07-16 | Labour | LAB-002 | Helper | VEN-013 | 6 | Worker | 9716.61 | 10044.18 | 1807.95 | 11852.13 | Paid | Medium
EXP-05415 | PRJ-006 | PRJ-006-ACT-03 | 2026-07-16 | Material | MAT-007 | PVC Pipe | VEN-013 | 2.57 | Meter | 276.39 | 279.65 | 50.34 | 329.99 | Pending | Low
EXP-05416 | PRJ-006 | PRJ-006-ACT-09 | 2026-07-16 | Equipment | EQ-001 | Crane | VEN-013 | 2 | Day | 35049.88 | 37151.25 | 6687.22 | 43838.47 | Paid | Low
EXP-05417 | PRJ-006 | PRJ-006-ACT-06 | 2026-07-16 | Material | MAT-009 | Paint | VEN-015 | 11.56 | Litre | 2438.91 | 2522.41 | 454.03 | 2976.44 | Paid | Low
EXP-05418 | PRJ-006 | PRJ-006-ACT-07 | 2026-07-16 | Labour | LAB-006 | Painter | VEN-015 | 10 | Worker | 8675.41 | 8375.83 | 1507.65 | 9883.48 | Pending | Medium
EXP-05419 | PRJ-006 | PRJ-006-ACT-04 | 2026-07-16 | Material | MAT-003 | Sand | VEN-016 | 14.9 | Ton | 25387.56 | 25029.42 | 4505.3 | 29534.72 | Paid | Low
EXP-05420 | PRJ-006 | PRJ-006-ACT-06 | 2026-07-21 | Contractor | CON-003 | Plumbing Contract | VEN-013 | 1 | Contract | 345124.67 | 327771.46 | 58998.86 | 386770.32 | Paid | Low
EXP-05421 | PRJ-006 | PRJ-006-ACT-09 | 2026-07-21 | Labour | LAB-005 | Plumber | VEN-016 | 17 | Worker | 12872.39 | 12510.16 | 2251.83 | 14761.99 | Paid | Low
EXP-05422 | PRJ-006 | PRJ-006-ACT-07 | 2026-07-21 | Material | MAT-009 | Paint | VEN-013 | 5.26 | Litre | 986.14 | 1042.21 | 187.6 | 1229.81 | Partially Paid | Low
EXP-05423 | PRJ-006 | PRJ-006-ACT-04 | 2026-07-21 | Labour | LAB-004 | Electrician | VEN-015 | 14 | Worker | 9449.21 | 9316.17 | 1676.91 | 10993.08 | Paid | Low
EXP-05424 | PRJ-006 | PRJ-006-ACT-05 | 2026-07-21 | Material | MAT-010 | Glass | VEN-016 | 4.77 | Sq Ft | 668.11 | 694.62 | 125.03 | 819.65 | Paid | Medium
EXP-05425 | PRJ-006 | PRJ-006-ACT-09 | 2026-07-21 | Labour | LAB-004 | Electrician | VEN-015 | 4 | Worker | 3603.28 | 3662.64 | 659.28 | 4321.92 | Paid | Low
EXP-05426 | PRJ-006 | PRJ-006-ACT-01 | 2026-07-21 | Labour | LAB-001 | Mason | VEN-014 | 27 | Worker | 18512.86 | 17614.94 | 3170.69 | 20785.63 | Paid | Low
EXP-05427 | PRJ-006 | PRJ-006-ACT-05 | 2026-07-26 | Contractor | CON-003 | Plumbing Contract | VEN-013 | 1 | Contract | 378637.55 | 391105.38 | 70398.97 | 461504.35 | Paid | Medium
EXP-05428 | PRJ-006 | PRJ-006-ACT-05 | 2026-07-26 | Contractor | CON-003 | Plumbing Contract | VEN-014 | 1 | Contract | 163826.81 | 163997.94 | 29519.63 | 193517.57 | Paid | Low
EXP-05429 | PRJ-006 | PRJ-006-ACT-01 | 2026-07-26 | Equipment | EQ-004 | Scaffolding | VEN-013 | 2 | Day | 5061.23 | 5462.34 | 983.22 | 6445.56 | Paid | Low
EXP-05430 | PRJ-006 | PRJ-006-ACT-08 | 2026-07-26 | Equipment | EQ-004 | Scaffolding | VEN-014 | 2 | Day | 4887.53 | 5230.16 | 941.43 | 6171.59 | Paid | Low
EXP-05431 | PRJ-006 | PRJ-006-ACT-07 | 2026-07-26 | Labour | LAB-006 | Painter | VEN-016 | 17 | Worker | 12608.1 | 13637.71 | 2454.79 | 16092.5 | Paid | Low
EXP-05432 | PRJ-006 | PRJ-006-ACT-03 | 2026-07-26 | Labour | LAB-003 | Carpenter | VEN-016 | 23 | Worker | 20711.57 | 20568.07 | 3702.25 | 24270.32 | Paid | Low
EXP-05433 | PRJ-006 | PRJ-006-ACT-07 | 2026-07-26 | Labour | LAB-003 | Carpenter | VEN-013 | 28 | Worker | 48141.08 | 47442.38 | 8539.63 | 55982.01 | Paid | Medium
EXP-05434 | PRJ-006 | PRJ-006-ACT-05 | 2026-07-26 | Material | MAT-006 | Electrical Cable | VEN-013 | 2.22 | Meter | 187.02 | 202.34 | 36.42 | 238.76 | Paid | Medium
EXP-05435 | PRJ-006 | PRJ-006-ACT-01 | 2026-07-26 | Equipment | EQ-004 | Scaffolding | VEN-014 | 1 | Day | 2258.59 | 2341.5 | 421.47 | 2762.97 | Paid | High
EXP-05436 | PRJ-006 | PRJ-006-ACT-10 | 2026-07-31 | Material | MAT-002 | Steel | VEN-013 | 8.66 | Ton | 495548.73 | 476076.64 | 85693.8 | 561770.44 | Paid | Low
EXP-05437 | PRJ-006 | PRJ-006-ACT-09 | 2026-07-31 | Material | MAT-002 | Steel | VEN-013 | 4.28 | Ton | 250604.25 | 232942.34 | 41929.62 | 274871.96 | Paid | Medium
EXP-05438 | PRJ-006 | PRJ-006-ACT-02 | 2026-07-31 | Labour | LAB-002 | Helper | VEN-016 | 8 | Worker | 13759.14 | 13043.71 | 2347.87 | 15391.58 | Paid | Low
EXP-05439 | PRJ-006 | PRJ-006-ACT-02 | 2026-07-31 | Material | MAT-005 | Bricks | VEN-016 | 16.91 | Piece | 140.79 | 136.99 | 24.66 | 161.65 | Partially Paid | Low
EXP-05440 | PRJ-006 | PRJ-006-ACT-03 | 2026-07-31 | Material | MAT-008 | Tiles | VEN-015 | 15.05 | Sq Ft | 999.24 | 1071.13 | 192.8 | 1263.93 | Paid | High
EXP-05441 | PRJ-006 | PRJ-006-ACT-08 | 2026-07-31 | Labour | LAB-006 | Painter | VEN-013 | 27 | Worker | 18054.54 | 18228.25 | 3281.09 | 21509.34 | Paid | Low
EXP-05442 | PRJ-006 | PRJ-006-ACT-02 | 2026-07-31 | Contractor | CON-001 | Civil Structure Contract | VEN-014 | 1 | Contract | 83596.33 | 84368.85 | 15186.39 | 99555.24 | Paid | Low
EXP-05443 | PRJ-006 | PRJ-006-ACT-07 | 2026-07-31 | Contractor | CON-003 | Plumbing Contract | VEN-016 | 1 | Contract | 272530.19 | 267532.34 | 48155.82 | 315688.16 | Paid | Medium
EXP-05444 | PRJ-006 | PRJ-006-ACT-08 | 2026-07-31 | Labour | LAB-006 | Painter | VEN-015 | 27 | Worker | 36576.01 | 36792.67 | 6622.68 | 43415.35 | Paid | Medium
EXP-05445 | PRJ-006 | PRJ-006-ACT-04 | 2026-08-05 | Contractor | CON-003 | Plumbing Contract | VEN-013 | 1 | Contract | 202424.79 | 196474.18 | 35365.35 | 231839.53 | Paid | Low
EXP-05446 | PRJ-006 | PRJ-006-ACT-09 | 2026-08-05 | Material | MAT-010 | Glass | VEN-013 | 6.94 | Sq Ft | 1042.55 | 985.02 | 177.3 | 1162.32 | Partially Paid | Low
EXP-05447 | PRJ-006 | PRJ-006-ACT-08 | 2026-08-05 | Material | MAT-008 | Tiles | VEN-014 | 13.47 | Sq Ft | 988.38 | 995.8 | 179.24 | 1175.04 | Paid | Low
EXP-05448 | PRJ-006 | PRJ-006-ACT-05 | 2026-08-05 | Material | MAT-002 | Steel | VEN-016 | 10.96 | Ton | 651545.6 | 632575.95 | 113863.67 | 746439.62 | Paid | Low
EXP-05449 | PRJ-006 | PRJ-006-ACT-07 | 2026-08-05 | Contractor | CON-002 | Electrical Contract | VEN-016 | 1 | Contract | 366997.81 | 347960.62 | 62632.91 | 410593.53 | Paid | Low
EXP-05450 | PRJ-006 | PRJ-006-ACT-02 | 2026-08-05 | Contractor | CON-003 | Plumbing Contract | VEN-013 | 1 | Contract | 382197.51 | 367080.49 | 66074.49 | 433154.98 | Paid | Low
EXP-05451 | PRJ-006 | PRJ-006-ACT-01 | 2026-08-05 | Material | MAT-004 | Aggregate | VEN-015 | 13.12 | Ton | 20381.11 | 22120.55 | 3981.7 | 26102.25 | Partially Paid | Low
EXP-05452 | PRJ-006 | PRJ-006-ACT-06 | 2026-08-10 | Labour | LAB-002 | Helper | VEN-015 | 19 | Worker | 15716 | 14845.59 | 2672.21 | 17517.8 | Paid | High
EXP-05453 | PRJ-006 | PRJ-006-ACT-04 | 2026-08-10 | Material | MAT-002 | Steel | VEN-014 | 12.95 | Ton | 825876.02 | 825479.55 | 148586.32 | 974065.87 | Pending | Medium
EXP-05454 | PRJ-006 | PRJ-006-ACT-10 | 2026-08-10 | Material | MAT-008 | Tiles | VEN-016 | 6.75 | Sq Ft | 553.64 | 522.56 | 94.06 | 616.62 | Paid | Low
EXP-05455 | PRJ-006 | PRJ-006-ACT-04 | 2026-08-10 | Contractor | CON-002 | Electrical Contract | VEN-014 | 1 | Contract | 312747.09 | 300461.58 | 54083.08 | 354544.66 | Paid | Low
EXP-05456 | PRJ-006 | PRJ-006-ACT-02 | 2026-08-10 | Material | MAT-008 | Tiles | VEN-015 | 19.96 | Sq Ft | 1713.35 | 1680.68 | 302.52 | 1983.2 | Paid | Low
EXP-05457 | PRJ-006 | PRJ-006-ACT-03 | 2026-08-10 | Contractor | CON-004 | Finishing Contract | VEN-015 | 1 | Contract | 153893.78 | 162038.59 | 29166.95 | 191205.54 | Paid | Low
EXP-05458 | PRJ-006 | PRJ-006-ACT-10 | 2026-08-10 | Labour | LAB-004 | Electrician | VEN-015 | 11 | Worker | 10724.03 | 11229.92 | 2021.39 | 13251.31 | Paid | Medium
EXP-05459 | PRJ-006 | PRJ-006-ACT-05 | 2026-08-10 | Labour | LAB-001 | Mason | VEN-016 | 15 | Worker | 14943.95 | 15728.45 | 2831.12 | 18559.57 | Paid | Low
EXP-05460 | PRJ-006 | PRJ-006-ACT-04 | 2026-08-10 | Equipment | EQ-003 | Concrete Mixer | VEN-015 | 4 | Day | 19562.63 | 18430.34 | 3317.46 | 21747.8 | Paid | Medium
EXP-05461 | PRJ-006 | PRJ-006-ACT-08 | 2026-08-15 | Equipment | EQ-003 | Concrete Mixer | VEN-016 | 1 | Day | 4648.4 | 4515.61 | 812.81 | 5328.42 | Paid | Low
EXP-05462 | PRJ-006 | PRJ-006-ACT-06 | 2026-08-15 | Labour | LAB-002 | Helper | VEN-015 | 17 | Worker | 17157.18 | 16879.56 | 3038.32 | 19917.88 | Paid | Medium
EXP-05463 | PRJ-006 | PRJ-006-ACT-05 | 2026-08-15 | Contractor | CON-001 | Civil Structure Contract | VEN-016 | 1 | Contract | 391229.42 | 390927.84 | 70367.01 | 461294.85 | Paid | Medium
EXP-05464 | PRJ-006 | PRJ-006-ACT-10 | 2026-08-15 | Contractor | CON-002 | Electrical Contract | VEN-014 | 1 | Contract | 229155.99 | 233995.45 | 42119.18 | 276114.63 | Paid | Low
EXP-05465 | PRJ-006 | PRJ-006-ACT-07 | 2026-08-15 | Contractor | CON-001 | Civil Structure Contract | VEN-016 | 1 | Contract | 204075.37 | 220876.69 | 39757.8 | 260634.49 | Paid | Low
EXP-05466 | PRJ-006 | PRJ-006-ACT-07 | 2026-08-15 | Equipment | EQ-002 | Excavator | VEN-015 | 6 | Day | 81518.32 | 87203.47 | 15696.62 | 102900.09 | Pending | High
EXP-05467 | PRJ-006 | PRJ-006-ACT-09 | 2026-08-15 | Equipment | EQ-002 | Excavator | VEN-015 | 1 | Day | 14285.12 | 13444.64 | 2420.04 | 15864.68 | Paid | Medium
EXP-05468 | PRJ-006 | PRJ-006-ACT-02 | 2026-08-20 | Labour | LAB-003 | Carpenter | VEN-014 | 17 | Worker | 31290.96 | 29224.63 | 5260.43 | 34485.06 | Paid | Low
EXP-05469 | PRJ-006 | PRJ-006-ACT-06 | 2026-08-20 | Contractor | CON-003 | Plumbing Contract | VEN-013 | 1 | Contract | 361604.75 | 348836 | 62790.48 | 411626.48 | Paid | Medium
EXP-05470 | PRJ-006 | PRJ-006-ACT-09 | 2026-08-20 | Labour | LAB-005 | Plumber | VEN-013 | 32 | Worker | 36178.02 | 34065 | 6131.7 | 40196.7 | Paid | Low
EXP-05471 | PRJ-006 | PRJ-006-ACT-08 | 2026-08-20 | Material | MAT-005 | Bricks | VEN-014 | 2.87 | Piece | 28.43 | 29.43 | 5.3 | 34.73 | Paid | Medium
EXP-05472 | PRJ-006 | PRJ-006-ACT-07 | 2026-08-20 | Material | MAT-003 | Sand | VEN-015 | 7.5 | Ton | 13751.35 | 13893.4 | 2500.81 | 16394.21 | Paid | Low
EXP-05473 | PRJ-006 | PRJ-006-ACT-06 | 2026-08-20 | Equipment | EQ-003 | Concrete Mixer | VEN-014 | 6 | Day | 28463.89 | 29114.15 | 5240.55 | 34354.7 | Paid | Medium
EXP-05474 | PRJ-006 | PRJ-006-ACT-10 | 2026-08-20 | Material | MAT-002 | Steel | VEN-015 | 19.76 | Ton | 1094637.3 | 1184228.06 | 213161.05 | 1397389.11 | Partially Paid | Medium
EXP-05475 | PRJ-006 | PRJ-006-ACT-08 | 2026-08-25 | Material | MAT-002 | Steel | VEN-014 | 9.24 | Ton | 569930.81 | 532125.89 | 95782.66 | 627908.55 | Paid | Low
EXP-05476 | PRJ-006 | PRJ-006-ACT-04 | 2026-08-25 | Equipment | EQ-003 | Concrete Mixer | VEN-016 | 6 | Day | 28252.84 | 29665.16 | 5339.73 | 35004.89 | Partially Paid | Low
EXP-05477 | PRJ-006 | PRJ-006-ACT-10 | 2026-08-25 | Material | MAT-006 | Electrical Cable | VEN-013 | 10.1 | Meter | 793.54 | 736.06 | 132.49 | 868.55 | Partially Paid | Medium
EXP-05478 | PRJ-006 | PRJ-006-ACT-05 | 2026-08-25 | Contractor | CON-001 | Civil Structure Contract | VEN-015 | 1 | Contract | 293980.7 | 279226.01 | 50260.68 | 329486.69 | Paid | Low
EXP-05479 | PRJ-006 | PRJ-006-ACT-01 | 2026-08-25 | Labour | LAB-005 | Plumber | VEN-016 | 8 | Worker | 9110.45 | 9822.16 | 1767.99 | 11590.15 | Paid | Low
EXP-05480 | PRJ-006 | PRJ-006-ACT-05 | 2026-08-25 | Material | MAT-001 | Cement | VEN-014 | 15.38 | Bag | 7468.95 | 6956.11 | 1252.1 | 8208.21 | Paid | Low
EXP-05481 | PRJ-006 | PRJ-006-ACT-10 | 2026-08-25 | Material | MAT-002 | Steel | VEN-013 | 8.06 | Ton | 476972.02 | 476917.32 | 85845.12 | 562762.44 | Paid | Low
EXP-05482 | PRJ-006 | PRJ-006-ACT-04 | 2026-08-25 | Contractor | CON-002 | Electrical Contract | VEN-013 | 1 | Contract | 125263.28 | 117838.08 | 21210.85 | 139048.93 | Paid | Medium
EXP-05483 | PRJ-006 | PRJ-006-ACT-04 | 2026-08-30 | Material | MAT-006 | Electrical Cable | VEN-015 | 3.82 | Meter | 330.51 | 331.77 | 59.72 | 391.49 | Paid | Low
EXP-05484 | PRJ-006 | PRJ-006-ACT-01 | 2026-08-30 | Equipment | EQ-003 | Concrete Mixer | VEN-016 | 5 | Day | 24953.82 | 23573.78 | 4243.28 | 27817.06 | Paid | Low
EXP-05485 | PRJ-006 | PRJ-006-ACT-01 | 2026-08-30 | Labour | LAB-005 | Plumber | VEN-015 | 10 | Worker | 12286.31 | 12931.73 | 2327.71 | 15259.44 | Paid | Low
EXP-05486 | PRJ-006 | PRJ-006-ACT-06 | 2026-08-30 | Material | MAT-005 | Bricks | VEN-013 | 5.2 | Piece | 53.45 | 53.72 | 9.67 | 63.39 | Partially Paid | Low
EXP-05487 | PRJ-006 | PRJ-006-ACT-06 | 2026-08-30 | Other | OTH-001 | Safety | VEN-016 | 1 | Lot | 11531.47 | 11896.41 | 2141.35 | 14037.76 | Paid | Medium
EXP-05488 | PRJ-006 | PRJ-006-ACT-05 | 2026-08-30 | Labour | LAB-002 | Helper | VEN-015 | 19 | Worker | 21068.96 | 20048.69 | 3608.76 | 23657.45 | Partially Paid | Medium
EXP-05489 | PRJ-006 | PRJ-006-ACT-07 | 2026-09-04 | Labour | LAB-004 | Electrician | VEN-014 | 15 | Worker | 15820.37 | 15914.66 | 2864.64 | 18779.3 | Pending | Low
EXP-05490 | PRJ-006 | PRJ-006-ACT-08 | 2026-09-04 | Labour | LAB-006 | Painter | VEN-014 | 7 | Worker | 8568.66 | 8047.92 | 1448.63 | 9496.55 | Pending | Low
EXP-05491 | PRJ-006 | PRJ-006-ACT-03 | 2026-09-04 | Contractor | CON-001 | Civil Structure Contract | VEN-014 | 1 | Contract | 288074.25 | 284671.52 | 51240.87 | 335912.39 | Paid | Low
EXP-05492 | PRJ-006 | PRJ-006-ACT-06 | 2026-09-04 | Contractor | CON-001 | Civil Structure Contract | VEN-015 | 1 | Contract | 165275.78 | 179049.74 | 32228.95 | 211278.69 | Paid | High
EXP-05493 | PRJ-006 | PRJ-006-ACT-09 | 2026-09-04 | Other | OTH-001 | Safety | VEN-015 | 1 | Lot | 40090.34 | 39429.72 | 7097.35 | 46527.07 | Paid | Low
EXP-05494 | PRJ-006 | PRJ-006-ACT-09 | 2026-09-04 | Material | MAT-002 | Steel | VEN-014 | 5.51 | Ton | 328104.07 | 318941.14 | 57409.41 | 376350.55 | Paid | Low
EXP-05495 | PRJ-006 | PRJ-006-ACT-04 | 2026-09-04 | Material | MAT-010 | Glass | VEN-013 | 9.37 | Sq Ft | 1577.56 | 1567.77 | 282.2 | 1849.97 | Partially Paid | Medium
EXP-05496 | PRJ-006 | PRJ-006-ACT-07 | 2026-09-04 | Material | MAT-007 | PVC Pipe | VEN-016 | 11.03 | Meter | 1277.32 | 1291.05 | 232.39 | 1523.44 | Paid | Low
EXP-05497 | PRJ-006 | PRJ-006-ACT-04 | 2026-09-09 | Material | MAT-010 | Glass | VEN-013 | 8.38 | Sq Ft | 1333.85 | 1278.21 | 230.08 | 1508.29 | Paid | Low
EXP-05498 | PRJ-006 | PRJ-006-ACT-06 | 2026-09-09 | Labour | LAB-002 | Helper | VEN-016 | 10 | Worker | 13008.59 | 13320.89 | 2397.76 | 15718.65 | Paid | Low
EXP-05499 | PRJ-006 | PRJ-006-ACT-04 | 2026-09-09 | Contractor | CON-004 | Finishing Contract | VEN-013 | 1 | Contract | 272703.47 | 255156.77 | 45928.22 | 301084.99 | Pending | Medium
EXP-05500 | PRJ-006 | PRJ-006-ACT-07 | 2026-09-09 | Contractor | CON-002 | Electrical Contract | VEN-015 | 1 | Contract | 140293.72 | 141789.28 | 25522.07 | 167311.35 | Paid | Medium
EXP-05501 | PRJ-006 | PRJ-006-ACT-07 | 2026-09-09 | Contractor | CON-001 | Civil Structure Contract | VEN-016 | 1 | Contract | 379247.01 | 380751 | 68535.18 | 449286.18 | Paid | Low
EXP-05502 | PRJ-006 | PRJ-006-ACT-08 | 2026-09-09 | Material | MAT-001 | Cement | VEN-015 | 3.46 | Bag | 1947.01 | 1900.97 | 342.17 | 2243.14 | Paid | Low
EXP-05503 | PRJ-006 | PRJ-006-ACT-04 | 2026-09-09 | Other | OTH-001 | Permit | VEN-013 | 1 | Lot | 69424.73 | 73297.21 | 13193.5 | 86490.71 | Paid | Medium
EXP-05504 | PRJ-006 | PRJ-006-ACT-07 | 2026-09-09 | Labour | LAB-003 | Carpenter | VEN-014 | 30 | Worker | 52467.62 | 49599.41 | 8927.89 | 58527.3 | Paid | Medium
EXP-05505 | PRJ-006 | PRJ-006-ACT-02 | 2026-09-09 | Material | MAT-010 | Glass | VEN-014 | 6.63 | Sq Ft | 1010.32 | 1089.49 | 196.11 | 1285.6 | Paid | Low
EXP-05506 | PRJ-006 | PRJ-006-ACT-06 | 2026-09-14 | Equipment | EQ-002 | Excavator | VEN-014 | 3 | Day | 40140.45 | 42470.98 | 7644.78 | 50115.76 | Pending | Low
EXP-05507 | PRJ-006 | PRJ-006-ACT-03 | 2026-09-14 | Labour | LAB-003 | Carpenter | VEN-013 | 19 | Worker | 31412.79 | 32045.95 | 5768.27 | 37814.22 | Paid | Low
EXP-05508 | PRJ-006 | PRJ-006-ACT-09 | 2026-09-14 | Material | MAT-010 | Glass | VEN-015 | 11.57 | Sq Ft | 2067.07 | 2017.27 | 363.11 | 2380.38 | Paid | Low
EXP-05509 | PRJ-006 | PRJ-006-ACT-08 | 2026-09-14 | Material | MAT-007 | PVC Pipe | VEN-016 | 11.38 | Meter | 1513.83 | 1531.27 | 275.63 | 1806.9 | Partially Paid | Low
EXP-05510 | PRJ-006 | PRJ-006-ACT-09 | 2026-09-14 | Material | MAT-001 | Cement | VEN-013 | 8.54 | Bag | 3915.78 | 3971.08 | 714.79 | 4685.87 | Paid | Low
EXP-05511 | PRJ-006 | PRJ-006-ACT-07 | 2026-09-14 | Equipment | EQ-002 | Excavator | VEN-015 | 7 | Day | 87492.61 | 88348.55 | 15902.74 | 104251.29 | Paid | Low
EXP-05512 | PRJ-006 | PRJ-006-ACT-04 | 2026-09-14 | Material | MAT-006 | Electrical Cable | VEN-013 | 10.5 | Meter | 866.32 | 870.62 | 156.71 | 1027.33 | Paid | Medium
EXP-05513 | PRJ-006 | PRJ-006-ACT-02 | 2026-09-19 | Material | MAT-007 | PVC Pipe | VEN-014 | 1.05 | Meter | 132.19 | 131.64 | 23.7 | 155.34 | Paid | Low
EXP-05514 | PRJ-006 | PRJ-006-ACT-06 | 2026-09-19 | Contractor | CON-003 | Plumbing Contract | VEN-015 | 1 | Contract | 285785.82 | 292783.85 | 52701.09 | 345484.94 | Paid | Medium
EXP-05515 | PRJ-006 | PRJ-006-ACT-04 | 2026-09-19 | Material | MAT-003 | Sand | VEN-016 | 6.12 | Ton | 12494.84 | 12087.7 | 2175.79 | 14263.49 | Pending | Low
EXP-05516 | PRJ-006 | PRJ-006-ACT-07 | 2026-09-19 | Equipment | EQ-003 | Concrete Mixer | VEN-014 | 1 | Day | 4410.57 | 4727.72 | 850.99 | 5578.71 | Paid | Low
EXP-05517 | PRJ-006 | PRJ-006-ACT-05 | 2026-09-19 | Equipment | EQ-002 | Excavator | VEN-014 | 4 | Day | 56514.13 | 56850.88 | 10233.16 | 67084.04 | Paid | Medium
EXP-05518 | PRJ-006 | PRJ-006-ACT-05 | 2026-09-19 | Labour | LAB-001 | Mason | VEN-014 | 18 | Worker | 26484.18 | 26204.63 | 4716.83 | 30921.46 | Paid | Medium
EXP-05519 | PRJ-006 | PRJ-006-ACT-08 | 2026-09-24 | Material | MAT-002 | Steel | VEN-015 | 27.2 | Ton | 1772439.84 | 1706378.52 | 307148.13 | 2013526.65 | Paid | Low
EXP-05520 | PRJ-006 | PRJ-006-ACT-03 | 2026-09-24 | Material | MAT-005 | Bricks | VEN-016 | 11.47 | Piece | 107.52 | 102.49 | 18.45 | 120.94 | Paid | Low
EXP-05521 | PRJ-006 | PRJ-006-ACT-07 | 2026-09-24 | Contractor | CON-001 | Civil Structure Contract | VEN-013 | 1 | Contract | 215118.05 | 229249.02 | 41264.82 | 270513.84 | Paid | Medium
EXP-05522 | PRJ-006 | PRJ-006-ACT-04 | 2026-09-24 | Material | MAT-004 | Aggregate | VEN-016 | 17.72 | Ton | 28592.72 | 27117.22 | 4881.1 | 31998.32 | Paid | Low
EXP-05523 | PRJ-006 | PRJ-006-ACT-01 | 2026-09-24 | Material | MAT-005 | Bricks | VEN-015 | 2.2 | Piece | 18.32 | 17.02 | 3.06 | 20.08 | Partially Paid | Low
EXP-05524 | PRJ-006 | PRJ-006-ACT-09 | 2026-09-24 | Material | MAT-001 | Cement | VEN-014 | 13.99 | Bag | 8307.6 | 8201.63 | 1476.29 | 9677.92 | Paid | Low
EXP-05525 | PRJ-006 | PRJ-006-ACT-07 | 2026-09-24 | Material | MAT-003 | Sand | VEN-015 | 21.36 | Ton | 43122.55 | 43518.94 | 7833.41 | 51352.35 | Paid | Medium
EXP-05526 | PRJ-006 | PRJ-006-ACT-05 | 2026-09-29 | Material | MAT-009 | Paint | VEN-013 | 9.75 | Litre | 2204.98 | 2116.46 | 380.96 | 2497.42 | Paid | Medium
EXP-05527 | PRJ-006 | PRJ-006-ACT-02 | 2026-09-29 | Contractor | CON-002 | Electrical Contract | VEN-016 | 1 | Contract | 115319.61 | 113293.69 | 20392.86 | 133686.55 | Paid | Low
EXP-05528 | PRJ-006 | PRJ-006-ACT-02 | 2026-09-29 | Labour | LAB-004 | Electrician | VEN-013 | 29 | Worker | 28446.99 | 29280.14 | 5270.43 | 34550.57 | Paid | Low
EXP-05529 | PRJ-006 | PRJ-006-ACT-09 | 2026-09-29 | Labour | LAB-004 | Electrician | VEN-013 | 31 | Worker | 43784.96 | 44364.65 | 7985.64 | 52350.29 | Paid | Medium
EXP-05530 | PRJ-006 | PRJ-006-ACT-01 | 2026-09-29 | Labour | LAB-002 | Helper | VEN-016 | 22 | Worker | 22246.71 | 21825.6 | 3928.61 | 25754.21 | Pending | Medium
EXP-05531 | PRJ-006 | PRJ-006-ACT-02 | 2026-09-29 | Labour | LAB-001 | Mason | VEN-016 | 17 | Worker | 22249.16 | 21126.75 | 3802.82 | 24929.57 | Paid | High
EXP-05532 | PRJ-006 | PRJ-006-ACT-09 | 2026-09-29 | Labour | LAB-003 | Carpenter | VEN-016 | 5 | Worker | 3193.15 | 3459.04 | 622.63 | 4081.67 | Paid | Medium
EXP-05533 | PRJ-006 | PRJ-006-ACT-02 | 2026-09-29 | Material | MAT-006 | Electrical Cable | VEN-015 | 11.52 | Meter | 1117.99 | 1040.99 | 187.38 | 1228.37 | Partially Paid | High

## Monthly_Summary
Month | Actual_Cost | Total_Cost | Project_ID | Project_Name | Monthly_Budget | Cumulative_Actual_Cost
2025-01-01 | 5393016.94 | 6363759.97 | PRJ-001 | Green Valley Residential Complex | 6913580.25 | 5393016.94
2025-02-01 | 3587544.48 | 4233302.47 | PRJ-001 | Green Valley Residential Complex | 6913580.25 | 8980561.42
2025-03-01 | 2748486.53 | 3243214.11 | PRJ-001 | Green Valley Residential Complex | 6913580.25 | 11729047.95
2025-04-01 | 4236233.99 | 4998756.11 | PRJ-001 | Green Valley Residential Complex | 6913580.25 | 15965281.94
2025-05-01 | 6622506.3 | 7814557.4 | PRJ-001 | Green Valley Residential Complex | 6913580.25 | 22587788.24
2025-06-01 | 6697619.59 | 7903191.12 | PRJ-001 | Green Valley Residential Complex | 6913580.25 | 29285407.83
2025-07-01 | 3940850.14 | 4650203.17 | PRJ-001 | Green Valley Residential Complex | 6913580.25 | 33226257.97
2025-08-01 | 8242436.14 | 9726074.63 | PRJ-001 | Green Valley Residential Complex | 6913580.25 | 41468694.11
2025-09-01 | 3600959.94 | 4249132.73 | PRJ-001 | Green Valley Residential Complex | 6913580.25 | 45069654.05
2025-10-01 | 3274480.15 | 3863886.55 | PRJ-001 | Green Valley Residential Complex | 6913580.25 | 48344134.2
2025-11-01 | 4181414.86 | 4934069.5 | PRJ-001 | Green Valley Residential Complex | 6913580.25 | 52525549.06
2025-12-01 | 6153021.62 | 7260565.54 | PRJ-001 | Green Valley Residential Complex | 6913580.25 | 58678570.68
2026-01-01 | 5625036.32 | 6637542.84 | PRJ-001 | Green Valley Residential Complex | 6913580.25 | 64303607
2026-02-01 | 2664548.64 | 3144167.39 | PRJ-001 | Green Valley Residential Complex | 6913580.25 | 66968155.64
2026-03-01 | 3590425.97 | 4236702.63 | PRJ-001 | Green Valley Residential Complex | 6913580.25 | 70558581.61
2026-04-01 | 6170873.89 | 7281631.18 | PRJ-001 | Green Valley Residential Complex | 6913580.25 | 76729455.5
2026-05-01 | 5064512.42 | 5976124.67 | PRJ-001 | Green Valley Residential Complex | 6913580.25 | 81793967.92
2026-06-01 | 3350057.15 | 3953067.4 | PRJ-001 | Green Valley Residential Complex | 6913580.25 | 85144025.07
2026-07-01 | 5141416.23 | 6066871.2 | PRJ-001 | Green Valley Residential Complex | 6913580.25 | 90285441.3
2026-08-01 | 2399797.89 | 2831761.53 | PRJ-001 | Green Valley Residential Complex | 6913580.25 | 92685239.19
2026-09-01 | 4093522.11 | 4830356.11 | PRJ-001 | Green Valley Residential Complex | 6913580.25 | 96778761.3
2025-04-01 | 3733832.28 | 4405922.09 | PRJ-002 | Riverside Commercial Tower | 10082304.53 | 3733832.28
2025-05-01 | 6472047.49 | 7637016.05 | PRJ-002 | Riverside Commercial Tower | 10082304.53 | 10205879.77
2025-06-01 | 4152013.42 | 4899375.84 | PRJ-002 | Riverside Commercial Tower | 10082304.53 | 14357893.19
2025-07-01 | 5385406.81 | 6354780.06 | PRJ-002 | Riverside Commercial Tower | 10082304.53 | 19743300
2025-08-01 | 3698031.51 | 4363677.18 | PRJ-002 | Riverside Commercial Tower | 10082304.53 | 23441331.51
2025-09-01 | 3993196.05 | 4711971.33 | PRJ-002 | Riverside Commercial Tower | 10082304.53 | 27434527.56
2025-10-01 | 4907477.03 | 5790822.88 | PRJ-002 | Riverside Commercial Tower | 10082304.53 | 32342004.59
2025-11-01 | 3730416.28 | 4401891.21 | PRJ-002 | Riverside Commercial Tower | 10082304.53 | 36072420.87
2025-12-01 | 4179817.24 | 4932184.33 | PRJ-002 | Riverside Commercial Tower | 10082304.53 | 40252238.11
2026-01-01 | 5375568.75 | 6343171.13 | PRJ-002 | Riverside Commercial Tower | 10082304.53 | 45627806.86
2026-02-01 | 3990789.87 | 4709132.04 | PRJ-002 | Riverside Commercial Tower | 10082304.53 | 49618596.73
2026-03-01 | 4725850.43 | 5576503.48 | PRJ-002 | Riverside Commercial Tower | 10082304.53 | 54344447.16
2026-04-01 | 2810439.32 | 3316318.36 | PRJ-002 | Riverside Commercial Tower | 10082304.53 | 57154886.48
2026-05-01 | 5632137.87 | 6645922.67 | PRJ-002 | Riverside Commercial Tower | 10082304.53 | 62787024.35
2026-06-01 | 6255408.84 | 7381382.43 | PRJ-002 | Riverside Commercial Tower | 10082304.53 | 69042433.19
2026-07-01 | 3920484.19 | 4626171.34 | PRJ-002 | Riverside Commercial Tower | 10082304.53 | 72962917.38
2026-08-01 | 6847888.29 | 8080508.19 | PRJ-002 | Riverside Commercial Tower | 10082304.53 | 79810805.67
2026-09-01 | 4016348.11 | 4739290.74 | PRJ-002 | Riverside Commercial Tower | 10082304.53 | 83827153.78
2024-07-01 | 5856517.33 | 6910690.48 | PRJ-003 | Sunrise Industrial Park | 5432098.77 | 5856517.33
2024-08-01 | 3774425.65 | 4453822.26 | PRJ-003 | Sunrise Industrial Park | 5432098.77 | 9630942.98
2024-09-01 | 5659760.03 | 6678516.83 | PRJ-003 | Sunrise Industrial Park | 5432098.77 | 15290703.01
2024-10-01 | 6421501.26 | 7577371.49 | PRJ-003 | Sunrise Industrial Park | 5432098.77 | 21712204.27
2024-11-01 | 3687667.99 | 4351448.22 | PRJ-003 | Sunrise Industrial Park | 5432098.77 | 25399872.26
2024-12-01 | 5132784.47 | 6056685.68 | PRJ-003 | Sunrise Industrial Park | 5432098.77 | 30532656.73
2025-01-01 | 2054282.51 | 2424053.36 | PRJ-003 | Sunrise Industrial Park | 5432098.77 | 32586939.24
2025-02-01 | 6333046.93 | 7472995.35 | PRJ-003 | Sunrise Industrial Park | 5432098.77 | 38919986.17
2025-03-01 | 3367623.71 | 3973795.96 | PRJ-003 | Sunrise Industrial Park | 5432098.77 | 42287609.88
2025-04-01 | 7441580.94 | 8781065.51 | PRJ-003 | Sunrise Industrial Park | 5432098.77 | 49729190.82
2025-05-01 | 6432724.5 | 7590614.91 | PRJ-003 | Sunrise Industrial Park | 5432098.77 | 56161915.32
2025-06-01 | 3036702.95 | 3583309.47 | PRJ-003 | Sunrise Industrial Park | 5432098.77 | 59198618.27
2025-07-01 | 6992689.76 | 8251373.9 | PRJ-003 | Sunrise Industrial Park | 5432098.77 | 66191308.03
2025-08-01 | 4797564.98 | 5661126.68 | PRJ-003 | Sunrise Industrial Park | 5432098.77 | 70988873.01
2025-09-01 | 4606826.76 | 5436055.54 | PRJ-003 | Sunrise Industrial Park | 5432098.77 | 75595699.77
2025-10-01 | 4678646.39 | 5520802.73 | PRJ-003 | Sunrise Industrial Park | 5432098.77 | 80274346.16
2025-11-01 | 3661969.53 | 4321124.06 | PRJ-003 | Sunrise Industrial Park | 5432098.77 | 83936315.69
2025-12-01 | 3273984.35 | 3863301.5 | PRJ-003 | Sunrise Industrial Park | 5432098.77 | 87210300.04
2026-01-01 | 2888918.18 | 3408923.45 | PRJ-003 | Sunrise Industrial Park | 5432098.77 | 90099218.22
2026-02-01 | 5934980 | 7003276.41 | PRJ-003 | Sunrise Industrial Park | 5432098.77 | 96034198.22
2026-03-01 | 5608851.31 | 6618444.52 | PRJ-003 | Sunrise Industrial Park | 5432098.77 | 101643049.53
2026-04-01 | 7877047.41 | 9294915.94 | PRJ-003 | Sunrise Industrial Park | 5432098.77 | 109520096.94
2026-05-01 | 3271053.3 | 3859842.92 | PRJ-003 | Sunrise Industrial Park | 5432098.77 | 112791150.24
2026-06-01 | 2877843.5 | 3395855.33 | PRJ-003 | Sunrise Industrial Park | 5432098.77 | 115668993.74
2025-02-01 | 3392562.49 | 4003223.75 | PRJ-004 | CityCare Hospital Expansion | 5231316.73 | 3392562.49
2025-03-01 | 4200116.53 | 4956137.48 | PRJ-004 | CityCare Hospital Expansion | 5231316.73 | 7592679.02
2025-04-01 | 4153496.94 | 4901126.39 | PRJ-004 | CityCare Hospital Expansion | 5231316.73 | 11746175.96
2025-05-01 | 4782074.75 | 5642848.18 | PRJ-004 | CityCare Hospital Expansion | 5231316.73 | 16528250.71
2025-06-01 | 4635575.7 | 5469979.32 | PRJ-004 | CityCare Hospital Expansion | 5231316.73 | 21163826.41
2025-07-01 | 3184984.79 | 3758282.04 | PRJ-004 | CityCare Hospital Expansion | 5231316.73 | 24348811.2
2025-08-01 | 4961735.44 | 5854847.82 | PRJ-004 | CityCare Hospital Expansion | 5231316.73 | 29310546.64
2025-09-01 | 2467454.46 | 2911596.25 | PRJ-004 | CityCare Hospital Expansion | 5231316.73 | 31778001.1
2025-10-01 | 6030583.55 | 7116088.57 | PRJ-004 | CityCare Hospital Expansion | 5231316.73 | 37808584.65
2025-11-01 | 3759959.56 | 4436752.33 | PRJ-004 | CityCare Hospital Expansion | 5231316.73 | 41568544.21
2025-12-01 | 5621547.65 | 6633426.23 | PRJ-004 | CityCare Hospital Expansion | 5231316.73 | 47190091.86
2026-01-01 | 5269970.06 | 6218564.65 | PRJ-004 | CityCare Hospital Expansion | 5231316.73 | 52460061.92
2026-02-01 | 3525074.31 | 4159587.66 | PRJ-004 | CityCare Hospital Expansion | 5231316.73 | 55985136.23
2026-03-01 | 5283878.86 | 6234977.04 | PRJ-004 | CityCare Hospital Expansion | 5231316.73 | 61269015.09
2026-04-01 | 4697204.97 | 5542701.88 | PRJ-004 | CityCare Hospital Expansion | 5231316.73 | 65966220.06
2026-05-01 | 3959352.85 | 4672036.35 | PRJ-004 | CityCare Hospital Expansion | 5231316.73 | 69925572.91
2026-06-01 | 5039021.28 | 5946045.07 | PRJ-004 | CityCare Hospital Expansion | 5231316.73 | 74964594.19
2026-07-01 | 5464404.26 | 6447997.01 | PRJ-004 | CityCare Hospital Expansion | 5231316.73 | 80428998.45
2026-08-01 | 6345844.58 | 7488096.63 | PRJ-004 | CityCare Hospital Expansion | 5231316.73 | 86774843.03
2024-10-01 | 4915529.75 | 5800325.1 | PRJ-005 | Smart City Road Package A | 4175824.18 | 4915529.75
2024-11-01 | 5426928.05 | 6403775.08 | PRJ-005 | Smart City Road Package A | 4175824.18 | 10342457.8
2024-12-01 | 2306724.61 | 2721935.04 | PRJ-005 | Smart City Road Package A | 4175824.18 | 12649182.41
2025-01-01 | 3752379.27 | 4427807.52 | PRJ-005 | Smart City Road Package A | 4175824.18 | 16401561.68
2025-02-01 | 4251013.04 | 5016195.41 | PRJ-005 | Smart City Road Package A | 4175824.18 | 20652574.72
2025-03-01 | 3121341.21 | 3683182.64 | PRJ-005 | Smart City Road Package A | 4175824.18 | 23773915.93
2025-04-01 | 5191261.73 | 6125688.83 | PRJ-005 | Smart City Road Package A | 4175824.18 | 28965177.66
2025-05-01 | 3959150.17 | 4671797.24 | PRJ-005 | Smart City Road Package A | 4175824.18 | 32924327.83
2025-06-01 | 4145142.69 | 4891268.34 | PRJ-005 | Smart City Road Package A | 4175824.18 | 37069470.52
2025-07-01 | 5742908.34 | 6776631.82 | PRJ-005 | Smart City Road Package A | 4175824.18 | 42812378.86
2025-08-01 | 5147315.25 | 6073831.98 | PRJ-005 | Smart City Road Package A | 4175824.18 | 47959694.11
2025-09-01 | 3556260.95 | 4196387.95 | PRJ-005 | Smart City Road Package A | 4175824.18 | 51515955.06
2025-10-01 | 4930560.85 | 5818061.83 | PRJ-005 | Smart City Road Package A | 4175824.18 | 56446515.91
2025-11-01 | 3382135.33 | 3990919.71 | PRJ-005 | Smart City Road Package A | 4175824.18 | 59828651.24
2025-12-01 | 4455271.49 | 5257220.39 | PRJ-005 | Smart City Road Package A | 4175824.18 | 64283922.73
2026-01-01 | 3847375.02 | 4539902.53 | PRJ-005 | Smart City Road Package A | 4175824.18 | 68131297.75
2026-02-01 | 3900776.05 | 4602915.75 | PRJ-005 | Smart City Road Package A | 4175824.18 | 72032073.8
2026-03-01 | 5686878.31 | 6710516.39 | PRJ-005 | Smart City Road Package A | 4175824.18 | 77718952.11
2025-06-01 | 3457549.89 | 4079908.89 | PRJ-006 | Grand Horizon Hotel & Convention Centre | 6761904.7619 | 3457549.89
2025-07-01 | 6693172 | 7897942.97 | PRJ-006 | Grand Horizon Hotel & Convention Centre | 6761904.7619 | 10150721.89
2025-08-01 | 3016510.05 | 3559481.84 | PRJ-006 | Grand Horizon Hotel & Convention Centre | 6761904.7619 | 13167231.94
2025-09-01 | 5040931.93 | 5948299.67 | PRJ-006 | Grand Horizon Hotel & Convention Centre | 6761904.7619 | 18208163.87
2025-10-01 | 6794723.14 | 8017773.3 | PRJ-006 | Grand Horizon Hotel & Convention Centre | 6761904.7619 | 25002887.01
2025-11-01 | 5013282.61 | 5915673.46 | PRJ-006 | Grand Horizon Hotel & Convention Centre | 6761904.7619 | 30016169.62
2025-12-01 | 3726086.06 | 4396781.57 | PRJ-006 | Grand Horizon Hotel & Convention Centre | 6761904.7619 | 33742255.68
2026-01-01 | 5040036.49 | 5947243.06 | PRJ-006 | Grand Horizon Hotel & Convention Centre | 6761904.7619 | 38782292.17
2026-02-01 | 3965263.48 | 4679010.93 | PRJ-006 | Grand Horizon Hotel & Convention Centre | 6761904.7619 | 42747555.65
2026-03-01 | 3362348.1 | 3967570.78 | PRJ-006 | Grand Horizon Hotel & Convention Centre | 6761904.7619 | 46109903.75
2026-04-01 | 3117855.78 | 3679069.8 | PRJ-006 | Grand Horizon Hotel & Convention Centre | 6761904.7619 | 49227759.53
2026-05-01 | 3876641.9 | 4574437.45 | PRJ-006 | Grand Horizon Hotel & Convention Centre | 6761904.7619 | 53104401.43
2026-06-01 | 5841390.68 | 6892841 | PRJ-006 | Grand Horizon Hotel & Convention Centre | 6761904.7619 | 58945792.11
2026-07-01 | 4090438.82 | 4826717.79 | PRJ-006 | Grand Horizon Hotel & Convention Centre | 6761904.7619 | 63036230.93
2026-08-01 | 7047966.69 | 8316600.67 | PRJ-006 | Grand Horizon Hotel & Convention Centre | 6761904.7619 | 70084197.62
2026-09-01 | 4582231.05 | 5407032.65 | PRJ-006 | Grand Horizon Hotel & Convention Centre | 6761904.7619 | 74666428.67

## Progress_History
Project_ID | Month | Planned_Progress_Pct | Actual_Progress_Pct | Variance_Pct
PRJ-001 | 2025-01-01 | 4.3 | 3.8 | -0.5
PRJ-001 | 2025-02-01 | 8.6 | 6.6 | -2
PRJ-001 | 2025-03-01 | 12.6 | 8.7 | -3.9
PRJ-001 | 2025-04-01 | 18.2 | 14.2 | -4
PRJ-001 | 2025-05-01 | 24.8 | 21.6 | -3.2
PRJ-001 | 2025-06-01 | 30.2 | 26.4 | -3.8
PRJ-001 | 2025-07-01 | 30.8 | 29.1 | -1.7
PRJ-001 | 2025-08-01 | 35.8 | 34.4 | -1.4
PRJ-001 | 2025-09-01 | 41.3 | 36.5 | -4.8
PRJ-001 | 2025-10-01 | 45.1 | 47.6 | 2.5
PRJ-001 | 2025-11-01 | 53.8 | 48.9 | -4.9
PRJ-001 | 2025-12-01 | 55.6 | 59.1 | 3.5
PRJ-001 | 2026-01-01 | 61.8 | 59.8 | -2
PRJ-001 | 2026-02-01 | 66.9 | 66.7 | -0.2
PRJ-001 | 2026-03-01 | 71.4 | 68 | -3.4
PRJ-001 | 2026-04-01 | 72.2 | 71.1 | -1.1
PRJ-001 | 2026-05-01 | 77.3 | 74.8 | -2.5
PRJ-001 | 2026-06-01 | 84.4 | 81.2 | -3.2
PRJ-001 | 2026-07-01 | 91.3 | 89.7 | -1.6
PRJ-001 | 2026-08-01 | 96.2 | 89.8 | -6.4
PRJ-001 | 2026-09-01 | 100 | 100 | 0
PRJ-002 | 2025-04-01 | 5.5 | 10.3 | 4.8
PRJ-002 | 2025-05-01 | 12.5 | 11.4 | -1.1
PRJ-002 | 2025-06-01 | 19.5 | 18.8 | -0.7
PRJ-002 | 2025-07-01 | 20.4 | 21.8 | 1.4
PRJ-002 | 2025-08-01 | 30.8 | 25.2 | -5.6
PRJ-002 | 2025-09-01 | 32.4 | 29.9 | -2.5
PRJ-002 | 2025-10-01 | 36.3 | 34.5 | -1.8
PRJ-002 | 2025-11-01 | 42.9 | 43.2 | 0.3
PRJ-002 | 2025-12-01 | 51 | 50.4 | -0.6
PRJ-002 | 2026-01-01 | 56 | 59.5 | 3.5
PRJ-002 | 2026-02-01 | 65.1 | 65.9 | 0.8
PRJ-002 | 2026-03-01 | 65.7 | 65.5 | -0.2
PRJ-002 | 2026-04-01 | 72.3 | 73.3 | 1
PRJ-002 | 2026-05-01 | 76 | 77.2 | 1.2
PRJ-002 | 2026-06-01 | 83.5 | 82.2 | -1.3
PRJ-002 | 2026-07-01 | 88.8 | 91.8 | 3
PRJ-002 | 2026-08-01 | 99.9 | 99.3 | -0.6
PRJ-002 | 2026-09-01 | 98.5 | 97.5 | -1
PRJ-003 | 2024-07-01 | 4.8 | 4.3 | -0.5
PRJ-003 | 2024-08-01 | 8.7 | 7.2 | -1.5
PRJ-003 | 2024-09-01 | 15.2 | 13.4 | -1.8
PRJ-003 | 2024-10-01 | 18.3 | 12.8 | -5.5
PRJ-003 | 2024-11-01 | 19.7 | 19.6 | -0.1
PRJ-003 | 2024-12-01 | 24.9 | 27.6 | 2.7
PRJ-003 | 2025-01-01 | 29.7 | 32.7 | 3
PRJ-003 | 2025-02-01 | 34.3 | 30.9 | -3.4
PRJ-003 | 2025-03-01 | 37.1 | 35.7 | -1.4
PRJ-003 | 2025-04-01 | 44.2 | 42.5 | -1.7
PRJ-003 | 2025-05-01 | 45.6 | 43.4 | -2.2
PRJ-003 | 2025-06-01 | 50.2 | 51.2 | 1
PRJ-003 | 2025-07-01 | 55.6 | 53.7 | -1.9
PRJ-003 | 2025-08-01 | 54.3 | 54.1 | -0.2
PRJ-003 | 2025-09-01 | 62.7 | 62.2 | -0.5
PRJ-003 | 2025-10-01 | 66.7 | 66.6 | -0.1
PRJ-003 | 2025-11-01 | 66.8 | 66.2 | -0.6
PRJ-003 | 2025-12-01 | 73 | 75.6 | 2.6
PRJ-003 | 2026-01-01 | 79.4 | 76.2 | -3.2
PRJ-003 | 2026-02-01 | 81 | 77.4 | -3.6
PRJ-003 | 2026-03-01 | 86.2 | 85.3 | -0.9
PRJ-003 | 2026-04-01 | 89.3 | 89 | -0.3
PRJ-003 | 2026-05-01 | 97.8 | 100 | 2.2
PRJ-003 | 2026-06-01 | 99.2 | 98.1 | -1.1
PRJ-004 | 2025-02-01 | 3.9 | -0.7 | -4.6
PRJ-004 | 2025-03-01 | 9.4 | 3 | -6.4
PRJ-004 | 2025-04-01 | 11.8 | 11.7 | -0.1
PRJ-004 | 2025-05-01 | 21.6 | 24.3 | 2.7
PRJ-004 | 2025-06-01 | 29.2 | 28.7 | -0.5
PRJ-004 | 2025-07-01 | 29.7 | 25.9 | -3.8
PRJ-004 | 2025-08-01 | 34.8 | 34.6 | -0.2
PRJ-004 | 2025-09-01 | 40.6 | 35.4 | -5.2
PRJ-004 | 2025-10-01 | 48.2 | 49.8 | 1.6
PRJ-004 | 2025-11-01 | 51.1 | 50 | -1.1
PRJ-004 | 2025-12-01 | 60.8 | 62.6 | 1.8
PRJ-004 | 2026-01-01 | 61.3 | 65 | 3.7
PRJ-004 | 2026-02-01 | 69.9 | 73.8 | 3.9
PRJ-004 | 2026-03-01 | 73.3 | 69.7 | -3.6
PRJ-004 | 2026-04-01 | 78.9 | 73.7 | -5.2
PRJ-004 | 2026-05-01 | 85.9 | 83.2 | -2.7
PRJ-004 | 2026-06-01 | 90.3 | 95.8 | 5.5
PRJ-004 | 2026-07-01 | 93.8 | 92.8 | -1
PRJ-004 | 2026-08-01 | 99.1 | 97.7 | -1.4
PRJ-005 | 2024-10-01 | 5.1 | 7.1 | 2
PRJ-005 | 2024-11-01 | 12.9 | 11.2 | -1.7
PRJ-005 | 2024-12-01 | 16.9 | 14.9 | -2
PRJ-005 | 2025-01-01 | 25.1 | 16.4 | -8.7
PRJ-005 | 2025-02-01 | 26.2 | 26.5 | 0.3
PRJ-005 | 2025-03-01 | 35 | 37.8 | 2.8
PRJ-005 | 2025-04-01 | 38.9 | 36.1 | -2.8
PRJ-005 | 2025-05-01 | 44.4 | 46.3 | 1.9
PRJ-005 | 2025-06-01 | 48.8 | 47.6 | -1.2
PRJ-005 | 2025-07-01 | 55 | 57.7 | 2.7
PRJ-005 | 2025-08-01 | 58.8 | 50.2 | -8.6
PRJ-005 | 2025-09-01 | 66.4 | 67.3 | 0.9
PRJ-005 | 2025-10-01 | 71.2 | 64.7 | -6.5
PRJ-005 | 2025-11-01 | 79.1 | 76.8 | -2.3
PRJ-005 | 2025-12-01 | 83.8 | 81.9 | -1.9
PRJ-005 | 2026-01-01 | 84.5 | 84.5 | 0
PRJ-005 | 2026-02-01 | 95.6 | 94 | -1.6
PRJ-005 | 2026-03-01 | 97.7 | 100 | 2.3
PRJ-006 | 2025-06-01 | 9 | 8.8 | -0.2
PRJ-006 | 2025-07-01 | 16 | 15.9 | -0.1
PRJ-006 | 2025-08-01 | 18.1 | 16.8 | -1.3
PRJ-006 | 2025-09-01 | 25.1 | 18.7 | -6.4
PRJ-006 | 2025-10-01 | 31.6 | 33.3 | 1.7
PRJ-006 | 2025-11-01 | 38.8 | 34.9 | -3.9
PRJ-006 | 2025-12-01 | 43.9 | 42.6 | -1.3
PRJ-006 | 2026-01-01 | 51.7 | 49.7 | -2
PRJ-006 | 2026-02-01 | 57.4 | 50.4 | -7
PRJ-006 | 2026-03-01 | 61.4 | 63.5 | 2.1
PRJ-006 | 2026-04-01 | 66.9 | 69.7 | 2.8
PRJ-006 | 2026-05-01 | 73.9 | 63.7 | -10.2
PRJ-006 | 2026-06-01 | 82.6 | 78.4 | -4.2
PRJ-006 | 2026-07-01 | 88.3 | 91 | 2.7
PRJ-006 | 2026-08-01 | 94.3 | 93.1 | -1.2
PRJ-006 | 2026-09-01 | 100 | 96.7 | -3.3

## Budget_Allocation
Project_ID | Project_Name | Cost_Category | Budget_Amount
PRJ-001 | Green Valley Residential Complex | Material | 63840000
PRJ-001 | Green Valley Residential Complex | Labour | 33600000
PRJ-001 | Green Valley Residential Complex | Equipment | 16800000
PRJ-001 | Green Valley Residential Complex | Contractor | 42000000
PRJ-001 | Green Valley Residential Complex | Other | 11760000
PRJ-002 | Riverside Commercial Tower | Material | 93100000
PRJ-002 | Riverside Commercial Tower | Labour | 49000000
PRJ-002 | Riverside Commercial Tower | Equipment | 24500000
PRJ-002 | Riverside Commercial Tower | Contractor | 61250000
PRJ-002 | Riverside Commercial Tower | Other | 17150000
PRJ-003 | Sunrise Industrial Park | Material | 50160000
PRJ-003 | Sunrise Industrial Park | Labour | 26400000
PRJ-003 | Sunrise Industrial Park | Equipment | 13200000
PRJ-003 | Sunrise Industrial Park | Contractor | 33000000
PRJ-003 | Sunrise Industrial Park | Other | 9240000
PRJ-004 | CityCare Hospital Expansion | Material | 37240000
PRJ-004 | CityCare Hospital Expansion | Labour | 19600000
PRJ-004 | CityCare Hospital Expansion | Equipment | 9800000
PRJ-004 | CityCare Hospital Expansion | Contractor | 24500000
PRJ-004 | CityCare Hospital Expansion | Other | 6860000
PRJ-005 | Smart City Road Package A | Material | 28880000
PRJ-005 | Smart City Road Package A | Labour | 15200000
PRJ-005 | Smart City Road Package A | Equipment | 7600000
PRJ-005 | Smart City Road Package A | Contractor | 19000000
PRJ-005 | Smart City Road Package A | Other | 5320000
PRJ-006 | Grand Horizon Hotel & Convention Centre | Material | 53960000
PRJ-006 | Grand Horizon Hotel & Convention Centre | Labour | 28400000
PRJ-006 | Grand Horizon Hotel & Convention Centre | Equipment | 14200000
PRJ-006 | Grand Horizon Hotel & Convention Centre | Contractor | 35500000
PRJ-006 | Grand Horizon Hotel & Convention Centre | Other | 9940000

## Vendors
Vendor_ID | Vendor_Name | Vendor_Type | City | State
VEN-001 | ABC Cement & Materials | Material | Lucknow | UP
VEN-002 | Tata Steel Distribution | Material | Kanpur | UP
VEN-003 | BuildPro Electricals | Material | Noida | UP
VEN-004 | Modern Tiles & Sanitary | Material | Delhi | Delhi
VEN-005 | Shree Aggregates | Material | Agra | UP
VEN-006 | Prime Civil Contractors | Contractor | Lucknow | UP
VEN-007 | RK Structure Works | Contractor | Noida | UP
VEN-008 | Maa Construction Services | Contractor | Kanpur | UP
VEN-009 | Urban MEP Solutions | Contractor | Delhi | Delhi
VEN-010 | BuildEquip Rentals | Equipment | Lucknow | UP
VEN-011 | HeavyLift Equipment | Equipment | Noida | UP
VEN-012 | SafeScaffold Rentals | Equipment | Agra | UP
VEN-013 | Jaipur Build Materials | Material | Jaipur | Rajasthan
VEN-014 | Rajasthan Civil Works | Contractor | Jaipur | Rajasthan
VEN-015 | Royal MEP Services | Contractor | Jaipur | Rajasthan
VEN-016 | Pink City Equipment Rentals | Equipment | Jaipur | Rajasthan

## README
Dataset | Sheet | Description | Recommended_Relationship
Construction Project Management Dataset | Projects | Project master: contract value, budget, actual cost and status | Projects[Project_ID] -> all project-level tables
Construction Project Management Dataset | Activities | WBS/activity-level planned vs actual progress | Projects[Project_ID] -> Activities[Project_ID]
Construction Project Management Dataset | Expenses | Detailed cost transactions across material, labour, equipment and contractors | Projects[Project_ID] -> Expenses[Project_ID]; Vendors[Vendor_ID] -> Expenses[Vendor_ID]
Construction Project Management Dataset | Monthly_Summary | Monthly cost aggregation for trend charts | Projects[Project_ID] -> Monthly_Summary[Project_ID]
Construction Project Management Dataset | Progress_History | Monthly planned vs actual construction progress | Projects[Project_ID] -> Progress_History[Project_ID]
Construction Project Management Dataset | Budget_Allocation | Budget split by cost category | Projects[Project_ID] -> Budget_Allocation[Project_ID]
Construction Project Management Dataset | Vendors | Vendor master data | Vendors[Vendor_ID] -> Expenses[Vendor_ID]
Construction Project Management Dataset | README | Dataset documentation and Power BI relationship guidance | Use Projects as dimension; Expenses as main fact table
Construction Project Management Dataset | Update | Added Project Type: Hospitality and PRJ-006 with linked activities, expenses, vendors, monthly summary, progress history and budget allocation. | Use Project_ID for project relationships and Vendor_ID for expense-vendor relationships.